## Schedule
Activity ID | Activity Name | Original Duration | BL1 Start | BL1 Finish
RSG, TURTLE BAY VILLAGE, 13 NOS LINEAR BUILDINGS - REVISED UPDATED SCHEDULE |  | 546 | 2024-09-05 | 2026-01-05
CONTRACT MILESTONES |  | 535 | 2024-09-05 | 2026-01-05
R7-CM-1000 | Project Commencement Date | 0 | 2024-09-05
R7-CM-5000 | MS-01 Early Deliverables & Baseline Programme Submission (incl. all Support Documents) | 0 |  | 2024-11-20
R7S1-CM-2000 | MS-02 Priority -01, Completion of Management Apartments-6 Nos. (incl. associated Hub & Infra Works) | 0 |  | 2025-10-30
R7S2-CM-3000 | MS-03 Priority -02, Completion of Studios (5+2 Nos.) & Overall Completion | 0 |  | 2026-01-05
R7-CM-4000 | Project Completion Date | 0 |  | 2026-01-05
KEY MILESTONES |  | 0 | 2024-09-05 | 2024-09-05
R7S1-KM-1000 | Right of Access - Priority 1 (to provide bearing capacity of 200 KPA) - 6 Buildings (By Employer) | 0 | 2024-09-05
R7S2-KM-2000 | Right of Access - Priority 2 (to provide bearing capacity of 200 KPA) - 7 Buildings (By Employer) | 0 | 2024-09-05
EARLY DELIVERABLES |  | 120 | 2024-09-05 | 2025-01-02
PREPARATION & SUBMISSION |  | 77 | 2024-09-05 | 2024-11-20
R7-ED-S-4000 | Construction Environmental and Social Management Plan (CESMP) | 1 | 2024-09-12 | 2024-09-12
R7-ED-S-3000 | Quality Management Plan | 53 | 2024-09-14 | 2024-11-14
R7-ED-S-1000 | Safety Program | 64 | 2024-09-05 | 2024-11-19
R7-ED-S-2000 | Baseline Programme Submission | 77 | 2024-09-05 | 2024-11-20
APPROVAL - EMPLOYER |  | 81 | 2024-09-11 | 2025-01-02
R7-ED-A-3000 | Construction Environmental and Social Management Plan (CESMP) | 20 | 2024-09-19 | 2024-10-17
R7-ED-A-4000 | Baseline Programme Approval | 38 | 2024-10-06 | 2024-11-26
R7-ED-A-1000 | Safety Program | 60 | 2024-09-11 | 2024-12-04
R7-ED-A-2000 | Quality Management Plan | 75 | 2024-09-19 | 2025-01-02
SOIL INVESTIGATION |  | 17 | 2024-09-21 | 2024-10-10
R7S1-SI-1000 | Verification of Soil Bearing Capacity - Priority 1 | 17 | 2024-09-21 | 2024-10-10
R7S2-SI-2000 | Verification of Soil Bearing Capacity - Priority 2 | 17 | 2024-09-21 | 2024-10-10
ENGINEERING WORKS |  | 322 | 2024-09-05 | 2025-06-16
DESIGN |  | 176 | 2024-09-05 | 2025-02-27
1&2 BED LINEAR APARTMENTS BUILDINGS (MANAGEMENT TYPE A) |  | 93 | 2024-09-05 | 2024-12-06
R7S1-EDMP-1000 | Design Preparation/IFC by the Contractor (Str./Arch./MEP) | 1 | 2024-09-05 | 2024-09-05
R7S1-EDMP-1010 | Approval of the Design to the Employer (Str./Arch./MEP) | 26 | 2024-11-11 | 2024-12-06
LINEAR STUDIOS APARTMENTS BUILDINGS (STUDIOS - TYPE LARGE) |  | 135 | 2024-10-16 | 2025-02-27
ARCHITECTURAL DESIGN |  | 108 | 2024-10-16 | 2025-01-31
R7S1-EDLSAP-1000 | Arch.Design Preparation by the Contractor - Studio (Large) | 41 | 2024-10-16 | 2024-12-11
R7S1-EDLSSAS-1010 | Submission of the Arch. Design to the Employer - Studio (Large) | 1 | 2024-12-16 | 2024-12-16
R7S1-EDLSAA-1020 | Arch. Design Approval by the Employer - Studio (Large) | 47 | 2024-12-16 | 2025-01-31
STRUCTURAL DESIGN |  | 50 | 2024-11-13 | 2025-01-01
R7S1-EDLSSP-1000 | Str. Design Preparation by the Contractor - Studio (Large) | 29 | 2024-11-13 | 2024-12-23
R7S1-EDLSSS-1010 | Submission of the Str. Design to the Employer - Studio (Large) | 1 | 2024-12-24 | 2024-12-24
R7S1-EDLSSA-1020 | Str. Design Approval by the Employer - Studio (Large) | 8 | 2024-12-25 | 2025-01-01
MEP DESIGN |  | 121 | 2024-10-30 | 2025-02-27
MECHANICAL |  | 77 | 2024-10-30 | 2025-01-14
HVAC |  | 63 | 2024-11-13 | 2025-01-14
R7S1-EDLSMP-1000 | HVAC Design Preparation by the Contractor - Studio (Large) | 38 | 2024-11-13 | 2025-01-05
R7S1-EDLSMS-1010 | Submission of the HVAC Design to the Employer - Studio (Large) | 9 | 2024-12-24 | 2025-01-05
R7S1-EDLSMA-1020 | HVAC Design Approval by the Employer - Studio (Large) | 14 | 2025-01-01 | 2025-01-14
FIREFIGHTING |  | 63 | 2024-10-30 | 2024-12-31
R7S1-EDLSMP-3000 | Firefighting Design Preparation by the Contractor - Studio (Large) | 36 | 2024-10-30 | 2024-12-18
R7S1-EDLSMS-3010 | Submission of the Firefighting Design to the Employer - Studio (Large) | 8 | 2024-12-10 | 2024-12-19
R7S1-EDLSMA-3020 | Firefighting Design Approval by the Employer - Studio (Large) | 13 | 2024-12-19 | 2024-12-31
DRAINAGE |  | 64 | 2024-10-30 | 2025-01-01
R7S1-EDLSMP-4000 | Drainage Design Preparation by the Contractor - Studio (Large) | 33 | 2024-10-30 | 2024-12-15
R7S1-EDLSMS-4010 | Submission of the Drainage Design to the Employer - Studio (Large) | 5 | 2024-12-10 | 2024-12-16
R7S1-EDLSMA-4020 | Drainage Design Approval by the Employer - Studio (Large) | 16 | 2024-12-17 | 2025-01-01
WATER SUPPLY |  | 63 | 2024-10-30 | 2024-12-31
R7S1-EDLSMP-5000 | Water Supply Design Preparation by the Contractor - Studio (Large) | 36 | 2024-10-30 | 2024-12-18
R7S1-EDLSMS-5010 | Submission of the Water Supply Design to the Employer - Studio (Large) | 8 | 2024-12-10 | 2024-12-19
R7S1-EDLSMA-5020 | Water Supply Design Approval by the Employer - Studio (Large) | 13 | 2024-12-19 | 2024-12-31
ELECTRICAL |  | 121 | 2024-10-30 | 2025-02-27
LIGHTING SYSTEM |  | 63 | 2024-10-30 | 2024-12-31
R7S1-EDLSEP-1000 | Lighting System Design Preparation by the Contractor - Studio (Large) | 36 | 2024-10-30 | 2024-12-18
R7S1-EDLSES-1010 | Submission of the Lighting System Design to the Employer - Studio (Large) | 9 | 2024-12-10 | 2024-12-22
R7S1-EDLSEA-1020 | Lighting System Design Approval by the Employer - Studio (Large) | 13 | 2024-12-19 | 2024-12-31
POWER SYSTEM |  | 64 | 2024-10-30 | 2025-01-01
R7S1-EDLSEP-2000 | Power System Design Preparation by the Contractor - Studio (Large) | 37 | 2024-10-30 | 2024-12-19
R7S1-EDLSES-2010 | Submission of the Power System Design to the Employer - Studio (Large) | 9 | 2024-12-10 | 2024-12-22
R7S1-EDLSEA-2020 | Power System Design Approval by the Employer - Studio (Large) | 11 | 2024-12-22 | 2025-01-01
ICT SYSTEM |  | 56 | 2024-10-30 | 2024-12-25
R7S1-EDLSES-3010 | Submission of the ICT System Design to the Employer - Studio (Large) | 5 | 2024-12-10 | 2024-12-16
R7S1-EDLSEP-3000 | ICT System Design Preparation by the Contractor - Studio (Large) | 34 | 2024-10-30 | 2024-12-16
R7S1-EDLSEA-3020 | ICT System Design Approval by the Employer - Studio (Large) | 8 | 2024-12-17 | 2024-12-25
FIRE ALARM SYSTEM |  | 57 | 2024-10-30 | 2024-12-25
R7S1-EDLSEP-4000 | Fire Alarm System Design Preparation by the Contractor - Studio (Large) | 36 | 2024-10-30 | 2024-12-18
R7S1-EDLSES-4010 | Submission of the Fire Alarm System Design to the Employer - Studio (Large) | 8 | 2024-12-10 | 2024-12-19
R7S1-EDLSEA-4020 | Fire Alarm System Design Approval by the Employer - Studio (Large) | 7 | 2024-12-19 | 2024-12-25
ACCESS CONTROLSYSTEM |  | 94 | 2024-10-30 | 2025-01-31
R7S1-EDLSEP-5000 | Access Control system Design Preparation by the Contractor - Studio (Large) | 54 | 2024-10-30 | 2025-01-13
R7S1-EDLSES-5010 | Submission of the Access Control system Design to the Employer - Studio (Large) | 25 | 2024-12-10 | 2025-01-13
R7S1-EDLSEA-5020 | Access Control system Design Approval by the Employer - Studio (Large) | 45 | 2024-12-18 | 2025-01-31
CCTV SYSTEM |  | 85 | 2024-10-30 | 2025-01-22
R7S1-EDLSEP-6000 | CCTV System Design Preparation by the Contractor - Studio (Large) | 54 | 2024-10-30 | 2025-01-13
R7S1-EDLSES-6010 | Submission of the CCTV System Design to the Employer - Studio (Large) | 25 | 2024-12-10 | 2025-01-13
R7S1-EDLSEA-6020 | CCTV System Design Approval by the Employer - Studio (Large) | 36 | 2024-12-18 | 2025-01-22
LIGHTNING PROTECTION SYSTEM |  | 121 | 2024-10-30 | 2025-02-27
R7S1-EDLSEP-7000 | Lightning Protection System Design Preparation by the Contractor - Studio (Large) | 33 | 2024-10-30 | 2024-12-15
R7S1-EDLSES-7010 | Submission of the Lightning Protection System Design to the Employer - Studio (Large) | 53 | 2024-12-10 | 2025-02-20
R7S1-EDLSEA-7020 | Lightning Protection System Design Approval by the Employer - Studio (Large) | 73 | 2024-12-17 | 2025-02-27
INTEGRATED BUILDING MANAGEMENT SYSTEM |  | 64 | 2024-10-30 | 2025-01-01
R7S1-EDLSEP-8000 | Integrated Building Management System Design Preparation by the Contractor - Studio (Large) | 33 | 2024-10-30 | 2024-12-15
R7S1-EDLSES-8010 | Submission of the Integrated Building Management System Design to the Employer - Studio (Large) | 5 | 2024-12-10 | 2024-12-16
R7S1-EDLSEA-8020 | Integrated Building Management System Design Approval by the Employer - Studio (Large) | 16 | 2024-12-17 | 2025-01-01
LINEAR STUDIOS APARTMENTS BUILDINGS (STUDIOS -TYPE MEDIUM) |  | 79 | 2024-12-11 | 2025-02-27
ARCHITECTURAL DESIGN |  | 52 | 2024-12-11 | 2025-01-31
R7S1-EDMSAP-1000 | Arch.Design Preparation by the Contractor - Studio (Medium) | 5 | 2024-12-11 | 2024-12-17
R7S1-EDMSSAS-1010 | Submission of the Arch. Design to the Employer - Studio (Medium) | 32 | 2024-12-18 | 2025-01-30
R7S1-EDMSAA-1020 | Arch. Design Approval by the Employer - Studio (Medium) | 44 | 2024-12-19 | 2025-01-31
STRUCTURAL DESIGN |  | 21 | 2024-12-19 | 2025-01-08
R7S1-EDMSSP-1000 | Str. Design Preparation by the Contractor - Studio (Medium) | 10 | 2024-12-19 | 2025-01-01
R7S1-EDMSSS-1010 | Submission of the Str. Design to the Employer - Studio (Medium) | 1 | 2025-01-01 | 2025-01-01
R7S1-EDMSSA-1020 | Str. Design Approval by the Employer - Studio (Medium) | 8 | 2025-01-01 | 2025-01-08
MEP DESIGN |  | 61 | 2024-12-29 | 2025-02-27
MECHANICAL |  | 61 | 2024-12-29 | 2025-02-27
HVAC |  | 51 | 2024-12-29 | 2025-02-17
R7S1-EDMSMP-1000 | HVAC Design Preparation by the Contractor - Studio (Medium) | 30 | 2024-12-29 | 2025-02-06
R7S1-EDMSMS-1010 | Submission of the HVAC Design to the Employer - Studio (Medium) | 15 | 2025-01-23 | 2025-02-12
R7S1-EDMSMA-1020 | HVAC Design Approval by the Employer - Studio (Medium) | 12 | 2025-02-06 | 2025-02-17
FIREFIGHTING |  | 21 | 2025-01-05 | 2025-01-25
R7S1-EDMSMS-3010 | Submission of the Firefighting Design to the Employer - Studio (Medium) | 1 | 2025-01-13 | 2025-01-13
R7S1-EDMSMP-3000 | Firefighting Design Preparation by the Contractor - Studio (Medium) | 7 | 2025-01-05 | 2025-01-13
R7S1-EDMSMA-3020 | Firefighting Design Approval by the Employer - Studio (Medium) | 12 | 2025-01-14 | 2025-01-25
DRAINAGE |  | 22 | 2025-01-05 | 2025-01-26
R7S1-EDMSMS-4010 | Submission of the Drainage Design to the Employer - Studio (Medium) | 1 | 2025-01-16 | 2025-01-16
R7S1-EDMSMP-4000 | Drainage Design Preparation by the Contractor - Studio (Medium) | 10 | 2025-01-05 | 2025-01-16
R7S1-EDMSMA-4020 | Drainage Design Approval by the Employer - Studio (Medium) | 11 | 2025-01-16 | 2025-01-26
WATER SUPPLY |  | 54 | 2025-01-05 | 2025-02-27
R7S1-EDMSMP-5000 | Water Supply Design Preparation by the Contractor - Studio (Medium) | 29 | 2025-01-05 | 2025-02-12
R7S1-EDMSMS-5010 | Submission of the Water Supply Design to the Employer - Studio (Medium) | 16 | 2025-01-23 | 2025-02-13
R7S1-EDMSMA-5020 | Water Supply Design Approval by the Employer - Studio (Medium) | 35 | 2025-01-24 | 2025-02-27
ELECTRICAL |  | 54 | 2025-01-05 | 2025-02-27
LIGHTING SYSTEM |  | 26 | 2025-01-05 | 2025-01-30
R7S1-EDMSEP-1000 | Lighting System Design Preparation by the Contractor - Studio (Medium) | 12 | 2025-01-05 | 2025-01-20
R7S1-EDMSES-1010 | Submission of the Lighting System Design to the Employer - Studio (Medium) | 1 | 2025-01-20 | 2025-01-20
R7S1-EDMSEA-1020 | Lighting System Design Approval by the Employer - Studio (Medium) | 11 | 2025-01-20 | 2025-01-30
POWER SYSTEM |  | 23 | 2025-01-05 | 2025-01-27
R7S1-EDMSEP-2000 | Power System Design Preparation by the Contractor - Studio (Medium) | 12 | 2025-01-05 | 2025-01-20
R7S1-EDMSES-2010 | Submission of the Power System Design to the Employer - Studio (Medium) | 1 | 2025-01-20 | 2025-01-20
R7S1-EDMSEA-2020 | Power System Design Approval by the Employer - Studio (Medium) | 8 | 2025-01-20 | 2025-01-27
ICT SYSTEM |  | 26 | 2025-01-05 | 2025-01-30
R7S1-EDMSEP-3000 | ICT System Design Preparation by the Contractor - Studio (Medium) | 5 | 2025-01-05 | 2025-01-09
R7S1-EDMSES-3010 | Submission of the ICT System Design to the Employer - Studio (Medium) | 1 | 2025-01-12 | 2025-01-12
R7S1-EDMSEA-3020 | ICT System Design Approval by the Employer - Studio (Medium) | 20 | 2025-01-11 | 2025-01-30
FIRE ALARM SYSTEM |  | 18 | 2025-01-05 | 2025-01-22
R7S1-EDMSEP-4000 | Fire Alarm System Design Preparation by the Contractor - Studio (Medium) | 7 | 2025-01-05 | 2025-01-13
R7S1-EDMSES-4010 | Submission of the Fire Alarm System Design to the Employer - Studio (Medium) | 1 | 2025-01-13 | 2025-01-13
R7S1-EDMSEA-4020 | Fire Alarm System Design Approval by the Employer - Studio (Medium) | 10 | 2025-01-13 | 2025-01-22
ACCESS CONTROLSYSTEM |  | 26 | 2025-01-05 | 2025-01-30
R7S1-EDMSEP-5000 | Access Control system Design Preparation by the Contractor - Studio (Medium) | 5 | 2025-01-05 | 2025-01-09
R7S1-EDMSES-5010 | Submission of the Access Control system Design to the Employer - Studio (Medium) | 1 | 2025-01-12 | 2025-01-12
R7S1-EDMSEA-5020 | Access Control system Design Approval by the Employer - Studio (Medium) | 20 | 2025-01-11 | 2025-01-30
CCTV SYSTEM |  | 21 | 2025-01-05 | 2025-01-25
R7S1-EDMSEP-6000 | CCTV System Design Preparation by the Contractor - Studio (Medium) | 5 | 2025-01-05 | 2025-01-09
R7S1-EDMSES-6010 | Submission of the CCTV System Design to the Employer - Studio (Medium) | 1 | 2025-01-12 | 2025-01-12
R7S1-EDMSEA-6020 | CCTV System Design Approval by the Employer - Studio (Medium) | 15 | 2025-01-11 | 2025-01-25
LIGHTNING PROTECTION SYSTEM |  | 54 | 2025-01-05 | 2025-02-27
R7S1-EDMSEP-7000 | Lightning Protection System Design Preparation by the Contractor - Studio (Medium) | 15 | 2025-01-05 | 2025-01-23
R7S1-EDMSES-7010 | Submission of the Lightning Protection System Design to the Employer - Studio (Medium) | 19 | 2025-01-23 | 2025-02-18
R7S1-EDMSEA-7020 | Lightning Protection System Design Approval by the Employer - Studio (Medium) | 34 | 2025-01-25 | 2025-02-27
INTEGRATED BUILDING MANAGEMENT SYSTEM |  | 32 | 2025-01-05 | 2025-02-05
R7S1-EDMSEP-8000 | Integrated Building Management System Design Preparation by the Contractor - Studio (Medium) | 15 | 2025-01-05 | 2025-01-23
R7S1-EDMSES-8010 | Submission of the Integrated Building Management System Design to the Employer - Studio (Medium) | 1 | 2025-01-23 | 2025-01-23
R7S1-EDMSEA-8020 | Integrated Building Management System Design Approval by the Employer - Studio (Medium) | 3 | 2025-02-03 | 2025-02-05
SHOP DRAWINGS/IFC |  | 247 | 2024-09-11 | 2025-05-16
1&2 BED LINEAR APARTMENTS BUILDINGS (MANAGEMENT TYPE A) |  | 134 | 2024-09-11 | 2025-01-22
PREPARATION & SUBMISSION |  | 51 | 2024-10-31 | 2025-01-09
ARCH. |  | 7 | 2024-10-31 | 2024-11-10
R7S1-ESD-M-AR-S100 | Building Setting-Out And Coordinates - Preparation & Submission (Type Management) | 7 | 2024-10-31 | 2024-11-10
R7S1-ESD-M-AR-S110 | U - Value Calculation - Preparation & Submission (Type Management) | 7 | 2024-10-31 | 2024-11-10
R7S1-ESD-M-AR-S120 | Plan - General Arrangement - Ground Floor - Preparation & Submission (Type Management) | 7 | 2024-10-31 | 2024-11-10
R7S1-ESD-M-AR-S130 | Plan - General Arrangement - Level 1 (FF) - Preparation & Submission (Type Management) | 7 | 2024-10-31 | 2024-11-10
R7S1-ESD-M-AR-S140 | Plan - General Arrangement - Level 2 (SF) - Preparation & Submission (Type Management) | 7 | 2024-10-31 | 2024-11-10
R7S1-ESD-M-AR-S150 | Modular Layouts - Ground Floor - Preparation & Submission (Type Management) | 7 | 2024-10-31 | 2024-11-10
R7S1-ESD-M-AR-S160 | Modular Layouts - Level 1 (FF) - Preparation & Submission (Type Management) | 7 | 2024-10-31 | 2024-11-10
R7S1-ESD-M-AR-S170 | Modular Layouts - Level 2 (SF) - Preparation & Submission (Type Management) | 7 | 2024-10-31 | 2024-11-10
R7S1-ESD-M-AR-S180 | Modular Layouts - Roof - Preparation & Submission (Type Management) | 7 | 2024-10-31 | 2024-11-10
R7S1-ESD-M-AR-S190 | Building Elevations - Preparation & Submission (Type Management) | 7 | 2024-10-31 | 2024-11-10
R7S1-ESD-M-AR-S200 | Building Sections - Preparation & Submission (Type Management) | 7 | 2024-10-31 | 2024-11-10
R7S1-ESD-M-AR-S210 | Typical - Floor Finishes Layout - Preparation & Submission (Type Management) | 7 | 2024-10-31 | 2024-11-10
R7S1-ESD-M-AR-S220 | Typical - Reflected Ceiling Finishes Layout - Preparation & Submission (Type Management) | 7 | 2024-10-31 | 2024-11-10
R7S1-ESD-M-AR-S230 | Door Schedules - Preparation & Submission (Type Management) | 7 | 2024-10-31 | 2024-11-10
R7S1-ESD-M-AR-S240 | Window Schedules - Preparation & Submission (Type Management) | 7 | 2024-10-31 | 2024-11-10
R7S1-ESD-M-AR-S250 | One Bed Apartment Typical Furniture Layout - Preparation & Submission (Type Management) | 7 | 2024-10-31 | 2024-11-10
R7S1-ESD-M-AR-S260 | Two Bed Apartment Typical Furniture Layout - Preparation & Submission (Type Management) | 7 | 2024-10-31 | 2024-11-10
R7S1-ESD-M-AR-S270 | Bed Apartment Typical Furniture Layout - Preparation & Submission (Type Management) | 7 | 2024-10-31 | 2024-11-10
R7S1-ESD-M-AR-S280 | One - Bed Apartment Typical Furniture Layout - Preparation & Submission (Type Management) | 7 | 2024-10-31 | 2024-11-10
R7S1-ESD-M-AR-S290 | Two - Bed Apartment Typical Furniture Layout - Preparation & Submission (Type Management) | 7 | 2024-10-31 | 2024-11-10
STR. |  | 16 | 2024-11-10 | 2024-12-01
R7S1-ESD-M-ST-S300 | Ground Floor Loading Diagram--Preparation & Submission (Type Management) | 16 | 2024-11-10 | 2024-12-01
R7S1-ESD-M-ST-S310 | Typical Cover Slab Loading Diagram--Preparation & Submission (Type Management) | 16 | 2024-11-10 | 2024-12-01
R7S1-ESD-M-ST-S330 | First Floor Loading Diagram--Preparation & Submission (Type Management) | 16 | 2024-11-10 | 2024-12-01
R7S1-ESD-M-ST-S340 | Second Floor Loading Diagram--Preparation & Submission (Type Management) | 16 | 2024-11-10 | 2024-12-01
R7S1-ESD-M-ST-S350 | Roof Floor Loading Diagram--Preparation & Submission (Type Management) | 16 | 2024-11-10 | 2024-12-01
R7S1-ESD-M-ST-S360 | Foundation Layout --Preparation & Submission (Type Management) | 16 | 2024-11-10 | 2024-12-01
R7S1-ESD-M-ST-S370 | Top Blinding Layout At Foundation--Preparation & Submission (Type Management) | 16 | 2024-11-10 | 2024-12-01
R7S1-ESD-M-ST-S380 | Foundation Dowel Layout --Preparation & Submission (Type Management) | 16 | 2024-11-10 | 2024-12-01
R7S1-ESD-M-ST-S390 | Ground Floor Slab, Beam And Wall Layout--Preparation & Submission (Type Management) | 16 | 2024-11-10 | 2024-12-01
R7S1-ESD-M-ST-S400 | Ground Floor Slab Connection Layout--Preparation & Submission (Type Management) | 16 | 2024-11-10 | 2024-12-01
R7S1-ESD-M-ST-S410 | Ground Floor Cover Slab Layout--Preparation & Submission (Type Management) | 16 | 2024-11-10 | 2024-12-01
R7S1-ESD-M-ST-S420 | First Floor Slab, Beam And Wall Layout--Preparation & Submission (Type Management) | 16 | 2024-11-10 | 2024-12-01
R7S1-ESD-M-ST-S430 | First Floor Cover Slab Layout--Preparation & Submission (Type Management) | 16 | 2024-11-10 | 2024-12-01
R7S1-ESD-M-ST-S440 | Second Floor Slab, Beam And Wall Layout--Preparation & Submission (Type Management) | 16 | 2024-11-10 | 2024-12-01
R7S1-ESD-M-ST-S450 | First & Second Floor Slab Connection Layout--Preparation & Submission (Type Management) | 16 | 2024-11-10 | 2024-12-01
R7S1-ESD-M-ST-S460 | First & Second Floor Dowel Layout--Preparation & Submission (Type Management) | 16 | 2024-11-10 | 2024-12-01
R7S1-ESD-M-ST-S470 | Roof Slab And Beams Layout--Preparation & Submission (Type Management) | 16 | 2024-11-10 | 2024-12-01
R7S1-ESD-M-ST-S480 | Roof Parapet Layout--Preparation & Submission (Type Management) | 16 | 2024-11-10 | 2024-12-01
R7S1-ESD-M-ST-S490 | Roof Slab Connection Layout--Preparation & Submission (Type Management) | 16 | 2024-11-10 | 2024-12-01
R7S1-ESD-M-ST-S500 | Foundation Sections--Preparation & Submission (Type Management) | 16 | 2024-11-10 | 2024-12-01
R7S1-ESD-M-ST-S510 | Pod Structural Details--Preparation & Submission (Type Management) | 16 | 2024-11-10 | 2024-12-01
R7S1-ESD-M-ST-S520 | Precast Concrete Standard Details--Preparation & Submission (Type Management) | 16 | 2024-11-10 | 2024-12-01
R7S1-ESD-M-ST-S530 | Schedules--Preparation & Submission (Type Management) | 16 | 2024-11-10 | 2024-12-01
MECHANICAL |  | 27 | 2024-11-04 | 2024-12-10
HVAC/CHWP |  | 18 | 2024-11-14 | 2024-12-09
R7S1-ESD-M-HVAC-S100 | HVAC Ground Floor Layout--Preparation & Submission (Type Management) | 18 | 2024-11-14 | 2024-12-09
R7S1-ESD-M-HVAC-S110 | HVAC First Floor Layout--Preparation & Submission (Type Management) | 18 | 2024-11-14 | 2024-12-09
R7S1-ESD-M-HVAC-S120 | HVAC Second Floor Layout--Preparation & Submission (Type Management) | 18 | 2024-11-14 | 2024-12-09
R7S1-ESD-M-HVAC-S130 | HVAC Roof Floor Layout--Preparation & Submission (Type Management) | 18 | 2024-11-14 | 2024-12-09
R7S1-ESD-M-HVAC-S140 | Chilled Water Piping Ground Floor Layout--Preparation & Submission (Type Management) | 18 | 2024-11-14 | 2024-12-09
R7S1-ESD-M-HVAC-S150 | Chilled Water Piping First Floor Layout--Preparation & Submission (Type Management) | 18 | 2024-11-14 | 2024-12-09
R7S1-ESD-M-HVAC-S160 | Chilled Water Piping Second Floor Layout--Preparation & Submission (Type Management) | 18 | 2024-11-14 | 2024-12-09
R7S1-ESD-M-HVAC-S170 | Chilled Water Piping Roof Floor Layout--Preparation & Submission (Type Management) | 18 | 2024-11-14 | 2024-12-09
R7S1-ESD-M-HVAC-S180 | Chilled Water Schematic--Preparation & Submission (Type Management) | 18 | 2024-11-14 | 2024-12-09
R7S1-ESD-M-HVAC-S190 | HVAC Ventilation Schematic--Preparation & Submission (Type Management) | 18 | 2024-11-14 | 2024-12-09
R7S1-ESD-M-HVAC-S200 | HVAC Equipment Schedule--Preparation & Submission (Type Management) | 18 | 2024-11-14 | 2024-12-09
FIRE FIGHTING |  | 14 | 2024-11-10 | 2024-11-27
R7S1-ESD-M-FF-S100 | Ground Floor Plan Fire Fighting Layout--Preparation & Submission (Type Management) | 14 | 2024-11-10 | 2024-11-27
R7S1-ESD-M-FF-S110 | First Floor Fire Fighting Layout--Preparation & Submission (Type Management) | 14 | 2024-11-10 | 2024-11-27
R7S1-ESD-M-FF-S120 | Second Floor Fire Fighting Layout--Preparation & Submission (Type Management) | 14 | 2024-11-10 | 2024-11-27
R7S1-ESD-M-FF-S130 | Roof Floor Fire Fighting Layout--Preparation & Submission (Type Management) | 14 | 2024-11-10 | 2024-11-27
R7S1-ESD-M-FF-S140 | Fire Fighting Schematic Diagram--Preparation & Submission (Type Management) | 14 | 2024-11-10 | 2024-11-27
DRAINAGE |  | 13 | 2024-11-04 | 2024-11-20
R7S1-ESD-M-DR-S100 | Ground Floor Drainage Layout --Preparation & Submission (Type Management) | 13 | 2024-11-04 | 2024-11-20
R7S1-ESD-M-DR-S110 | First Floor Drainage Layout--Preparation & Submission (Type Management) | 13 | 2024-11-04 | 2024-11-20
R7S1-ESD-M-DR-S120 | Second Floor Drainage Layout--Preparation & Submission (Type Management) | 13 | 2024-11-04 | 2024-11-20
R7S1-ESD-M-DR-S130 | Roof Floor Drainage Layout--Preparation & Submission (Type Management) | 13 | 2024-11-04 | 2024-11-20
R7S1-ESD-M-DR-S140 | Drainage Schematic--Preparation & Submission (Type Management) | 13 | 2024-11-04 | 2024-11-20
WATER SUPPLY |  | 27 | 2024-11-04 | 2024-12-10
R7S1-ESD-M-WS-S100 | Water Supply Ground Floor Layout--Preparation & Submission (Type Management) | 27 | 2024-11-04 | 2024-12-10
R7S1-ESD-M-WS-S110 | Water Supply First Floor Layout--Preparation & Submission (Type Management) | 27 | 2024-11-04 | 2024-12-10
R7S1-ESD-M-WS-S120 | Water Supply Second Floor Layout--Preparation & Submission (Type Management) | 27 | 2024-11-04 | 2024-12-10
R7S1-ESD-M-WS-S130 | Water Supply Roof Floor Layout--Preparation & Submission (Type Management) | 27 | 2024-11-04 | 2024-12-10
R7S1-ESD-M-WS-S140 | Water Supplyschematic Layout--Preparation & Submission (Type Management) | 27 | 2024-11-04 | 2024-12-10
ELECTRICAL |  | 49 | 2024-11-04 | 2025-01-09
LIGHTING SYSTEM |  | 1 | 2024-11-11 | 2024-11-11
R7S1-ESD-M-LIG-S100 | Ground Floor Lighting System Layout --Preparation & Submission (Type Management) | 1 | 2024-11-11 | 2024-11-11
R7S1-ESD-M-LIG-S110 | First Floor Lighting System Layout--Preparation & Submission (Type Management) | 1 | 2024-11-11 | 2024-11-11
R7S1-ESD-M-LIG-S120 | Second Floor Lighting Layout --Preparation & Submission (Type Management) | 1 | 2024-11-11 | 2024-11-11
POWER SYSTEM |  | 1 | 2024-11-11 | 2024-11-11
R7S1-ESD-M-POW-S100 | Ground Floor Power System Layout --Preparation & Submission (Type Management) | 1 | 2024-11-11 | 2024-11-11
R7S1-ESD-M-POW-S110 | First Floor Power System Layout --Preparation & Submission (Type Management) | 1 | 2024-11-11 | 2024-11-11
R7S1-ESD-M-POW-S120 | Second Floor Power System Layout--Preparation & Submission (Type Management) | 1 | 2024-11-11 | 2024-11-11
R7S1-ESD-M-POW-S130 | Roof Floor Power System Layout--Preparation & Submission (Type Management) | 1 | 2024-11-11 | 2024-11-11
ICT SYSTEM |  | 2 | 2024-11-10 | 2024-11-11
R7S1-ESD-M-ICT-S100 | Ground Floor Telecom & ICT System Layout --Preparation & Submission (Type Management) | 1 | 2024-11-10 | 2024-11-10
R7S1-ESD-M-ICT-S110 | First Floor Telecom & ICT System Layout --Preparation & Submission (Type Management) | 1 | 2024-11-10 | 2024-11-10
R7S1-ESD-M-ICT-S120 | Second Floor Telecom& ICT System Layout --Preparation & Submission (Type Management) | 1 | 2024-11-10 | 2024-11-10
R7S1-ESD-M-ICT-S130 | Telecom System Schematic Diagram --Preparation & Submission (Type Management) | 1 | 2024-11-10 | 2024-11-10
R7S1-ESD-M-ICT-S140 | ICT System Schematic Diagram --Preparation & Submission (Type Management) | 1 | 2024-11-10 | 2024-11-10
R7S1-ESD-M-ICT-S150 | Single Line Diagram--Preparation & Submission (Type Management) | 1 | 2024-11-11 | 2024-11-11
R7S1-ESD-M-ICT-S160 | Power System Single Line Diagram --Preparation & Submission (Type Management) | 1 | 2024-11-11 | 2024-11-11
FIRE ALARM SYSTEM |  | 45 | 2024-11-10 | 2025-01-09
R7S1-ESD-M-FA-S100 | Ground Floor Fire Alarm & Voice Evacuation System Layout--Preparation & Submission (Type Management) | 45 | 2024-11-10 | 2025-01-09
R7S1-ESD-M-FA-S110 | First Floor Fire Alarm & Voice Evacuation System Layout--Preparation & Submission (Type Management) | 45 | 2024-11-10 | 2025-01-09
R7S1-ESD-M-FA-S120 | Second Floor Fire Alarm & Voice Evacuation System Layout--Preparation & Submission (Type Management) | 45 | 2024-11-10 | 2025-01-09
R7S1-ESD-M-FA-S130 | Fire Alarm & Voice Evacuation System Schematic Diagram --Preparation & Submission (Type Management) | 45 | 2024-11-10 | 2025-01-09
ACCESS CONTROLSYSTEM |  | 1 | 2024-11-10 | 2024-11-10
R7S1-ESD-M-ACC-S100 | Ground Floor Access Control System Layout--Preparation & Submission (Type Management) | 1 | 2024-11-10 | 2024-11-10
R7S1-ESD-M-ACC-S110 | First Floor Access Control System Layout--Preparation & Submission (Type Management) | 1 | 2024-11-10 | 2024-11-10
R7S1-ESD-M-ACC-S120 | Second Floor Access Control System Layout--Preparation & Submission (Type Management) | 1 | 2024-11-10 | 2024-11-10
R7S1-ESD-M-ACC-S130 | Access Control Schematic Diagram--Preparation & Submission (Type Management) | 1 | 2024-11-10 | 2024-11-10
CCTV SYSTEM |  | 1 | 2024-11-10 | 2024-11-10
R7S1-ESD-M-CCT-S100 | CCTV System Ground Floor Layout--Preparation & Submission (Type Management) | 1 | 2024-11-10 | 2024-11-10
R7S1-ESD-M-CCT-S110 | CCTV System First Floor Layout--Preparation & Submission (Type Management) | 1 | 2024-11-10 | 2024-11-10
R7S1-ESD-M-CCT-S120 | CCTV System Second Floor Layout--Preparation & Submission (Type Management) | 1 | 2024-11-10 | 2024-11-10
R7S1-ESD-M-CCT-S130 | CCTV System Schematic Diagram--Preparation & Submission (Type Management) | 1 | 2024-11-10 | 2024-11-10
LIGHTNING PROTECTION SYSTEM |  | 1 | 2024-11-11 | 2024-11-11
R7S1-ESD-M-LPS-S100 | Ground Floor Earthing Protection System Layout--Preparation & Submission (Type Management) | 1 | 2024-11-11 | 2024-11-11
R7S1-ESD-M-LPS-S110 | Roof Floor Lightning Protection System Layout.--Preparation & Submission (Type Management) | 1 | 2024-11-11 | 2024-11-11
INTEGRATED BUILDING MANAGEMENT SYSTEM |  | 9 | 2024-11-04 | 2024-11-14
R7S1-ESD-M-IBM-S100 | Ground Floor IBMS Layout--Preparation & Submission (Type Management) | 9 | 2024-11-04 | 2024-11-14
R7S1-ESD-M-IBM-S110 | First Floor IBMS Layout--Preparation & Submission (Type Management) | 9 | 2024-11-04 | 2024-11-14
R7S1-ESD-M-IBM-S120 | Second Floor IBMS Layout--Preparation & Submission (Type Management) | 9 | 2024-11-04 | 2024-11-14
R7S1-ESD-M-IBM-S130 | Roof Floor IBMS Layout--Preparation & Submission (Type Management) | 9 | 2024-11-04 | 2024-11-14
R7S1-ESD-M-IBM-S140 | IBMS KWHR Riser Diagram--Preparation & Submission (Type Management) | 9 | 2024-11-04 | 2024-11-14
R7S1-ESD-M-IBM-S150 | IBMS BTU, Cold & Hot Water Meter Riser Diagram--Preparation & Submission (Type Management) | 9 | 2024-11-04 | 2024-11-14
R7S1-ESD-M-IBM-S160 | IBMS Schematic Diagram--Preparation & Submission (Type Management) | 9 | 2024-11-04 | 2024-11-14
APPROVAL |  | 134 | 2024-09-11 | 2025-01-22
ARCH. |  | 8 | 2024-11-11 | 2024-11-18
R7S1-ESD-M-AR-A300 | Building Setting-Out And Coordinates - Approval (Type Management) | 8 | 2024-11-11 | 2024-11-18
R7S1-ESD-M-AR-A310 | U - Value Calculation - Approval (Type Management) | 8 | 2024-11-11 | 2024-11-18
R7S1-ESD-M-AR-A320 | Plan - General Arrangement - Ground Floor - Approval (Type Management) | 8 | 2024-11-11 | 2024-11-18
R7S1-ESD-M-AR-A330 | Plan - General Arrangement - Level 1 (FF) - Approval (Type Management) | 8 | 2024-11-11 | 2024-11-18
R7S1-ESD-M-AR-A340 | Plan - General Arrangement - Level 2 (SF) - Approval (Type Management) | 8 | 2024-11-11 | 2024-11-18
R7S1-ESD-M-AR-A350 | Modular Layouts - Ground Floor - Approval (Type Management) | 8 | 2024-11-11 | 2024-11-18
R7S1-ESD-M-AR-A360 | Modular Layouts - Level 1 (FF) - Approval (Type Management) | 8 | 2024-11-11 | 2024-11-18
R7S1-ESD-M-AR-A370 | Modular Layouts - Level 2 (SF) - Approval (Type Management) | 8 | 2024-11-11 | 2024-11-18
R7S1-ESD-M-AR-A380 | Modular Layouts - Roof - Approval (Type Management) | 8 | 2024-11-11 | 2024-11-18
R7S1-ESD-M-AR-A390 | Building Elevations - Approval (Type Management) | 8 | 2024-11-11 | 2024-11-18
R7S1-ESD-M-AR-A400 | Building Sections - Approval (Type Management) | 8 | 2024-11-11 | 2024-11-18
R7S1-ESD-M-AR-A410 | Typical - Floor Finishes Layout - Approval (Type Management) | 8 | 2024-11-11 | 2024-11-18
R7S1-ESD-M-AR-A420 | Typical - Reflected Ceiling Finishes Layout - Approval (Type Management) | 8 | 2024-11-11 | 2024-11-18
R7S1-ESD-M-AR-A430 | Door Schedules - Approval (Type Management) | 8 | 2024-11-11 | 2024-11-18
R7S1-ESD-M-AR-A440 | Window Schedules - Approval (Type Management) | 8 | 2024-11-11 | 2024-11-18
R7S1-ESD-M-AR-A450 | One Bed Apartment Typical Furniture Layout - Approval (Type Management) | 8 | 2024-11-11 | 2024-11-18
R7S1-ESD-M-AR-A460 | Two Bed Apartment Typical Furniture Layout - Approval (Type Management) | 8 | 2024-11-11 | 2024-11-18
R7S1-ESD-M-AR-A470 | Bed Apartment Typical Furniture Layout - Approval (Type Management) | 8 | 2024-11-11 | 2024-11-18
R7S1-ESD-M-AR-A480 | One - Bed Apartment Typical Furniture Layout - Approval (Type Management) | 8 | 2024-11-11 | 2024-11-18
R7S1-ESD-M-AR-A490 | Two - Bed Apartment Typical Furniture Layout - Approval (Type Management) | 8 | 2024-11-11 | 2024-11-18
STR. |  | 24 | 2024-11-11 | 2024-12-04
R7S1-ESD-M-AT-A100 | Ground Floor Loading Diagram--Approval (Type Management) | 24 | 2024-11-11 | 2024-12-04
R7S1-ESD-M-AT-A110 | Typical Cover Slab Loading Diagram--Approval (Type Management) | 24 | 2024-11-11 | 2024-12-04
R7S1-ESD-M-AT-A130 | First Floor Loading Diagram--Approval (Type Management) | 24 | 2024-11-11 | 2024-12-04
R7S1-ESD-M-AT-A140 | Second Floor Loading Diagram--Approval (Type Management) | 24 | 2024-11-11 | 2024-12-04
R7S1-ESD-M-AT-A150 | Roof Floor Loading Diagram--Approval (Type Management) | 24 | 2024-11-11 | 2024-12-04
R7S1-ESD-M-AT-A160 | Foundation Layout --Approval (Type Management) | 24 | 2024-11-11 | 2024-12-04
R7S1-ESD-M-AT-A170 | Top Blinding Layout At Foundation--Approval (Type Management) | 24 | 2024-11-11 | 2024-12-04
R7S1-ESD-M-AT-A180 | Foundation Dowel Layout --Approval (Type Management) | 24 | 2024-11-11 | 2024-12-04
R7S1-ESD-M-AT-A190 | Ground Floor Slab, Beam And Wall Layout--Approval (Type Management) | 24 | 2024-11-11 | 2024-12-04
R7S1-ESD-M-AT-A200 | Ground Floor Slab Connection Layout--Approval (Type Management) | 24 | 2024-11-11 | 2024-12-04
R7S1-ESD-M-AT-A210 | Ground Floor Cover Slab Layout--Approval (Type Management) | 24 | 2024-11-11 | 2024-12-04
R7S1-ESD-M-AT-A220 | First Floor Slab, Beam And Wall Layout--Approval (Type Management) | 24 | 2024-11-11 | 2024-12-04
R7S1-ESD-M-AT-A230 | First Floor Cover Slab Layout--Approval (Type Management) | 24 | 2024-11-11 | 2024-12-04
R7S1-ESD-M-AT-A240 | Second Floor Slab, Beam And Wall Layout--Approval (Type Management) | 24 | 2024-11-11 | 2024-12-04
R7S1-ESD-M-AT-A250 | First & Second Floor Slab Connection Layout--Approval (Type Management) | 24 | 2024-11-11 | 2024-12-04
R7S1-ESD-M-AT-A260 | First & Second Floor Dowel Layout--Approval (Type Management) | 24 | 2024-11-11 | 2024-12-04
R7S1-ESD-M-AT-A270 | Roof Slab And Beams Layout--Approval (Type Management) | 24 | 2024-11-11 | 2024-12-04
R7S1-ESD-M-AT-A280 | Roof Parapet Layout--Approval (Type Management) | 24 | 2024-11-11 | 2024-12-04
R7S1-ESD-M-AT-A290 | Roof Slab Connection Layout--Approval (Type Management) | 24 | 2024-11-11 | 2024-12-04
R7S1-ESD-M-AT-A300 | Foundation Sections--Approval (Type Management) | 24 | 2024-11-11 | 2024-12-04
R7S1-ESD-M-AT-A310 | Pod Structural Details--Approval (Type Management) | 24 | 2024-11-11 | 2024-12-04
R7S1-ESD-M-AT-A320 | Precast Concrete Standard Details--Approval (Type Management) | 24 | 2024-11-11 | 2024-12-04
R7S1-ESD-M-AT-A330 | Schedules--Approval (Type Management) | 24 | 2024-11-11 | 2024-12-04
MECHANICAL |  | 41 | 2024-11-13 | 2024-12-23
HVAC/CHWP |  | 39 | 2024-11-15 | 2024-12-23
R7S1-ESD-M-HVAC-A210 | HVAC Ground Floor Layout--Approval (Type Management) | 39 | 2024-11-15 | 2024-12-23
R7S1-ESD-M-HVAC-A220 | HVAC First Floor Layout--Approval (Type Management) | 39 | 2024-11-15 | 2024-12-23
R7S1-ESD-M-HVAC-A230 | HVAC Second Floor Layout--Approval (Type Management) | 39 | 2024-11-15 | 2024-12-23
R7S1-ESD-M-HVAC-A240 | HVAC Roof Floor Layout--Approval (Type Management) | 39 | 2024-11-15 | 2024-12-23
R7S1-ESD-M-HVAC-A250 | Chilled Water Piping Ground Floor Layout--Approval (Type Management) | 39 | 2024-11-15 | 2024-12-23
R7S1-ESD-M-HVAC-A260 | Chilled Water Piping First Floor Layout--Approval (Type Management) | 39 | 2024-11-15 | 2024-12-23
R7S1-ESD-M-HVAC-A270 | Chilled Water Piping Second Floor Layout--Approval (Type Management) | 39 | 2024-11-15 | 2024-12-23
R7S1-ESD-M-HVAC-A280 | Chilled Water Piping Roof Floor Layout--Approval (Type Management) | 39 | 2024-11-15 | 2024-12-23
R7S1-ESD-M-HVAC-A290 | Chilled Water Schematic--Approval (Type Management) | 39 | 2024-11-15 | 2024-12-23
R7S1-ESD-M-HVAC-A300 | HVAC Ventilation Schematic--Approval (Type Management) | 39 | 2024-11-15 | 2024-12-23
R7S1-ESD-M-HVAC-A310 | HVAC Equipment Schedule--Approval (Type Management) | 39 | 2024-11-15 | 2024-12-23
FIRE FIGHTING |  | 20 | 2024-11-13 | 2024-12-02
R7S1-ESD-M-FF-A150 | Ground Floor Plan Fire Fighting Layout--Approval (Type Management) | 20 | 2024-11-13 | 2024-12-02
R7S1-ESD-M-FF-A160 | First Floor Fire Fighting Layout--Approval (Type Management) | 20 | 2024-11-13 | 2024-12-02
R7S1-ESD-M-FF-A170 | Second Floor Fire Fighting Layout--Approval (Type Management) | 20 | 2024-11-13 | 2024-12-02
R7S1-ESD-M-FF-A180 | Roof Floor Fire Fighting Layout--Approval (Type Management) | 20 | 2024-11-13 | 2024-12-02
R7S1-ESD-M-FF-A190 | Fire Fighting Schematic Diagram--Approval (Type Management) | 20 | 2024-11-13 | 2024-12-02
DRAINAGE |  | 6 | 2024-11-21 | 2024-11-26
R7S1-ESD-M-DR-A150 | Ground Floor Drainage Layout --Approval (Type Management) | 6 | 2024-11-21 | 2024-11-26
R7S1-ESD-M-DR-A160 | First Floor Drainage Layout--Approval (Type Management) | 6 | 2024-11-21 | 2024-11-26
R7S1-ESD-M-DR-A170 | Second Floor Drainage Layout--Approval (Type Management) | 6 | 2024-11-21 | 2024-11-26
R7S1-ESD-M-DR-A180 | Roof Floor Drainage Layout--Approval (Type Management) | 6 | 2024-11-21 | 2024-11-26
R7S1-ESD-M-DR-A190 | Drainage Schematic--Approval (Type Management) | 6 | 2024-11-21 | 2024-11-26
WATER SUPPLY |  | 29 | 2024-11-24 | 2024-12-22
R7S1-ESD-M-WS-A150 | Water Supply Ground Floor Layout--Approval (Type Management) | 29 | 2024-11-24 | 2024-12-22
R7S1-ESD-M-WS-A160 | Water Supply First Floor Layout--Approval (Type Management) | 29 | 2024-11-24 | 2024-12-22
R7S1-ESD-M-WS-A170 | Water Supply Second Floor Layout--Approval (Type Management) | 29 | 2024-11-24 | 2024-12-22
R7S1-ESD-M-WS-A180 | Water Supply Roof Floor Layout--Approval (Type Management) | 29 | 2024-11-24 | 2024-12-22
R7S1-ESD-M-WS-A190 | Water Supplyschematic Layout--Approval (Type Management) | 29 | 2024-11-24 | 2024-12-22
ELECTRICAL |  | 134 | 2024-09-11 | 2025-01-22
LIGHTING SYSTEM |  | 9 | 2024-11-12 | 2024-11-20
R7S1-ESD-M-LIG-A130 | Ground Floor Lighting System Layout --Approval (Type Management) | 9 | 2024-11-12 | 2024-11-20
R7S1-ESD-M-LIG-A140 | First Floor Lighting System Layout--Approval (Type Management) | 9 | 2024-11-12 | 2024-11-20
R7S1-ESD-M-LIG-A150 | Second Floor Lighting Layout --Approval (Type Management) | 9 | 2024-11-12 | 2024-11-20
POWER SYSTEM |  | 9 | 2024-11-12 | 2024-11-20
R7S1-ESD-M-POW-A140 | Ground Floor Power System Layout --Approval (Type Management) | 9 | 2024-11-12 | 2024-11-20
R7S1-ESD-M-POW-A150 | First Floor Power System Layout --Approval (Type Management) | 9 | 2024-11-12 | 2024-11-20
R7S1-ESD-M-POW-A160 | Second Floor Power System Layout--Approval (Type Management) | 9 | 2024-11-12 | 2024-11-20
R7S1-ESD-M-POW-A170 | Roof Floor Power System Layout--Approval (Type Management) | 9 | 2024-11-12 | 2024-11-20
ICT SYSTEM |  | 71 | 2024-09-11 | 2024-11-20
R7S1-ESD-M-ICT-A170 | Ground Floor Telecom & ICT System Layout --Approval (Type Management) | 71 | 2024-09-11 | 2024-11-20
R7S1-ESD-M-ICT-A180 | First Floor Telecom & ICT System Layout --Approval (Type Management) | 71 | 2024-09-11 | 2024-11-20
R7S1-ESD-M-ICT-A190 | Second Floor Telecom& ICT System Layout --Approval (Type Management) | 71 | 2024-09-11 | 2024-11-20
R7S1-ESD-M-ICT-A200 | Telecom System Schematic Diagram --Approval (Type Management) | 71 | 2024-09-11 | 2024-11-20
R7S1-ESD-M-ICT-A210 | ICT System Schematic Diagram --Approval (Type Management) | 71 | 2024-09-11 | 2024-11-20
R7S1-ESD-M-ICT-A220 | Single Line Diagram--Approval (Type Management) | 9 | 2024-11-12 | 2024-11-20
R7S1-ESD-M-ICT-A230 | Power System Single Line Diagram --Approval (Type Management) | 9 | 2024-11-12 | 2024-11-20
FIRE ALARM SYSTEM |  | 134 | 2024-09-11 | 2025-01-22
R7S1-ESD-M-FA-A140 | Ground Floor Fire Alarm & Voice Evacuation System Layout--Approval (Type Management) | 134 | 2024-09-11 | 2025-01-22
R7S1-ESD-M-FA-A150 | First Floor Fire Alarm & Voice Evacuation System Layout--Approval (Type Management) | 134 | 2024-09-11 | 2025-01-22
R7S1-ESD-M-FA-A160 | Second Floor Fire Alarm & Voice Evacuation System Layout--Approval (Type Management) | 134 | 2024-09-11 | 2025-01-22
R7S1-ESD-M-FA-A170 | Fire Alarm & Voice Evacuation System Schematic Diagram --Approval (Type Management) | 134 | 2024-09-11 | 2025-01-22
ACCESS CONTROLSYSTEM |  | 11 | 2024-11-10 | 2024-11-20
R7S1-ESD-M-ACC-A140 | Ground Floor Access Control System Layout--Approval (Type Management) | 11 | 2024-11-10 | 2024-11-20
R7S1-ESD-M-ACC-A150 | First Floor Access Control System Layout--Approval (Type Management) | 11 | 2024-11-10 | 2024-11-20
R7S1-ESD-M-ACC-A160 | Second Floor Access Control System Layout--Approval (Type Management) | 11 | 2024-11-10 | 2024-11-20
R7S1-ESD-M-ACC-A170 | Access Control Schematic Diagram--Approval (Type Management) | 11 | 2024-11-10 | 2024-11-20
CCTV SYSTEM |  | 10 | 2024-11-11 | 2024-11-20
R7S1-ESD-M-CCT-A140 | CCTV System Ground Floor Layout--Approval (Type Management) | 10 | 2024-11-11 | 2024-11-20
R7S1-ESD-M-CCT-A150 | CCTV System First Floor Layout--Approval (Type Management) | 10 | 2024-11-11 | 2024-11-20
R7S1-ESD-M-CCT-A160 | CCTV System Second Floor Layout--Approval (Type Management) | 10 | 2024-11-11 | 2024-11-20
R7S1-ESD-M-CCT-A170 | CCTV System Schematic Diagram--Approval (Type Management) | 10 | 2024-11-11 | 2024-11-20
LIGHTNING PROTECTION SYSTEM |  | 9 | 2024-11-12 | 2024-11-20
R7S1-ESD-M-LPS-A120 | Ground Floor Earthing Protection System Layout--Approval (Type Management) | 9 | 2024-11-12 | 2024-11-20
R7S1-ESD-M-LPS-A130 | Roof Floor Lightning Protection System Layout.--Approval (Type Management) | 9 | 2024-11-12 | 2024-11-20
INTEGRATED BUILDING MANAGEMENT SYSTEM |  | 9 | 2024-11-17 | 2024-11-25
R7S1-ESD-M-IBM-A170 | Ground Floor IBMS Layout--Approval (Type Management) | 9 | 2024-11-17 | 2024-11-25
R7S1-ESD-M-IBM-A180 | First Floor IBMS Layout--Approval (Type Management) | 9 | 2024-11-17 | 2024-11-25
R7S1-ESD-M-IBM-A190 | Second Floor IBMS Layout--Approval (Type Management) | 9 | 2024-11-17 | 2024-11-25
R7S1-ESD-M-IBM-A200 | Roof Floor IBMS Layout--Approval (Type Management) | 9 | 2024-11-17 | 2024-11-25
R7S1-ESD-M-IBM-A210 | IBMS KWHR Riser Diagram--Approval (Type Management) | 9 | 2024-11-17 | 2024-11-25
R7S1-ESD-M-IBM-A220 | IBMS BTU, Cold & Hot Water Meter Riser Diagram--Approval (Type Management) | 9 | 2024-11-17 | 2024-11-25
R7S1-ESD-M-IBM-A230 | IBMS Schematic Diagram--Approval (Type Management) | 9 | 2024-11-17 | 2024-11-25
LINEAR STUDIOS APARTMENTS BUILDINGS (STUDIOS - TYPE LARGE) |  | 186 | 2024-11-11 | 2025-05-16
PREPARATION & SUBMISSION |  | 101 | 2024-11-11 | 2025-03-31
ARCH. |  | 33 | 2025-01-05 | 2025-02-18
R7S1-ESD-SL-AR-S300 | Building Setting-Out And Coordinates - Preparation & Submission (Studio - Large) | 33 | 2025-01-05 | 2025-02-18
R7S1-ESD-SL-AR-S310 | U - Value Calculation - Preparation & Submission (Studio - Large) | 33 | 2025-01-05 | 2025-02-18
R7S1-ESD-SL-AR-S320 | Plan - General Arrangement - Ground Floor - Preparation & Submission (Studio - Large) | 33 | 2025-01-05 | 2025-02-18
R7S1-ESD-SL-AR-S330 | Plan - General Arrangement - Level 1 (FF) - Preparation & Submission (Studio - Large) | 33 | 2025-01-05 | 2025-02-18
R7S1-ESD-SL-AR-S340 | Plan - General Arrangement - Level 2 (SF) - Preparation & Submission (Studio - Large) | 33 | 2025-01-05 | 2025-02-18
R7S1-ESD-SL-AR-S350 | Modular Layouts - Ground Floor - Preparation & Submission (Studio - Large) | 33 | 2025-01-05 | 2025-02-18
R7S1-ESD-SL-AR-S360 | Modular Layouts - Level 1 (FF) - Preparation & Submission (Studio - Large) | 33 | 2025-01-05 | 2025-02-18
R7S1-ESD-SL-AR-S370 | Modular Layouts - Level 2 (SF) - Preparation & Submission (Studio - Large) | 33 | 2025-01-05 | 2025-02-18
R7S1-ESD-SL-AR-S380 | Modular Layouts - Roof - Preparation & Submission (Studio - Large) | 33 | 2025-01-05 | 2025-02-18
R7S1-ESD-SL-AR-S390 | Building Elevations - Preparation & Submission (Studio - Large) | 29 | 2025-01-09 | 2025-02-18
R7S1-ESD-SL-AR-S400 | Building Sections - Preparation & Submission (Studio - Large) | 33 | 2025-01-05 | 2025-02-18
R7S1-ESD-SL-AR-S410 | Typical - Floor Finishes Layout - Preparation & Submission (Studio - Large) | 33 | 2025-01-05 | 2025-02-18
R7S1-ESD-SL-AR-S420 | Typical - Reflected Ceiling Finishes Layout - Preparation & Submission (Studio - Large) | 29 | 2025-01-09 | 2025-02-18
R7S1-ESD-SL-AR-S430 | Door Schedules - Preparation & Submission (Studio - Large) | 33 | 2025-01-05 | 2025-02-18
R7S1-ESD-SL-AR-S440 | Window Schedules - Preparation & Submission (Studio - Large) | 33 | 2025-01-05 | 2025-02-18
R7S1-ESD-SL-AR-S450 | One Bed Apartment Typical Furniture Layout - Preparation & Submission (Studio - Large) | 29 | 2025-01-09 | 2025-02-18
R7S1-ESD-SL-AR-S460 | Two Bed Apartment Typical Furniture Layout - Preparation & Submission (Studio - Large) | 29 | 2025-01-09 | 2025-02-18
R7S1-ESD-SL-AR-S470 | Bed Apartment Typical Furniture Layout - Preparation & Submission (Studio - Large) | 29 | 2025-01-09 | 2025-02-18
R7S1-ESD-SL-AR-S480 | One - Bed Apartment Typical Furniture Layout - Preparation & Submission (Studio - Large) | 29 | 2025-01-09 | 2025-02-18
R7S1-ESD-SL-AR-S490 | Two - Bed Apartment Typical Furniture Layout - Preparation & Submission (Studio - Large) | 29 | 2025-01-09 | 2025-02-18
STR. |  | 1 | 2025-03-24 | 2025-03-24
R7S1-ESD-SL-ST-S540 | Ground Floor Loading Diagram--Preparation & Submission (Studio - Large) | 1 | 2025-03-24 | 2025-03-24
R7S1-ESD-SL-ST-S550 | Typical Cover Slab Loading Diagram--Preparation & Submission (Studio - Large) | 1 | 2025-03-24 | 2025-03-24
R7S1-ESD-SL-ST-S560 | First Floor Loading Diagram--Preparation & Submission (Studio - Large) | 1 | 2025-03-24 | 2025-03-24
R7S1-ESD-SL-ST-S570 | Second Floor Loading Diagram--Preparation & Submission (Studio - Large) | 1 | 2025-03-24 | 2025-03-24
R7S1-ESD-SL-ST-S580 | Roof Floor Loading Diagram--Preparation & Submission (Studio - Large) | 1 | 2025-03-24 | 2025-03-24
R7S1-ESD-SL-ST-S590 | Foundation Layout --Preparation & Submission (Studio - Large) | 1 | 2025-03-24 | 2025-03-24
R7S1-ESD-SL-ST-S600 | Top Blinding Layout At Foundation--Preparation & Submission (Studio - Large) | 1 | 2025-03-24 | 2025-03-24
R7S1-ESD-SL-ST-S610 | Foundation Dowel Layout --Preparation & Submission (Studio - Large) | 1 | 2025-03-24 | 2025-03-24
R7S1-ESD-SL-ST-S620 | Ground Floor Slab, Beam And Wall Layout--Preparation & Submission (Studio - Large) | 1 | 2025-03-24 | 2025-03-24
R7S1-ESD-SL-ST-S630 | Ground Floor Slab Connection Layout--Preparation & Submission (Studio - Large) | 1 | 2025-03-24 | 2025-03-24
R7S1-ESD-SL-ST-S640 | Ground Floor Cover Slab Layout--Preparation & Submission (Studio - Large) | 1 | 2025-03-24 | 2025-03-24
R7S1-ESD-SL-ST-S650 | First Floor Slab, Beam And Wall Layout--Preparation & Submission (Studio - Large) | 1 | 2025-03-24 | 2025-03-24
R7S1-ESD-SL-ST-S660 | First Floor Cover Slab Layout--Preparation & Submission (Studio - Large) | 1 | 2025-03-24 | 2025-03-24
R7S1-ESD-SL-ST-S670 | Second Floor Slab, Beam And Wall Layout--Preparation & Submission (Studio - Large) | 1 | 2025-03-24 | 2025-03-24
R7S1-ESD-SL-ST-S680 | First & Second Floor Slab Connection Layout--Preparation & Submission (Studio - Large) | 1 | 2025-03-24 | 2025-03-24
R7S1-ESD-SL-ST-S690 | First & Second Floor Dowel Layout--Preparation & Submission (Studio - Large) | 1 | 2025-03-24 | 2025-03-24
R7S1-ESD-SL-ST-S700 | Roof Slab And Beams Layout--Preparation & Submission (Studio - Large) | 1 | 2025-03-24 | 2025-03-24
R7S1-ESD-SL-ST-S710 | Roof Parapet Layout--Preparation & Submission (Studio - Large) | 1 | 2025-03-24 | 2025-03-24
R7S1-ESD-SL-ST-S720 | Roof Slab Connection Layout--Preparation & Submission (Studio - Large) | 1 | 2025-03-24 | 2025-03-24
R7S1-ESD-SL-ST-S730 | Foundation Sections--Preparation & Submission (Studio - Large) | 1 | 2025-03-24 | 2025-03-24
R7S1-ESD-SL-ST-S740 | Pod Structural Details--Preparation & Submission (Studio - Large) | 1 | 2025-03-24 | 2025-03-24
R7S1-ESD-SL-ST-S750 | Precast Concrete Standard Details--Preparation & Submission (Studio - Large) | 1 | 2025-03-24 | 2025-03-24
R7S1-ESD-SL-ST-S760 | Schedules--Preparation & Submission (Studio - Large) | 1 | 2025-03-24 | 2025-03-24
MECHANICAL |  | 63 | 2025-01-02 | 2025-03-31
HVAC/CHWP |  | 46 | 2025-01-15 | 2025-03-19
R7S1-ESD-SL-HVA-S50 | Chilled Water Piping Ground Floor Layout--Preparation & Submission (Studio - Large) | 37 | 2025-01-15 | 2025-03-06
R7S1-ESD-SL-HVA-S60 | Chilled Water Piping First Floor Layout--Preparation & Submission (Studio - Large) | 37 | 2025-01-15 | 2025-03-06
R7S1-ESD-SL-HVA-S70 | Chilled Water Piping Second Floor Layout--Preparation & Submission (Studio - Large) | 37 | 2025-01-15 | 2025-03-06
R7S1-ESD-SL-HVA-S80 | Chilled Water Piping Roof Floor Layout--Preparation & Submission (Studio - Large) | 37 | 2025-01-15 | 2025-03-06
R7S1-ESD-SL-HVA-S90 | Chilled Water Schematic--Preparation & Submission (Studio - Large) | 37 | 2025-01-15 | 2025-03-06
R7S1-ESD-SL-HVA-S98 | HVAC Equipment Schedule--Preparation & Submission (Studio - Large) | 37 | 2025-01-15 | 2025-03-06
R7S1-ESD-SL-HVA-S10 | HVAC Ground Floor Layout--Preparation & Submission (Studio - Large) | 46 | 2025-01-15 | 2025-03-19
R7S1-ESD-SL-HVA-S20 | HVAC First Floor Layout--Preparation & Submission (Studio - Large) | 46 | 2025-01-15 | 2025-03-19
R7S1-ESD-SL-HVA-S30 | HVAC Second Floor Layout--Preparation & Submission (Studio - Large) | 46 | 2025-01-15 | 2025-03-19
R7S1-ESD-SL-HVA-S40 | HVAC Roof Floor Layout--Preparation & Submission (Studio - Large) | 46 | 2025-01-15 | 2025-03-19
R7S1-ESD-SL-HVA-S95 | HVAC Ventilation Schematic--Preparation & Submission (Studio - Large) | 46 | 2025-01-15 | 2025-03-19
FIRE FIGHTING |  | 60 | 2025-01-02 | 2025-03-26
R7S1-ESD-SL-FF-S150 | Ground Floor Plan Fire Fighting Layout--Preparation & Submission (Studio - Large) | 60 | 2025-01-02 | 2025-03-26
R7S1-ESD-SL-FF-S160 | First Floor Fire Fighting Layout--Preparation & Submission (Studio - Large) | 60 | 2025-01-02 | 2025-03-26
R7S1-ESD-SL-FF-S170 | Second Floor Fire Fighting Layout--Preparation & Submission (Studio - Large) | 60 | 2025-01-02 | 2025-03-26
R7S1-ESD-SL-FF-S180 | Roof Floor Fire Fighting Layout--Preparation & Submission (Studio - Large) | 60 | 2025-01-02 | 2025-03-26
R7S1-ESD-SL-FF-S190 | Fire Fighting Schematic Diagram--Preparation & Submission (Studio - Large) | 60 | 2025-01-02 | 2025-03-26
DRAINAGE |  | 63 | 2025-01-02 | 2025-03-31
R7S1-ESD-SL-DR-S150 | Ground Floor Drainage Layout --Preparation & Submission (Studio - Large) | 63 | 2025-01-02 | 2025-03-31
R7S1-ESD-SL-DR-S160 | First Floor Drainage Layout--Preparation & Submission (Studio - Large) | 63 | 2025-01-02 | 2025-03-31
R7S1-ESD-SL-DR-S170 | Second Floor Drainage Layout--Preparation & Submission (Studio - Large) | 63 | 2025-01-02 | 2025-03-31
R7S1-ESD-SL-DR-S180 | Roof Floor Drainage Layout--Preparation & Submission (Studio - Large) | 63 | 2025-01-02 | 2025-03-31
R7S1-ESD-SL-DR-S190 | Drainage Schematic--Preparation & Submission (Studio - Large) | 63 | 2025-01-02 | 2025-03-31
WATER SUPPLY |  | 63 | 2025-01-02 | 2025-03-31
R7S1-ESD-SL-WS-S150 | Water Supply Ground Floor Layout--Preparation & Submission (Studio - Large) | 63 | 2025-01-02 | 2025-03-31
R7S1-ESD-SL-WS-S160 | Water Supply First Floor Layout--Preparation & Submission (Studio - Large) | 63 | 2025-01-02 | 2025-03-31
R7S1-ESD-SL-WS-S170 | Water Supply Second Floor Layout--Preparation & Submission (Studio - Large) | 63 | 2025-01-02 | 2025-03-31
R7S1-ESD-SL-WS-S180 | Water Supply Roof Floor Layout--Preparation & Submission (Studio - Large) | 63 | 2025-01-02 | 2025-03-31
R7S1-ESD-SL-WS-S190 | Water Supplyschematic Layout--Preparation & Submission (Studio - Large) | 63 | 2025-01-02 | 2025-03-31
ELECTRICAL |  | 87 | 2024-11-11 | 2025-03-11
LIGHTING SYSTEM |  | 45 | 2025-01-02 | 2025-03-05
R7S1-ESD-SL-LIG-S130 | Ground Floor Lighting System Layout --Preparation & Submission (Studio - Large) | 45 | 2025-01-02 | 2025-03-05
R7S1-ESD-SL-LIG-S140 | First Floor Lighting System Layout--Preparation & Submission (Studio - Large) | 45 | 2025-01-02 | 2025-03-05
R7S1-ESD-SL-LIG-S150 | Second Floor Lighting Layout --Preparation & Submission (Studio - Large) | 45 | 2025-01-02 | 2025-03-05
POWER SYSTEM |  | 46 | 2025-01-02 | 2025-03-06
R7S1-ESD-SL-POW-S140 | Ground Floor Power System Layout --Preparation & Submission (Studio - Large) | 46 | 2025-01-02 | 2025-03-06
R7S1-ESD-SL-POW-S150 | First Floor Power System Layout --Preparation & Submission (Studio - Large) | 46 | 2025-01-02 | 2025-03-06
R7S1-ESD-SL-POW-S160 | Second Floor Power System Layout--Preparation & Submission (Studio - Large) | 46 | 2025-01-02 | 2025-03-06
R7S1-ESD-SL-POW-S170 | Roof Floor Power System Layout--Preparation & Submission (Studio - Large) | 46 | 2025-01-02 | 2025-03-06
ICT SYSTEM |  | 51 | 2024-12-29 | 2025-03-09
R7S1-ESD-SL-ICT-S170 | Ground Floor Telecom & ICT System Layout --Preparation & Submission (Studio - Large) | 51 | 2024-12-29 | 2025-03-09
R7S1-ESD-SL-ICT-S180 | First Floor Telecom & ICT System Layout --Preparation & Submission (Studio - Large) | 51 | 2024-12-29 | 2025-03-09
R7S1-ESD-SL-ICT-S190 | Second Floor Telecom& ICT System Layout --Preparation & Submission (Studio - Large) | 51 | 2024-12-29 | 2025-03-09
R7S1-ESD-SL-ICT-S200 | Telecom System Schematic Diagram --Preparation & Submission (Studio - Large) | 51 | 2024-12-29 | 2025-03-09
R7S1-ESD-SL-ICT-S210 | ICT System Schematic Diagram --Preparation & Submission (Studio - Large) | 51 | 2024-12-29 | 2025-03-09
R7S1-ESD-SL-ICT-S220 | Single Line Diagram--Preparation & Submission (Studio - Large) | 51 | 2024-12-29 | 2025-03-09
R7S1-ESD-SL-ICT-S230 | Power System Single Line Diagram --Preparation & Submission (Studio - Large) | 51 | 2024-12-29 | 2025-03-09
FIRE ALARM SYSTEM |  | 53 | 2024-12-29 | 2025-03-11
R7S1-ESD-SL-FA-S140 | Ground Floor Fire Alarm & Voice Evacuation System Layout--Preparation & Submission (Studio - Large) | 53 | 2024-12-29 | 2025-03-11
R7S1-ESD-SL-FA-S150 | First Floor Fire Alarm & Voice Evacuation System Layout--Preparation & Submission (Studio - Large) | 53 | 2024-12-29 | 2025-03-11
R7S1-ESD-SL-FA-S160 | Second Floor Fire Alarm & Voice Evacuation System Layout--Preparation & Submission (Studio - Large) | 53 | 2024-12-29 | 2025-03-11
R7S1-ESD-SL-FA-S170 | Fire Alarm & Voice Evacuation System Schematic Diagram --Preparation & Submission (Studio - Large) | 53 | 2024-12-29 | 2025-03-11
ACCESS CONTROLSYSTEM |  | 50 | 2024-12-29 | 2025-03-06
R7S1-ESD-SL-ACC-S140 | Ground Floor Access Control System Layout--Preparation & Submission (Studio - Large) | 50 | 2024-12-29 | 2025-03-06
R7S1-ESD-SL-ACC-S150 | First Floor Access Control System Layout--Preparation & Submission (Studio - Large) | 50 | 2024-12-29 | 2025-03-06
R7S1-ESD-SL-ACC-S160 | Second Floor Access Control System Layout--Preparation & Submission (Studio - Large) | 50 | 2024-12-29 | 2025-03-06
R7S1-ESD-SL-ACC-S170 | Access Control Schematic Diagram--Preparation & Submission (Studio - Large) | 50 | 2024-12-29 | 2025-03-06
CCTV SYSTEM |  | 50 | 2024-12-29 | 2025-03-06
R7S1-ESD-SL-CCT-S140 | CCTV System Ground Floor Layout--Preparation & Submission (Studio - Large) | 50 | 2024-12-29 | 2025-03-06
R7S1-ESD-SL-CCT-S150 | CCTV System First Floor Layout--Preparation & Submission (Studio - Large) | 50 | 2024-12-29 | 2025-03-06
R7S1-ESD-SL-CCT-S160 | CCTV System Second Floor Layout--Preparation & Submission (Studio - Large) | 50 | 2024-12-29 | 2025-03-06
R7S1-ESD-SL-CCT-S170 | CCTV System Schematic Diagram--Preparation & Submission (Studio - Large) | 50 | 2024-12-29 | 2025-03-06
LIGHTNING PROTECTION SYSTEM |  | 1 | 2024-11-11 | 2024-11-11
R7S1-ESD-SL-LPS-S120 | Ground Floor Earthing Protection System Layout--Preparation & Submission (Studio - Large) | 1 | 2024-11-11 | 2024-11-11
R7S1-ESD-SL-LPS-S130 | Roof Floor Lightning Protection System Layout.--Preparation & Submission (Studio - Large) | 1 | 2024-11-11 | 2024-11-11
INTEGRATED BUILDING MANAGEMENT SYSTEM |  | 49 | 2025-01-02 | 2025-03-11
R7S1-ESD-SL-IBM-S170 | Ground Floor IBMS Layout--Preparation & Submission (Studio - Large) | 49 | 2025-01-02 | 2025-03-11
R7S1-ESD-SL-IBM-S180 | First Floor IBMS Layout--Preparation & Submission (Studio - Large) | 49 | 2025-01-02 | 2025-03-11
R7S1-ESD-SL-IBM-S190 | Second Floor IBMS Layout--Preparation & Submission (Studio - Large) | 49 | 2025-01-02 | 2025-03-11
R7S1-ESD-SL-IBM-S200 | Roof Floor IBMS Layout--Preparation & Submission (Studio - Large) | 49 | 2025-01-02 | 2025-03-11
R7S1-ESD-SL-IBM-S210 | IBMS KWHR Riser Diagram--Preparation & Submission (Studio - Large) | 49 | 2025-01-02 | 2025-03-11
R7S1-ESD-SL-IBM-S220 | IBMS BTU, Cold & Hot Water Meter Riser Diagram--Preparation & Submission (Studio - Large) | 49 | 2025-01-02 | 2025-03-11
R7S1-ESD-SL-IBM-S230 | IBMS Schematic Diagram--Preparation & Submission (Studio - Large) | 49 | 2025-01-02 | 2025-03-11
APPROVAL |  | 186 | 2024-11-11 | 2025-05-16
ARCH. |  | 41 | 2025-01-17 | 2025-02-26
R7S1-ESD-SL-AR-A500 | Building Setting-Out And Coordinates - Approval (Studio - Large) | 41 | 2025-01-17 | 2025-02-26
R7S1-ESD-SL-AR-A510 | U - Value Calculation - Approval (Studio - Large) | 41 | 2025-01-17 | 2025-02-26
R7S1-ESD-SL-AR-A520 | Plan - General Arrangement - Ground Floor - Approval (Studio - Large) | 41 | 2025-01-17 | 2025-02-26
R7S1-ESD-SL-AR-A530 | Plan - General Arrangement - Level 1 (FF) - Approval (Studio - Large) | 41 | 2025-01-17 | 2025-02-26
R7S1-ESD-SL-AR-A540 | Plan - General Arrangement - Level 2 (SF) - Approval (Studio - Large) | 41 | 2025-01-17 | 2025-02-26
R7S1-ESD-SL-AR-A550 | Modular Layouts - Ground Floor - Approval (Studio - Large) | 41 | 2025-01-17 | 2025-02-26
R7S1-ESD-SL-AR-A560 | Modular Layouts - Level 1 (FF) - Approval (Studio - Large) | 41 | 2025-01-17 | 2025-02-26
R7S1-ESD-SL-AR-A570 | Modular Layouts - Level 2 (SF) - Approval (Studio - Large) | 41 | 2025-01-17 | 2025-02-26
R7S1-ESD-SL-AR-A580 | Modular Layouts - Roof - Approval (Studio - Large) | 41 | 2025-01-17 | 2025-02-26
R7S1-ESD-SL-AR-A590 | Building Elevations - Approval (Studio - Large) | 41 | 2025-01-17 | 2025-02-26
R7S1-ESD-SL-AR-A600 | Building Sections - Approval (Studio - Large) | 41 | 2025-01-17 | 2025-02-26
R7S1-ESD-SL-AR-A610 | Typical - Floor Finishes Layout - Approval (Studio - Large) | 41 | 2025-01-17 | 2025-02-26
R7S1-ESD-SL-AR-A620 | Typical - Reflected Ceiling Finishes Layout - Approval (Studio - Large) | 41 | 2025-01-17 | 2025-02-26
R7S1-ESD-SL-AR-A630 | Door Schedules - Approval (Studio - Large) | 41 | 2025-01-17 | 2025-02-26
R7S1-ESD-SL-AR-A640 | Window Schedules - Approval (Studio - Large) | 41 | 2025-01-17 | 2025-02-26
R7S1-ESD-SL-AR-A650 | One Bed Apartment Typical Furniture Layout - Approval (Studio - Large) | 41 | 2025-01-17 | 2025-02-26
R7S1-ESD-SL-AR-A660 | Two Bed Apartment Typical Furniture Layout - Approval (Studio - Large) | 41 | 2025-01-17 | 2025-02-26
R7S1-ESD-SL-AR-A670 | Bed Apartment Typical Furniture Layout - Approval (Studio - Large) | 41 | 2025-01-17 | 2025-02-26
R7S1-ESD-SL-AR-A680 | One - Bed Apartment Typical Furniture Layout - Approval (Studio - Large) | 41 | 2025-01-17 | 2025-02-26
R7S1-ESD-SL-AR-A690 | Two - Bed Apartment Typical Furniture Layout - Approval (Studio - Large) | 41 | 2025-01-17 | 2025-02-26
STR. |  | 10 | 2025-03-25 | 2025-04-03
R7S1-ESD-SL-AT-A340 | Ground Floor Loading Diagram--Approval (Studio - Large) | 10 | 2025-03-25 | 2025-04-03
R7S1-ESD-SL-AT-A350 | Typical Cover Slab Loading Diagram--Approval (Studio - Large) | 10 | 2025-03-25 | 2025-04-03
R7S1-ESD-SL-AT-A360 | First Floor Loading Diagram--Approval (Studio - Large) | 10 | 2025-03-25 | 2025-04-03
R7S1-ESD-SL-AT-A370 | Second Floor Loading Diagram--Approval (Studio - Large) | 10 | 2025-03-25 | 2025-04-03
R7S1-ESD-SL-AT-A380 | Roof Floor Loading Diagram--Approval (Studio - Large) | 10 | 2025-03-25 | 2025-04-03
R7S1-ESD-SL-AT-A390 | Foundation Layout --Approval (Studio - Large) | 10 | 2025-03-25 | 2025-04-03
R7S1-ESD-SL-AT-A400 | Top Blinding Layout At Foundation--Approval (Studio - Large) | 10 | 2025-03-25 | 2025-04-03
R7S1-ESD-SL-AT-A410 | Foundation Dowel Layout --Approval (Studio - Large) | 10 | 2025-03-25 | 2025-04-03
R7S1-ESD-SL-AT-A420 | Ground Floor Slab, Beam And Wall Layout--Approval (Studio - Large) | 10 | 2025-03-25 | 2025-04-03
R7S1-ESD-SL-AT-A430 | Ground Floor Slab Connection Layout--Approval (Studio - Large) | 10 | 2025-03-25 | 2025-04-03
R7S1-ESD-SL-AT-A440 | Ground Floor Cover Slab Layout--Approval (Studio - Large) | 10 | 2025-03-25 | 2025-04-03
R7S1-ESD-SL-AT-A450 | First Floor Slab, Beam And Wall Layout--Approval (Studio - Large) | 10 | 2025-03-25 | 2025-04-03
R7S1-ESD-SL-AT-A460 | First Floor Cover Slab Layout--Approval (Studio - Large) | 10 | 2025-03-25 | 2025-04-03
R7S1-ESD-SL-AT-A470 | Second Floor Slab, Beam And Wall Layout--Approval (Studio - Large) | 10 | 2025-03-25 | 2025-04-03
R7S1-ESD-SL-AT-A480 | First & Second Floor Slab Connection Layout--Approval (Studio - Large) | 10 | 2025-03-25 | 2025-04-03
R7S1-ESD-SL-AT-A490 | First & Second Floor Dowel Layout--Approval (Studio - Large) | 10 | 2025-03-25 | 2025-04-03
R7S1-ESD-SL-AT-A500 | Roof Slab And Beams Layout--Approval (Studio - Large) | 10 | 2025-03-25 | 2025-04-03
R7S1-ESD-SL-AT-A510 | Roof Parapet Layout--Approval (Studio - Large) | 10 | 2025-03-25 | 2025-04-03
R7S1-ESD-SL-AT-A520 | Roof Slab Connection Layout--Approval (Studio - Large) | 10 | 2025-03-25 | 2025-04-03
R7S1-ESD-SL-AT-A530 | Foundation Sections--Approval (Studio - Large) | 10 | 2025-03-25 | 2025-04-03
R7S1-ESD-SL-AT-A540 | Pod Structural Details--Approval (Studio - Large) | 10 | 2025-03-25 | 2025-04-03
R7S1-ESD-SL-AT-A550 | Precast Concrete Standard Details--Approval (Studio - Large) | 10 | 2025-03-25 | 2025-04-03
R7S1-ESD-SL-AT-A560 | Schedules--Approval (Studio - Large) | 10 | 2025-03-25 | 2025-04-03
MECHANICAL |  | 80 | 2025-02-25 | 2025-05-16
HVAC/CHWP |  | 68 | 2025-03-06 | 2025-05-13
R7S1-ESD-SL-HVA-A50 | Chilled Water Piping Ground Floor Layout--Approval (Studio - Large) | 7 | 2025-03-06 | 2025-03-12
R7S1-ESD-SL-HVA-A60 | Chilled Water Piping First Floor Layout--Approval (Studio - Large) | 7 | 2025-03-06 | 2025-03-12
R7S1-ESD-SL-HVA-A70 | Chilled Water Piping Second Floor Layout--Approval (Studio - Large) | 7 | 2025-03-06 | 2025-03-12
R7S1-ESD-SL-HVA-A80 | Chilled Water Piping Roof Floor Layout--Approval (Studio - Large) | 7 | 2025-03-06 | 2025-03-12
R7S1-ESD-SL-HVA-A90 | Chilled Water Schematic--Approval (Studio - Large) | 7 | 2025-03-06 | 2025-03-12
R7S1-ESD-SL-HVA-A10 | HVAC Ground Floor Layout--Approval (Studio - Large) | 50 | 2025-03-20 | 2025-05-08
R7S1-ESD-SL-HVA-A20 | HVAC First Floor Layout--Approval (Studio - Large) | 50 | 2025-03-20 | 2025-05-08
R7S1-ESD-SL-HVA-A30 | HVAC Second Floor Layout--Approval (Studio - Large) | 50 | 2025-03-20 | 2025-05-08
R7S1-ESD-SL-HVA-A40 | HVAC Roof Floor Layout--Approval (Studio - Large) | 50 | 2025-03-20 | 2025-05-08
R7S1-ESD-SL-HVA-A95 | HVAC Ventilation Schematic--Approval (Studio - Large) | 50 | 2025-03-20 | 2025-05-08
R7S1-ESD-SL-HVA-A98 | HVAC Equipment Schedule--Approval (Studio - Large) | 68 | 2025-03-06 | 2025-05-13
FIRE FIGHTING |  | 35 | 2025-03-10 | 2025-04-13
R7S1-ESD-SL-FF-A200 | Ground Floor Plan Fire Fighting Layout--Approval (Studio - Large) | 35 | 2025-03-10 | 2025-04-13
R7S1-ESD-SL-FF-A210 | First Floor Fire Fighting Layout--Approval (Studio - Large) | 35 | 2025-03-10 | 2025-04-13
R7S1-ESD-SL-FF-A220 | Second Floor Fire Fighting Layout--Approval (Studio - Large) | 35 | 2025-03-10 | 2025-04-13
R7S1-ESD-SL-FF-A230 | Roof Floor Fire Fighting Layout--Approval (Studio - Large) | 35 | 2025-03-10 | 2025-04-13
R7S1-ESD-SL-FF-A240 | Fire Fighting Schematic Diagram--Approval (Studio - Large) | 35 | 2025-03-10 | 2025-04-13
DRAINAGE |  | 78 | 2025-02-27 | 2025-05-15
R7S1-ESD-SL-DR-A200 | Ground Floor Drainage Layout --Approval (Studio - Large) | 78 | 2025-02-27 | 2025-05-15
R7S1-ESD-SL-DR-A210 | First Floor Drainage Layout--Approval (Studio - Large) | 78 | 2025-02-27 | 2025-05-15
R7S1-ESD-SL-DR-A220 | Second Floor Drainage Layout--Approval (Studio - Large) | 78 | 2025-02-27 | 2025-05-15
R7S1-ESD-SL-DR-A230 | Roof Floor Drainage Layout--Approval (Studio - Large) | 78 | 2025-02-27 | 2025-05-15
R7S1-ESD-SL-DR-A240 | Drainage Schematic--Approval (Studio - Large) | 78 | 2025-02-27 | 2025-05-15
WATER SUPPLY |  | 80 | 2025-02-25 | 2025-05-16
R7S1-ESD-SL-WS-A200 | Water Supply Ground Floor Layout--Approval (Studio - Large) | 80 | 2025-02-25 | 2025-05-16
R7S1-ESD-SL-WS-A210 | Water Supply First Floor Layout--Approval (Studio - Large) | 80 | 2025-02-25 | 2025-05-16
R7S1-ESD-SL-WS-A220 | Water Supply Second Floor Layout--Approval (Studio - Large) | 80 | 2025-02-25 | 2025-05-16
R7S1-ESD-SL-WS-A230 | Water Supply Roof Floor Layout--Approval (Studio - Large) | 80 | 2025-02-25 | 2025-05-16
R7S1-ESD-SL-WS-A240 | Water Supplyschematic Layout--Approval (Studio - Large) | 80 | 2025-02-25 | 2025-05-16
ELECTRICAL |  | 144 | 2024-11-11 | 2025-04-03
LIGHTING SYSTEM |  | 14 | 2025-03-06 | 2025-03-19
R7S1-ESD-SL-LIG-A160 | Ground Floor Lighting System Layout --Approval (Studio - Large) | 14 | 2025-03-06 | 2025-03-19
R7S1-ESD-SL-LIG-A170 | First Floor Lighting System Layout--Approval (Studio - Large) | 14 | 2025-03-06 | 2025-03-19
R7S1-ESD-SL-LIG-A180 | Second Floor Lighting Layout --Approval (Studio - Large) | 14 | 2025-03-06 | 2025-03-19
POWER SYSTEM |  | 14 | 2025-03-06 | 2025-03-19
R7S1-ESD-SL-POW-A180 | Ground Floor Power System Layout --Approval (Studio - Large) | 14 | 2025-03-06 | 2025-03-19
R7S1-ESD-SL-POW-A190 | First Floor Power System Layout --Approval (Studio - Large) | 14 | 2025-03-06 | 2025-03-19
R7S1-ESD-SL-POW-A200 | Second Floor Power System Layout--Approval (Studio - Large) | 14 | 2025-03-06 | 2025-03-19
R7S1-ESD-SL-POW-A210 | Roof Floor Power System Layout--Approval (Studio - Large) | 14 | 2025-03-06 | 2025-03-19
ICT SYSTEM |  | 25 | 2025-03-10 | 2025-04-03
R7S1-ESD-SL-ICT-A240 | Ground Floor Telecom & ICT System Layout --Approval (Studio - Large) | 25 | 2025-03-10 | 2025-04-03
R7S1-ESD-SL-ICT-A250 | First Floor Telecom & ICT System Layout --Approval (Studio - Large) | 25 | 2025-03-10 | 2025-04-03
R7S1-ESD-SL-ICT-A260 | Second Floor Telecom& ICT System Layout --Approval (Studio - Large) | 25 | 2025-03-10 | 2025-04-03
R7S1-ESD-SL-ICT-A270 | Telecom System Schematic Diagram --Approval (Studio - Large) | 25 | 2025-03-10 | 2025-04-03
R7S1-ESD-SL-ICT-A280 | ICT System Schematic Diagram --Approval (Studio - Large) | 25 | 2025-03-10 | 2025-04-03
R7S1-ESD-SL-ICT-A290 | Single Line Diagram--Approval (Studio - Large) | 25 | 2025-03-10 | 2025-04-03
R7S1-ESD-SL-ICT-A300 | Power System Single Line Diagram --Approval (Studio - Large) | 25 | 2025-03-10 | 2025-04-03
FIRE ALARM SYSTEM |  | 23 | 2025-03-12 | 2025-04-03
R7S1-ESD-SL-FA-A180 | Ground Floor Fire Alarm & Voice Evacuation System Layout--Approval (Studio - Large) | 23 | 2025-03-12 | 2025-04-03
R7S1-ESD-SL-FA-A190 | First Floor Fire Alarm & Voice Evacuation System Layout--Approval (Studio - Large) | 23 | 2025-03-12 | 2025-04-03
R7S1-ESD-SL-FA-A200 | Second Floor Fire Alarm & Voice Evacuation System Layout--Approval (Studio - Large) | 23 | 2025-03-12 | 2025-04-03
R7S1-ESD-SL-FA-A210 | Fire Alarm & Voice Evacuation System Schematic Diagram--Approval (Studio - Large) | 23 | 2025-03-12 | 2025-04-03
ACCESS CONTROLSYSTEM |  | 27 | 2025-03-08 | 2025-04-03
R7S1-ESD-SL-ACC-A180 | Ground Floor Access Control System Layout--Approval (Studio - Large) | 27 | 2025-03-08 | 2025-04-03
R7S1-ESD-SL-ACC-A190 | First Floor Access Control System Layout--Approval (Studio - Large) | 27 | 2025-03-08 | 2025-04-03
R7S1-ESD-SL-ACC-A200 | Second Floor Access Control System Layout--Approval (Studio - Large) | 27 | 2025-03-08 | 2025-04-03
R7S1-ESD-SL-ACC-A210 | Access Control Schematic Diagram--Approval (Studio - Large) | 27 | 2025-03-08 | 2025-04-03
CCTV SYSTEM |  | 18 | 2025-03-06 | 2025-03-23
R7S1-ESD-SL-CCT-A180 | CCTV System Ground Floor Layout--Approval (Studio - Large) | 18 | 2025-03-06 | 2025-03-23
R7S1-ESD-SL-CCT-A190 | CCTV System First Floor Layout--Approval (Studio - Large) | 18 | 2025-03-06 | 2025-03-23
R7S1-ESD-SL-CCT-A200 | CCTV System Second Floor Layout--Approval (Studio - Large) | 18 | 2025-03-06 | 2025-03-23
R7S1-ESD-SL-CCT-A210 | CCTV System Schematic Diagram--Approval (Studio - Large) | 18 | 2025-03-06 | 2025-03-23
LIGHTNING PROTECTION SYSTEM |  | 10 | 2024-11-11 | 2024-11-20
R7S1-ESD-SL-LPS-A140 | Ground Floor Earthing Protection System Layout--Approval (Studio - Large) | 9 | 2024-11-12 | 2024-11-20
R7S1-ESD-SL-LPS-A150 | Roof Floor Lightning Protection System Layout.--Approval (Studio - Large) | 10 | 2024-11-11 | 2024-11-20
INTEGRATED BUILDING MANAGEMENT SYSTEM |  | 23 | 2025-03-12 | 2025-04-03
R7S1-ESD-SL-IBM-A240 | Ground Floor IBMS Layout--Approval (Studio - Large) | 23 | 2025-03-12 | 2025-04-03
R7S1-ESD-SL-IBM-A250 | First Floor IBMS Layout--Approval (Studio - Large) | 23 | 2025-03-12 | 2025-04-03
R7S1-ESD-SL-IBM-A260 | Second Floor IBMS Layout--Approval (Studio - Large) | 23 | 2025-03-12 | 2025-04-03
R7S1-ESD-SL-IBM-A270 | Roof Floor IBMS Layout--Approval (Studio - Large) | 23 | 2025-03-12 | 2025-04-03
R7S1-ESD-SL-IBM-A280 | IBMS KWHR Riser Diagram--Approval (Studio - Large) | 23 | 2025-03-12 | 2025-04-03
R7S1-ESD-SL-IBM-A290 | IBMS BTU, Cold & Hot Water Meter Riser Diagram--Approval (Studio - Large) | 23 | 2025-03-12 | 2025-04-03
R7S1-ESD-SL-IBM-A300 | IBMS Schematic Diagram--Approval (Studio - Large) | 23 | 2025-03-12 | 2025-04-03
LINEAR STUDIOS APARTMENTS BUILDINGS (STUDIOS - TYPE MEDIUM) |  | 108 | 2025-01-26 | 2025-05-13
PREPARATION & SUBMISSION |  | 54 | 2025-01-26 | 2025-04-16
ARCH. |  | 25 | 2025-02-02 | 2025-03-06
R7S1-ESD-SM-AR-S500 | Building Setting-Out And Coordinates - Preparation & Submission (Studio - Medium) | 25 | 2025-02-02 | 2025-03-06
R7S1-ESD-SM-AR-S510 | U - Value Calculation - Preparation & Submission (Studio - Medium) | 25 | 2025-02-02 | 2025-03-06
R7S1-ESD-SM-AR-S520 | Plan - General Arrangement - Ground Floor - Preparation & Submission (Studio - Medium) | 25 | 2025-02-02 | 2025-03-06
R7S1-ESD-SM-AR-S530 | Plan - General Arrangement - Level 1 (FF) - Preparation & Submission (Studio - Medium) | 25 | 2025-02-02 | 2025-03-06
R7S1-ESD-SM-AR-S540 | Plan - General Arrangement - Level 2 (SF) - Preparation & Submission (Studio - Medium) | 25 | 2025-02-02 | 2025-03-06
R7S1-ESD-SM-AR-S550 | Modular Layouts - Ground Floor - Preparation & Submission (Studio - Medium) | 25 | 2025-02-02 | 2025-03-06
R7S1-ESD-SM-AR-S560 | Modular Layouts - Level 1 (FF) - Preparation & Submission (Studio - Medium) | 25 | 2025-02-02 | 2025-03-06
R7S1-ESD-SM-AR-S570 | Modular Layouts - Level 2 (SF) - Preparation & Submission (Studio - Medium) | 25 | 2025-02-02 | 2025-03-06
R7S1-ESD-SM-AR-S580 | Modular Layouts - Roof - Preparation & Submission (Studio - Medium) | 25 | 2025-02-02 | 2025-03-06
R7S1-ESD-SM-AR-S590 | Building Elevations - Preparation & Submission (Studio - Medium) | 18 | 2025-02-11 | 2025-03-06
R7S1-ESD-SM-AR-S600 | Building Sections - Preparation & Submission (Studio - Medium) | 18 | 2025-02-11 | 2025-03-06
R7S1-ESD-SM-AR-S610 | Typical - Floor Finishes Layout - Preparation & Submission (Studio - Medium) | 25 | 2025-02-02 | 2025-03-06
R7S1-ESD-SM-AR-S620 | Typical - Reflected Ceiling Finishes Layout - Preparation & Submission (Studio - Medium) | 25 | 2025-02-02 | 2025-03-06
R7S1-ESD-SM-AR-S630 | Door Schedules - Preparation & Submission (Studio - Medium) | 25 | 2025-02-02 | 2025-03-06
R7S1-ESD-SM-AR-S640 | Window Schedules - Preparation & Submission (Studio - Medium) | 25 | 2025-02-02 | 2025-03-06
R7S1-ESD-SM-AR-S650 | One Bed Apartment Typical Furniture Layout - Preparation & Submission (Studio - Medium) | 18 | 2025-02-11 | 2025-03-06
R7S1-ESD-SM-AR-S660 | Two Bed Apartment Typical Furniture Layout - Preparation & Submission (Studio - Medium) | 18 | 2025-02-11 | 2025-03-06
R7S1-ESD-SM-AR-S670 | Bed Apartment Typical Furniture Layout - Preparation & Submission (Studio - Medium) | 18 | 2025-02-11 | 2025-03-06
R7S1-ESD-SM-AR-S680 | One - Bed Apartment Typical Furniture Layout - Preparation & Submission (Studio - Medium) | 18 | 2025-02-11 | 2025-03-06
R7S1-ESD-SM-AR-S690 | Two - Bed Apartment Typical Furniture Layout - Preparation & Submission (Studio - Medium) | 18 | 2025-02-11 | 2025-03-06
STR. |  | 6 | 2025-03-30 | 2025-04-13
R7S1-ESD-SM-ST-S770 | Ground Floor Loading Diagram--Preparation & Submission (Studio - Medium) | 6 | 2025-03-30 | 2025-04-13
R7S1-ESD-SM-ST-S780 | Typical Cover Slab Loading Diagram--Preparation & Submission (Studio - Medium) | 6 | 2025-03-30 | 2025-04-13
R7S1-ESD-SM-ST-S790 | First Floor Loading Diagram--Preparation & Submission (Studio - Medium) | 6 | 2025-03-30 | 2025-04-13
R7S1-ESD-SM-ST-S800 | Second Floor Loading Diagram--Preparation & Submission (Studio - Medium) | 6 | 2025-03-30 | 2025-04-13
R7S1-ESD-SM-ST-S810 | Roof Floor Loading Diagram--Preparation & Submission (Studio - Medium) | 6 | 2025-03-30 | 2025-04-13
R7S1-ESD-SM-ST-S820 | Foundation Layout --Preparation & Submission (Studio - Medium) | 6 | 2025-03-30 | 2025-04-13
R7S1-ESD-SM-ST-S830 | Top Blinding Layout At Foundation--Preparation & Submission (Studio - Medium) | 6 | 2025-03-30 | 2025-04-13
R7S1-ESD-SM-ST-S840 | Foundation Dowel Layout --Preparation & Submission (Studio - Medium) | 6 | 2025-03-30 | 2025-04-13
R7S1-ESD-SM-ST-S850 | Ground Floor Slab, Beam And Wall Layout--Preparation & Submission (Studio - Medium) | 6 | 2025-03-30 | 2025-04-13
R7S1-ESD-SM-ST-S860 | Ground Floor Slab Connection Layout--Preparation & Submission (Studio - Medium) | 6 | 2025-03-30 | 2025-04-13
R7S1-ESD-SM-ST-S870 | Ground Floor Cover Slab Layout--Preparation & Submission (Studio - Medium) | 6 | 2025-03-30 | 2025-04-13
R7S1-ESD-SM-ST-S880 | First Floor Slab, Beam And Wall Layout--Preparation & Submission (Studio - Medium) | 6 | 2025-03-30 | 2025-04-13
R7S1-ESD-SM-ST-S890 | First Floor Cover Slab Layout--Preparation & Submission (Studio - Medium) | 6 | 2025-03-30 | 2025-04-13
R7S1-ESD-SM-ST-S900 | Second Floor Slab, Beam And Wall Layout--Preparation & Submission (Studio - Medium) | 6 | 2025-03-30 | 2025-04-13
R7S1-ESD-SM-ST-S910 | First & Second Floor Slab Connection Layout--Preparation & Submission (Studio - Medium) | 6 | 2025-03-30 | 2025-04-13
R7S1-ESD-SM-ST-S920 | First & Second Floor Dowel Layout--Preparation & Submission (Studio - Medium) | 6 | 2025-03-30 | 2025-04-13
R7S1-ESD-SM-ST-S930 | Roof Slab And Beams Layout--Preparation & Submission (Studio - Medium) | 6 | 2025-03-30 | 2025-04-13
R7S1-ESD-SM-ST-S940 | Roof Parapet Layout--Preparation & Submission (Studio - Medium) | 6 | 2025-03-30 | 2025-04-13
R7S1-ESD-SM-ST-S950 | Roof Slab Connection Layout--Preparation & Submission (Studio - Medium) | 6 | 2025-03-30 | 2025-04-13
R7S1-ESD-SM-ST-S960 | Foundation Sections--Preparation & Submission (Studio - Medium) | 6 | 2025-03-30 | 2025-04-13
R7S1-ESD-SM-ST-S970 | Pod Structural Details--Preparation & Submission (Studio - Medium) | 6 | 2025-03-30 | 2025-04-13
R7S1-ESD-SM-ST-S980 | Precast Concrete Standard Details--Preparation & Submission (Studio - Medium) | 6 | 2025-03-30 | 2025-04-13
R7S1-ESD-SM-ST-S990 | Schedules--Preparation & Submission (Studio - Medium) | 6 | 2025-03-30 | 2025-04-13
MECHANICAL |  | 49 | 2025-02-02 | 2025-04-16
HVAC/CHWP |  | 29 | 2025-02-09 | 2025-03-19
R7S1-ESD-SM-HVAC-S50 | Chilled Water Piping Ground Floor Layout--Preparation & Submission (Studio - Medium) | 17 | 2025-02-09 | 2025-03-03
R7S1-ESD-SM-HVAC-S60 | Chilled Water Piping First Floor Layout--Preparation & Submission (Studio - Medium) | 17 | 2025-02-09 | 2025-03-03
R7S1-ESD-SM-HVAC-S70 | Chilled Water Piping Second Floor Layout--Preparation & Submission (Studio - Medium) | 17 | 2025-02-09 | 2025-03-03
R7S1-ESD-SM-HVAC-S80 | Chilled Water Piping Roof Floor Layout--Preparation & Submission (Studio - Medium) | 17 | 2025-02-09 | 2025-03-03
R7S1-ESD-SM-HVAC-S90 | Chilled Water Schematic--Preparation & Submission (Studio - Medium) | 17 | 2025-02-09 | 2025-03-03
R7S1-ESD-SM-HVAC-S98 | HVAC Equipment Schedule--Preparation & Submission (Studio - Medium) | 7 | 2025-02-23 | 2025-03-03
R7S1-ESD-SM-HVAC-S10 | HVAC Ground Floor Layout--Preparation & Submission (Studio - Medium) | 19 | 2025-02-23 | 2025-03-19
R7S1-ESD-SM-HVAC-S20 | HVAC First Floor Layout--Preparation & Submission (Studio - Medium) | 19 | 2025-02-23 | 2025-03-19
R7S1-ESD-SM-HVAC-S30 | HVAC Second Floor Layout--Preparation & Submission (Studio - Medium) | 19 | 2025-02-23 | 2025-03-19
R7S1-ESD-SM-HVAC-S40 | HVAC Roof Floor Layout--Preparation & Submission (Studio - Medium) | 19 | 2025-02-23 | 2025-03-19
R7S1-ESD-SM-HVAC-S95 | HVAC Ventilation Schematic--Preparation & Submission (Studio - Medium) | 19 | 2025-02-23 | 2025-03-19
FIRE FIGHTING |  | 16 | 2025-02-23 | 2025-03-16
R7S1-ESD-SM-FF-S200 | Ground Floor Plan Fire Fighting Layout--Preparation & Submission (Studio - Medium) | 16 | 2025-02-23 | 2025-03-16
R7S1-ESD-SM-FF-S210 | First Floor Fire Fighting Layout--Preparation & Submission (Studio - Medium) | 16 | 2025-02-23 | 2025-03-16
R7S1-ESD-SM-FF-S220 | Second Floor Fire Fighting Layout--Preparation & Submission (Studio - Medium) | 16 | 2025-02-23 | 2025-03-16
R7S1-ESD-SM-FF-S230 | Roof Floor Fire Fighting Layout--Preparation & Submission (Studio - Medium) | 16 | 2025-02-23 | 2025-03-16
R7S1-ESD-SM-FF-S240 | Fire Fighting Schematic Diagram--Preparation & Submission (Studio - Medium) | 16 | 2025-02-23 | 2025-03-16
DRAINAGE |  | 49 | 2025-02-02 | 2025-04-16
R7S1-ESD-SM-DR-S200 | Ground Floor Drainage Layout --Preparation & Submission (Studio - Medium) | 49 | 2025-02-02 | 2025-04-16
R7S1-ESD-SM-DR-S210 | First Floor Drainage Layout--Preparation & Submission (Studio - Medium) | 49 | 2025-02-02 | 2025-04-16
R7S1-ESD-SM-DR-S220 | Second Floor Drainage Layout--Preparation & Submission (Studio - Medium) | 49 | 2025-02-02 | 2025-04-16
R7S1-ESD-SM-DR-S230 | Roof Floor Drainage Layout--Preparation & Submission (Studio - Medium) | 49 | 2025-02-02 | 2025-04-16
R7S1-ESD-SM-DR-S240 | Drainage Schematic--Preparation & Submission (Studio - Medium) | 49 | 2025-02-02 | 2025-04-16
WATER SUPPLY |  | 23 | 2025-02-27 | 2025-03-31
R7S1-ESD-SM-WS-S200 | Water Supply Ground Floor Layout--Preparation & Submission (Studio - Medium) | 23 | 2025-02-27 | 2025-03-31
R7S1-ESD-SM-WS-S210 | Water Supply First Floor Layout--Preparation & Submission (Studio - Medium) | 23 | 2025-02-27 | 2025-03-31
R7S1-ESD-SM-WS-S220 | Water Supply Second Floor Layout--Preparation & Submission (Studio - Medium) | 23 | 2025-02-27 | 2025-03-31
R7S1-ESD-SM-WS-S230 | Water Supply Roof Floor Layout--Preparation & Submission (Studio - Medium) | 23 | 2025-02-27 | 2025-03-31
R7S1-ESD-SM-WS-S240 | Water Supplyschematic Layout--Preparation & Submission (Studio - Medium) | 23 | 2025-02-27 | 2025-03-31
ELECTRICAL |  | 37 | 2025-01-26 | 2025-03-17
LIGHTING SYSTEM |  | 30 | 2025-02-02 | 2025-03-13
R7S1-ESD-SM-LIG-S160 | Ground Floor Lighting System Layout --Preparation & Submission (Studio - Medium) | 30 | 2025-02-02 | 2025-03-13
R7S1-ESD-SM-LIG-S170 | First Floor Lighting System Layout--Preparation & Submission (Studio - Medium) | 30 | 2025-02-02 | 2025-03-13
R7S1-ESD-SM-LIG-S180 | Second Floor Lighting Layout --Preparation & Submission (Studio - Medium) | 30 | 2025-02-02 | 2025-03-13
POWER SYSTEM |  | 30 | 2025-02-02 | 2025-03-13
R7S1-ESD-SM-POW-S180 | Ground Floor Power System Layout --Preparation & Submission (Studio - Medium) | 30 | 2025-02-02 | 2025-03-13
R7S1-ESD-SM-POW-S190 | First Floor Power System Layout --Preparation & Submission (Studio - Medium) | 30 | 2025-02-02 | 2025-03-13
R7S1-ESD-SM-POW-S200 | Second Floor Power System Layout--Preparation & Submission (Studio - Medium) | 30 | 2025-02-02 | 2025-03-13
R7S1-ESD-SM-POW-S210 | Roof Floor Power System Layout--Preparation & Submission (Studio - Medium) | 30 | 2025-02-02 | 2025-03-13
ICT SYSTEM |  | 30 | 2025-02-02 | 2025-03-13
R7S1-ESD-SM-ICT-S240 | Ground Floor Telecom & ICT System Layout --Preparation & Submission (Studio - Medium) | 30 | 2025-02-02 | 2025-03-13
R7S1-ESD-SM-ICT-S250 | First Floor Telecom & ICT System Layout --Preparation & Submission (Studio - Medium) | 30 | 2025-02-02 | 2025-03-13
R7S1-ESD-SM-ICT-S260 | Second Floor Telecom& ICT System Layout --Preparation & Submission (Studio - Medium) | 30 | 2025-02-02 | 2025-03-13
R7S1-ESD-SM-ICT-S270 | Telecom System Schematic Diagram --Preparation & Submission (Studio - Medium) | 30 | 2025-02-02 | 2025-03-13
R7S1-ESD-SM-ICT-S280 | ICT System Schematic Diagram --Preparation & Submission (Studio - Medium) | 30 | 2025-02-02 | 2025-03-13
R7S1-ESD-SM-ICT-S290 | Single Line Diagram--Preparation & Submission (Studio - Medium) | 30 | 2025-02-02 | 2025-03-13
R7S1-ESD-SM-ICT-S300 | Power System Single Line Diagram --Preparation & Submission (Studio - Medium) | 30 | 2025-02-02 | 2025-03-13
FIRE ALARM SYSTEM |  | 36 | 2025-01-26 | 2025-03-16
R7S1-ESD-SM-FA-S180 | Ground Floor Fire Alarm & Voice Evacuation System Layout--Preparation & Submission (Studio - Medium) | 36 | 2025-01-26 | 2025-03-16
R7S1-ESD-SM-FA-S190 | First Floor Fire Alarm & Voice Evacuation System Layout--Preparation & Submission (Studio - Medium) | 36 | 2025-01-26 | 2025-03-16
R7S1-ESD-SM-FA-S200 | Second Floor Fire Alarm & Voice Evacuation System Layout--Preparation & Submission (Studio - Medium) | 36 | 2025-01-26 | 2025-03-16
R7S1-ESD-SM-FA-S210 | Fire Alarm & Voice Evacuation System Schematic Diagram --Preparation & Submission (Studio - Medium) | 36 | 2025-01-26 | 2025-03-16
ACCESS CONTROLSYSTEM |  | 30 | 2025-02-02 | 2025-03-13
R7S1-ESD-SM-ACC-S180 | Ground Floor Access Control System Layout--Preparation & Submission (Studio - Medium) | 30 | 2025-02-02 | 2025-03-13
R7S1-ESD-SM-ACC-S190 | First Floor Access Control System Layout--Preparation & Submission (Studio - Medium) | 30 | 2025-02-02 | 2025-03-13
R7S1-ESD-SM-ACC-S200 | Second Floor Access Control System Layout--Preparation & Submission (Studio - Medium) | 30 | 2025-02-02 | 2025-03-13
R7S1-ESD-SM-ACC-S210 | Access Control Schematic Diagram--Preparation & Submission (Studio - Medium) | 30 | 2025-02-02 | 2025-03-13
CCTV SYSTEM |  | 32 | 2025-01-29 | 2025-03-13
R7S1-ESD-SM-CCT-S180 | CCTV System Ground Floor Layout--Preparation & Submission (Studio - Medium) | 32 | 2025-01-29 | 2025-03-13
R7S1-ESD-SM-CCT-S190 | CCTV System First Floor Layout--Preparation & Submission (Studio - Medium) | 30 | 2025-02-02 | 2025-03-13
R7S1-ESD-SM-CCT-S200 | CCTV System Second Floor Layout--Preparation & Submission (Studio - Medium) | 30 | 2025-02-02 | 2025-03-13
R7S1-ESD-SM-CCT-S210 | CCTV System Schematic Diagram--Preparation & Submission (Studio - Medium) | 30 | 2025-02-02 | 2025-03-13
LIGHTNING PROTECTION SYSTEM |  | 11 | 2025-02-27 | 2025-03-13
R7S1-ESD-SM-LPS-S140 | Ground Floor Earthing Protection System Layout--Preparation & Submission (Studio - Medium) | 11 | 2025-02-27 | 2025-03-13
R7S1-ESD-SM-LPS-S150 | Roof Floor Lightning Protection System Layout.--Preparation & Submission (Studio - Medium) | 11 | 2025-02-27 | 2025-03-13
INTEGRATED BUILDING MANAGEMENT SYSTEM |  | 28 | 2025-02-06 | 2025-03-17
R7S1-ESD-SM-IBM-S240 | Ground Floor IBMS Layout--Preparation & Submission (Studio - Medium) | 20 | 2025-02-18 | 2025-03-17
R7S1-ESD-SM-IBM-S250 | First Floor IBMS Layout--Preparation & Submission (Studio - Medium) | 28 | 2025-02-06 | 2025-03-17
R7S1-ESD-SM-IBM-S260 | Second Floor IBMS Layout--Preparation & Submission (Studio - Medium) | 28 | 2025-02-06 | 2025-03-17
R7S1-ESD-SM-IBM-S270 | Roof Floor IBMS Layout--Preparation & Submission (Studio - Medium) | 28 | 2025-02-06 | 2025-03-17
R7S1-ESD-SM-IBM-S280 | IBMS KWHR Riser Diagram--Preparation & Submission (Studio - Medium) | 28 | 2025-02-06 | 2025-03-17
R7S1-ESD-SM-IBM-S290 | IBMS BTU, Cold & Hot Water Meter Riser Diagram--Preparation & Submission (Studio - Medium) | 28 | 2025-02-06 | 2025-03-17
R7S1-ESD-SM-IBM-S300 | IBMS Schematic Diagram--Preparation & Submission (Studio - Medium) | 28 | 2025-02-06 | 2025-03-17
APPROVAL |  | 89 | 2025-02-14 | 2025-05-13
ARCH. |  | 27 | 2025-02-14 | 2025-03-12
R7S1-ESD-SM-AR-A700 | Building Setting-Out And Coordinates - Approval (Studio - Medium) | 4 | 2025-03-09 | 2025-03-12
R7S1-ESD-SM-AR-A710 | U - Value Calculation - Approval (Studio - Medium) | 4 | 2025-03-09 | 2025-03-12
R7S1-ESD-SM-AR-A720 | Plan - General Arrangement - Ground Floor - Approval (Studio - Medium) | 4 | 2025-03-09 | 2025-03-12
R7S1-ESD-SM-AR-A730 | Plan - General Arrangement - Level 1 (FF) - Approval (Studio - Medium) | 4 | 2025-03-09 | 2025-03-12
R7S1-ESD-SM-AR-A740 | Plan - General Arrangement - Level 2 (SF) - Approval (Studio - Medium) | 4 | 2025-03-09 | 2025-03-12
R7S1-ESD-SM-AR-A750 | Modular Layouts - Ground Floor - Approval (Studio - Medium) | 27 | 2025-02-14 | 2025-03-12
R7S1-ESD-SM-AR-A760 | Modular Layouts - Level 1 (FF) - Approval (Studio - Medium) | 4 | 2025-03-09 | 2025-03-12
R7S1-ESD-SM-AR-A770 | Modular Layouts - Level 2 (SF) - Approval (Studio - Medium) | 4 | 2025-03-09 | 2025-03-12
R7S1-ESD-SM-AR-A780 | Modular Layouts - Roof - Approval (Studio - Medium) | 4 | 2025-03-09 | 2025-03-12
R7S1-ESD-SM-AR-A790 | Building Elevations - Approval (Studio - Medium) | 4 | 2025-03-09 | 2025-03-12
R7S1-ESD-SM-AR-A800 | Building Sections - Approval (Studio - Medium) | 4 | 2025-03-09 | 2025-03-12
R7S1-ESD-SM-AR-A810 | Typical - Floor Finishes Layout - Approval (Studio - Medium) | 4 | 2025-03-09 | 2025-03-12
R7S1-ESD-SM-AR-A820 | Typical - Reflected Ceiling Finishes Layout - Approval (Studio - Medium) | 4 | 2025-03-09 | 2025-03-12
R7S1-ESD-SM-AR-A830 | Door Schedules - Approval (Studio - Medium) | 4 | 2025-03-09 | 2025-03-12
R7S1-ESD-SM-AR-A840 | Window Schedules - Approval (Studio - Medium) | 4 | 2025-03-09 | 2025-03-12
R7S1-ESD-SM-AR-A850 | One Bed Apartment Typical Furniture Layout - Approval (Studio - Medium) | 4 | 2025-03-09 | 2025-03-12
R7S1-ESD-SM-AR-A860 | Two Bed Apartment Typical Furniture Layout - Approval (Studio - Medium) | 4 | 2025-03-09 | 2025-03-12
R7S1-ESD-SM-AR-A870 | Bed Apartment Typical Furniture Layout - Approval (Studio - Medium) | 4 | 2025-03-09 | 2025-03-12
R7S1-ESD-SM-AR-A880 | One - Bed Apartment Typical Furniture Layout - Approval (Studio - Medium) | 4 | 2025-03-09 | 2025-03-12
R7S1-ESD-SM-AR-A890 | Two - Bed Apartment Typical Furniture Layout - Approval (Studio - Medium) | 4 | 2025-03-09 | 2025-03-12
STR. |  | 1 | 2025-04-03 | 2025-04-03
R7S1-ESD-SM-AT-A570 | Ground Floor Loading Diagram--Approval (Studio - Medium) | 1 | 2025-04-03 | 2025-04-03
R7S1-ESD-SM-AT-A580 | Typical Cover Slab Loading Diagram--Approval (Studio - Medium) | 1 | 2025-04-03 | 2025-04-03
R7S1-ESD-SM-AT-A590 | First Floor Loading Diagram--Approval (Studio - Medium) | 1 | 2025-04-03 | 2025-04-03
R7S1-ESD-SM-AT-A600 | Second Floor Loading Diagram--Approval (Studio - Medium) | 1 | 2025-04-03 | 2025-04-03
R7S1-ESD-SM-AT-A610 | Roof Floor Loading Diagram--Approval (Studio - Medium) | 1 | 2025-04-03 | 2025-04-03
R7S1-ESD-SM-AT-A620 | Foundation Layout --Approval (Studio - Medium) | 1 | 2025-04-03 | 2025-04-03
R7S1-ESD-SM-AT-A630 | Top Blinding Layout At Foundation--Approval (Studio - Medium) | 1 | 2025-04-03 | 2025-04-03
R7S1-ESD-SM-AT-A640 | Foundation Dowel Layout --Approval (Studio - Medium) | 1 | 2025-04-03 | 2025-04-03
R7S1-ESD-SM-AT-A650 | Ground Floor Slab, Beam And Wall Layout--Approval (Studio - Medium) | 1 | 2025-04-03 | 2025-04-03
R7S1-ESD-SM-AT-A660 | Ground Floor Slab Connection Layout--Approval (Studio - Medium) | 1 | 2025-04-03 | 2025-04-03
R7S1-ESD-SM-AT-A670 | Ground Floor Cover Slab Layout--Approval (Studio - Medium) | 1 | 2025-04-03 | 2025-04-03
R7S1-ESD-SM-AT-A680 | First Floor Slab, Beam And Wall Layout--Approval (Studio - Medium) | 1 | 2025-04-03 | 2025-04-03
R7S1-ESD-SM-AT-A690 | First Floor Cover Slab Layout--Approval (Studio - Medium) | 1 | 2025-04-03 | 2025-04-03
R7S1-ESD-SM-AT-A700 | Second Floor Slab, Beam And Wall Layout--Approval (Studio - Medium) | 1 | 2025-04-03 | 2025-04-03
R7S1-ESD-SM-AT-A710 | First & Second Floor Slab Connection Layout--Approval (Studio - Medium) | 1 | 2025-04-03 | 2025-04-03
R7S1-ESD-SM-AT-A720 | First & Second Floor Dowel Layout--Approval (Studio - Medium) | 1 | 2025-04-03 | 2025-04-03
R7S1-ESD-SM-AT-A730 | Roof Slab And Beams Layout--Approval (Studio - Medium) | 1 | 2025-04-03 | 2025-04-03
R7S1-ESD-SM-AT-A740 | Roof Parapet Layout--Approval (Studio - Medium) | 1 | 2025-04-03 | 2025-04-03
R7S1-ESD-SM-AT-A750 | Roof Slab Connection Layout--Approval (Studio - Medium) | 1 | 2025-04-03 | 2025-04-03
R7S1-ESD-SM-AT-A760 | Foundation Sections--Approval (Studio - Medium) | 1 | 2025-04-03 | 2025-04-03
R7S1-ESD-SM-AT-A770 | Pod Structural Details--Approval (Studio - Medium) | 1 | 2025-04-03 | 2025-04-03
R7S1-ESD-SM-AT-A780 | Precast Concrete Standard Details--Approval (Studio - Medium) | 1 | 2025-04-03 | 2025-04-03
R7S1-ESD-SM-AT-A790 | Schedules--Approval (Studio - Medium) | 1 | 2025-04-03 | 2025-04-03
MECHANICAL |  | 71 | 2025-03-04 | 2025-05-13
HVAC/CHWP |  | 71 | 2025-03-04 | 2025-05-13
R7S1-ESD-SM-HVAC-A50 | Chilled Water Piping Ground Floor Layout--Approval (Studio - Medium) | 8 | 2025-03-04 | 2025-03-11
R7S1-ESD-SM-HVAC-A60 | Chilled Water Piping First Floor Layout--Approval (Studio - Medium) | 8 | 2025-03-04 | 2025-03-11
R7S1-ESD-SM-HVAC-A70 | Chilled Water Piping Second Floor Layout--Approval (Studio - Medium) | 8 | 2025-03-04 | 2025-03-11
R7S1-ESD-SM-HVAC-A80 | Chilled Water Piping Roof Floor Layout--Approval (Studio - Medium) | 8 | 2025-03-04 | 2025-03-11
R7S1-ESD-SM-HVAC-A90 | Chilled Water Schematic--Approval (Studio - Medium) | 8 | 2025-03-04 | 2025-03-11
R7S1-ESD-SM-HVAC-A10 | HVAC Ground Floor Layout--Approval (Studio - Medium) | 50 | 2025-03-20 | 2025-05-08
R7S1-ESD-SM-HVAC-A20 | HVAC First Floor Layout--Approval (Studio - Medium) | 50 | 2025-03-20 | 2025-05-08
R7S1-ESD-SM-HVAC-A30 | HVAC Second Floor Layout--Approval (Studio - Medium) | 50 | 2025-03-20 | 2025-05-08
R7S1-ESD-SM-HVAC-A40 | HVAC Roof Floor Layout--Approval (Studio - Medium) | 50 | 2025-03-20 | 2025-05-08
R7S1-ESD-SM-HVAC-A95 | HVAC Ventilation Schematic--Approval (Studio - Medium) | 50 | 2025-03-20 | 2025-05-08
R7S1-ESD-SM-HVAC-A98 | HVAC Equipment Schedule--Approval (Studio - Medium) | 71 | 2025-03-04 | 2025-05-13
FIRE FIGHTING |  | 18 | 2025-03-17 | 2025-04-03
R7S1-ESD-SM-FF-A250 | Ground Floor Plan Fire Fighting Layout--Approval (Studio - Medium) | 18 | 2025-03-17 | 2025-04-03
R7S1-ESD-SM-FF-A260 | First Floor Fire Fighting Layout--Approval (Studio - Medium) | 18 | 2025-03-17 | 2025-04-03
R7S1-ESD-SM-FF-A270 | Second Floor Fire Fighting Layout--Approval (Studio - Medium) | 18 | 2025-03-17 | 2025-04-03
R7S1-ESD-SM-FF-A280 | Roof Floor Fire Fighting Layout--Approval (Studio - Medium) | 18 | 2025-03-17 | 2025-04-03
R7S1-ESD-SM-FF-A290 | Fire Fighting Schematic Diagram--Approval (Studio - Medium) | 18 | 2025-03-17 | 2025-04-03
DRAINAGE |  | 68 | 2025-03-06 | 2025-05-13
R7S1-ESD-SM-DR-A250 | Ground Floor Drainage Layout --Approval (Studio - Medium) | 68 | 2025-03-06 | 2025-05-13
R7S1-ESD-SM-DR-A260 | First Floor Drainage Layout--Approval (Studio - Medium) | 68 | 2025-03-06 | 2025-05-13
R7S1-ESD-SM-DR-A270 | Second Floor Drainage Layout--Approval (Studio - Medium) | 68 | 2025-03-06 | 2025-05-13
R7S1-ESD-SM-DR-A280 | Roof Floor Drainage Layout--Approval (Studio - Medium) | 68 | 2025-03-06 | 2025-05-13
R7S1-ESD-SM-DR-A290 | Drainage Schematic--Approval (Studio - Medium) | 68 | 2025-03-06 | 2025-05-13
WATER SUPPLY |  | 48 | 2025-03-04 | 2025-04-20
R7S1-ESD-SM-WS-A250 | Water Supply Ground Floor Layout--Approval (Studio - Medium) | 48 | 2025-03-04 | 2025-04-20
R7S1-ESD-SM-WS-A260 | Water Supply First Floor Layout--Approval (Studio - Medium) | 48 | 2025-03-04 | 2025-04-20
R7S1-ESD-SM-WS-A270 | Water Supply Second Floor Layout--Approval (Studio - Medium) | 48 | 2025-03-04 | 2025-04-20
R7S1-ESD-SM-WS-A280 | Water Supply Roof Floor Layout--Approval (Studio - Medium) | 48 | 2025-03-04 | 2025-04-20
R7S1-ESD-SM-WS-A290 | Water Supplyschematic Layout--Approval (Studio - Medium) | 48 | 2025-03-04 | 2025-04-20
ELECTRICAL |  | 28 | 2025-03-13 | 2025-04-09
LIGHTING SYSTEM |  | 22 | 2025-03-13 | 2025-04-03
R7S1-ESD-SM-LIG-A190 | Ground Floor Lighting System Layout --Approval (Studio - Medium) | 22 | 2025-03-13 | 2025-04-03
R7S1-ESD-SM-LIG-A200 | First Floor Lighting System Layout--Approval (Studio - Medium) | 22 | 2025-03-13 | 2025-04-03
R7S1-ESD-SM-LIG-A210 | Second Floor Lighting Layout --Approval (Studio - Medium) | 22 | 2025-03-13 | 2025-04-03
POWER SYSTEM |  | 13 | 2025-03-13 | 2025-03-25
R7S1-ESD-SM-POW-A220 | Ground Floor Power System Layout --Approval (Studio - Medium) | 13 | 2025-03-13 | 2025-03-25
R7S1-ESD-SM-POW-A230 | First Floor Power System Layout --Approval (Studio - Medium) | 13 | 2025-03-13 | 2025-03-25
R7S1-ESD-SM-POW-A240 | Second Floor Power System Layout--Approval (Studio - Medium) | 13 | 2025-03-13 | 2025-03-25
R7S1-ESD-SM-POW-A250 | Roof Floor Power System Layout--Approval (Studio - Medium) | 13 | 2025-03-13 | 2025-03-25
ICT SYSTEM |  | 22 | 2025-03-13 | 2025-04-03
R7S1-ESD-SM-ICT-A310 | Ground Floor Telecom & ICT System Layout --Approval (Studio - Medium) | 22 | 2025-03-13 | 2025-04-03
R7S1-ESD-SM-ICT-A320 | First Floor Telecom & ICT System Layout --Approval (Studio - Medium) | 22 | 2025-03-13 | 2025-04-03
R7S1-ESD-SM-ICT-A330 | Second Floor Telecom& ICT System Layout --Approval (Studio - Medium) | 22 | 2025-03-13 | 2025-04-03
R7S1-ESD-SM-ICT-A340 | Telecom System Schematic Diagram --Approval (Studio - Medium) | 22 | 2025-03-13 | 2025-04-03
R7S1-ESD-SM-ICT-A350 | ICT System Schematic Diagram --Approval (Studio - Medium) | 22 | 2025-03-13 | 2025-04-03
R7S1-ESD-SM-ICT-A360 | Single Line Diagram--Approval (Studio - Medium) | 22 | 2025-03-13 | 2025-04-03
R7S1-ESD-SM-ICT-A370 | Power System Single Line Diagram --Approval (Studio - Medium) | 22 | 2025-03-13 | 2025-04-03
FIRE ALARM SYSTEM |  | 18 | 2025-03-17 | 2025-04-03
R7S1-ESD-SM-FA-A220 | Ground Floor Fire Alarm & Voice Evacuation System Layout--Approval (Studio - Medium) | 18 | 2025-03-17 | 2025-04-03
R7S1-ESD-SM-FA-A230 | First Floor Fire Alarm & Voice Evacuation System Layout--Approval (Studio - Medium) | 18 | 2025-03-17 | 2025-04-03
R7S1-ESD-SM-FA-A240 | Second Floor Fire Alarm & Voice Evacuation System Layout--Approval (Studio - Medium) | 18 | 2025-03-17 | 2025-04-03
R7S1-ESD-SM-FA-A250 | Fire Alarm & Voice Evacuation System Schematic Diagram --Approval (Studio - Medium) | 18 | 2025-03-17 | 2025-04-03
ACCESS CONTROLSYSTEM |  | 22 | 2025-03-13 | 2025-04-03
R7S1-ESD-SM-ACC-A220 | Ground Floor Access Control System Layout--Approval (Studio - Medium) | 22 | 2025-03-13 | 2025-04-03
R7S1-ESD-SM-ACC-A230 | First Floor Access Control System Layout--Approval (Studio - Medium) | 22 | 2025-03-13 | 2025-04-03
R7S1-ESD-SM-ACC-A240 | Second Floor Access Control System Layout--Approval (Studio - Medium) | 22 | 2025-03-13 | 2025-04-03
R7S1-ESD-SM-ACC-A250 | Access Control Schematic Diagram--Approval (Studio - Medium) | 22 | 2025-03-13 | 2025-04-03
CCTV SYSTEM |  | 22 | 2025-03-13 | 2025-04-03
R7S1-ESD-SM-CCT-A220 | CCTV System Ground Floor Layout--Approval (Studio - Medium) | 22 | 2025-03-13 | 2025-04-03
R7S1-ESD-SM-CCT-A230 | CCTV System First Floor Layout--Approval (Studio - Medium) | 22 | 2025-03-13 | 2025-04-03
R7S1-ESD-SM-CCT-A240 | CCTV System Second Floor Layout--Approval (Studio - Medium) | 22 | 2025-03-13 | 2025-04-03
R7S1-ESD-SM-CCT-A250 | CCTV System Schematic Diagram--Approval (Studio - Medium) | 22 | 2025-03-13 | 2025-04-03
LIGHTNING PROTECTION SYSTEM |  | 11 | 2025-03-13 | 2025-03-23
R7S1-ESD-SM-LPS-A160 | Ground Floor Earthing Protection System Layout--Approval (Studio - Medium) | 11 | 2025-03-13 | 2025-03-23
R7S1-ESD-SM-LPS-A170 | Roof Floor Lightning Protection System Layout.--Approval (Studio - Medium) | 11 | 2025-03-13 | 2025-03-23
INTEGRATED BUILDING MANAGEMENT SYSTEM |  | 23 | 2025-03-18 | 2025-04-09
R7S1-ESD-SM-IBM-A310 | Ground Floor IBMS Layout--Approval (Studio - Medium) | 23 | 2025-03-18 | 2025-04-09
R7S1-ESD-SM-IBM-A320 | First Floor IBMS Layout--Approval (Studio - Medium) | 23 | 2025-03-18 | 2025-04-09
R7S1-ESD-SM-IBM-A330 | Second Floor IBMS Layout--Approval (Studio - Medium) | 23 | 2025-03-18 | 2025-04-09
R7S1-ESD-SM-IBM-A340 | Roof Floor IBMS Layout--Approval (Studio - Medium) | 23 | 2025-03-18 | 2025-04-09
R7S1-ESD-SM-IBM-A350 | IBMS KWHR Riser Diagram--Approval (Studio - Medium) | 23 | 2025-03-18 | 2025-04-09
R7S1-ESD-SM-IBM-A360 | IBMS BTU, Cold & Hot Water Meter Riser Diagram--Approval (Studio - Medium) | 23 | 2025-03-18 | 2025-04-09
R7S1-ESD-SM-IBM-A370 | IBMS Schematic Diagram--Approval (Studio - Medium) | 23 | 2025-03-18 | 2025-04-09
METHOD STATEMENTS |  | 303 | 2024-09-24 | 2025-06-16
PREPARATION & SUBMISSION OF METHOD STATEMENTS |  | 238 | 2024-09-24 | 2025-06-01
GENERAL |  | 28 | 2024-09-24 | 2024-10-26
R7S1-EMS-S-1000 | Method Statement Preparation & Submission for Site Mobilization | 2 | 2024-09-24 | 2024-09-25
R7S1-EMS-S-1010 | Method Statement Preparation & Submission for Survey Works | 6 | 2024-10-20 | 2024-10-26
STRUCTURAL WORKS |  | 72 | 2024-10-26 | 2025-01-16
R7S1-EMS-S-1030 | Method Statement Preparation & Submission for Anti Termite Application | 1 | 2024-10-26 | 2024-10-26
R7S1-EMS-S-1060 | Method Statement Preparation & Submission for Concrete Works | 1 | 2024-10-27 | 2024-10-27
R7S1-EMS-S-1020 | Method Statement Preparation & Submission for Excavation and Back Filling Works | 1 | 2024-10-31 | 2024-10-31
R7S1-EMS-S-1070 | Method Statement Preparation & Submission for Concrete Repairing Works | 1 | 2024-10-31 | 2024-10-31
R7S1-EMS-S-1080 | Method Statement Preparation & Submission for Concrete Repairing Works (Cracks, Modular Joints, Alignment) | 1 | 2024-10-31 | 2024-10-31
R7S1-EMS-S-1120 | Method Statement Preparation & Submission for Slab-On-Grade | 10 | 2024-10-27 | 2024-11-06
R7S1-EMS-S-1090 | Method Statement Preparation & Submission for Bitumen Paint/Waterproofing Works - Liquid Application | 1 | 2024-11-07 | 2024-11-07
R7S1-EMS-S-1040 | Method Statement Preparation & Submission for Production of Precast Concrete Elements | 1 | 2024-11-18 | 2024-11-18
R7S1-EMS-S-1100 | Method Statement Preparation & Submission for Construction of Precast Concrete Modular | 1 | 2024-11-21 | 2024-11-21
R7S1-EMS-S-1050 | Method Statement Preparation & Submission for Loading, Unloading and Transporting of Construction Materials from Laydown | 1 | 2024-11-27 | 2024-11-27
R7S1-EMS-S-1110 | Method Statement Preparation & Submission for Erection of Precast Concrete Modular | 13 | 2025-01-02 | 2025-01-16
R7S1-EMS-S-1130 | Method Statement Preparation & Submission for Loading and Transportation of Concrete Modular | 7 | 2025-01-09 | 2025-01-16
FINISHING WORKS |  | 149 | 2024-11-30 | 2025-05-06
R7S1-EMS-S-1190 | Method Statement Preparation & Submission for Gypsum Wall Cladding | 1 | 2024-11-30 | 2024-11-30
R7S1-EMS-S-1180 | Method Statement Preparation & Submission for Tile Work in Corridors | 1 | 2024-12-01 | 2024-12-01
R7S1-EMS-S-1220 | Method Statement Preparation & Submission for False Ceiling | 4 | 2024-12-07 | 2024-12-10
R7S1-EMS-S-1150 | Method Statement Preparation & Submission for Installation of Wooden Doors | 5 | 2024-12-08 | 2024-12-12
R7S1-EMS-S-1240 | Method Statement Preparation & Submission for Block Works | 2 | 2025-01-01 | 2025-01-02
R7S1-EMS-S-1250 | Method Statement Preparation & Submission for Plastering Works | 2 | 2025-01-01 | 2025-01-02
R7S1-EMS-S-1160 | Method Statement Preparation & Submission for Wet area Water Proofing Works | 23 | 2024-12-15 | 2025-01-09
R7S1-EMS-S-1260 | Method Statement Preparation & Submission for Painting Works | 1 | 2025-01-11 | 2025-01-11
R7S1-EMS-S-1140 | Method Statement Preparation & Submission for Installation of Steel Doors | 33 | 2024-12-04 | 2025-01-11
R7S1-EMS-S-1230 | Method Statement Preparation & Submission for Installation of Aluminium Doors, Windows, Louvers & Curtain Walls | 14 | 2025-01-22 | 2025-02-06
R7S1-EMS-S-1210 | Method Statement Preparation & Submission for Installation of Garbage Chute System | 13 | 2025-02-02 | 2025-02-16
R7S1-EMS-S-1270 | Method Statement Preparation & Submission for Roof Water Proofing Works | 1 | 2025-04-17 | 2025-04-17
R7S1-EMS-S-1200 | Method Statement Preparation & Submission for Installation of Metal Handrails | 5 | 2025-04-20 | 2025-04-24
R7S1-EMS-S-1170 | Method Statement Preparation & Submission for Elevator Installation | 4 | 2025-05-03 | 2025-05-06
HVAC SYSTEM |  | 95 | 2024-11-30 | 2025-03-20
R7S1-EMS-S-1300 | Method Statement Preparation & Submission for Installation of HVAC Duct & Accessories | 5 | 2024-12-14 | 2024-12-18
R7S1-EMS-S-1280 | Method Statement Preparation & Submission for Installation of FCU | 19 | 2024-11-30 | 2024-12-21
R7S1-EMS-S-1290 | Method Statement Preparation & Submission for Installation of Refrigeration Pipes (copper pipes) | 12 | 2025-01-11 | 2025-01-23
R7S1-EMS-S-1310 | Method Statement Preparation & Submission for Installation of Chilled Water Pipes & Fittings | 36 | 2024-12-14 | 2025-01-23
R7S1-EMS-S-1330 | Method Statement Preparation & Submission forInstallation of Fans (Fresh Air, Exhaust, Smoke Extract, Pressurization Fan | 1 | 2025-01-30 | 2025-01-30
R7S1-EMS-S-1340 | Method Statement Preparation & Submission for Installation of FAHU / AHU | 5 | 2025-02-01 | 2025-02-05
R7S1-EMS-S-1320 | Method Statement Preparation & Submission for Installation of Flushing of the Chilled Water System | 41 | 2025-02-01 | 2025-03-20
WATERSUPPLY & DRAINAGE |  | 97 | 2024-11-19 | 2025-03-12
R7S1-EMS-S-1360 | Method Statement Preparation & Submission for Underground Pipe Installation (Pressure Flow/Gravity Flow - Drainage ) | 7 | 2024-11-19 | 2024-11-26
R7S1-EMS-S-1370 | Method Statement Preparation & Submission for Above Ground Pipe Installation (Pressure Flow/Gravity Flow - Drainage | 10 | 2024-11-19 | 2024-11-30
R7S1-EMS-S-1350 | Method Statement Preparation & Submission for Installation of Sanitary Ware & Fittings | 10 | 2024-11-28 | 2024-12-09
R7S1-EMS-S-1380 | Method Statement Preparation & Submission for Underground Pipe Installation (Pressure Flow/Gravity Flow - Water Supply | 12 | 2024-11-30 | 2024-12-12
R7S1-EMS-S-1390 | Method Statement Preparation & Submission for Above Ground Pipe Installation (Pressure Flow/Gravity Flow - Water Supply | 20 | 2024-11-26 | 2024-12-18
R7S1-EMS-S-1400 | Method Statement Preparation & Submission forI nstallation of Solar Water Heater | 5 | 2025-03-08 | 2025-03-12
FIRE FIGHTING WORKS |  | 23 | 2024-11-19 | 2024-12-15
R7S1-EMS-S-1410 | Method Statement Preparation & Submission for Installation of Undeground Firefighting pipes | 21 | 2024-11-19 | 2024-12-12
R7S1-EMS-S-1420 | Method Statement Preparation & Submission for Installation of Fire Protection services Above Ground | 23 | 2024-11-19 | 2024-12-15
ELECTRICAL |  | 193 | 2024-11-16 | 2025-06-01
R7S1-EMS-S-2200 | Method Statement Preparation & Submission for Installation of Underground Duct Pipes and Banks | 7 | 2024-11-30 | 2024-12-07
R7S1-EMS-S-2230 | Method Statement Preparation & Submission for Installation of Conduits (PVC,GI & SS) | 6 | 2024-12-01 | 2024-12-07
R7S1-EMS-S-2240 | Method Statement Preparation & Submission for Installation of SMDBs, DBs, MCCs & MCPs | 4 | 2024-12-07 | 2024-12-10
R7S1-EMS-S-1430 | Method Statement Preparation & Submission for Installation of Light Fixtures | 17 | 2024-11-21 | 2024-12-10
R7S1-EMS-S-2260 | Method Statement Preparation & Submission for Installation of Wiring Accessories | 22 | 2024-11-16 | 2024-12-10
R7S1-EMS-S-1450 | Method Statement Preparation & Submission for Installation of Fire Alarm & Voice Evacuation System | 4 | 2024-12-07 | 2024-12-10
R7S1-EMS-S-2210 | Method Statement Preparation & Submission for installation of Cables and Wires -Above Ground | 13 | 2024-12-04 | 2024-12-18
R7S1-EMS-S-2290 | Method Statement Preparation & Submission for Installation of Structured Cabling System (Telephone /Data) | 5 | 2024-12-14 | 2024-12-18
R7S1-EMS-S-2180 | Method Statement Preparation & Submission for Installation of Earthing System | 8 | 2024-12-12 | 2024-12-21
R7S1-EMS-S-1440 | Method Statement Preparation & Submission for Installation of Emergency Lighting | 39 | 2024-11-21 | 2025-01-05
R7S1-EMS-S-2280 | Method Statement Preparation & Submission for Installation of CCTV System | 25 | 2024-12-12 | 2025-01-09
R7S1-EMS-S-2220 | Method Statement Preparation & Submission for Installation of Cable Tray, Ladder & Trunking | 43 | 2024-12-05 | 2025-01-23
R7S1-EMS-S-2190 | Method Statement Preparation & Submission for Installation of Lightning Protection System | 42 | 2024-12-12 | 2025-01-29
R7S1-EMS-S-2320 | Method Statement Preparation & Submission for Installation of UPS | 36 | 2025-01-02 | 2025-02-12
R7S1-EMS-S-2330 | Method Statement Preparation & Submission for Installation of BMS System | 4 | 2025-05-28 | 2025-06-01
APPROVAL OF OF METHOD STATEMENTS |  | 301 | 2024-09-26 | 2025-06-16
GENERAL |  | 35 | 2024-09-26 | 2024-10-30
R7S1-EMS-A-2340 | Method Statement approval for Site Mobilization | 5 | 2024-09-26 | 2024-09-30
R7S1-EMS-A-2350 | Method Statement approval for Survey Works | 5 | 2024-10-26 | 2024-10-30
STRUCTURAL WORKS |  | 103 | 2024-10-26 | 2025-02-05
R7S1-EMS-A-2370 | Method Statement approval for Anti Termite Application | 5 | 2024-10-26 | 2024-10-30
R7S1-EMS-A-2360 | Method Statement approval for Excavation and Back Filling Works | 1 | 2024-11-06 | 2024-11-06
R7S1-EMS-A-2380 | Method Statement approval for Concrete Works | 11 | 2024-10-27 | 2024-11-06
R7S1-EMS-A-2460 | Method Statement approval for Concrete Repairing Works | 7 | 2024-10-31 | 2024-11-06
R7S1-EMS-A-2470 | Method Statement approval for Concrete Repairing Works (Cracks, Modular Joints, Alignment) | 7 | 2024-10-31 | 2024-11-06
R7S1-EMS-A-2400 | Method Statement approval for Bitumen Paint/Waterproofing Works - Liquid Application | 6 | 2024-11-07 | 2024-11-12
R7S1-EMS-A-2410 | Method Statement approval Fabrication of Precast Concrete Elements | 3 | 2024-11-19 | 2024-11-21
R7S1-EMS-A-2420 | Method Statement approval for Construction of Precast Concrete Modular | 5 | 2024-11-21 | 2024-11-25
R7S1-EMS-A-2450 | Method Statement approval for Loading, Unloading and Transporting of Construction Materials from Laydown to Site | 6 | 2024-11-28 | 2024-12-03
R7S1-EMS-A-2430 | Method Statement approval for Erection of Precast Concrete Modular | 5 | 2025-01-17 | 2025-01-21
R7S1-EMS-A-2440 | Method Statement approval for Loading and Transportation of Concrete Modular | 5 | 2025-01-17 | 2025-01-21
R7S1-EMS-A-2390 | Method Statement approval for Slab-On-Grade | 4 | 2025-02-02 | 2025-02-05
FINISHING WORKS |  | 194 | 2024-11-30 | 2025-05-21
R7S1-EMS-A-2520 | Method Statement approval for Tile Work in corridors | 3 | 2024-12-01 | 2024-12-03
R7S1-EMS-A-2530 | Method Statement approval for Gypsum Wall Cladding | 4 | 2024-11-30 | 2024-12-03
R7S1-EMS-A-2540 | Method Statement approval for False Ceiling | 4 | 2024-12-07 | 2024-12-10
R7S1-EMS-A-2570 | Method Statement approval for Installation of Wooden Doors | 4 | 2024-12-08 | 2024-12-12
R7S1-EMS-A-2480 | Method Statement approval for Block Works | 5 | 2025-01-02 | 2025-01-06
R7S1-EMS-A-2490 | Method Statement approval for Plastering Works | 5 | 2025-01-02 | 2025-01-06
R7S1-EMS-A-2500 | Method Statement approval for Painting Works | 4 | 2025-01-11 | 2025-01-14
R7S1-EMS-A-2510 | Method Statement approval for Wet area Water Proofing Works | 27 | 2024-12-19 | 2025-01-14
R7S1-EMS-A-2560 | Method Statement approval for Installation of Steel Doors | 37 | 2024-12-09 | 2025-01-14
R7S1-EMS-A-2550 | Method Statement approval for Installation of Aluminium Doors, Windows, Louvers & Curtain Walls | 5 | 2025-02-02 | 2025-02-06
R7S1-EMS-A-2630 | Method Statement approval for Installation of Garbage Chute System | 3 | 2025-02-17 | 2025-02-19
R7S1-EMS-A-2580 | Method Statement approval for Roof Water Proofing Works | 4 | 2025-04-19 | 2025-04-22
R7S1-EMS-A-2620 | Method Statement approval for Installation of Metal Handrails | 1 | 2025-04-24 | 2025-04-24
R7S1-EMS-A-2590 | Method Statement approval for Lift Installation | 15 | 2025-05-07 | 2025-05-21
HVAC SYSTEM |  | 112 | 2024-12-04 | 2025-03-25
R7S1-EMS-A-2670 | Method Statement approval for Installation of HVAC Duct & Accessories | 5 | 2024-12-19 | 2024-12-24
R7S1-EMS-A-2650 | Method Statement approval for Installation of FCU | 21 | 2024-12-04 | 2024-12-24
R7S1-EMS-A-2660 | Method Statement approval for Installation of Refrigeration Pipes (copper pipes) | 8 | 2025-01-23 | 2025-01-30
R7S1-EMS-A-2680 | Method Statement approval for Installation of Chilled Water Pipes & Fittings | 44 | 2024-12-18 | 2025-01-30
R7S1-EMS-A-2700 | Method Statement approval for Installation of Fans (Fresh Air, Exhaust, Smoke Extract, Pressurization Fan) | 3 | 2025-01-30 | 2025-02-01
R7S1-EMS-A-2640 | Method Statement approval for Installation of FAHU / AHU | 1 | 2025-02-05 | 2025-02-05
R7S1-EMS-A-2690 | Method Statement approval for Installation of Flushing of the Chilled Water System | 9 | 2025-03-17 | 2025-03-25
WATERSUPPLY & DRAINAGE |  | 114 | 2024-11-27 | 2025-03-20
R7S1-EMS-A-2710 | Method Statement approval for Underground Pipe Installation (Pressure Flow/Gravity Flow - Drainage ) | 7 | 2024-11-27 | 2024-12-03
R7S1-EMS-A-2720 | Method Statement approval for Above Ground Pipe Installation (Pressure Flow/Gravity Flow - Drainage | 4 | 2024-11-30 | 2024-12-03
R7S1-EMS-A-2730 | Method Statement approval for Underground Pipe Installation (Pressure Flow/Gravity Flow - Water Supply | 13 | 2024-11-30 | 2024-12-12
R7S1-EMS-A-2760 | Method Statement approval for Installation of Sanitary Ware & Fittings | 3 | 2024-12-10 | 2024-12-12
R7S1-EMS-A-2750 | Method Statement approval for Above Ground Pipe Installation (Pressure Flow/Gravity Flow - Water Supply | 23 | 2024-12-01 | 2024-12-24
R7S1-EMS-A-2740 | Method Statement approval for Installation of Solar Water Heater | 8 | 2025-03-13 | 2025-03-20
FIRE FIGHTING WORKS |  | 22 | 2024-11-24 | 2024-12-15
R7S1-EMS-A-2790 | Method Statement approval for Installation of Undeground Firefighting pipes | 19 | 2024-11-24 | 2024-12-12
R7S1-EMS-A-2800 | Method Statement approval for Installation of Fire Protection services Above Ground | 22 | 2024-11-24 | 2024-12-15
ELECTRICAL APPROVAL OF OF METHOD STATEMENTS |  | 246 | 2024-11-20 | 2025-06-16
R7S1-EMS-A-2840 | Method Statement approval for Installation of Underground Duct Pipes and Banks | 8 | 2024-11-30 | 2024-12-07
R7S1-EMS-A-2870 | Method Statement approval for Installation of Conduits (PVC,GI & SS) | 7 | 2024-12-01 | 2024-12-07
R7S1-EMS-A-2880 | Method Statement approval for Installation of SMDBs, DBs, MCCs & MCPs | 4 | 2024-12-07 | 2024-12-10
R7S1-EMS-A-2890 | Method Statement approval for Installation of Light Fixtures | 6 | 2024-12-05 | 2024-12-10
R7S1-EMS-A-2900 | Method Statement approval for Installation of Wiring Accessories | 21 | 2024-11-20 | 2024-12-10
R7S1-EMS-A-2940 | Method Statement approval for Installation of Fire Alarm & Voice Evacuation System | 4 | 2024-12-07 | 2024-12-10
R7S1-EMS-A-2950 | Method Statement approval for Installation of Emergency Lighting | 6 | 2024-12-05 | 2024-12-10
R7S1-EMS-A-2930 | Method Statement approval for Installation of Structured Cabling System (Telephone /Data) | 5 | 2024-12-19 | 2024-12-24
R7S1-EMS-A-2850 | Method Statement approval for installation of Cables and Wires -Above Ground | 21 | 2024-12-04 | 2024-12-24
R7S1-EMS-A-2820 | Method Statement approval for Installation of Earthing System | 8 | 2024-12-22 | 2024-12-29
R7S1-EMS-A-2920 | Method Statement approval for Installation of CCTV System | 24 | 2024-12-17 | 2025-01-09
R7S1-EMS-A-2860 | Method Statement approval for Installation of Cable Tray, Ladder & Trunking | 53 | 2024-12-09 | 2025-01-30
R7S1-EMS-A-2830 | Method Statement approval for Installation of Lightning Protection System | 50 | 2024-12-17 | 2025-02-04
R7S1-EMS-A-2960 | Method Statement approval for Installation of UPS | 37 | 2025-01-07 | 2025-02-12
R7S1-EMS-A-2970 | Method Statement approval for Installation of BMS System | 15 | 2025-06-02 | 2025-06-16
PROVISIONAL SUM ITEM |  | 92 | 2024-11-21 | 2025-02-20
HUBS & INFRASTRICTURE |  | 92 | 2024-11-21 | 2025-02-20
R7-KM-3000 | Employer instructions to proceed with the PS item along with 100 % Detailed Design of Infrastructure & utility Hubs | 0 | 2024-11-21
R7-KM-4000 | Receiving updated master plan layout showing the external site levels adjacent to the Buildings (By Employer) | 0 | 2024-11-24
R7S1-EDHUB-1000 | Engineering Activities & Design Verification for Infra & Hub Works incl. Modular Design | 58 | 2024-11-21 | 2025-02-10
R7S1-EDHUB-1020 | Employer Review and Approval on the Modular Design (Hubs) | 45 | 2025-01-07 | 2025-02-20
PROCUREMENT WORKS |  | 458 | 2024-09-17 | 2025-11-02
MANAGEMENT & STUDIO BUILDINGS |  | 458 | 2024-09-17 | 2025-11-02
PREQUALIFICATION (PQ) |  | 261 | 2024-09-17 | 2025-05-14
PQ SUBMITTALS |  | 246 | 2024-09-17 | 2025-04-29
CIVIL/ARCH |  | 246 | 2024-09-17 | 2025-04-29
R7S1-PPQ-S-1000 | Soil Investigation & Data collection - PQ Submission | 1 | 2024-09-17 | 2024-09-17
R7S1-PPQ-S-1130 | 3rd Party Testing Lab for Construction Materials - PQ Submission | 1 | 2024-10-23 | 2024-10-23
R7S1-PPQ-S-1060 | AOR Consultant - PQ Submission | 1 | 2024-10-23 | 2024-10-23
R7S1-PPQ-S-1070 | Aluminium and Glazing works - PQ Submission | 5 | 2024-10-30 | 2024-11-04
R7S1-PPQ-S-1100 | Supply and Installation of Kitchen Top Cabinet & Accessories - PQ Submission | 14 | 2024-10-20 | 2024-11-04
R7S1-PPQ-S-1110 | Supply and Erection of Precast Concrete Modular Buildings - PQ Submission | 12 | 2024-10-26 | 2024-11-07
R7S1-PPQ-S-1090 | FLS Consultancy Services - PQ Submission | 1 | 2024-11-07 | 2024-11-07
R7S1-PPQ-S-1050 | Supply of Precast Elements - PQ Submission | 12 | 2024-10-26 | 2024-11-07
R7S1-PPQ-S-1140 | Supply and Installation of Elevator - PQ Submission | 1 | 2024-11-07 | 2024-11-07
R7S1-PPQ-S-1010 | Steel Reinforcement - PQ Submission | 1 | 2024-11-12 | 2024-11-12
R7S1-PPQ-S-1040 | Supply of Onsite Ready Mix Concrete - PQ Submission | 30 | 2024-10-15 | 2024-11-18
R7S1-PPQ-S-1030 | Application of Anti Termite - PQ Submission | 1 | 2024-11-25 | 2024-11-25
R7S1-PPQ-S-1120 | Supply and Installation of Wooden Doors and Hardware - PQ Submission | 16 | 2024-11-04 | 2024-11-25
R7S1-PPQ-S-1080 | Supply and Installation of Steel Doors and Hardware - PQ Submission | 29 | 2024-11-14 | 2024-12-17
R7S1-PPQ-S-1160 | Application of Roof waterproofing - PQ Submission | 4 | 2025-02-08 | 2025-02-11
R7S1-PPQ-S-1150. | Supply and Installation of Miscl. Steel Items - PQ Submission | 4 | 2025-04-26 | 2025-04-29
PQ APPROVALS |  | 261 | 2024-09-17 | 2025-05-14
CIVIL/ARCH |  | 261 | 2024-09-17 | 2025-05-14
R7S1-PPQ-A-1000 | Soil Investigation & Data collection - PQ Approval | 2 | 2024-09-17 | 2024-09-18
R7S1-PPQ-A-1130 | 3rd Party Testing Lab for Construction Materials - PQ Approval | 9 | 2024-10-23 | 2024-10-31
R7S1-PPQ-A-1060 | AOR Consultant - PQ Approval | 13 | 2024-10-24 | 2024-11-05
R7S1-PPQ-A-1070 | Aluminium and Glazing works - PQ Approval | 2 | 2024-11-04 | 2024-11-05
R7S1-PPQ-A-1110 | Supply and Installation of Kitchen Top Cabinet & Accessories - PQ Approval | 4 | 2024-11-04 | 2024-11-07
R7S1-PPQ-A-1100 | Supply and Erection of Precast Concrete Modular Buildings - PQ Approval | 4 | 2024-11-07 | 2024-11-10
R7S1-PPQ-A-1050 | Supply of Precast Elements - PQ Approval | 4 | 2024-11-07 | 2024-11-10
R7S1-PPQ-A-1090 | FLS Consultancy Services - PQ Approval | 6 | 2024-11-07 | 2024-11-12
R7S1-PPQ-A-1140 | Supply and Installation of Elevator - PQ Approval | 6 | 2024-11-07 | 2024-11-12
R7S1-PPQ-A-1010 | Steel Reinforcement, - PQ Approval | 8 | 2024-11-12 | 2024-11-19
R7S1-PPQ-A-1040 | Supply of Onsite Ready Mix Concrete - PQ Approval | 32 | 2024-10-20 | 2024-11-20
R7S1-PPQ-A-1030 | Application of Anti-Termite - PQ Approval | 4 | 2024-11-25 | 2024-11-28
R7S1-PPQ-A-1120 | Supply and Installation of Wooden Doors and Hardware - PQ Approval | 23 | 2024-11-06 | 2024-11-28
R7S1-PPQ-A-1080 | Supply and Installation of Steel Doors and Hardware - PQ Approval | 36 | 2024-11-19 | 2024-12-24
R7S1-PPQ-A-1160 | Application of Roof waterproofing - PQ Approval | 6 | 2025-02-12 | 2025-02-17
R7S1-PPQ-A-1150 | Supply and Installation of Miscl. Steel Items - PQ Approval | 15 | 2025-04-30 | 2025-05-14
MATERIAL SUBMITTAL & APPROVAL |  | 256 | 2024-10-20 | 2025-06-03
MATERIAL SUBMITTALS |  | 198 | 2024-10-20 | 2025-05-19
CIVIL |  | 96 | 2024-10-22 | 2025-02-10
CONCRETE WORKS |  | 96 | 2024-10-22 | 2025-02-10
R7S1-EMMS-1050 | Bonding Agent - Material Submittal | 1 | 2024-10-22 | 2024-10-22
R7S1-EMMS-1120 | Release Agent (Weber.ad dem 22) - Material Submittal | 1 | 2024-10-22 | 2024-10-22
R7S1-EMMS-1150 | Vapor barrier Sheet - 1000 gauge - Material Submittal | 1 | 2024-10-22 | 2024-10-22
R7S1-EMMS-1035 | Concrete Curing Compound Weber Cure Y20 - Material Submittal | 1 | 2024-10-22 | 2024-10-22
R7S1-EMMS-1070 | MasterKure 161, Bitumen based damp proofing membrane for protection and curing of concrete structures. - Material Submit | 1 | 2024-10-23 | 2024-10-23
R7S1-EMMS-1100 | Expansion Joint Filler - Bitu-Flex "Bitumen Impregnated Expansion Joint Filler - Material Submittal | 1 | 2024-10-23 | 2024-10-23
R7S1-EMMS-1060 | Bitumen Protective coating (Bitumen Paint) - Material Submittal | 1 | 2024-10-26 | 2024-10-26
R7S1-EMMS-1080 | Concrete Repair Material (WEBEREP ST), Non-Metallic Non Shrink Fiber reinforced repair mortar - Material Submittal | 1 | 2024-10-26 | 2024-10-26
R7S1-EMMS-1030 | CEMENT (SRC & OPC) - Material Submittal | 1 | 2024-10-31 | 2024-10-31
R7S1-EMMS-1090 | Non-shrink, cement-based plastering for concrete repair 3 : 10 mm - Material Submittal | 1 | 2024-10-31 | 2024-10-31
R7S1-EMMS-1020 | Concrete Mix Design C20, C40 - Material Submittal | 9 | 2024-11-04 | 2024-11-13
R7S1-EMMS-1130 | Concrete cover spacer - Material Submittal | 1 | 2024-11-13 | 2024-11-13
R7S1-EMMS-1140 | Binding Wire - Material Submittal | 1 | 2024-11-13 | 2024-11-13
R7S1-EMMS-1160 | GULF 1200 Silicone (Anti-fungus & Anti Bacterial Silicone Sealant) - Material Submittal | 1 | 2024-11-13 | 2024-11-13
R7S1-EMMS-1180 | Reinforcement Steel - Material Submittal | 1 | 2024-11-13 | 2024-11-13
R7S1-EMMS-1040 | Anti-termite Treatment - Material Submittal | 14 | 2024-11-24 | 2024-12-09
R7S1-EMMS-1170 | Solid block work 20x20x40 cm - Material Submittal | 14 | 2024-11-30 | 2024-12-15
R7S1-EMMS-1110 | Epoxy Anchoring (Weberanc 405) - Material Submittal | 15 | 2024-12-14 | 2024-12-30
R7S1-EMMS-1190 | Floor Expansion Joint - Material Submittal | 33 | 2025-01-04 | 2025-02-10
TILE WORKS |  | 47 | 2024-11-13 | 2025-01-06
R7S1-EMMS-1200 | Water resistant tile grout - Material Submittal | 1 | 2024-11-13 | 2024-11-13
R7S1-EMMS-1220 | Tile Grout (Vitonit) - Material Submittal | 1 | 2024-11-13 | 2024-11-13
R7S1-EMMS-1230 | Fire Stop Sealant - Material Submittal | 13 | 2024-12-05 | 2024-12-19
R7S1-EMMS-1210 | Tile Adhesive 1) MasterTile® FLX 23 & 2) MasterTile® FLX 24 - Material Submittal | 39 | 2024-11-23 | 2025-01-06
EXTERNAL WORKS |  | 77 | 2024-11-13 | 2025-02-10
R7S1-EMMS-1240 | Aluminum decorative hinged screen with wood finish fixed on glazed windows - Material Submittal | 1 | 2024-11-13 | 2024-11-13
R7S1-EMMS-1250 | Decorative Louvers/Perforated sheet to cover MEP services at Roof - Material Submittal | 4 | 2025-02-06 | 2025-02-10
PRECAST SYSTEM |  | 40 | 2024-10-30 | 2024-12-15
R7S1-EMMS-1320 | Mix design for precast concrete walls - Material Submittal | 1 | 2024-11-13 | 2024-11-13
R7S1-EMMS-1260 | Concure WB309 - Material Submittal | 22 | 2024-10-30 | 2024-11-24
R7S1-EMMS-1270 | Reebol WB - Material Submittal | 22 | 2024-10-30 | 2024-11-24
R7S1-EMMS-1280 | Cbond - Material Submittal | 22 | 2024-10-30 | 2024-11-24
R7S1-EMMS-1290 | SikaRep fine - Material Submittal | 22 | 2024-10-30 | 2024-11-24
R7S1-EMMS-1300 | Sika Grout 114 - Material Submittal | 22 | 2024-10-30 | 2024-11-24
R7S1-EMMS-1310 | Master Flow 522 - Material Submittal | 22 | 2024-10-30 | 2024-11-24
R7S1-EMMS-1350 | Wire Mesh (Reinforcement Steel Wire Mesh) - Material Submittal | 22 | 2024-10-30 | 2024-11-24
R7S1-EMMS-1360 | PVC Tie Wire & Black Annealed Wire - Material Submittal | 22 | 2024-10-30 | 2024-11-24
R7S1-EMMS-1370 | Lifting Socket - Material Submittal | 22 | 2024-10-30 | 2024-11-24
R7S1-EMMS-1380 | Ties and Connector Pins - Material Submittal | 22 | 2024-10-30 | 2024-11-24
R7S1-EMMS-1390 | Low Relaxation Pre-Stressing Strands - Material Submittal | 22 | 2024-10-30 | 2024-11-24
R7S1-EMMS-1400 | Concrete Spacers & Chamfers - Material Submittal | 22 | 2024-10-30 | 2024-11-24
R7S1-EMMS-1420 | Cast In Channel - Material Submittal | 22 | 2024-10-30 | 2024-11-24
R7S1-EMMS-1430 | Connecting Loop - Material Submittal | 22 | 2024-10-30 | 2024-11-24
R7S1-EMMS-1440 | Corrugated Pipe - Material Submittal | 22 | 2024-10-30 | 2024-11-24
R7S1-EMMS-1330 | Thermal Insulation - Material Submittal | 40 | 2024-10-30 | 2024-12-15
R7S1-EMMS-1340 | Thermal Insulation Esscofoam 40 (material and prequalification) - Material Submittal | 40 | 2024-10-30 | 2024-12-15
R7S1-EMMS-1410 | Backup Rods (Filler Rods) - Material Submittal | 40 | 2024-10-30 | 2024-12-15
ARCHITECTURE |  | 194 | 2024-10-24 | 2025-05-19
EXTERNAL WORKS |  | 4 | 2025-05-15 | 2025-05-19
R7S1-EMMS-1450 | Balcony metal grating handrail - Material Submittal | 4 | 2025-05-15 | 2025-05-19
R7S1-EMMS-1460 | Ladders - Material Submittal | 4 | 2025-05-15 | 2025-05-19
THERMAL & MOISTURE PROTECTION: |  | 5 | 2025-02-06 | 2025-02-11
R7S1-EMMS-1470 | Roof Water Proofing - Material Submittal | 5 | 2025-02-06 | 2025-02-11
DOORS & WINDOWS |  | 28 | 2024-11-13 | 2024-12-15
R7S1-EMMS-1510 | Aluminum Profiles - Material Submittal | 1 | 2024-11-13 | 2024-11-13
R7S1-EMMS-1520 | Glazing details for external doors and windows (Guardian Sungurad)/ Acoustic performance datasheet. - Material Submittal | 1 | 2024-11-13 | 2024-11-13
R7S1-EMMS-1530 | Aluminum doors & windows - Material Submittal | 1 | 2024-11-13 | 2024-11-13
R7S1-EMMS-1540 | Ironmongery & Hardware - Material Submittal | 1 | 2024-11-13 | 2024-11-13
R7S1-EMMS-1550 | Wooden Doors materials and Hardwares - Material Submittal | 12 | 2024-11-21 | 2024-12-04
R7S1-EMMS-1560 | Hollow Metal Doors for Utility Rooms - Material Submittal | 10 | 2024-12-04 | 2024-12-15
FINISHES |  | 150 | 2024-10-31 | 2025-04-29
R7S1-EMMS-1610 | Paint "External" - Material Submittal | 1 | 2024-10-31 | 2024-10-31
R7S1-EMMS-1620 | Paint "Internal" - Material Submittal | 1 | 2024-10-31 | 2024-10-31
R7S1-EMMS-1630 | Gypsum board (MADA GYPSUM) - Material Submittal | 1 | 2024-11-14 | 2024-11-14
R7S1-EMMS-1650 | Ceiling Tiles "Suspenstion System" - Material Submittal | 1 | 2024-11-14 | 2024-11-14
R7S1-EMMS-1640 | Acoustic insulation - Material Submittal | 4 | 2024-11-17 | 2024-11-20
R7S1-EMMS-1570 | 60X60X9 Porcelain Floor Tiles - Material Submittal | 8 | 2024-11-19 | 2024-11-27
R7S1-EMMS-1580 | 60X60X9 Porcelain Floor Tiles, Apartment Balconies - Material Submittal | 8 | 2024-11-19 | 2024-11-27
R7S1-EMMS-1590 | Glazed Ceramic Tile 30X30 - Material Submittal | 8 | 2024-11-19 | 2024-11-27
R7S1-EMMS-1680 | 30 X 30 cm Porcelain tiles - Material Submittal | 8 | 2024-11-19 | 2024-11-27
R7S1-EMMS-1710 | Weber Polyurethane jointseal PU MC - Material Submittal | 24 | 2024-11-14 | 2024-12-11
R7S1-EMMS-1700 | Proterminal Tile Trim - Material Submittal | 8 | 2024-12-08 | 2024-12-16
R7S1-EMMS-1660 | Stair Tile and Details - Material Submittal | 91 | 2025-01-01 | 2025-04-22
R7S1-EMMS-1670 | Epoxy Paint System - Material Submittal | 74 | 2025-01-23 | 2025-04-24
R7S1-EMMS-1690 | Entrance Floor Matt UCFM 24 Anti-slip Heavy duty - Material Submittal | 4 | 2025-04-26 | 2025-04-29
SPECIAL ITEMS |  | 182 | 2024-11-07 | 2025-05-01
R7S1-EMMS-1740 | Elevator - Material Submittal | 1 | 2024-11-07 | 2024-11-07
R7S1-EMMS-1720 | Fall Arrest System - Material Submittal | 42 | 2025-01-21 | 2025-03-11
R7S1-EMMS-1750 | Chute system - Material Submittal | 60 | 2025-02-02 | 2025-04-17
R7S1-EMMS-1730 | Cross- Over Bridges for Roof Access - Material Submittal | 4 | 2025-04-28 | 2025-05-01
KITCHENETTE |  | 30 | 2024-10-24 | 2024-11-27
R7S1-EMMS-1760 | Kitchen Top Cabinet & Accessories - Material Submittal | 30 | 2024-10-24 | 2024-11-27
R7S1-EMMS-1770 | Wardrobe - Material Submittal | 26 | 2024-10-29 | 2024-11-27
TOILET POD |  | 30 | 2024-11-09 | 2024-12-12
R7S1-EMMS-1780 | Toilet Pod Material (Arch & Civil) - Material Submittal | 30 | 2024-11-09 | 2024-12-12
MECHANICAL |  | 127 | 2024-10-22 | 2025-03-19
HVAC |  | 115 | 2024-10-29 | 2025-03-12
R7S1-EMMS-1790 | Concealed FCU's - Material Submittal | 1 | 2024-10-29 | 2024-10-29
R7S1-EMMS-2930 | PICV for FCUS & FAHU's - Material Submittal | 1 | 2024-11-07 | 2024-11-07
R7S1-EMMS-1970 | Chilled Water Valves Accessories - Material Submittal | 1 | 2024-11-11 | 2024-11-11
R7S1-EMMS-1910 | Vibration Isolators - Material Submittal | 1 | 2024-11-14 | 2024-11-14
R7S1-EMMS-1880 | Acoustic Insulation - HVAC - Material Submittal | 1 | 2024-11-17 | 2024-11-17
R7S1-EMMS-1890 | Flexible Ducts - Material Submittal | 1 | 2024-11-18 | 2024-11-18
R7S1-EMMS-1900 | Flexible Duct Connectors - Material Submittal | 6 | 2024-11-12 | 2024-11-18
R7S1-EMMS-1950 | CHW Pipes & Fittings - Aboveground - Material Submittal | 13 | 2024-11-05 | 2024-11-19
R7S1-EMMS-1850 | Pre-Insulated Ducts for HVAC Ducting System (Internal) - Material Submittal | 1 | 2024-11-23 | 2024-11-23
R7S1-EMMS-1820 | Thermostat - Material Submittal | 6 | 2024-11-21 | 2024-11-27
R7S1-EMMS-2970 | BTU Meter - Material Submittal | 1 | 2024-12-02 | 2024-12-02
R7S1-EMMS-2940 | Copper Tubes & Fittings - Material Submittal | 5 | 2024-12-02 | 2024-12-07
R7S1-EMMS-2980 | Insulation Duct Tape / Duct Flange Gasket / Rubber Support Insert for Insulated Pipe - Material Submittal | 19 | 2024-11-16 | 2024-12-07
R7S1-EMMS-1870 | Chilled Water, Refrigerant & Condensate Insulation - Material Submittal | 15 | 2024-11-23 | 2024-12-09
R7S1-EMMS-1940 | Air Outlets (Grilles / Diffusers / Registers / Louvers, Exhaust Disc etc.,) - Material Submittal | 29 | 2024-11-09 | 2024-12-11
R7S1-EMMS-1810 | DX Split Units - Material Submittal | 7 | 2024-12-04 | 2024-12-11
R7S1-EMMS-1930 | Dampers (VCD, FD, NRD, MFD, Motorized Volume Damper & Motorized Fire Smoke Damper - Material Submittal | 20 | 2024-11-20 | 2024-12-12
R7S1-EMMS-1960 | CHW Pipes & Fittings - Underground - Material Submittal | 15 | 2024-11-30 | 2024-12-16
R7S1-EMMS-2950 | Kitchen Exhaust Hood (Recirculation type) - Material Submittal | 26 | 2024-11-18 | 2024-12-17
R7S1-EMMS-2990 | Chilled water Expansion joint (If required) - Material Submittal | 21 | 2024-12-09 | 2025-01-01
R7S1-EMMS-1860 | Preinsulated Phenolic HVAC Ducting System (External) - Material Submittal | 2 | 2025-01-20 | 2025-01-21
R7S1-EMMS-1800 | FAHU's - Material Submittal | 2 | 2025-01-22 | 2025-01-23
R7S1-EMMS-1840 | Sound Attenuator - Material Submittal | 52 | 2024-12-15 | 2025-02-12
R7S1-EMMS-1830 | Ventilation Fans - Material Submittal | 59 | 2024-12-14 | 2025-02-19
R7S1-EMMS-2960 | Chemical Treatment for Chilled water system - Material Submittal | 58 | 2025-01-04 | 2025-03-12
PLUMBING - WATER SUPPLY |  | 127 | 2024-10-22 | 2025-03-19
R7S1-EMMS-1980 | PEX Pipes & Fittings - Material Submittal | 1 | 2024-10-22 | 2024-10-22
R7S1-EMMS-1990 | A/G Water supply Pipes & Fittings - PPR - Material Submittal | 1 | 2024-10-22 | 2024-10-22
R7S1-EMMS-2000 | U/G Water supply pipes & Fittings - HDPE - Material Submittal | 1 | 2024-10-22 | 2024-10-22
R7S1-EMMS-2050 | Sanitary Fixtures & Wares (Kitchen Sink & its Mixer, Janitor Sink & Its Faucets, Angle Valve etc.) - Material Submittal | 1 | 2024-11-11 | 2024-11-11
R7S1-EMMS-2010 | Water Supply Valves & Accessories. (Incl PRV, AAV, WHA & TMV) - Material Submittal | 20 | 2024-11-16 | 2024-12-08
R7S1-EMMS-2030 | Thermal Insulation (For Hot Water Supply & Return) - Material Submittal | 30 | 2024-11-16 | 2024-12-19
R7S1-EMMS-2020 | Solar Water Heaters (Includingr Pumps, Valves & Accessories) - Material Submittal | 28 | 2025-02-15 | 2025-03-19
R7S1-EMMS-2040 | Steel pipe and fitting for solar system closed loop - Material Submittal | 28 | 2025-02-15 | 2025-03-19
DRAINAGE |  | 33 | 2024-10-22 | 2024-11-28
R7S1-EMMS-2170 | Drainage A/G and U/G Pipes & Fittings (Soil, Waste, Vent, RWP, CDP) - Material Submittal | 1 | 2024-10-22 | 2024-10-22
R7S1-EMMS-2180 | Bottle Gully Trap - Material Submittal | 1 | 2024-10-22 | 2024-10-22
R7S1-EMMS-2210 | Rain Water Down Spout Nozzle - Material Submittal | 1 | 2024-10-22 | 2024-10-22
R7S1-EMMS-2200 | Roof Drain, Funnel Drain, Rain Water Outlet - Material Submittal | 1 | 2024-11-25 | 2024-11-25
R7S1-EMMS-2190 | Floor cleanout, Floor Drain, Balcony Drain, etc. - Material Submittal | 10 | 2024-11-18 | 2024-11-28
FIRE FIGHTING |  | 42 | 2024-10-22 | 2024-12-09
R7S1-EMMS-2360 | Above Ground Fire Fighting pipes & Fittings - Material Submittal | 1 | 2024-10-22 | 2024-10-22
R7S1-EMMS-2370 | Underground Fire Fighting Pipes & Fittings - Material Submittal | 1 | 2024-10-23 | 2024-10-23
R7S1-EMMS-2390 | Sprinklers - Material Submittal | 8 | 2024-11-18 | 2024-11-26
R7S1-EMMS-2380 | Fire Fighting Specialities (FHC, Valves, Fire Blanket etc.) - Material Submittal | 15 | 2024-11-23 | 2024-12-09
R7S1-EMMS-2400 | Fire Extinguishers - Material Submittal | 1 | 2024-12-09 | 2024-12-09
MECHANICAL - GENERAL |  | 2 | 2024-11-05 | 2024-11-06
R7S1-EMMS-2550 | Mechanical Hangers & Supports for MEP Services - Material Submittal | 1 | 2024-11-05 | 2024-11-05
R7S1-EMMS-2560 | Identification Labels & Warning Tapes - Material Submittal | 1 | 2024-11-06 | 2024-11-06
R7S1-EMMS-2570 | Paints for CHW and Firefighting Pipes & Fittings - Material Submittal | 1 | 2024-11-06 | 2024-11-06
TOILET PODS MEP MATERIALS |  | 1 | 2024-10-31 | 2024-10-31
R7S1-EMMS-2740 | Toilet Pods MEP Material Submital - Linear Apartments - Material Submittal | 1 | 2024-10-31 | 2024-10-31
ELECTRICAL |  | 171 | 2024-10-20 | 2025-05-12
ELECTRICAL - LOW VOLTAGE |  | 144 | 2024-10-20 | 2025-04-10
R7S1-EMMS-3000 | PVC Conduits,PVC Boxes,GI Back Boxes - Material Submittal | 1 | 2024-10-20 | 2024-10-20
R7S1-EMMS-3020 | Galvanised Steel Back box - Material Submittal | 1 | 2024-10-20 | 2024-10-20
R7S1-EMMS-3030 | Steel Flexible Conduits and Accessories - Material Submittal | 1 | 2024-10-20 | 2024-10-20
R7S1-EMMS-3010 | EMT Conduits and Accessories / RSC / IMC Conduits and Accessories - Material Submittal | 1 | 2024-10-22 | 2024-10-22
R7S1-EMMS-3090 | Wiring Accessories - Material Submittal | 1 | 2024-10-29 | 2024-10-29
R7S1-EMMS-3040 | LV Cables & Wires - Material Submittal | 1 | 2024-11-06 | 2024-11-06
R7S1-EMMS-3130 | Internal & External Lighting Fixtures including Emergency & Exit Lighting Fixtures - Material Submittal | 4 | 2024-11-04 | 2024-11-07
R7S1-EMMS-3060 | UPVC Ducts and Accessories (For Under ground Sleeves & Duct bank) - Material Submittal | 1 | 2024-11-11 | 2024-11-11
R7S1-EMMS-3070 | Cables Lugs and Glands - Material Submittal | 8 | 2024-11-12 | 2024-11-20
R7S1-EMMS-3080 | Cables Management System (Trays, Basket, Accessories, Fittings). - Material Submittal | 6 | 2024-11-14 | 2024-11-20
R7S1-EMMS-3100 | LV Panels (Final DBs Inside Apartments & Studios) - Material Submittal | 24 | 2024-11-16 | 2024-12-12
R7S1-EMMS-3120 | Earthing and Lightning Protection System - Material Submittal | 18 | 2024-11-26 | 2024-12-17
R7S1-EMMS-3110 | LVPanels (MDB, SMDB) & Final DBs for service areas - Material Submittal | 52 | 2024-11-30 | 2025-01-28
R7S1-EMMS-3050 | Isolator (Disconnector Switch) - Material Submittal | 59 | 2025-01-27 | 2025-04-10
EXTRA LOW VOLTAGE |  | 167 | 2024-10-24 | 2025-05-12
R7S1-EMMS-3230 | Optical Network Terminal Cabinet (ONT) for Studios & Apartments - Material Submittal | 1 | 2024-10-24 | 2024-10-24
R7S1-EMMS-3190 | Fire Alarm Cable - Material Submittal | 1 | 2024-10-31 | 2024-10-31
R7S1-EMMS-3250 | Fire Alarm System & Voice Evacuation System - Material Submittal | 1 | 2024-11-14 | 2024-11-14
R7S1-EMMS-3270 | Access Control system - Material Submittal | 1 | 2024-11-17 | 2024-11-17
R7S1-EMMS-3200 | IBMS Cables - Material Submittal | 1 | 2024-11-25 | 2024-11-25
R7S1-EMMS-3220 | Access control Sytem Cables - Material Submittal | 1 | 2024-11-25 | 2024-11-25
R7S1-EMMS-3210 | Low Current System - Passive Components - Material Submittal | 22 | 2024-11-18 | 2024-12-12
R7S1-EMMS-3240 | CCTV System - Material Submittal | 25 | 2024-11-17 | 2024-12-15
R7S1-EMMS-3300 | Uniterruptable Power Supply - UPS (for BMS & Security Network only) - Material Submittal | 8 | 2024-12-11 | 2024-12-19
R7S1-EMMS-3280 | Active Components for complete ELV System - Material Submittal | 48 | 2024-12-09 | 2025-02-02
R7S1-EMMS-3290 | Motion Sensor - Material Submittal | 86 | 2024-12-29 | 2025-04-13
R7S1-EMMS-3260 | Integrated Building Management system - Material Submittal | 4 | 2025-05-08 | 2025-05-12
MATERIAL APPROVALS |  | 256 | 2024-10-20 | 2025-06-03
CIVIL |  | 119 | 2024-10-22 | 2025-02-17
CONCRETE WORKS |  | 119 | 2024-10-22 | 2025-02-17
R7S1-EMMA-3360 | MasterKure 161, Bitumen based damp proofing membrane for protection and curing of concrete- structures Material Approval | 4 | 2024-10-23 | 2024-10-26
R7S1-EMMA-3390 | Expansion Joint Filler - Bitu-Flex "Bitumen Impregnated Expansion Joint Filler - Material Approval | 4 | 2024-10-23 | 2024-10-26
R7S1-EMMA-3340 | Bonding Agent - Material Approval | 6 | 2024-10-22 | 2024-10-27
R7S1-EMMA-3350 | Bitumen Protective coating (Bitumen Paint) - Material Approval | 3 | 2024-10-26 | 2024-10-28
R7S1-EMMA-3370 | Concrete Repair Material (WEBEREP ST), Non-Metallic Non Shrink Fiber reinforced repair mortar - Material Approval | 3 | 2024-10-26 | 2024-10-28
R7S1-EMMA-3410 | Release Agent (Weber.ad dem 22) - Material Approval | 7 | 2024-10-22 | 2024-10-28
R7S1-EMMA-3440 | Vapor barrier Sheet - 1000 gauge - Material Approval | 7 | 2024-10-22 | 2024-10-28
R7S1-EMMA-3325 | Concrete Curing Compound Weber Cure Y20 - Material Approval | 7 | 2024-10-22 | 2024-10-28
R7S1-EMMA-3320 | CEMENT (SRC & OPC) - Material Approval | 7 | 2024-10-31 | 2024-11-06
R7S1-EMMA-3380 | Non-shrink, cement-based plastering for concrete repair 3 : 10 mm - Material Approval | 7 | 2024-10-31 | 2024-11-06
R7S1-EMMA-3310 | Concrete Mix Design C20, C40 - Material Approval | 8 | 2024-11-13 | 2024-11-20
R7S1-EMMA-3420 | Concrete cover spacer - Material Approval | 8 | 2024-11-13 | 2024-11-20
R7S1-EMMA-3450 | GULF 1200 Silicone (Anti-fungus & Anti Bacterial Silicone Sealant) - Material Approval | 8 | 2024-11-13 | 2024-11-20
R7S1-EMMA-3470 | Reinforcement Steel - Material Approval | 8 | 2024-11-13 | 2024-11-20
R7S1-EMMA-3430 | Binding Wire - Material Approval | 14 | 2024-11-13 | 2024-11-26
R7S1-EMMA-3330 | Anti-termite Treatment - Material Approval | 16 | 2024-11-24 | 2024-12-09
R7S1-EMMA-3460 | Solid block work 20x20x40 cm - Material Approval | 5 | 2024-12-16 | 2024-12-21
R7S1-EMMA-3400 | Epoxy Anchoring (Weberanc 405) - Material Approval | 2 | 2024-12-31 | 2025-01-01
R7S1-EMMA-3480 | Floor Expansion Joint - Material Approval | 41 | 2025-01-08 | 2025-02-17
TILE WORKS |  | 58 | 2024-11-13 | 2025-01-09
R7S1-EMMA-3490 | Water resistant tile grout - Material Approval | 7 | 2024-11-13 | 2024-11-19
R7S1-EMMA-3510 | Tile Grout (Vitonit) - Material Approval | 7 | 2024-11-13 | 2024-11-19
R7S1-EMMA-3520 | Fire Stop Sealant - Material Approval | 11 | 2024-12-19 | 2024-12-29
R7S1-EMMA-3500 | Tile Adhesive 1) MasterTile® FLX 23 & 2) MasterTile® FLX 24 - Material Approval | 47 | 2024-11-24 | 2025-01-09
EXTERNAL WORKS |  | 97 | 2024-11-13 | 2025-02-17
R7S1-EMMA-3530 | Aluminum decorative hinged screen with wood finish fixed on glazed windows - Material Approval | 9 | 2024-11-13 | 2024-11-21
R7S1-EMMA-3540 | Decorative Louvers/Perforated sheet to cover MEP services at Roof - Material Approval | 8 | 2025-02-10 | 2025-02-17
PRECAST SYSTEM |  | 41 | 2024-11-04 | 2024-12-15
R7S1-EMMA-3610 | Mix design for precast concrete walls - Material Approval | 8 | 2024-11-13 | 2024-11-20
R7S1-EMMA-3550 | Concure WB309 - Material Approval | 24 | 2024-11-04 | 2024-11-27
R7S1-EMMA-3560 | Reebol WB - Material Approval | 24 | 2024-11-04 | 2024-11-27
R7S1-EMMA-3570 | Cbond - Material Approval | 24 | 2024-11-04 | 2024-11-27
R7S1-EMMA-3580 | SikaRep fine - Material Approval | 24 | 2024-11-04 | 2024-11-27
R7S1-EMMA-3590 | Sika Grout 114 - Material Approval | 24 | 2024-11-04 | 2024-11-27
R7S1-EMMA-3600 | Master Flow 522 - Material Approval | 24 | 2024-11-04 | 2024-11-27
R7S1-EMMA-3640 | Wire Mesh (Reinforcement Steel Wire Mesh) - Material Approval | 24 | 2024-11-04 | 2024-11-27
R7S1-EMMA-3650 | PVC Tie Wire & Black Annealed Wire - Material Approval | 24 | 2024-11-04 | 2024-11-27
R7S1-EMMA-3660 | Lifting Socket - Material Approval | 24 | 2024-11-04 | 2024-11-27
R7S1-EMMA-3670 | Ties and Connector Pins - Material Approval | 24 | 2024-11-04 | 2024-11-27
R7S1-EMMA-3680 | Low Relaxation Pre-Stressing Strands - Material Approval | 24 | 2024-11-04 | 2024-11-27
R7S1-EMMA-3690 | Concrete Spacers & Chamfers - Material Approval | 24 | 2024-11-04 | 2024-11-27
R7S1-EMMA-3710 | Cast In Channel - Material Approval | 24 | 2024-11-04 | 2024-11-27
R7S1-EMMA-3720 | Connecting Loop - Material Approval | 24 | 2024-11-04 | 2024-11-27
R7S1-EMMA-3730 | Corrugated Pipe - Material Approval | 24 | 2024-11-04 | 2024-11-27
R7S1-EMMA-3620 | Thermal Insulation - Material Approval | 41 | 2024-11-04 | 2024-12-15
R7S1-EMMA-3630 | Thermal Insulation Esscofoam 40 (material and prequalification) - Material Approval | 41 | 2024-11-04 | 2024-12-15
R7S1-EMMA-3700 | Backup Rods (Filler Rods) - Material Approval | 41 | 2024-11-04 | 2024-12-15
ARCHITECTURE |  | 247 | 2024-10-29 | 2025-06-03
EXTERNAL WORKS |  | 15 | 2025-05-20 | 2025-06-03
R7S1-EMMA-3740 | Balcony metal grating handrail - Material Approval | 15 | 2025-05-20 | 2025-06-03
R7S1-EMMA-3750 | Ladders - Material Approval | 15 | 2025-05-20 | 2025-06-03
THERMAL & MOISTURE PROTECTION: |  | 6 | 2025-02-12 | 2025-02-17
R7S1-EMMA-3760 | Roof Water Proofing - Material Approval | 6 | 2025-02-12 | 2025-02-17
DOORS & WINDOWS |  | 42 | 2024-11-13 | 2024-12-24
R7S1-EMMA-3780 | Aluminum Profiles - Material Approval | 9 | 2024-11-13 | 2024-11-21
R7S1-EMMA-3790 | Glazing details for external doors and windows (Guardian Sungurad)/ Acoustic performance datasheet. - Material Approval | 9 | 2024-11-13 | 2024-11-21
R7S1-EMMA-3800 | Aluminum doors & windows - Material Approval | 9 | 2024-11-13 | 2024-11-21
R7S1-EMMA-3810 | Ironmongery & Hardware - Material Approval | 9 | 2024-11-13 | 2024-11-21
R7S1-EMMA-3820 | Wooden Doors materials and Hardwares - Material Approval | 4 | 2024-12-01 | 2024-12-04
R7S1-EMMA-3830 | Hollow Metal Doors for Utility Rooms - Material Approval | 9 | 2024-12-16 | 2024-12-24
FINISHES |  | 195 | 2024-11-01 | 2025-05-14
R7S1-EMMA-3910 | Acoustic insulation - Material Approval | 4 | 2024-11-17 | 2024-11-20
R7S1-EMMA-3900 | Gypsum board (MADA GYPSUM) - Material Approval | 11 | 2024-11-14 | 2024-11-24
R7S1-EMMA-3920 | Ceiling Tiles "Suspenstion System" - Material Approval | 11 | 2024-11-14 | 2024-11-24
R7S1-EMMA-3880 | Paint "External" - Material Approval | 27 | 2024-11-01 | 2024-11-27
R7S1-EMMA-3890 | Paint "Internal" - Material Approval | 27 | 2024-11-01 | 2024-11-27
R7S1-EMMA-3840 | 60X60X9 Porcelain Floor Tiles - Material Approval | 5 | 2024-11-27 | 2024-12-01
R7S1-EMMA-3850 | 60X60X9 Porcelain Floor Tiles, Apartment Balconies - Material Approval | 5 | 2024-11-27 | 2024-12-01
R7S1-EMMA-3860 | Glazed Ceramic Tile 30X30 - Material Approval | 5 | 2024-11-27 | 2024-12-01
R7S1-EMMA-3950 | 30 X 30 cm Porcelain tiles - Material Approval | 5 | 2024-11-27 | 2024-12-01
R7S1-EMMA-3980 | Weber Polyurethane jointseal PU MC - Material Approval | 23 | 2024-11-19 | 2024-12-11
R7S1-EMMA-3970 | Proterminal Tile Trim - Material Approval | 8 | 2024-12-08 | 2024-12-16
R7S1-EMMA-3930 | Stair Tile and Details - Material Approval | 114 | 2025-01-01 | 2025-04-24
R7S1-EMMA-3940 | Epoxy Paint System - Material Approval | 78 | 2025-02-06 | 2025-04-24
R7S1-EMMA-3960 | Entrance Floor Matt UCFM 24 Anti-slip Heavy duty - Material Approval | 15 | 2025-04-30 | 2025-05-14
SPECIAL ITEMS |  | 238 | 2024-11-07 | 2025-05-16
R7S1-EMMA-4010 | Elevator - Material Approval | 7 | 2024-11-07 | 2024-11-13
R7S1-EMMA-3990 | Fall Arrest System - Material Approval | 54 | 2025-01-22 | 2025-03-16
R7S1-EMMA-4020 | Chute system - Material Approval | 78 | 2025-02-06 | 2025-04-24
R7S1-EMMA-4000 | Cross- Over Bridges for Roof Access - Material Approval | 15 | 2025-05-02 | 2025-05-16
KITCHENETTE |  | 36 | 2024-10-29 | 2024-12-03
R7S1-EMMA-4030 | Kitchen Top Cabinet & Accessories - Material Approval | 36 | 2024-10-29 | 2024-12-03
R7S1-EMMA-4040 | Wardrobe - Material Approval | 31 | 2024-11-03 | 2024-12-03
TOILET POD |  | 30 | 2024-11-13 | 2024-12-12
R7S1-EMMA-4050 | Toilet Pod Material (Arch & Civil) - Material Approval | 30 | 2024-11-13 | 2024-12-12
MECHANICAL |  | 167 | 2024-10-22 | 2025-04-06
HVAC |  | 146 | 2024-10-29 | 2025-03-23
R7S1-EMMA-4060 | Concealed FCU's - Material Approval | 3 | 2024-10-29 | 2024-10-31
R7S1-EMMA-4470 | PICV for FCUS & FAHU's - Material Approval | 7 | 2024-11-07 | 2024-11-13
R7S1-EMMA-4160 | Flexible Ducts - Material Approval | 3 | 2024-11-18 | 2024-11-20
R7S1-EMMA-4180 | Vibration Isolators - Material Approval | 7 | 2024-11-14 | 2024-11-20
R7S1-EMMA-4150 | Acoustic Insulation - HVAC - Material Approval | 5 | 2024-11-17 | 2024-11-21
R7S1-EMMA-4170 | Flexible Duct Connectors - Material Approval | 4 | 2024-11-18 | 2024-11-21
R7S1-EMMA-4220 | CHW Pipes & Fittings - Aboveground - Material Approval | 3 | 2024-11-19 | 2024-11-21
R7S1-EMMA-4240 | Chilled Water Valves Accessories - Material Approval | 11 | 2024-11-11 | 2024-11-21
R7S1-EMMA-4120 | Pre-Insulated Ducts for HVAC Ducting System (Internal) - Material Approval | 6 | 2024-11-23 | 2024-11-28
R7S1-EMMA-4090 | Thermostat - Material Approval | 5 | 2024-11-27 | 2024-12-01
R7S1-EMMA-4510 | BTU Meter - Material Approval | 2 | 2024-12-03 | 2024-12-04
R7S1-EMMA-4480 | Copper Tubes & Fittings - Material Approval | 36 | 2024-11-02 | 2024-12-07
R7S1-EMMA-4520 | Insulation Duct Tape / Duct Flange Gasket / Rubber Support Insert for Insulated Pipe - Material Approval | 5 | 2024-12-03 | 2024-12-07
R7S1-EMMA-4140 | Chilled Water, Refrigerant & Condensate Insulation - Material Approval | 7 | 2024-12-03 | 2024-12-09
R7S1-EMMA-4210 | Air Outlets (Grilles / Diffusers / Registers / Louvers, Exhaust Disc etc.,) - Material Approval | 31 | 2024-11-11 | 2024-12-11
R7S1-EMMA-4080 | DX Split Units - Material Approval | 8 | 2024-12-04 | 2024-12-11
R7S1-EMMA-4200 | Dampers (VCD, FD, NRD, MFD, Motorized Volume Damper & Motorized Fire Smoke Damper - Material Approval | 16 | 2024-11-27 | 2024-12-12
R7S1-EMMA-4230 | CHW Pipes & Fittings - Underground - Material Approval | 24 | 2024-11-30 | 2024-12-23
R7S1-EMMA-4490 | Kitchen Exhaust Hood (Recirculation type) - Material Approval | 21 | 2024-12-03 | 2024-12-23
R7S1-EMMA-4530 | Chilled water Expansion joint (If required) - Material Approval | 27 | 2024-12-13 | 2025-01-08
R7S1-EMMA-4070 | FAHU's - Material Approval | 3 | 2025-01-23 | 2025-01-25
R7S1-EMMA-4130 | Preinsulated Phenolic HVAC Ducting System (External) - Material Approval | 5 | 2025-01-21 | 2025-01-25
R7S1-EMMA-4110 | Sound Attenuator - Material Approval | 68 | 2024-12-19 | 2025-02-24
R7S1-EMMA-4100 | Ventilation Fans - Material Approval | 77 | 2024-12-18 | 2025-03-04
R7S1-EMMA-4500 | Chemical Treatment for Chilled water system - Material Approval | 26 | 2025-02-26 | 2025-03-23
PLUMBING - WATER SUPPLY |  | 167 | 2024-10-22 | 2025-04-06
R7S1-EMMA-4250 | PEX Pipes & Fittings - Material Approval | 9 | 2024-10-22 | 2024-10-30
R7S1-EMMA-4260 | A/G Water supply Pipes & Fittings - PPR - Material Approval | 9 | 2024-10-22 | 2024-10-30
R7S1-EMMA-4270 | U/G Water supply pipes & Fittings - HDPE - Material Approval | 9 | 2024-10-22 | 2024-10-30
R7S1-EMMA-4320 | Sanitary Fixtures & Wares (Kitchen Sink & its Mixer, Janitor Sink & Its Faucets, Angle Valve etc.) - Material Approval | 16 | 2024-11-11 | 2024-11-26
R7S1-EMMA-4280 | Water Supply Valves & Accessories. (Incl PRV, AAV, WHA & TMV) - Material Approval | 23 | 2024-11-16 | 2024-12-08
R7S1-EMMA-4300 | Thermal Insulation (For Hot Water Supply & Return) - Material Approval | 30 | 2024-11-20 | 2024-12-19
R7S1-EMMA-4290 | Solar Water Heaters (Includingr Pumps, Valves & Accessories) - Material Approval | 46 | 2025-02-20 | 2025-04-06
R7S1-EMMA-4310 | Steel pipe and fitting for solar system closed loop - Material Approval | 46 | 2025-02-20 | 2025-04-06
DRAINAGE |  | 41 | 2024-10-22 | 2024-12-01
R7S1-EMMA-4330 | Drainage A/G and U/G Pipes & Fittings (Soil, Waste, Vent, RWP, CDP) - Material Approval | 8 | 2024-10-22 | 2024-10-29
R7S1-EMMA-4370 | Rain Water Down Spout Nozzle - Material Approval | 8 | 2024-10-22 | 2024-10-29
R7S1-EMMA-4340 | Bottle Gully Trap - Material Approval | 9 | 2024-10-22 | 2024-10-30
R7S1-EMMA-4360 | Roof Drain, Funnel Drain, Rain Water Outlet - Material Approval | 3 | 2024-11-26 | 2024-11-28
R7S1-EMMA-4350 | Floor cleanout, Floor Drain, Balcony Drain, etc. - Material Approval | 4 | 2024-11-28 | 2024-12-01
FIRE FIGHTING |  | 63 | 2024-10-22 | 2024-12-23
R7S1-EMMA-4380 | Above Ground Fire Fighting pipes & Fittings - Material Approval | 10 | 2024-10-22 | 2024-10-31
R7S1-EMMA-4390 | Underground Fire Fighting Pipes & Fittings - Material Approval | 9 | 2024-10-23 | 2024-10-31
R7S1-EMMA-4410 | Sprinklers - Material Approval | 6 | 2024-11-26 | 2024-12-01
R7S1-EMMA-4400 | Fire Fighting Specialities (FHC, Valves, Fire Blanket etc.) - Material Approval | 15 | 2024-12-09 | 2024-12-23
R7S1-EMMA-4420 | Fire Extinguishers - Material Approval | 15 | 2024-12-09 | 2024-12-23
MECHANICAL - GENERAL |  | 12 | 2024-11-05 | 2024-11-16
R7S1-EMMA-4450 | Paints for CHW and Firefighting Pipes & Fittings - Material Approval | 1 | 2024-11-06 | 2024-11-06
R7S1-EMMA-4430 | Mechanical Hangers & Supports for MEP Services - Material Approval | 6 | 2024-11-05 | 2024-11-10
R7S1-EMMA-4440 | Identification Labels & Warning Tapes - Material Approval | 11 | 2024-11-06 | 2024-11-16
TOILET PODS MEP MATERIALS |  | 8 | 2024-10-31 | 2024-11-07
R7S1-EMMA-4460 | Toilet Pods MEP Material - Linear Apartments - Material Approval | 8 | 2024-10-31 | 2024-11-07
ELECTRICAL |  | 220 | 2024-10-20 | 2025-05-27
ELECTRICAL - LOW VOLTAGE |  | 185 | 2024-10-20 | 2025-04-22
R7S1-EMMA-4560 | Galvanised Steel Back box - Material Approval | 10 | 2024-10-20 | 2024-10-29
R7S1-EMMA-4540 | PVC Conduits,PVC Boxes,GI Back Boxes - Material Approval | 11 | 2024-10-20 | 2024-10-30
R7S1-EMMA-4550 | EMT Conduits and Accessories / RSC / IMC Conduits and Accessories - Material Approval | 9 | 2024-10-22 | 2024-10-30
R7S1-EMMA-4570 | Steel Flexible Conduits and Accessories - Material Approval | 11 | 2024-10-20 | 2024-10-30
R7S1-EMMA-4630 | Wiring Accessories - Material Approval | 7 | 2024-10-29 | 2024-11-04
R7S1-EMMA-4580 | LV Cables & Wires - Material Approval | 11 | 2024-11-06 | 2024-11-16
R7S1-EMMA-4670 | Internal & External Lighting Fixtures including Emergency & Exit Lighting Fixtures - Material Approval | 10 | 2024-11-07 | 2024-11-16
R7S1-EMMA-4600 | UPVC Ducts and Accessories (For Under ground Sleeves & Duct bank) - Material Approval | 9 | 2024-11-11 | 2024-11-19
R7S1-EMMA-4610 | Cables Lugs and Glands - Material Approval | 8 | 2024-11-20 | 2024-11-27
R7S1-EMMA-4620 | Cables Management System (Trays, Basket, Accessories, Fittings). - Material Approval | 7 | 2024-11-21 | 2024-11-27
R7S1-EMMA-4640 | LV Panels (Final DBs Inside Apartments & Studios) - Material Approval | 9 | 2024-12-04 | 2024-12-12
R7S1-EMMA-4660 | Earthing and Lightning Protection System - Material Approval | 29 | 2024-11-27 | 2024-12-25
R7S1-EMMA-4650 | LVPanels (MDB, SMDB) & Final DBs for service areas - Material Approval | 71 | 2024-12-02 | 2025-02-10
R7S1-EMMA-4590 | Isolator (Disconnector Switch) - Material Approval | 86 | 2025-01-27 | 2025-04-22
EXTRA LOW VOLTAGE |  | 216 | 2024-10-24 | 2025-05-27
R7S1-EMMA-4720 | Optical Network Terminal Cabinet (ONT) for Studios & Apartments - Material Approval | 8 | 2024-10-24 | 2024-10-31
R7S1-EMMA-4680 | Fire Alarm Cable - Material Approval | 11 | 2024-10-31 | 2024-11-10
R7S1-EMMA-4740 | Fire Alarm System & Voice Evacuation System - Material Approval | 14 | 2024-11-14 | 2024-11-27
R7S1-EMMA-4760 | Access Control system - Material Approval | 11 | 2024-11-17 | 2024-11-27
R7S1-EMMA-4690 | IBMS Cables - Material Approval | 10 | 2024-11-25 | 2024-12-04
R7S1-EMMA-4710 | Access control Sytem Cables - Material Approval | 10 | 2024-11-25 | 2024-12-04
R7S1-EMMA-4700 | Low Current System - Passive Components - Material Approval | 8 | 2024-12-04 | 2024-12-12
R7S1-EMMA-4790 | Uniterruptable Power Supply - UPS (for BMS & Security Network only) - Material Approval | 9 | 2024-12-11 | 2024-12-19
R7S1-EMMA-4730 | CCTV System - Material Approval | 37 | 2024-11-17 | 2024-12-23
R7S1-EMMA-4770 | Active Components for complete ELV System - Material Approval | 66 | 2024-12-09 | 2025-02-12
R7S1-EMMA-4780 | Motion Sensor - Material Approval | 55 | 2025-02-26 | 2025-04-21
R7S1-EMMA-4750 | Integrated Building Management system - Material Approval | 15 | 2025-05-13 | 2025-05-27
P. O |  | 272 | 2024-09-24 | 2025-06-30
SERVICES |  | 46 | 2024-09-24 | 2024-11-16
R7S1-EMPO-7780 | Appoint Soil Investigation & Data collection - P.O | 1 | 2024-09-24 | 2024-09-24
R7S1-EMPO-7790 | Appoint AOR Consultant - P.O | 1 | 2024-11-06 | 2024-11-06
R7S1-EMPO-7800 | 3rd Party Testing Lab for Construction Materials - P.O | 1 | 2024-11-06 | 2024-11-06
R7S1-EMPO-7810 | Appoint FLS Consultancy Services - P.O | 1 | 2024-11-16 | 2024-11-16
CIVIL |  | 197 | 2024-11-03 | 2025-06-30
CONCRETE WORKS |  | 93 | 2024-11-03 | 2025-02-18
R7S1-EMPO-4850 | MasterKure 161, Bitumen based damp proofing membrane for protection and curing of concrete structures. - PO | 1 | 2024-11-03 | 2024-11-03
R7S1-EMPO-4810 | CEMENT (SRC & OPC) - P.O | 1 | 2024-11-10 | 2024-11-10
R7S1-EMPO-4960 | Reinforcement Steel - P.O | 1 | 2024-11-14 | 2024-11-14
R7S1-EMPO-4800 | Concrete Mix Design C20, C40 - P.O | 6 | 2024-11-23 | 2024-11-28
R7S1-EMPO-4870 | Non-shrink, cement-based plastering for concrete repair 3 : 10 mm - P.O | 8 | 2024-11-20 | 2024-11-28
R7S1-EMPO-4910 | Concrete cover spacer - P.O | 1 | 2024-11-28 | 2024-11-28
R7S1-EMPO-4920 | Binding Wire - P.O | 1 | 2024-11-28 | 2024-11-28
R7S1-EMPO-4930 | Vapor barrier Sheet - 1000 gauge - P.O | 1 | 2024-11-28 | 2024-11-28
R7S1-EMPO-4815 | Concrete Curing Compound Weber Cure Y20 - P.O | 1 | 2024-11-28 | 2024-11-28
R7S1-EMPO-4830 | Bonding Agent - P.O | 1 | 2024-11-30 | 2024-11-30
R7S1-EMPO-4840 | Bitumen Protective coating (Bitumen Paint) - P.O | 1 | 2024-11-30 | 2024-11-30
R7S1-EMPO-4900 | Release Agent (Weber.ad dem 22) - P.O | 1 | 2024-11-30 | 2024-11-30
R7S1-EMPO-4860 | Concrete Repair Material (WEBEREP ST), Non-Metallic Non Shrink Fiber reinforced repair mortar - P.O | 1 | 2024-12-04 | 2024-12-04
R7S1-EMPO-4820 | Anti-termite Treatment - P.O | 2 | 2024-12-09 | 2024-12-10
R7S1-EMPO-4880 | Expansion Joint Filler - Bitu-Flex "Bitumen Impregnated Expansion Joint Filler - P.O | 7 | 2024-12-07 | 2024-12-14
R7S1-EMPO-4940 | GULF 1200 Silicone (Anti-fungus & Anti Bacterial Silicone Sealant) - P.O | 7 | 2024-12-07 | 2024-12-14
R7S1-EMPO-4950 | Solid block work 20x20x40 cm - P.O | 9 | 2024-12-19 | 2024-12-29
R7S1-EMPO-4890 | Epoxy Anchoring (Weberanc 405) - P.O | 1 | 2025-01-01 | 2025-01-01
R7S1-EMPO-4970 | Floor Expansion Joint - P.O | 23 | 2025-01-23 | 2025-02-18
TILE WORKS |  | 37 | 2024-11-18 | 2024-12-30
R7S1-EMPO-5000 | Tile Grout (Vitonit) - P.O | 1 | 2024-11-18 | 2024-11-18
R7S1-EMPO-4990 | Tile Adhesive 1) MasterTile® FLX 23 & 2) MasterTile® FLX 24 - P.O | 1 | 2024-11-30 | 2024-11-30
R7S1-EMPO-4980 | Water resistant tile grout - P.O | 1 | 2024-12-07 | 2024-12-07
R7S1-EMPO-5010 | Fire Stop Sealant - P.O | 7 | 2024-12-23 | 2024-12-30
EXTERNAL WORKS |  | 181 | 2024-11-21 | 2025-06-30
R7S1-EMPO-5020 | Aluminum decorative hinged screen with wood finish fixed on glazed windows - P.O | 1 | 2024-11-21 | 2024-11-21
R7S1-EMPO-5030 | Decorative Louvers/Perforated sheet to cover MEP services at Roof - P.O | 53 | 2025-04-26 | 2025-06-30
PRECAST SYSTEM |  | 22 | 2024-11-19 | 2024-12-14
R7S1-EMPO-5100 | Mix design for precast concrete walls - P.O | 1 | 2024-11-21 | 2024-11-21
R7S1-EMPO-5040 | Concure WB309 - P.O | 9 | 2024-11-19 | 2024-11-28
R7S1-EMPO-5050 | Reebol WB - P.O | 9 | 2024-11-19 | 2024-11-28
R7S1-EMPO-5060 | Cbond - P.O | 9 | 2024-11-19 | 2024-11-28
R7S1-EMPO-5070 | SikaRep fine - P.O | 9 | 2024-11-19 | 2024-11-28
R7S1-EMPO-5080 | Sika Grout 114 - P.O | 9 | 2024-11-19 | 2024-11-28
R7S1-EMPO-5090 | Master Flow 522 - P.O | 9 | 2024-11-19 | 2024-11-28
R7S1-EMPO-5130 | Wire Mesh (Reinforcement Steel Wire Mesh) - P.O | 9 | 2024-11-19 | 2024-11-28
R7S1-EMPO-5140 | PVC Tie Wire & Black Annealed Wire - P.O | 9 | 2024-11-19 | 2024-11-28
R7S1-EMPO-5150 | Lifting Socket - P.O | 9 | 2024-11-19 | 2024-11-28
R7S1-EMPO-5160 | Ties and Connector Pins - P.O | 9 | 2024-11-19 | 2024-11-28
R7S1-EMPO-5170 | Low Relaxation Pre-Stressing Strands - P.O | 9 | 2024-11-19 | 2024-11-28
R7S1-EMPO-5180 | Concrete Spacers & Chamfers - P.O | 9 | 2024-11-19 | 2024-11-28
R7S1-EMPO-5200 | Cast In Channel - P.O | 9 | 2024-11-19 | 2024-11-28
R7S1-EMPO-5210 | Connecting Loop - P.O | 9 | 2024-11-19 | 2024-11-28
R7S1-EMPO-5220 | Corrugated Pipe - P.O | 9 | 2024-11-19 | 2024-11-28
R7S1-EMPO-5110 | Thermal Insulation - P.O | 22 | 2024-11-19 | 2024-12-14
R7S1-EMPO-5120 | Thermal Insulation Esscofoam 40 (material and prequalification) - P.O | 22 | 2024-11-19 | 2024-12-14
R7S1-EMPO-5190 | Backup Rods (Filler Rods) - P.O | 22 | 2024-11-19 | 2024-12-14
ARCHITECTURE |  | 229 | 2024-11-13 | 2025-06-04
EXTERNAL WORKS |  | 1 | 2025-06-04 | 2025-06-04
R7S1-EMPO-5230 | Balcony metal grating handrail - P.O | 1 | 2025-06-04 | 2025-06-04
R7S1-EMPO-5240 | Ladders - P.O | 1 | 2025-06-04 | 2025-06-04
THERMAL & MOISTURE PROTECTION: |  | 1 | 2025-02-18 | 2025-02-18
R7S1-EMPO-5250 | Roof Water Proofing - P.O | 1 | 2025-02-18 | 2025-02-18
DOORS & WINDOWS |  | 31 | 2024-11-21 | 2024-12-26
R7S1-EMPO-5270 | Aluminum Profiles - P.O | 3 | 2024-11-21 | 2024-11-24
R7S1-EMPO-5280 | Glazing details for external doors and windows (Guardian Sungurad)/ Acoustic performance datasheet. - P.O | 3 | 2024-11-21 | 2024-11-24
R7S1-EMPO-5290 | Aluminum doors & windows - P.O | 3 | 2024-11-21 | 2024-11-24
R7S1-EMPO-5300 | Ironmongery & Hardware - P.O | 3 | 2024-11-21 | 2024-11-24
R7S1-EMPO-5310 | Wooden Doors materials and Hardwares - P.O | 7 | 2024-12-07 | 2024-12-14
R7S1-EMPO-5320 | Hollow Metal Doors for Utility Rooms - P.O | 3 | 2024-12-24 | 2024-12-26
FINISHES |  | 149 | 2024-11-28 | 2025-05-15
R7S1-EMPO-5390 | Gypsum board (MADA GYPSUM) - P.O | 1 | 2024-12-01 | 2024-12-01
R7S1-EMPO-5410 | Ceiling Tiles "Suspenstion System" - P.O | 1 | 2024-12-01 | 2024-12-01
R7S1-EMPO-5370 | Paint "External" - P.O | 4 | 2024-11-28 | 2024-12-02
R7S1-EMPO-5380 | Paint "Internal" - P.O | 4 | 2024-11-28 | 2024-12-02
R7S1-EMPO-5330 | 60X60X9 Porcelain Floor Tiles - P.O | 1 | 2024-12-03 | 2024-12-03
R7S1-EMPO-5340 | 60X60X9 Porcelain Floor Tiles, Apartment Balconies - P.O | 1 | 2024-12-03 | 2024-12-03
R7S1-EMPO-5350 | Glazed Ceramic Tile 30X30 - P.O | 1 | 2024-12-03 | 2024-12-03
R7S1-EMPO-5440 | 30 X 30 cm Porcelain tiles - P.O | 1 | 2024-12-03 | 2024-12-03
R7S1-EMPO-5400 | Acoustic insulation - P.O | 1 | 2024-12-07 | 2024-12-07
R7S1-EMPO-5470 | Weber Polyurethane jointseal PU MC - P.O | 8 | 2024-12-04 | 2024-12-12
R7S1-EMPO-5460 | Proterminal Tile Trim - P.O | 1 | 2024-12-17 | 2024-12-17
R7S1-EMPO-5420 | Stair Tile and Details - P.O | 3 | 2025-02-24 | 2025-02-26
R7S1-EMPO-5430 | Epoxy Paint System - P.O | 3 | 2025-02-24 | 2025-02-26
R7S1-EMPO-5450 | Entrance Floor Matt UCFM 24 Anti-slip Heavy duty - P.O | 1 | 2025-05-15 | 2025-05-15
SPECIAL ITEMS |  | 223 | 2024-11-20 | 2025-05-17
R7S1-EMPO-5500 | Elevator - P.O | 1 | 2024-11-20 | 2024-11-20
R7S1-EMPO-5510 | Chute system - P.O | 1 | 2025-02-08 | 2025-02-08
R7S1-EMPO-5480 | Fall Arrest System - P.O | 1 | 2025-03-18 | 2025-03-18
R7S1-EMPO-5490 | Cross- Over Bridges for Roof Access - P.O | 1 | 2025-05-17 | 2025-05-17
KITCHENETTE |  | 18 | 2024-11-13 | 2024-12-03
R7S1-EMPO-5520 | Kitchen Top Cabinet & Accessories - P.O | 18 | 2024-11-13 | 2024-12-03
R7S1-EMPO-5530 | Wardrobe - P.O | 14 | 2024-11-18 | 2024-12-03
TOILET POD |  | 2 | 2024-11-26 | 2024-11-27
R7S1-EMPO-5540 | Toilet Pod Material (Arch & Civil) - P.O | 2 | 2024-11-26 | 2024-11-27
MECHANICAL |  | 130 | 2024-11-03 | 2025-04-08
HVAC |  | 126 | 2024-11-04 | 2025-04-05
R7S1-EMPO-5550 | Concealed FCU's - P.O | 1 | 2024-11-04 | 2024-11-04
R7S1-EMPO-5710 | CHW Pipes & Fittings - Aboveground - P.O | 1 | 2024-11-25 | 2024-11-25
R7S1-EMPO-5700 | Air Outlets (Grilles / Diffusers / Registers / Louvers, Exhaust Disc etc.,) - P.O | 2 | 2024-11-26 | 2024-11-27
R7S1-EMPO-5730 | Chilled Water Valves Accessories - P.O | 1 | 2024-11-27 | 2024-11-27
R7S1-EMPO-5960 | PICV for FCUS & FAHU's - P.O | 1 | 2024-11-28 | 2024-11-28
R7S1-EMPO-5660 | Flexible Duct Connectors - P.O | 1 | 2024-11-30 | 2024-11-30
R7S1-EMPO-5650 | Flexible Ducts - P.O | 1 | 2024-12-01 | 2024-12-01
R7S1-EMPO-5580 | Thermostat - P.O | 1 | 2024-12-03 | 2024-12-03
R7S1-EMPO-5640 | Acoustic Insulation - HVAC - P.O | 1 | 2024-12-03 | 2024-12-03
R7S1-EMPO-5670 | Vibration Isolators - P.O | 1 | 2024-12-03 | 2024-12-03
R7S1-EMPO-5610 | Pre-Insulated Ducts for HVAC Ducting System (Internal) - P.O | 1 | 2024-12-04 | 2024-12-04
R7S1-EMPO-6000 | BTU Meter - P.O | 1 | 2024-12-05 | 2024-12-05
R7S1-EMPO-6010 | Insulation Duct Tape / Duct Flange Gasket / Rubber Support Insert for Insulated Pipe - P.O | 1 | 2024-12-05 | 2024-12-05
R7S1-EMPO-5980 | Kitchen Exhaust Hood (Recirculation type) - P.O | 2 | 2024-12-07 | 2024-12-08
R7S1-EMPO-5630 | Chilled Water, Refrigerant & Condensate Insulation - P.O | 1 | 2024-12-10 | 2024-12-10
R7S1-EMPO-5690 | Dampers (VCD, FD, NRD, MFD, Motorized Volume Damper & Motorized Fire Smoke Damper - P.O | 3 | 2024-12-10 | 2024-12-12
R7S1-EMPO-5570 | DX Split Units - P.O | 1 | 2024-12-15 | 2024-12-15
R7S1-EMPO-5970 | Copper Tubes & Fittings - P.O | 1 | 2024-12-15 | 2024-12-15
R7S1-EMPO-5720 | CHW Pipes & Fittings - Underground - P.O | 1 | 2024-12-25 | 2024-12-25
R7S1-EMPO-6020 | Chilled water Expansion joint (If required) - P.O | 11 | 2024-12-28 | 2025-01-08
R7S1-EMPO-5560 | FAHU's - P.O | 1 | 2025-02-08 | 2025-02-08
R7S1-EMPO-5620 | Preinsulated Phenolic HVAC Ducting System (External) - P.O | 1 | 2025-02-08 | 2025-02-08
R7S1-EMPO-5600 | Sound Attenuator - P.O | 1 | 2025-02-25 | 2025-02-25
R7S1-EMPO-5590 | Ventilation Fans - P.O | 1 | 2025-03-06 | 2025-03-06
R7S1-EMPO-5990 | Chemical Treatment for Chilled water system - P.O | 1 | 2025-04-05 | 2025-04-05
PLUMBING - WATER SUPPLY |  | 130 | 2024-11-03 | 2025-04-08
R7S1-EMPO-5740 | PEX Pipes & Fittings - P.O | 1 | 2024-11-03 | 2024-11-03
R7S1-EMPO-5750 | A/G Water supply Pipes & Fittings - PPR - P.O | 1 | 2024-11-04 | 2024-11-04
R7S1-EMPO-5810 | Sanitary Fixtures & Wares (Kitchen Sink & its Mixer, Janitor Sink & Its Faucets, Angle Valve etc.) - P.O | 1 | 2024-11-27 | 2024-11-27
R7S1-EMPO-5760 | U/G Water supply pipes & Fittings - HDPE - P.O | 1 | 2024-12-01 | 2024-12-01
R7S1-EMPO-5790 | Thermal Insulation (For Hot Water Supply & Return) - P.O | 1 | 2024-12-05 | 2024-12-05
R7S1-EMPO-5770 | Water Supply Valves & Accessories. (Incl PRV, AAV, WHA & TMV) - P.O | 7 | 2024-12-02 | 2024-12-09
R7S1-EMPO-5780 | Solar Water Heaters (Includingr Pumps, Valves & Accessories) - P.O | 6 | 2025-03-29 | 2025-04-08
R7S1-EMPO-5800 | Steel pipe and fitting for solar system closed loop - P.O | 1 | 2025-04-08 | 2025-04-08
DRAINAGE |  | 13 | 2024-11-19 | 2024-12-03
R7S1-EMPO-5820 | Drainage A/G and U/G Pipes & Fittings (Soil, Waste, Vent, RWP, CDP) - P.O | 2 | 2024-11-19 | 2024-11-20
R7S1-EMPO-5830 | Bottle Gully Trap - P.O | 1 | 2024-11-25 | 2024-11-25
R7S1-EMPO-5860 | Rain Water Down Spout Nozzle - P.O | 1 | 2024-11-26 | 2024-11-26
R7S1-EMPO-5850 | Roof Drain, Funnel Drain, Rain Water Outlet - P.O | 1 | 2024-11-30 | 2024-11-30
R7S1-EMPO-5840 | Floor cleanout, Floor Drain, Balcony Drain, etc. - P.O | 1 | 2024-12-03 | 2024-12-03
FIRE FIGHTING |  | 34 | 2024-11-25 | 2025-01-02
R7S1-EMPO-5870 | Above Ground Fire Fighting pipes & Fittings - P.O | 1 | 2024-11-25 | 2024-11-25
R7S1-EMPO-5900 | Sprinklers - P.O | 1 | 2024-12-02 | 2024-12-02
R7S1-EMPO-5890 | Fire Fighting Specialities (FHC, Valves, Fire Blanket etc.) - P.O | 1 | 2024-12-12 | 2024-12-12
R7S1-EMPO-5880 | Underground Fire Fighting Pipes & Fittings - P.O | 2 | 2024-12-31 | 2025-01-01
R7S1-EMPO-5910 | Fire Extinguishers - P.O | 1 | 2025-01-02 | 2025-01-02
MECHANICAL - GENERAL |  | 19 | 2024-11-06 | 2024-11-27
R7S1-EMPO-5940 | Paints for CHW and Firefighting Pipes & Fittings - P.O | 1 | 2024-11-06 | 2024-11-06
R7S1-EMPO-5920 | Mechanical Hangers & Supports for MEP Services - P.O | 1 | 2024-11-12 | 2024-11-12
R7S1-EMPO-5930 | Identification Labels & Warning Tapes - P.O | 5 | 2024-11-23 | 2024-11-27
TOILET PODS MEP MATERIALS |  | 1 | 2024-11-09 | 2024-11-09
R7S1-EMPO-5950 | Toilet Pods MEP Material - Linear Apartments - P.O | 1 | 2024-11-09 | 2024-11-09
ELECTRICAL |  | 171 | 2024-11-02 | 2025-05-28
ELECTRICAL - LOW VOLTAGE |  | 144 | 2024-11-02 | 2025-04-23
R7S1-EMPO-6050 | Galvanised Steel Back box - P.O | 1 | 2024-11-02 | 2024-11-02
R7S1-EMPO-6030 | PVC Conduits,PVC Boxes,GI Back Boxes - P.O | 1 | 2024-11-03 | 2024-11-03
R7S1-EMPO-6040 | EMT Conduits and Accessories / RSC / IMC Conduits and Accessories - P.O | 1 | 2024-11-03 | 2024-11-03
R7S1-EMPO-6060 | Steel Flexible Conduits and Accessories - P.O | 1 | 2024-11-04 | 2024-11-04
R7S1-EMPO-6120 | Wiring Accessories - P.O | 1 | 2024-11-06 | 2024-11-06
R7S1-EMPO-6090 | UPVC Ducts and Accessories (For Under ground Sleeves & Duct bank) - P.O | 1 | 2024-11-19 | 2024-11-19
R7S1-EMPO-6070 | LV Cables & Wires - P.O | 1 | 2024-11-21 | 2024-11-21
R7S1-EMPO-6160 | Internal & External Lighting Fixtures including Emergency & Exit Lighting Fixtures - P.O | 5 | 2024-11-21 | 2024-11-26
R7S1-EMPO-6110 | Cables Management System (Trays, Basket, Accessories, Fittings). - P.O | 1 | 2024-11-27 | 2024-11-27
R7S1-EMPO-6100 | Cables Lugs and Glands - P.O | 1 | 2024-11-28 | 2024-11-28
R7S1-EMPO-6130 | LV Panels (Final DBs Inside Apartments & Studios) - P.O | 1 | 2024-12-05 | 2024-12-05
R7S1-EMPO-6150 | Earthing and Lightning Protection System - P.O | 1 | 2024-12-12 | 2024-12-12
R7S1-EMPO-6140 | LVPanels (MDB, SMDB) & Final DBs for service areas - P.O | 52 | 2024-12-17 | 2025-02-15
R7S1-EMPO-6080 | Isolator (Disconnector Switch) - P.O | 2 | 2025-04-22 | 2025-04-23
EXTRA LOW VOLTAGE |  | 169 | 2024-11-04 | 2025-05-28
R7S1-EMPO-6210 | Optical Network Terminal Cabinet (ONT) for Studios & Apartments - P.O | 1 | 2024-11-04 | 2024-11-04
R7S1-EMPO-6170 | Fire Alarm Cable - P.O | 1 | 2024-11-19 | 2024-11-19
R7S1-EMPO-6230 | Fire Alarm System & Voice Evacuation System - P.O | 1 | 2024-11-27 | 2024-11-27
R7S1-EMPO-6180 | IBMS Cables - P.O | 1 | 2024-12-04 | 2024-12-04
R7S1-EMPO-6200 | Access control Sytem Cables - P.O | 1 | 2024-12-04 | 2024-12-04
R7S1-EMPO-6250 | Access Control system - P.O | 1 | 2024-12-04 | 2024-12-04
R7S1-EMPO-6190 | Low Current System - Passive Components - P.O | 1 | 2024-12-05 | 2024-12-05
R7S1-EMPO-6220 | CCTV System - P.O | 1 | 2024-12-12 | 2024-12-12
R7S1-EMPO-6280 | Uniterruptable Power Supply - UPS (for BMS & Security Network only) - P.O | 1 | 2024-12-19 | 2024-12-19
R7S1-EMPO-6260 | Active Components for complete ELV System - P.O | 37 | 2025-01-02 | 2025-02-13
R7S1-EMPO-6270 | Motion Sensor - P.O | 2 | 2025-04-21 | 2025-04-22
R7S1-EMPO-6240 | Integrated Building Management system - P.O | 1 | 2025-05-28 | 2025-05-28
FABRICATION/DELIVERY (LEAD TIME) |  | 410 | 2024-11-04 | 2025-11-02
CIVIL |  | 349 | 2024-11-19 | 2025-11-02
CONCRETE WORKS |  | 125 | 2024-11-23 | 2025-03-27
R7S1-EMFD-6400 | Concrete cover spacer - Fabrication / Delivery period | 26 | 2024-12-01 | 2024-12-26
R7S1-EMFD-6300 | CEMENT (SRC & OPC) - Fabrication / Delivery period | 28 | 2024-12-01 | 2024-12-28
R7S1-EMFD-6305 | Concrete Curing Compound Weber Cure Y20 - Fabrication / Delivery period | 29 | 2024-11-30 | 2024-12-28
R7S1-EMFD-6310 | Anti-termite Treatment - Fabrication / Delivery period | 16 | 2024-12-14 | 2024-12-29
R7S1-EMFD-6450 | Reinforcement Steel - Fabrication / Delivery period | 37 | 2024-11-23 | 2024-12-29
R7S1-EMFD-6290 | Concrete Mix Design C20, C40 - Fabrication / Delivery period | 31 | 2024-11-30 | 2024-12-30
R7S1-EMFD-6360 | Non-shrink, cement-based plastering for concrete repair 3 : 10 mm - Fabrication / Delivery period | 33 | 2024-11-28 | 2024-12-30
R7S1-EMFD-6340 | MasterKure 161, Bitumen based damp proofing membrane for protection and curing of concrete structures. - Delivery | 28 | 2024-12-04 | 2024-12-31
R7S1-EMFD-6390 | Release Agent (Weber.ad dem 22) - Fabrication / Delivery period | 32 | 2024-12-01 | 2025-01-01
R7S1-EMFD-6420 | Vapor barrier Sheet - 1000 gauge - Fabrication / Delivery period | 38 | 2024-11-25 | 2025-01-01
R7S1-EMFD-6350 | Concrete Repair Material (WEBEREP ST), Non-Metallic Non Shrink Fiber reinforced repair mortar - Fabrication / Delivery | 29 | 2024-12-05 | 2025-01-02
R7S1-EMFD-6410 | Binding Wire - Fabrication / Delivery period | 41 | 2024-11-23 | 2025-01-02
R7S1-EMFD-6320 | Bonding Agent - Fabrication / Delivery period | 40 | 2024-12-01 | 2025-01-09
R7S1-EMFD-6330 | Bitumen Protective coating (Bitumen Paint) - Fabrication / Delivery period | 40 | 2024-12-01 | 2025-01-09
R7S1-EMFD-6380 | Epoxy Anchoring (Weberanc 405) - Fabrication / Delivery period | 40 | 2024-12-01 | 2025-01-09
R7S1-EMFD-6430 | GULF 1200 Silicone (Anti-fungus & Anti Bacterial Silicone Sealant) - Fabrication / Delivery period | 24 | 2024-12-17 | 2025-01-09
R7S1-EMFD-6440 | Solid block work 20x20x40 cm - Fabrication / Delivery period | 9 | 2025-01-01 | 2025-01-09
R7S1-EMFD-6370 | Expansion Joint Filler - Bitu-Flex "Bitumen Impregnated Expansion Joint Filler - Fabrication / Delivery period | 89 | 2024-12-14 | 2025-03-12
R7S1-EMFD-6460 | Floor Expansion Joint - Fabrication / Delivery period | 37 | 2025-02-19 | 2025-03-27
TILE WORKS |  | 52 | 2024-11-19 | 2025-01-09
R7S1-EMFD-6470 | Water resistant tile grout - Fabrication / Delivery period | 32 | 2024-12-09 | 2025-01-09
R7S1-EMFD-6480 | Tile Adhesive 1) MasterTile® FLX 23 & 2) MasterTile® FLX 24 - Fabrication / Delivery period | 40 | 2024-12-01 | 2025-01-09
R7S1-EMFD-6490 | Tile Grout (Vitonit) - Fabrication / Delivery period | 52 | 2024-11-19 | 2025-01-09
R7S1-EMFD-6500 | Fire Stop Sealant - Fabrication / Delivery period | 40 | 2024-12-01 | 2025-01-09
EXTERNAL WORKS |  | 346 | 2024-11-22 | 2025-11-02
R7S1-EMFD-6510 | Aluminum decorative hinged screen with wood finish fixed on glazed windows - Fabrication / Delivery period | 42 | 2024-11-22 | 2025-01-02
R7S1-EMFD-6520 | Decorative Louvers/Perforated sheet to cover MEP services at Roof - Fabrication / Delivery period | 125 | 2025-07-01 | 2025-11-02
PRECAST SYSTEM |  | 35 | 2024-11-29 | 2025-01-02
R7S1-EMFD-6590 | Mix design for precast concrete walls - Fabrication / Delivery period | 4 | 2024-11-29 | 2024-12-02
R7S1-EMFD-6530 | Concure WB309 - Fabrication / Delivery period | 35 | 2024-11-29 | 2025-01-02
R7S1-EMFD-6540 | Reebol WB - Fabrication / Delivery period | 35 | 2024-11-29 | 2025-01-02
R7S1-EMFD-6550 | Cbond - Fabrication / Delivery period | 35 | 2024-11-29 | 2025-01-02
R7S1-EMFD-6560 | SikaRep fine - Fabrication / Delivery period | 35 | 2024-11-29 | 2025-01-02
R7S1-EMFD-6570 | Sika Grout 114 - Fabrication / Delivery period | 35 | 2024-11-29 | 2025-01-02
R7S1-EMFD-6580 | Master Flow 522 - Fabrication / Delivery period | 35 | 2024-11-29 | 2025-01-02
R7S1-EMFD-6600 | Thermal Insulation - Fabrication / Delivery period | 20 | 2024-12-14 | 2025-01-02
R7S1-EMFD-6610 | Thermal Insulation Esscofoam 40 (material and prequalification) - Fabrication / Delivery period | 20 | 2024-12-14 | 2025-01-02
R7S1-EMFD-6620 | Wire Mesh (Reinforcement Steel Wire Mesh) - Fabrication / Delivery period | 35 | 2024-11-29 | 2025-01-02
R7S1-EMFD-6630 | PVC Tie Wire & Black Annealed Wire - Fabrication / Delivery period | 35 | 2024-11-29 | 2025-01-02
R7S1-EMFD-6640 | Lifting Socket - Fabrication / Delivery period | 35 | 2024-11-29 | 2025-01-02
R7S1-EMFD-6650 | Ties and Connector Pins - Fabrication / Delivery period | 35 | 2024-11-29 | 2025-01-02
R7S1-EMFD-6660 | Low Relaxation Pre-Stressing Strands - Fabrication / Delivery period | 35 | 2024-11-29 | 2025-01-02
R7S1-EMFD-6670 | Concrete Spacers & Chamfers - Fabrication / Delivery period | 35 | 2024-11-29 | 2025-01-02
R7S1-EMFD-6680 | Backup Rods (Filler Rods) - Fabrication / Delivery period | 20 | 2024-12-14 | 2025-01-02
R7S1-EMFD-6690 | Cast In Channel - Fabrication / Delivery period | 35 | 2024-11-29 | 2025-01-02
R7S1-EMFD-6700 | Connecting Loop - Fabrication / Delivery period | 35 | 2024-11-29 | 2025-01-02
R7S1-EMFD-6710 | Corrugated Pipe - Fabrication / Delivery period | 35 | 2024-11-29 | 2025-01-02
ARCHITECTURE |  | 387 | 2024-11-27 | 2025-10-12
EXTERNAL WORKS |  | 125 | 2025-06-05 | 2025-10-07
R7S1-EMFD-6730 | Ladders - Fabrication / Delivery period | 80 | 2025-06-05 | 2025-08-23
R7S1-EMFD-6720 | Balcony metal grating handrail - Fabrication / Delivery period | 125 | 2025-06-05 | 2025-10-07
THERMAL & MOISTURE PROTECTION: |  | 198 | 2025-02-19 | 2025-09-04
R7S1-EMFD-6740 | Roof Water Proofing - Fabrication / Delivery period | 198 | 2025-02-19 | 2025-09-04
DOORS & WINDOWS |  | 237 | 2024-12-01 | 2025-07-25
R7S1-EMFD-6810 | Hollow Metal Doors for Utility Rooms - Fabrication / Delivery period | 205 | 2024-12-27 | 2025-07-20
R7S1-EMFD-6800 | Wooden Doors materials and Hardwares - Fabrication / Delivery period | 221 | 2024-12-16 | 2025-07-24
R7S1-EMFD-6760 | Aluminum Profiles - Fabrication / Delivery period | 237 | 2024-12-01 | 2025-07-25
R7S1-EMFD-6770 | Glazing details for external doors and windows (Guardian Sungurad)/ Acoustic performance datasheet. - Fabrication / Deli | 237 | 2024-12-01 | 2025-07-25
R7S1-EMFD-6780 | Aluminum doors & windows - Fabrication / Delivery period | 237 | 2024-12-01 | 2025-07-25
R7S1-EMFD-6790 | Ironmongery & Hardware - Fabrication / Delivery period | 237 | 2024-12-01 | 2025-07-25
FINISHES |  | 326 | 2024-12-02 | 2025-10-12
R7S1-EMFD-6890 | Acoustic insulation - Fabrication / Delivery period | 25 | 2024-12-08 | 2025-01-01
R7S1-EMFD-6820 | 60X60X9 Porcelain Floor Tiles - Fabrication / Delivery period | 20 | 2024-12-14 | 2025-01-02
R7S1-EMFD-6960 | Weber Polyurethane jointseal PU MC - Fabrication / Delivery period | 24 | 2024-12-14 | 2025-01-06
R7S1-EMFD-6910 | Stair Tile and Details - Fabrication / Delivery period | 125 | 2025-02-27 | 2025-07-02
R7S1-EMFD-6920 | Epoxy Paint System - Fabrication / Delivery period | 125 | 2025-02-27 | 2025-07-02
R7S1-EMFD-6830 | 60X60X9 Porcelain Floor Tiles, Apartment Balconies - Fabrication / Delivery period | 206 | 2024-12-14 | 2025-07-07
R7S1-EMFD-6840 | Glazed Ceramic Tile 30X30 - Fabrication / Delivery period | 206 | 2024-12-14 | 2025-07-07
R7S1-EMFD-6930 | 30 X 30 cm Porcelain tiles - Fabrication / Delivery period | 206 | 2024-12-14 | 2025-07-07
R7S1-EMFD-6860 | Paint "External" - Fabrication / Delivery period | 238 | 2024-12-02 | 2025-07-28
R7S1-EMFD-6870 | Paint "Internal" - Fabrication / Delivery period | 238 | 2024-12-02 | 2025-07-28
R7S1-EMFD-6880 | Gypsum board (MADA GYPSUM) - Fabrication / Delivery period | 281 | 2024-12-02 | 2025-09-09
R7S1-EMFD-6950 | Proterminal Tile Trim - Fabrication / Delivery period | 272 | 2024-12-18 | 2025-09-16
R7S1-EMFD-6900 | Ceiling Tiles "Suspenstion System" - Fabrication / Delivery period | 304 | 2024-12-02 | 2025-10-01
R7S1-EMFD-6940 | Entrance Floor Matt UCFM 24 Anti-slip Heavy duty - Fabrication / Delivery period | 150 | 2025-05-16 | 2025-10-12
SPECIAL ITEMS |  | 337 | 2024-12-19 | 2025-08-15
R7S1-EMFD-7000 | Chute system - Fabrication / Delivery period | 55 | 2025-04-25 | 2025-06-18
R7S1-EMFD-6990 | Elevator - Fabrication / Delivery period | 219 | 2024-12-19 | 2025-07-25
R7S1-EMFD-6970 | Fall Arrest System - Fabrication / Delivery period | 140 | 2025-03-19 | 2025-08-06
R7S1-EMFD-6980 | Cross- Over Bridges for Roof Access - Fabrication / Delivery period | 90 | 2025-05-18 | 2025-08-15
KITCHENETTE |  | 227 | 2024-12-04 | 2025-07-19
R7S1-EMFD-7020 | Wardrobe - Fabrication / Delivery period | 217 | 2024-12-04 | 2025-07-09
R7S1-EMFD-7010 | Kitchen Top Cabinet & Accessories - Fabrication / Delivery period | 227 | 2024-12-04 | 2025-07-19
TOILET POD |  | 37 | 2024-11-27 | 2025-01-02
R7S1-EMFD-7030 | Toilet Pod Material (Arch & Civil) - Fabrication / Delivery period | 37 | 2024-11-27 | 2025-01-02
MECHANICAL |  | 307 | 2024-11-04 | 2025-09-07
HVAC |  | 285 | 2024-11-26 | 2025-09-07
R7S1-EMFD-7210 | CHW Pipes & Fittings - Underground - Fabrication / Delivery period | 16 | 2024-12-25 | 2025-01-09
R7S1-EMFD-7460 | Copper Tubes & Fittings - Fabrication / Delivery period | 25 | 2024-12-16 | 2025-01-09
R7S1-EMFD-7130 | Acoustic Insulation - HVAC - Fabrication / Delivery period | 51 | 2024-12-04 | 2025-01-23
R7S1-EMFD-7140 | Flexible Ducts - Fabrication / Delivery period | 54 | 2024-12-01 | 2025-01-23
R7S1-EMFD-7150 | Flexible Duct Connectors - Fabrication / Delivery period | 54 | 2024-12-01 | 2025-01-23
R7S1-EMFD-7160 | Vibration Isolators - Fabrication / Delivery period | 51 | 2024-12-04 | 2025-01-23
R7S1-EMFD-7190 | Air Outlets (Grilles / Diffusers / Registers / Louvers, Exhaust Disc etc.,) - Fabrication / Delivery period | 58 | 2024-11-27 | 2025-01-23
R7S1-EMFD-7200 | CHW Pipes & Fittings - Aboveground - Fabrication / Delivery period | 59 | 2024-11-26 | 2025-01-23
R7S1-EMFD-7500 | Insulation Duct Tape / Duct Flange Gasket / Rubber Support Insert for Insulated Pipe - Fabrication / Delivery period | 50 | 2024-12-05 | 2025-01-23
R7S1-EMFD-7510 | Chilled water Expansion joint (If required) - Fabrication / Delivery period - Site | 38 | 2025-01-09 | 2025-02-15
R7S1-EMFD-7060 | DX Split Units - Fabrication / Delivery period | 64 | 2024-12-16 | 2025-02-17
R7S1-EMFD-7120 | Chilled Water, Refrigerant & Condensate Insulation - Fabrication / Delivery period | 206 | 2024-12-11 | 2025-07-05
R7S1-EMFD-7220 | Chilled Water Valves Accessories - Fabrication / Delivery period | 221 | 2024-11-28 | 2025-07-07
R7S1-EMFD-7040 | Concealed FCU's - Fabrication / Delivery period | 216 | 2024-12-04 | 2025-07-08
R7S1-EMFD-7100 | Pre-Insulated Ducts for HVAC Ducting System (Internal) - Fabrication / Delivery period | 216 | 2024-12-05 | 2025-07-08
R7S1-EMFD-7180 | Dampers - Fabrication / Delivery period - FActory/Site | 213 | 2024-12-14 | 2025-07-14
R7S1-EMFD-7450 | PICV for FCUS & FAHU's - Fabrication / Delivery period | 227 | 2024-11-30 | 2025-07-14
R7S1-EMFD-7470 | Kitchen Exhaust Hood (Recirculation type) - Fabrication / Delivery period | 219 | 2024-12-08 | 2025-07-15
R7S1-EMFD-7070 | Thermostat - Fabrication / Delivery period | 225 | 2024-12-04 | 2025-07-17
R7S1-EMFD-7090 | Sound Attenuator - Fabrication / Delivery period - Site | 147 | 2025-02-26 | 2025-07-22
R7S1-EMFD-7490 | BTU Meter - Fabrication / Delivery period | 237 | 2024-12-05 | 2025-07-29
R7S1-EMFD-7480 | Chemical Treatment for Chilled water system - Fabrication / Delivery period - Site (T & C) | 116 | 2025-04-06 | 2025-07-31
R7S1-EMFD-7050 | FAHU's - Fabrication / Delivery period - Site | 162 | 2025-02-22 | 2025-08-03
R7S1-EMFD-7080 | Ventilation Fans - Fabrication / Delivery period - Site | 173 | 2025-03-08 | 2025-08-27
R7S1-EMFD-7110 | Preinsulated Phenolic HVAC Ducting System (External) - Fabrication / Delivery period | 183 | 2025-03-08 | 2025-09-07
PLUMBING - WATER SUPPLY |  | 294 | 2024-11-04 | 2025-08-24
R7S1-EMFD-7230 | PEX Pipes & Fittings - Fabrication / Delivery period | 80 | 2024-11-04 | 2025-01-22
R7S1-EMFD-7300 | Sanitary Fixtures & Wares (Kitchen Sink & its Mixer, Janitor Sink & Its Faucets, Angle Valve etc.) - Delivery | 217 | 2024-11-28 | 2025-07-03
R7S1-EMFD-7250 | U/G Water supply pipes & Fittings - HDPE - Fabrication / Delivery period | 226 | 2024-12-02 | 2025-07-15
R7S1-EMFD-7260 | Water Supply Valves & Accessories. (Incl PRV, AAV, WHA & TMV) - Fabrication / Delivery period | 241 | 2024-11-20 | 2025-07-18
R7S1-EMFD-7280 | Thermal Insulation (For Hot Water Supply & Return) - Fabrication / Delivery period | 225 | 2024-12-06 | 2025-07-19
R7S1-EMFD-7240 | A/G Water supply Pipes & Fittings - PPR - Fabrication / Delivery period | 268 | 2024-11-04 | 2025-07-30
R7S1-EMFD-7270 | Solar Water Heaters (Includingr Pumps, Valves & Accessories) - Fabrication / Delivery period | 137 | 2025-04-10 | 2025-08-24
R7S1-EMFD-7290 | Steel pipe and fitting for solar system closed loop - Fabrication / Delivery period | 137 | 2025-04-10 | 2025-08-24
DRAINAGE |  | 286 | 2024-11-20 | 2025-09-02
R7S1-EMFD-7310 | Drainage A/G and U/G Pipes & Fittings (Soil, Waste, Vent, RWP, CDP) - Fabrication / Delivery period | 227 | 2024-11-20 | 2025-07-05
R7S1-EMFD-7330 | Floor cleanout, Floor Drain, Balcony Drain, etc. - Fabrication / Delivery period | 217 | 2024-12-03 | 2025-07-08
R7S1-EMFD-7350 | Rain Water Down Spout Nozzle - Fabrication / Delivery period | 244 | 2024-11-27 | 2025-07-28
R7S1-EMFD-7340 | Roof Drain, Funnel Drain, Rain Water Outlet - Fabrication / Delivery period | 267 | 2024-11-30 | 2025-08-23
R7S1-EMFD-7320 | Bottle Gully Trap - Fabrication / Delivery period | 279 | 2024-11-27 | 2025-09-02
FIRE FIGHTING |  | 273 | 2024-11-26 | 2025-08-25
R7S1-EMFD-7360 | Above Ground Fire Fighting pipes & Fittings - Fabrication / Delivery period | 237 | 2024-11-26 | 2025-07-20
R7S1-EMFD-7380 | Fire Fighting Specialities (FHC, Valves, Fire Blanket etc.) - Fabrication / Delivery period - Factory | 221 | 2024-12-13 | 2025-07-21
R7S1-EMFD-7390 | Sprinklers - Fabrication / Delivery period | 237 | 2024-12-02 | 2025-07-26
R7S1-EMFD-7400 | Fire Extinguishers - Fabrication / Delivery period | 209 | 2025-01-03 | 2025-07-30
R7S1-EMFD-7370 | Underground Fire Fighting Pipes & Fittings - Fabrication / Delivery period | 237 | 2025-01-01 | 2025-08-25
MECHANICAL - GENERAL |  | 260 | 2024-11-07 | 2025-07-24
R7S1-EMFD-7420 | Identification Labels & Warning Tapes - Fabrication / Delivery period - Factory | 56 | 2024-11-28 | 2025-01-22
R7S1-EMFD-7430 | Paints for CHW and Firefighting Pipes & Fittings - Fabrication / Delivery period - Factory | 77 | 2024-11-07 | 2025-01-22
R7S1-EMFD-7410 | Mechanical Hangers & Supports for MEP Services - Fabrication / Delivery period - Factory | 249 | 2024-11-18 | 2025-07-24
TOILET PODS MEP MATERIALS |  | 54 | 2024-11-10 | 2025-01-02
R7S1-EMFD-7440 | Toilet Pods MEP Material - Linear Apartments - Fabrication / Delivery period - Factory | 54 | 2024-11-10 | 2025-01-02
ELECTRICAL |  | 344 | 2024-11-06 | 2025-10-15
ELECTRICAL - LOW VOLTAGE |  | 329 | 2024-11-06 | 2025-10-01
R7S1-EMFD-7540 | Galvanised Steel Back box - Fabrication / Delivery period - Factory (Concealed) | 42 | 2024-11-20 | 2024-12-31
R7S1-EMFD-7520 | PVC Conduits,PVC Boxes,GI Back Boxes - Fabrication / Delivery period | 43 | 2024-11-20 | 2025-01-01
R7S1-EMFD-7530 | EMT Conduits and Accessories / RSC / IMC Conduits and Accessories - Fabrication / Delivery period - Factory | 65 | 2024-11-20 | 2025-01-23
R7S1-EMFD-7550 | Steel Flexible Conduits and Accessories - Fabrication / Delivery period - Factory | 65 | 2024-11-20 | 2025-01-23
R7S1-EMFD-7580 | UPVC Ducts and Accessories (For Under ground Sleeves & Duct bank) - Fabrication / Delivery period - Factory | 65 | 2024-11-20 | 2025-01-23
R7S1-EMFD-7590 | Cables Lugs and Glands - Fabrication / Delivery period - Factory | 52 | 2024-12-03 | 2025-01-23
R7S1-EMFD-7610 | Wiring Accessories - Fabrication / Delivery period - Factory | 200 | 2024-11-06 | 2025-05-25
R7S1-EMFD-7650 | Internal & External Lighting Fixtures including Emergency & Exit Lighting Fixtures - Fabrication / Delivery period - F | 236 | 2024-11-21 | 2025-07-14
R7S1-EMFD-7600 | Cables Management System (Trays, Basket, Accessories, Fittings). - Fabrication / Delivery period - Factory | 226 | 2024-12-03 | 2025-07-16
R7S1-EMFD-7620 | LV Panels (Final DBs Inside Apartments & Studios) - Fabrication / Delivery period - Factory | 226 | 2024-12-05 | 2025-07-18
R7S1-EMFD-7560 | LV Cables & Wires - Fabrication / Delivery period - Factory | 243 | 2024-11-20 | 2025-07-21
R7S1-EMFD-7640 | Earthing and Lightning Protection System - Fabrication / Delivery period - Factory | 257 | 2024-11-13 | 2025-07-28
R7S1-EMFD-7570 | Isolator (Disconnector Switch) - Fabrication / Delivery period - Site (Service Rooms & Roof) | 148 | 2025-04-23 | 2025-09-18
R7S1-EMFD-7630 | LVPanels (MDB, SMDB) & Final DBs for service areas - Fabrication / Delivery period - Factory | 221 | 2025-02-22 | 2025-10-01
EXTRA LOW VOLTAGE |  | 329 | 2024-11-21 | 2025-10-15
R7S1-EMFD-7660 | Fire Alarm Cable - Fabrication / Delivery period- Factory | 64 | 2024-11-21 | 2025-01-23
R7S1-EMFD-7700 | Optical Network Terminal Cabinet (ONT) for Studios & Apartments - Fabrication / Delivery period- Factory | 235 | 2024-11-21 | 2025-07-13
R7S1-EMFD-7670 | IBMS Cables - Fabrication / Delivery period- Factory | 222 | 2024-12-09 | 2025-07-19
R7S1-EMFD-7680 | Low Current System - Passive Components - Fabrication / Delivery period | 229 | 2024-12-05 | 2025-07-22
R7S1-EMFD-7720 | Fire Alarm System & Voice Evacuation System - Fabrication / Delivery period - Factory | 235 | 2024-12-06 | 2025-07-29
R7S1-EMFD-7690 | Access control Sytem Cables - Fabrication / Delivery period- | 229 | 2024-12-24 | 2025-08-09
R7S1-EMFD-7740 | Access Control system - Fabrication / Delivery period - Factory | 252 | 2024-12-06 | 2025-08-15
R7S1-EMFD-7710 | CCTV System - Fabrication / Delivery period - Site (Corridor) | 261 | 2024-12-14 | 2025-08-31
R7S1-EMFD-7770 | Uniterruptable Power Supply - UPS (for BMS & Security Network only) - Fabrication / Delivery period - Site (ICT Rooms) | 263 | 2024-12-19 | 2025-09-07
R7S1-EMFD-7750 | Active Components for complete ELV System - Fabrication / Delivery period - Site (ICT Rooms) | 215 | 2025-02-15 | 2025-09-18
R7S1-EMFD-7730 | Integrated Building Management system - Fabrication / Delivery period - Site (Corridors, Elec Rooms & Roof) | 125 | 2025-05-29 | 2025-09-30
R7S1-EMFD-7760 | Motion Sensor - Fabrication / Delivery period - Site | 174 | 2025-04-25 | 2025-10-15
HUBS (EV18 & 16) & INFRA |  | 262 | 2024-11-17 | 2025-08-06
MATERIAL SUBMITTAL & APPROVAL |  | 178 | 2024-11-17 | 2025-05-13
MATERIAL SUBMITTALS |  | 142 | 2024-11-17 | 2025-05-06
MECHANICAL |  | 119 | 2024-12-14 | 2025-05-06
CHILLED WATER |  | 119 | 2024-12-14 | 2025-05-06
R7S1-EMMS-3360 | Pipes/Valves/Fittings (Infra) - Material Submittal | 39 | 2025-01-16 | 2025-03-03
R7S1-EMMS-3370 | Pipes/Valves/Fittings (Inside Hubs) - Material Submittal | 39 | 2025-01-16 | 2025-03-03
R7S1-EMMS-3310 | FCU (Hubs) - Material Submittal | 20 | 2025-02-09 | 2025-03-04
R7S1-EMMS-3320 | Chilled water pumps (Hubs) - Material Submittal | 24 | 2025-02-09 | 2025-03-09
R7S1-EMMS-3330 | Chemical Dosing units (Hubs) - Material Submittal | 71 | 2024-12-19 | 2025-03-12
R7S1-EMMS-3350 | Pressurization units (Hubs) - Material Submittal | 101 | 2024-12-14 | 2025-04-15
R7S1-EMMS-3380 | Road Crossing pipes/Conduits (Infra) - Material Submittal | 10 | 2025-04-26 | 2025-05-06
WATER SUPPLY |  | 73 | 2025-01-16 | 2025-04-16
R7S1-EMMS-3440 | PPR Pipes/Valves/Fittings - Material Submittal | 15 | 2025-01-21 | 2025-02-06
R7S1-EMMS-3430 | HDPE Pipes/Valves/Fittings - Material Submittal | 23 | 2025-01-18 | 2025-02-12
R7S1-EMMS-3390 | GRP Tank (Hubs) - Material Submittal | 29 | 2025-01-16 | 2025-02-18
R7S1-EMMS-3400 | Booster Pumps (Hubs) - Material Submittal | 29 | 2025-02-08 | 2025-03-13
R7S1-EMMS-3340 | Filteration System (Hubs) - Material Submittal | 51 | 2025-02-11 | 2025-04-16
R7S1-EMMS-3420 | Ionization Filter (Hubs) - Material Submittal | 51 | 2025-02-11 | 2025-04-16
DRAINAGE |  | 15 | 2025-01-21 | 2025-02-06
R7S1-EMMS-3450 | Drainage Pipes - Material Submittal | 15 | 2025-01-21 | 2025-02-06
FIRE FIGHTING |  | 20 | 2025-01-21 | 2025-02-12
R7S1-EMMS-3460 | Pipes/Valves/Fittings (Hubs) - Material Submittal | 20 | 2025-01-21 | 2025-02-12
R7S1-EMMS-3470 | Pipes/Valves/Fittings (Infra) - Material Submittal | 20 | 2025-01-21 | 2025-02-12
GENERAL |  | 5 | 2025-04-19 | 2025-04-23
R7S1-EMMS-3560 | MH Covers (Mech.) - Material Submittal | 5 | 2025-04-19 | 2025-04-23
ELECTRICAL |  | 131 | 2024-11-17 | 2025-04-23
POWER |  | 29 | 2025-01-16 | 2025-02-18
R7S1-EMMS-3480 | Power Cables - Material Submittal | 19 | 2025-01-18 | 2025-02-08
R7S1-EMMS-3490 | UPVC Pipes (Duct) - Material Submittal | 19 | 2025-01-18 | 2025-02-08
R7S1-EMMS-3500 | SMDBs & DBs - Material Submittal | 29 | 2025-01-16 | 2025-02-18
ICT |  | 82 | 2024-11-17 | 2025-02-19
R7S1-EMMS-3540 | CCTV/Security System - Material Submittal | 25 | 2024-11-17 | 2024-12-15
R7S1-EMMS-3550 | Access control - Material Submittal | 10 | 2024-12-23 | 2025-01-02
R7S1-EMMS-3520 | UPVC Pipes (Duct Bank) - Material Submittal | 19 | 2025-01-18 | 2025-02-08
R7S1-EMMS-3530 | ICT Equipment with Racks - Material Submittal | 2 | 2025-02-11 | 2025-02-12
R7S1-EMMS-3510 | ICT Cables - Material Submittal | 30 | 2025-01-16 | 2025-02-19
GENERAL |  | 42 | 2025-03-02 | 2025-04-23
R7S1-EMMS-3410 | MH Covers (Elec..) - Material Submittal | 42 | 2025-03-02 | 2025-04-23
MATERIAL APPROVALS |  | 149 | 2024-12-16 | 2025-05-13
MECHANICAL |  | 134 | 2024-12-31 | 2025-05-13
CHILLED WATER |  | 134 | 2024-12-31 | 2025-05-13
R7S1-EMMA-4800 | FCU (Hubs) - Material Approval | 9 | 2025-03-04 | 2025-03-12
R7S1-EMMA-4810 | Chilled water pumps (Hubs) - Material Approval | 33 | 2025-02-13 | 2025-03-17
R7S1-EMMA-4820 | Chemical Dosing units (Hubs) - Material Approval | 83 | 2024-12-31 | 2025-03-23
R7S1-EMMA-4850 | Pipes/Valves/Fittings (Infra) - Material Approval | 82 | 2025-01-28 | 2025-04-19
R7S1-EMMA-4860 | Pipes/Valves/Fittings (Inside Hubs) - Material Approval | 82 | 2025-01-28 | 2025-04-19
R7S1-EMMA-4840 | Pressurization units (Hubs) - Material Approval | 76 | 2025-02-18 | 2025-05-04
R7S1-EMMA-4870 | Road Crossing pipes/Conduits (Infra) - Material Approval | 7 | 2025-05-07 | 2025-05-13
WATER SUPPLY |  | 101 | 2025-01-20 | 2025-04-30
R7S1-EMMA-4920 | HDPE Pipes/Valves/Fittings - Material Approval | 24 | 2025-01-20 | 2025-02-12
R7S1-EMMA-4930 | PPR Pipes/Valves/Fittings - Material Approval | 16 | 2025-01-28 | 2025-02-12
R7S1-EMMA-4880 | GRP Tank (Hubs) - Material Approval | 31 | 2025-01-28 | 2025-02-27
R7S1-EMMA-4890 | Booster Pumps (Hubs) - Material Approval | 49 | 2025-02-17 | 2025-04-06
R7S1-EMMA-4830 | Filteration System (Hubs) - Material Approval | 38 | 2025-03-18 | 2025-04-24
R7S1-EMMA-4910 | Ionization Filter (Hubs) - Material Approval | 44 | 2025-03-18 | 2025-04-30
DRAINAGE |  | 16 | 2025-01-28 | 2025-02-12
R7S1-EMMA-4940 | Drainage Pipes - Material Approval | 16 | 2025-01-28 | 2025-02-12
FIRE FIGHTING |  | 16 | 2025-01-28 | 2025-02-12
R7S1-EMMA-4950 | Pipes/Valves/Fittings (Hubs) - Material Approval | 16 | 2025-01-28 | 2025-02-12
R7S1-EMMA-4960 | Pipes/Valves/Fittings (Infra) - Material Approval | 16 | 2025-01-28 | 2025-02-12
GENERAL |  | 7 | 2025-04-24 | 2025-04-30
R7S1-EMMA-5050 | MH Covers (Mech.) - Material Approval | 7 | 2025-04-24 | 2025-04-30
ELECTRICAL |  | 136 | 2024-12-16 | 2025-04-30
POWER |  | 25 | 2025-02-09 | 2025-03-05
R7S1-EMMA-4980 | UPVC Pipes (Duct) - Material Approval | 4 | 2025-02-09 | 2025-02-12
R7S1-EMMA-4970 | Power Cables - Material Approval | 7 | 2025-02-09 | 2025-02-15
R7S1-EMMA-4990 | SMDBs & DBs - Material Approval | 25 | 2025-02-09 | 2025-03-05
ICT |  | 73 | 2024-12-16 | 2025-02-26
R7S1-EMMA-5030 | CCTV/Security System - Material Approval | 8 | 2024-12-16 | 2024-12-23
R7S1-EMMA-5040 | Access control - Material Approval | 6 | 2025-01-04 | 2025-01-09
R7S1-EMMA-5010 | UPVC Pipes (Duct Bank) - Material Approval | 7 | 2025-02-13 | 2025-02-19
R7S1-EMMA-5000 | ICT Cables - Material Approval | 7 | 2025-02-20 | 2025-02-26
R7S1-EMMA-5020 | ICT Equipment with Racks - Material Approval | 14 | 2025-02-13 | 2025-02-26
GENERAL |  | 7 | 2025-04-24 | 2025-04-30
R7S1-EMMA-4900 | MH Covers (Elec..) - Material Approval | 7 | 2025-04-24 | 2025-04-30
P. O |  | 117 | 2024-12-24 | 2025-05-14
MECHANICAL |  | 105 | 2025-01-07 | 2025-05-14
CHILLED WATER |  | 105 | 2025-01-07 | 2025-05-14
R7S1-EMPO-7820 | FCU (Hubs) - P.O | 1 | 2025-03-13 | 2025-03-13
R7S1-EMPO-7880 | Pipes/Valves/Fittings (Inside Hubs) - P.O | 35 | 2025-02-04 | 2025-03-17
R7S1-EMPO-7830 | Chilled water pumps (Hubs) - P.O | 16 | 2025-03-01 | 2025-03-18
R7S1-EMPO-7840 | Chemical Dosing units (Hubs) - P.O | 66 | 2025-01-07 | 2025-03-25
R7S1-EMPO-7870 | Pipes/Valves/Fittings (Infra) - P.O | 46 | 2025-02-04 | 2025-03-30
R7S1-EMPO-7860 | Pressurization units (Hubs) - P.O | 2 | 2025-05-04 | 2025-05-06
R7S1-EMPO-7890 | Road Crossing pipes/Conduits (Infra) - P.O | 1 | 2025-05-14 | 2025-05-14
WATER SUPPLY |  | 74 | 2025-02-04 | 2025-05-06
R7S1-EMPO-7940 | HDPE Pipes/Valves/Fittings - P.O | 10 | 2025-02-04 | 2025-02-15
R7S1-EMPO-7950 | PPR Pipes/Valves/Fittings - P.O | 10 | 2025-02-04 | 2025-02-15
R7S1-EMPO-7900 | GRP Tank (Hubs) - P.O | 25 | 2025-02-04 | 2025-03-05
R7S1-EMPO-7910 | Booster Pumps (Hubs) - P.O | 1 | 2025-03-15 | 2025-03-15
R7S1-EMPO-7850 | Filteration System (Hubs) - P.O | 5 | 2025-04-26 | 2025-04-30
R7S1-EMPO-7930 | Ionization Filter (Hubs) - P.O | 5 | 2025-04-30 | 2025-05-06
DRAINAGE |  | 10 | 2025-02-04 | 2025-02-15
R7S1-EMPO-7960 | Drainage Pipes - P.O | 10 | 2025-02-04 | 2025-02-15
FIRE FIGHTING |  | 10 | 2025-02-04 | 2025-02-15
R7S1-EMPO-7970 | Pipes/Valves/Fittings (Hubs) - P.O | 10 | 2025-02-04 | 2025-02-15
R7S1-EMPO-7980 | Pipes/Valves/Fittings (Infra) - P.O | 10 | 2025-02-04 | 2025-02-15
GENERAL |  | 7 | 2025-05-01 | 2025-05-08
R7S1-EMPO-8070 | MH Covers (Mech.) - P.O | 7 | 2025-05-01 | 2025-05-08
ELECTRICAL |  | 112 | 2024-12-24 | 2025-05-08
POWER |  | 22 | 2025-02-16 | 2025-03-13
R7S1-EMPO-7990 | Power Cables - P.O | 1 | 2025-02-16 | 2025-02-16
R7S1-EMPO-8000 | UPVC Pipes (Duct) - P.O | 1 | 2025-02-23 | 2025-02-23
R7S1-EMPO-8010 | SMDBs & DBs - P.O | 22 | 2025-02-16 | 2025-03-13
ICT |  | 62 | 2024-12-24 | 2025-03-06
R7S1-EMPO-8050 | CCTV/Security System - P.O | 1 | 2024-12-24 | 2024-12-24
R7S1-EMPO-8060 | Access control - P.O | 6 | 2025-01-11 | 2025-01-16
R7S1-EMPO-8030 | UPVC Pipes (Duct Bank) - P.O | 2 | 2025-02-20 | 2025-02-23
R7S1-EMPO-8040 | ICT Equipment with Racks - P.O | 5 | 2025-02-23 | 2025-02-27
R7S1-EMPO-8020 | ICT Cables - P.O | 7 | 2025-02-27 | 2025-03-06
GENERAL |  | 7 | 2025-05-01 | 2025-05-08
R7S1-EMPO-7920 | MH Covers (Elec..) - P.O | 7 | 2025-05-01 | 2025-05-08
FABRICATION/DELIVERY (LEAD TIME) |  | 157 | 2025-03-02 | 2025-08-06
MECHANICAL |  | 150 | 2025-03-08 | 2025-08-04
CHILLED WATER |  | 130 | 2025-03-13 | 2025-07-20
R7S1-EMFD-7840 | Pipes/Valves/Fittings (Inside Hubs) - Fabrication / Delivery period - Factory | 49 | 2025-03-23 | 2025-05-11
R7S1-EMFD-7830 | Pipes/Valves/Fittings (Infra) - Fabrication / Delivery period - Site | 50 | 2025-03-23 | 2025-05-12
R7S1-EMFD-7780 | FCU (Hubs) - Fabrication / Delivery period - Site | 115 | 2025-03-13 | 2025-07-05
R7S1-EMFD-7800 | Chemical Dosing units (Hubs) - Fabrication / Delivery period - Factory | 97 | 2025-04-01 | 2025-07-07
R7S1-EMFD-7850 | Road Crossing pipes/Conduits (Infra) - Fabrication / Delivery period - Site | 56 | 2025-05-15 | 2025-07-09
R7S1-EMFD-7790 | Chilled water pumps (Hubs) - Fabrication / Delivery period - Factory | 114 | 2025-03-18 | 2025-07-10
R7S1-EMFD-7820 | Pressurization units (Hubs) - Fabrication / Delivery period - Factory | 75 | 2025-05-06 | 2025-07-20
WATER SUPPLY |  | 150 | 2025-03-08 | 2025-08-04
R7S1-EMFD-7910 | PPR Pipes/Valves/Fittings - Fabrication / Delivery period - Factory | 4 | 2025-03-08 | 2025-03-11
R7S1-EMFD-7900 | HDPE Pipes/Valves/Fittings - Fabrication / Delivery period - Site | 12 | 2025-03-08 | 2025-03-19
R7S1-EMFD-7870 | Booster Pumps (Hubs) - Fabrication / Delivery period - Factory | 99 | 2025-04-01 | 2025-07-09
R7S1-EMFD-7860 | GRP Tank (Hubs) - Fabrication / Delivery period-Site | 123 | 2025-03-08 | 2025-07-09
R7S1-EMFD-7810 | Filteration System (Hubs) - Fabrication / Delivery period - Factory | 85 | 2025-05-01 | 2025-07-24
R7S1-EMFD-7890 | Ionization Filter (Hubs) - Fabrication / Delivery period - Factory | 90 | 2025-05-06 | 2025-08-04
DRAINAGE |  | 13 | 2025-03-08 | 2025-03-20
R7S1-EMFD-7920 | Drainage Pipes - Fabrication / Delivery period - Site | 13 | 2025-03-08 | 2025-03-20
FIRE FIGHTING |  | 56 | 2025-03-08 | 2025-05-03
R7S1-EMFD-7930 | Pipes/Valves/Fittings (Hubs) - Fabrication / Delivery period - Factory | 56 | 2025-03-08 | 2025-05-03
R7S1-EMFD-7940 | Pipes/Valves/Fittings (Infra) - Fabrication / Delivery period - Site | 56 | 2025-03-08 | 2025-05-03
GENERAL |  | 60 | 2025-05-09 | 2025-07-07
R7S1-EMFD-8030 | MH Covers (Mech.) - Fabrication / Delivery period - Site | 60 | 2025-05-09 | 2025-07-07
ELECTRICAL |  | 157 | 2025-03-02 | 2025-08-06
POWER |  | 151 | 2025-03-08 | 2025-08-06
R7S1-EMFD-7960 | UPVC Pipes (Duct) - Fabrication / Delivery period - Site | 77 | 2025-03-08 | 2025-05-24
R7S1-EMFD-7950 | Power Cables - Fabrication / Delivery period - Site | 126 | 2025-03-08 | 2025-07-12
R7S1-EMFD-7970 | SMDBs & DBs - Fabrication / Delivery period - Site | 144 | 2025-03-15 | 2025-08-06
ICT |  | 119 | 2025-03-02 | 2025-06-28
R7S1-EMFD-7990 | UPVC Pipes (Duct Bank) - Fabrication / Delivery period - Site | 60 | 2025-03-08 | 2025-05-07
R7S1-EMFD-8020 | Access control - Fabrication / Delivery period - Factory | 75 | 2025-03-09 | 2025-05-22
R7S1-EMFD-8000 | ICT Equipment with Racks - Fabrication / Delivery period - Site | 82 | 2025-03-02 | 2025-05-23
R7S1-EMFD-7980 | ICT Cables - Fabrication / Delivery period - Site | 87 | 2025-03-08 | 2025-06-03
R7S1-EMFD-8010 | CCTV/Security System - Fabrication / Delivery period - Site | 118 | 2025-03-03 | 2025-06-28
GENERAL |  | 50 | 2025-05-09 | 2025-06-27
R7S1-EMFD-7880 | MH Covers (Elec..) - Fabrication / Delivery period - Site | 50 | 2025-05-09 | 2025-06-27
CONSTRUCTION |  | 486 | 2024-10-01 | 2025-12-22
OFF-SITE WORKS |  | 276 | 2024-11-26 | 2025-08-24
PRIORITY - 1 |  | 244 | 2024-11-26 | 2025-07-08
PRODUCTION DRAWINGS & MOLD PREPARATION (FOR AMANA USE ONLY) |  | 174 | 2024-11-26 | 2025-05-18
1&2 BED LINEAR APARTMENTS BUILDINGS (MANAGEMENT TYPE A) |  | 79 | 2024-11-26 | 2025-02-12
GROUND FLOOR |  | 37 | 2024-11-26 | 2025-01-01
R7S1-M-PRGF-1010 | Issue of GF Boxes for Production to the Factory - Civil & MEP (Internal purpose only) | 10 | 2024-12-02 | 2024-12-11
R7S1-M-PRGF-1020 | Qanbar Internal Study on the Drawings (GF) | 14 | 2024-12-03 | 2024-12-18
R7S1-M-PRGF-1000 | Production Drawings GF Boxes Preparation - Civil & MEP (Internal purpose only) | 17 | 2024-11-26 | 2024-12-18
R7S1-M-PRGF-1030 | Qanbar Issuance of Mold Drawings (GF) | 9 | 2024-12-16 | 2024-12-25
R7S1-M-PRGF-1040 | Mold Fabrication - 1&2 Bed Linear Apartments Buildings (Type A) (GF) | 22 | 2024-12-08 | 2025-01-01
FIRST FLOOR |  | 33 | 2024-12-22 | 2025-01-23
R7S1-M-PRFF-1000 | Preparation & Issuance of Production Drawings of First Floor Boxes - Civil & MEP (Internal purpose only) | 15 | 2024-12-22 | 2025-01-09
R7S1-M-PRFF-1010 | Qanbar Internal Study on the Drawings (FF) | 6 | 2025-01-04 | 2025-01-09
R7S1-M-PRFF-1020 | Qanbar Issuance of Mold Drawings (FF) | 6 | 2025-01-11 | 2025-01-16
R7S1-M-PRFF-1030 | Mold Fabrication - 1&2 Bed Linear Apartments Buildings (Type A) (FF) | 11 | 2025-01-12 | 2025-01-23
SECOND FLOOR |  | 37 | 2025-01-07 | 2025-02-12
R7S1-M-PRSF-1000 | Preparation & Issuance of Production Drawings of Second Floor Boxes - Civil & MEP (Internal purpose only) | 13 | 2025-01-07 | 2025-01-23
R7S1-M-PRSF-1010 | Qanbar Internal Study on the Drawings (SF) | 11 | 2025-01-19 | 2025-01-30
R7S1-M-PRSF-1030 | Mold Fabrication - 1&2 Bed Linear Apartments Buildings (Type A) (SF) | 3 | 2025-02-10 | 2025-02-12
R7S1-M-PRSF-1020 | Qanbar Issuance of Mold Drawings (SF) | 14 | 2025-01-28 | 2025-02-12
HUBS (EV18 & 16) & INFRA |  | 22 | 2025-04-27 | 2025-05-18
R7S1-LS-PR-1040 | Preparation & Issuance of Production Drawings of Boxes - Civil & MEP (Internal purpose only) | 15 | 2025-04-27 | 2025-05-15
R7S1-LS-PR-1050 | Qanbar Internal Study on the Drawings | 2 | 2025-05-17 | 2025-05-18
R7S1-LS-PR-1060 | Qanbar Issuance of Mold Drawings | 2 | 2025-05-17 | 2025-05-18
R7S1-LS-PR-1070 | Mold Fabrication - EV18 & 16 | 6 | 2025-05-12 | 2025-05-18
PRECAST PANELS DELIVERY |  | 147 | 2024-12-21 | 2025-06-11
R7S1-OFPR-M-GFAP1 | Precast Panels Delivery - 1&2 Bed Linear Apartments Buildings (Type A) Ground Floor - AP#01 | 18 | 2024-12-21 | 2025-01-09
R7S1-OFPR-M-GFAP2 | Precast Panels Delivery - 1&2 Bed Linear Apartments Buildings (Type A) - Ground Floor - AP#02 | 20 | 2024-12-21 | 2025-01-12
R7S1-OFPR-M-GFAP3 | Precast Panels Delivery - 1&2 Bed Linear Apartments Buildings (Type A) - Ground Floor - AP#03 | 24 | 2024-12-21 | 2025-01-16
R7S1-OFPR-M-GFAP4 | Precast Panels Delivery - 1&2 Bed Linear Apartments Buildings (Type A) - Ground Floor - AP#04 | 29 | 2024-12-21 | 2025-01-22
R7S1-OFPR-M-GFAP6 | Precast Panels Delivery - 1&2 Bed Linear Apartments Buildings (Type A) - Ground Floor - AP#06 | 34 | 2024-12-21 | 2025-01-28
R7S1-OFPR-M-GFAP7 | Precast Panels Delivery - 1&2 Bed Linear Apartments Buildings (Type A) - Ground Floor - AP#07 | 35 | 2024-12-21 | 2025-01-29
R7S1-OFPR-M-FFAP1 | Precast Panels Delivery - 1&2 Bed Linear Apartments Buildings (Type A) - First Floor - AP#01 | 21 | 2025-01-20 | 2025-02-12
R7S1-OFPR-M-FFAP2 | Precast Panels Delivery - 1&2 Bed Linear Apartments Buildings (Type A) - First Floor - AP#02 | 17 | 2025-01-27 | 2025-02-15
R7S1-OFPR-M-FFAP3 | Precast Panels Delivery - 1&2 Bed Linear Apartments Buildings (Type A) - First Floor - AP#03 | 16 | 2025-01-29 | 2025-02-16
R7S1-OFPR-M-FFAP4 | Precast Panels Delivery - 1&2 Bed Linear Apartments Buildings (Type A) - First Floor - AP#04 | 7 | 2025-02-11 | 2025-02-18
R7S1-OFPR-M-FFAP6 | Precast Panels Delivery - 1&2 Bed Linear Apartments Buildings (Type A) - First Floor - AP#06 | 11 | 2025-02-08 | 2025-02-19
R7S1-OFPR-M-FFAP7 | Precast Panels Delivery - 1&2 Bed Linear Apartments Buildings (Type A) - First Floor - AP#07 | 9 | 2025-02-15 | 2025-02-25
R7S1-OFPR-M-SFAP1 | Precast Panels Delivery - 1&2 Bed Linear Apartments Buildings (Type A) - Second Floor - AP#01 | 9 | 2025-02-19 | 2025-03-02
R7S1-OFPR-M-SFAP2 | Precast Panels Delivery - 1&2 Bed Linear Apartments Buildings (Type A) - Second Floor - AP#02 | 10 | 2025-02-25 | 2025-03-08
R7S1-OFPR-M-SFAP3 | Precast Panels Delivery - 1&2 Bed Linear Apartments Buildings (Type A) - Second Floor - AP#03 | 13 | 2025-02-26 | 2025-03-12
R7S1-OFPR-M-SFAP4 | Precast Panels Delivery - 1&2 Bed Linear Apartments Buildings (Type A) - Second Floor - AP#04 | 13 | 2025-03-03 | 2025-03-17
R7S1-OFPR-M-SFAP6 | Precast Panels Delivery - 1&2 Bed Linear Apartments Buildings (Type A) - Second Floor - AP#06 | 18 | 2025-03-08 | 2025-03-27
R7S1-OFPR-M-SFAP7 | Precast Panels Delivery - 1&2 Bed Linear Apartments Buildings (Type A) - Second Floor - AP#07 | 24 | 2025-03-10 | 2025-04-10
R7S1-OFPR-M-HUB-EV18 | Precast Panels Delivery - EV18 | 20 | 2025-05-15 | 2025-06-11
POD WORKS - DUBAI |  | 80 | 2024-12-07 | 2025-03-10
R7S1-OFPW-M-PW10 | Preparation Works - Mold, Slab casting,W/P, Assembly etc | 9 | 2024-12-07 | 2024-12-16
R7S1-OFPW-M-GFAP1 | Pod Works - 1&2 Bed Linear Apartments Buildings (Type A) Ground Floor - AP#01 | 10 | 2024-12-17 | 2024-12-28
R7S1-OFPW-M-GFAP2 | Pod Works - 1&2 Bed Linear Apartments Buildings (Type A) - Ground Floor - AP#02 | 12 | 2024-12-17 | 2024-12-30
R7S1-OFPW-M-GFAP3 | Pod Works - 1&2 Bed Linear Apartments Buildings (Type A) - Ground Floor - AP#03 | 19 | 2024-12-12 | 2025-01-02
R7S1-OFPW-M-GFAP4 | Pod Works - 1&2 Bed Linear Apartments Buildings (Type A) - Ground Floor - AP#04 | 30 | 2024-12-07 | 2025-01-09
R7S1-OFPW-M-GFAP6 | Pod Works - 1&2 Bed Linear Apartments Buildings (Type A) - Ground Floor - AP#06 | 32 | 2024-12-09 | 2025-01-14
R7S1-OFPW-M-GFAP7 | Pod Works - 1&2 Bed Linear Apartments Buildings (Type A) - Ground Floor - AP#07 | 32 | 2024-12-14 | 2025-01-19
R7S1-OFPW-M-FFAP1 | Pod Works - 1&2 Bed Linear Apartments Buildings (Type A) - First Floor - AP#01 | 5 | 2025-01-18 | 2025-01-22
R7S1-OFPW-M-FFAP2 | Pod Works - 1&2 Bed Linear Apartments Buildings (Type A) - First Floor - AP#02 | 12 | 2025-01-15 | 2025-01-28
R7S1-OFPW-M-FFAP3 | Pod Works - 1&2 Bed Linear Apartments Buildings (Type A) - First Floor - AP#03 | 19 | 2025-01-11 | 2025-02-01
R7S1-OFPW-M-FFAP4 | Pod Works - 1&2 Bed Linear Apartments Buildings (Type A) - First Floor - AP#04 | 10 | 2025-01-23 | 2025-02-03
R7S1-OFPW-M-FFAP6 | Pod Works - 1&2 Bed Linear Apartments Buildings (Type A) - First Floor - AP#06 | 16 | 2025-01-26 | 2025-02-12
R7S1-OFPW-M-FFAP7 | Pod Works - 1&2 Bed Linear Apartments Buildings (Type A) - First Floor - AP#07 | 13 | 2025-01-29 | 2025-02-12
R7S1-OFPW-M-SFAP1 | Pod Works - 1&2 Bed Linear Apartments Buildings (Type A) - Second Floor - AP#01 | 4 | 2025-02-09 | 2025-02-12
R7S1-OFPW-M-SFAP2 | Pod Works - 1&2 Bed Linear Apartments Buildings (Type A) - Second Floor - AP#02 | 4 | 2025-02-09 | 2025-02-12
R7S1-OFPW-M-SFAP3 | Pod Works - 1&2 Bed Linear Apartments Buildings (Type A) - Second Floor - AP#03 | 6 | 2025-02-10 | 2025-02-16
R7S1-OFPW-M-SFAP4 | Pod Works - 1&2 Bed Linear Apartments Buildings (Type A) - Second Floor - AP#04 | 4 | 2025-02-18 | 2025-02-23
R7S1-OFPW-M-SFAP6 | Pod Works - 1&2 Bed Linear Apartments Buildings (Type A) - Second Floor - AP#06 | 10 | 2025-02-25 | 2025-03-08
R7S1-OFPW-M-SFAP7 | Pod Works - 1&2 Bed Linear Apartments Buildings (Type A) - Second Floor - AP#07 | 5 | 2025-03-05 | 2025-03-10
POD (SHIPPING - DXB TO KSA) |  | 95 | 2024-12-05 | 2025-03-26
R7S1-OFPD-M-GFAP1 | Pod Delivery to KSA - 1&2 Bed Linear Apartments Buildings (Type A) Ground Floor - AP#01 | 9 | 2024-12-25 | 2025-01-04
R7S1-OFPD-M-GFAP2 | Pod Delivery to KSA - 1&2 Bed Linear Apartments Buildings (Type A) - Ground Floor - AP#02 | 11 | 2024-12-30 | 2025-01-11
R7S1-OFPD-M-GFAP3 | Pod Delivery to KSA - 1&2 Bed Linear Apartments Buildings (Type A) - Ground Floor - AP#03 | 35 | 2024-12-05 | 2025-01-14
R7S1-OFPD-M-GFAP4 | Pod Delivery to KSA - 1&2 Bed Linear Apartments Buildings (Type A) - Ground Floor - AP#04 | 35 | 2024-12-09 | 2025-01-18
R7S1-OFPD-M-GFAP6 | Pod Delivery to KSA - 1&2 Bed Linear Apartments Buildings (Type A) - Ground Floor - AP#06 | 33 | 2024-12-14 | 2025-01-20
R7S1-OFPD-M-GFAP7 | Pod Delivery to KSA - 1&2 Bed Linear Apartments Buildings (Type A) - Ground Floor - AP#07 | 3 | 2025-01-19 | 2025-01-21
R7S1-OFPD-M-FFAP1 | Pod Delivery to KSA - 1&2 Bed Linear Apartments Buildings (Type A) - First Floor - AP#01 | 8 | 2025-01-21 | 2025-01-29
R7S1-OFPD-M-FFAP2 | Pod Delivery to KSA - 1&2 Bed Linear Apartments Buildings (Type A) - First Floor - AP#02 | 4 | 2025-01-28 | 2025-02-01
R7S1-OFPD-M-FFAP3 | Pod Delivery to KSA - 1&2 Bed Linear Apartments Buildings (Type A) - First Floor - AP#03 | 17 | 2025-01-15 | 2025-02-03
R7S1-OFPD-M-FFAP4 | Pod Delivery to KSA - 1&2 Bed Linear Apartments Buildings (Type A) - First Floor - AP#04 | 2 | 2025-02-04 | 2025-02-05
R7S1-OFPD-M-FFAP6 | Pod Delivery to KSA - 1&2 Bed Linear Apartments Buildings (Type A) - First Floor - AP#06 | 4 | 2025-02-06 | 2025-02-10
R7S1-OFPD-M-FFAP7 | Pod Delivery to KSA - 1&2 Bed Linear Apartments Buildings (Type A) - First Floor - AP#07 | 4 | 2025-02-08 | 2025-02-11
R7S1-OFPD-M-SFAP1 | Pod Delivery to KSA - 1&2 Bed Linear Apartments Buildings (Type A) - Second Floor - AP#01 | 4 | 2025-02-09 | 2025-02-12
R7S1-OFPD-M-SFAP2 | Pod Delivery to KSA - 1&2 Bed Linear Apartments Buildings (Type A) - Second Floor - AP#02 | 4 | 2025-02-10 | 2025-02-13
R7S1-OFPD-M-SFAP3 | Pod Delivery to KSA - 1&2 Bed Linear Apartments Buildings (Type A) - Second Floor - AP#03 | 7 | 2025-02-11 | 2025-02-18
R7S1-OFPD-M-SFAP4 | Pod Delivery to KSA - 1&2 Bed Linear Apartments Buildings (Type A) - Second Floor - AP#04 | 4 | 2025-02-23 | 2025-02-26
R7S1-OFPD-M-SFAP6 | Pod Delivery to KSA - 1&2 Bed Linear Apartments Buildings (Type A) - Second Floor - AP#06 | 13 | 2025-02-26 | 2025-03-12
R7S1-OFPD-M-SFAP7 | Pod Delivery to KSA - 1&2 Bed Linear Apartments Buildings (Type A) - Second Floor - AP#07 | 15 | 2025-03-10 | 2025-03-26
ASSEMBLY OF BOXES |  | 171 | 2024-12-05 | 2025-06-17
R7S1-OFAS-M-GFAP1 | Assembly of Boxes - 1&2 Bed Linear Apartments Buildings (Type A) - Ground Floor - AP#01 | 12 | 2024-12-29 | 2025-01-11
R7S1-OFAS-M-GFAP2 | Assembly of Boxes - 1&2 Bed Linear Apartments Buildings (Type A) - Ground Floor - AP#02 | 38 | 2024-12-05 | 2025-01-18
R7S1-OFAS-M-GFAP3 | Assembly of Boxes - 1&2 Bed Linear Apartments Buildings (Type A) - Ground Floor - AP#03 | 14 | 2025-01-02 | 2025-01-18
R7S1-OFAS-M-GFAP4 | Assembly of Boxes - 1&2 Bed Linear Apartments Buildings (Type A) - Ground Floor - AP#04 | 6 | 2025-01-16 | 2025-01-22
R7S1-OFAS-M-GFAP7 | Assembly of Boxes - 1&2 Bed Linear Apartments Buildings (Type A) - Ground Floor - AP#07 | 8 | 2025-02-01 | 2025-02-09
R7S1-OFAS-M-GFAP6 | Assembly of Boxes - 1&2 Bed Linear Apartments Buildings (Type A) - Ground Floor - AP#06 | 18 | 2025-01-21 | 2025-02-10
R7S1-OFAS-M-FFAP1 | Assembly of Boxes - 1&2 Bed Linear Apartments Buildings (Type A) - First Floor - AP#01 | 13 | 2025-02-08 | 2025-02-23
R7S1-OFAS-M-FFAP2 | Assembly of Boxes - 1&2 Bed Linear Apartments Buildings (Type A) - First Floor - AP#02 | 10 | 2025-02-13 | 2025-02-25
R7S1-OFAS-M-FFAP3 | Assembly of Boxes - 1&2 Bed Linear Apartments Buildings (Type A) - First Floor - AP#03 | 16 | 2025-02-09 | 2025-02-27
R7S1-OFAS-M-FFAP4 | Assembly of Boxes- 1&2 Bed Linear Apartments Buildings (Type A) - First Floor - AP#04 | 18 | 2025-02-08 | 2025-03-01
R7S1-OFAS-M-FFAP6 | Assembly of Boxes - 1&2 Bed Linear Apartments Buildings (Type A) - First Floor - AP#06 | 20 | 2025-02-08 | 2025-03-03
R7S1-OFAS-M-FFAP7 | Assembly of Boxes - 1&2 Bed Linear Apartments Buildings (Type A) - First Floor - AP#07 | 22 | 2025-02-08 | 2025-03-05
R7S1-OFAS-M-SFAP1 | Assembly of Boxes - Linear Studios Apartments Buildings (Type A) - Second Floor - AP#01 | 28 | 2025-02-26 | 2025-03-30
R7S1-OFAS-M-SFAP2 | Assembly of Boxes - 1&2 Bed Linear Apartments Buildings (Type A) - Second Floor - AP#02 | 21 | 2025-03-06 | 2025-03-30
R7S1-OFAS-M-SFAP3 | Assembly of Boxes - 1&2 Bed Linear Apartments Buildings (Type A) - Second Floor - AP#03 | 17 | 2025-03-11 | 2025-03-30
R7S1-OFAS-M-SFAP4 | Assembly of Boxes - 1&2 Bed Linear Apartments Buildings (Type A) - Second Floor - AP#04 | 18 | 2025-03-13 | 2025-04-07
R7S1-OFAS-M-SFAP6 | Assembly of Boxes - 1&2 Bed Linear Apartments Buildings (Type A) - Second Floor - AP#06 | 18 | 2025-03-17 | 2025-04-10
R7S1-OFAS-M-SFAP7 | Assembly of Boxes - 1&2 Bed Linear Apartments Buildings (Type A) - Second Floor - AP#07 | 10 | 2025-03-27 | 2025-04-12
R7S1-OFAS-HUB-EV18 | Assembly of Boxes - EV18 | 5 | 2025-06-12 | 2025-06-17
FINISHES/MEP WORKS |  | 168 | 2025-01-02 | 2025-07-08
R7S1-OFMF-M-GFAP1 | Finishes & MEP Works inside the Boxes - 1&2 Bed Linear Apartments Buildings (Type A) - Ground Floor - AP#01 | 35 | 2025-01-02 | 2025-02-11
R7S1-OFMF-M-GFAP2 | Finishes & MEP Works inside the Boxes - 1&2 Bed Linear Apartments Buildings (Type A) - Ground Floor - AP#02 | 28 | 2025-01-11 | 2025-02-11
R7S1-OFMF-M-GFAP3 | Finishes & MEP Works inside the Boxes - 1&2 Bed Linear Apartments Buildings (Type A) - Ground Floor - AP#03 | 22 | 2025-01-18 | 2025-02-11
R7S1-OFMF-M-GFAP4 | Finishes & MEP Works inside the Boxes - 1&2 Bed Linear Apartments Buildings (Type A) - Ground Floor - AP#04 | 14 | 2025-01-27 | 2025-02-11
R7S1-OFMF-M-GFAP6 | Finishes & MEP Works inside the Boxes - 1&2 Bed Linear Apartments Buildings (Type A) - Ground Floor - AP#06 | 19 | 2025-01-29 | 2025-02-19
R7S1-OFMF-M-GFAP7 | Finishes & MEP Works inside the Boxes - 1&2 Bed Linear Apartments Buildings (Type A) - Ground Floor - AP#07 | 10 | 2025-02-09 | 2025-02-20
R7S1-OFMF-M-FFAP1 | Finishes & MEP Works inside the Boxes - 1&2 Bed Linear Apartments Buildings (Type A) - First Floor - AP#01 | 11 | 2025-02-10 | 2025-02-24
R7S1-OFMF-M-FFAP2 | Finishes & MEP Works inside the Boxes - 1&2 Bed Linear Apartments Buildings (Type A) - First Floor - AP#02 | 11 | 2025-02-12 | 2025-02-26
R7S1-OFMF-M-FFAP3 | Finishes & MEP Works inside the Boxes - 1&2 Bed Linear Apartments Buildings (Type A) - First Floor - AP#03 | 17 | 2025-02-08 | 2025-02-27
R7S1-OFMF-M-FFAP4 | Finishes & MEP Works inside the Boxes - 1&2 Bed Linear Apartments Buildings (Type A) - First Floor - AP#04 | 22 | 2025-02-17 | 2025-03-15
R7S1-OFMF-M-FFAP6 | Finishes & MEP Works inside the Boxes - 1&2 Bed Linear Apartments Buildings (Type A) - First Floor - AP#06 | 34 | 2025-02-26 | 2025-04-10
R7S1-OFMF-M-FFAP7 | Finishes & MEP Works inside the Boxes - 1&2 Bed Linear Apartments Buildings (Type A) - First Floor - AP#07 | 34 | 2025-02-26 | 2025-04-10
R7S1-OFMF-M-SFAP1 | Finishes & MEP Works inside the Boxes - Linear Studios Apartments Buildings (Type A) - Second Floor - AP#01 | 28 | 2025-03-08 | 2025-04-13
R7S1-OFMF-M-SFAP2 | Finishes & MEP Works inside the Boxes - 1&2 Bed Linear Apartments Buildings (Type A) - Second Floor - AP#02 | 31 | 2025-03-10 | 2025-04-19
R7S1-OFMF-M-SFAP4 | Finishes & MEP Works inside the Boxes - 1&2 Bed Linear Apartments Buildings (Type A) - Second Floor - AP#04 | 24 | 2025-03-19 | 2025-04-20
R7S1-OFMF-M-SFAP3 | Finishes & MEP Works inside the Boxes - 1&2 Bed Linear Apartments Buildings (Type A) - Second Floor - AP#03 | 31 | 2025-03-12 | 2025-04-21
R7S1-OFMF-M-SFAP6 | Finishes & MEP Works inside the Boxes - 1&2 Bed Linear Apartments Buildings (Type A) - Second Floor - AP#06 | 20 | 2025-04-07 | 2025-04-29
R7S1-OFMF-M-SFAP7 | Finishes & MEP Works inside the Boxes - 1&2 Bed Linear Apartments Buildings (Type A) - Second Floor - AP#07 | 24 | 2025-04-05 | 2025-05-01
R7S1-OFMF-HUB-EV18 | Finishes & MEP Works inside the Boxes - EV18 | 20 | 2025-06-16 | 2025-07-08
PRIORITY - 2 |  | 234 | 2025-01-07 | 2025-08-24
PRODUCTION DRAWINGS & MOLD PREPARATION (FOR AMANA USE ONLY) |  | 162 | 2025-01-07 | 2025-06-17
LINEAR STUDIOS APARTMENTS BUILDINGS (STUDIOS - TYPE LARGE) |  | 49 | 2025-02-24 | 2025-04-13
R7S1-LS-PR-1000 | Preparation & Issuance of Production Drawings of Boxes - Civil & MEP (Internal purpose only) | 23 | 2025-02-24 | 2025-03-27
R7S1-LS-PR-1010 | Qanbar Internal Study on the Drawings (GF+FF+SF) | 18 | 2025-03-06 | 2025-03-27
R7S1-LS-PR-1020 | Qanbar Issuance of Mold Drawings (GF+FF+SF) | 12 | 2025-03-13 | 2025-03-27
R7S1-LS-PR-1030 | Mold Fabrication - 1&2 Bed Linear Apartments Buildings (Type A) (GF+FF+SF) | 17 | 2025-03-20 | 2025-04-13
LINEAR STUDIOS APARTMENTS BUILDINGS (STUDIOS -TYPE MEDIUM) |  | 162 | 2025-01-07 | 2025-06-17
R7S1-MS-MOD-1000 | Fabrication model preparation by the Contractor - Studio (Medium) | 42 | 2025-01-07 | 2025-03-05
GROUND FLOOR |  | 47 | 2025-03-09 | 2025-04-24
R7S1-MS-PRGF-1000 | Preparation & Issuance of GF Boxes for Prodiuction to the Factory - Civil & MEP (Internal purpose only) | 15 | 2025-03-09 | 2025-03-27
R7S1-MS-PRGF-1010 | Qanbar Internal Study on the Drawings (GF) | 17 | 2025-03-11 | 2025-03-30
R7S1-MS-PRGF-1020 | Qanbar Issuance of Mold Drawings (GF) | 36 | 2025-03-10 | 2025-04-24
R7S1-MS-PRGF-1030 | Mold Fabrication - 1&2 Bed Linear Apartments Buildings (Type M) (GF) | 18 | 2025-04-05 | 2025-04-24
FIRST FLOOR |  | 46 | 2025-03-10 | 2025-04-24
R7S1-MS-PRFF-1000 | Preparation & Issuance of FF Boxes for Prodiuction to the Factory - Civil & MEP (Internal purpose only) | 29 | 2025-03-10 | 2025-04-24
R7S1-MS-PRFF-1010 | Qanbar Internal Study on the Drawings (FF) | 23 | 2025-03-25 | 2025-04-24
R7S1-MS-PRFF-1020 | Qanbar Issuance of Mold Drawings (FF) | 13 | 2025-04-10 | 2025-04-24
R7S1-MS-PRFF-1030 | Mold Fabrication - 1&2 Bed Linear Apartments Buildings (Type M) (FF) | 3 | 2025-04-22 | 2025-04-24
SECOND FLOOR |  | 52 | 2025-04-27 | 2025-06-17
R7S1-MS-PRSF-1000 | Preparation & Issuance of SF Boxes for Prodiuction to the Factory - Civil & MEP (Internal purpose only) | 10 | 2025-04-27 | 2025-05-08
R7S1-MS-PRSF-1010 | Qanbar Internal Study on the Drawings (SF) | 10 | 2025-05-10 | 2025-05-20
R7S1-MS-PRSF-1020 | Qanbar Issuance of Mold Drawings (SF) | 10 | 2025-05-21 | 2025-06-01
R7S1-MS-PRSF-1030 | Mold Fabrication - 1&2 Bed Linear Apartments Buildings (Type M) (SF) | 10 | 2025-06-02 | 2025-06-17
PRECAST PANELS DELIVERY |  | 110 | 2025-04-05 | 2025-08-12
R7S2-OFPR-SL-GFAP18 | Precast Panels Delivery - 1&2 Bed Linear Apartments Buildings (Type L) - Ground Floor - AP#18 | 8 | 2025-04-21 | 2025-04-29
R7S2-OFPR-SLGFAP17 | Precast Panels Delivery - 1&2 Bed Linear Apartments Buildings (Type L) - Ground Floor - AP#17 | 8 | 2025-04-21 | 2025-04-29
R7S2-OFPR-SLGFAP16 | Precast Panels Delivery - 1&2 Bed Linear Apartments Buildings (Type L) - Ground Floor - AP#16 | 12 | 2025-04-16 | 2025-04-29
R7S2-OFPR-SM-GFAP19 | Precast Panels Delivery - 1&2 Bed Linear Apartments Buildings (Type M) - Ground Floor - AP#19 | 6 | 2025-04-23 | 2025-04-30
R7S2-OFPR-SLGFAP14 | Precast Panels Delivery - 1&2 Bed Linear Apartments Buildings (Type L) - Ground Floor - AP#14 | 6 | 2025-04-23 | 2025-04-30
R7S2-OFPR-SM-GFAP5 | Precast Panels Delivery - Linear Studios Apartments Buildings (Type M) - Ground Floor - AP#05 | 23 | 2025-04-05 | 2025-04-30
R7S2-OFPR-SLGFAP15 | Precast Panels Delivery - 1&2 Bed Linear Apartments Buildings (Type L) - Ground Floor - AP#15 | 5 | 2025-05-27 | 2025-06-01
R7S2-OFPR-SLFFAP17 | Precast Panels Delivery - 1&2 Bed Linear Apartments Buildings (Type L) - First Floor - AP#17 | 5 | 2025-06-02 | 2025-06-11
R7S2-OFPR-SL-FFAP18 | Precast Panels Delivery - 1&2 Bed Linear Apartments Buildings (Type L) - First Floor - AP#18 | 5 | 2025-06-12 | 2025-06-17
R7S2-OFPR-SL-FFAP19 | Precast Panels Delivery - 1&2 Bed Linear Apartments Buildings (Type M) - First Floor - AP#19 | 5 | 2025-06-18 | 2025-06-23
R7S2-OFPR-SM-FFAP5 | Precast Panels Delivery - 1&2 Bed Linear Apartments Buildings (Type M) - First Floor - AP#05 | 5 | 2025-06-24 | 2025-06-29
R7S2-OFPR-SLFFAP14 | Precast Panels Delivery - 1&2 Bed Linear Apartments Buildings (Type L) - First Floor - AP#14 | 5 | 2025-06-30 | 2025-07-05
R7S2-OFPR-SLFFAP15 | Precast Panels Delivery - 1&2 Bed Linear Apartments Buildings (Type L) - First Floor - AP#15 | 4 | 2025-07-06 | 2025-07-09
R7S2-OFPR-SLFFAP16 | Precast Panels Delivery - 1&2 Bed Linear Apartments Buildings (Type L) - First Floor - AP#16 | 4 | 2025-07-10 | 2025-07-14
R7S2-OFPR-SLSFAP16 | Precast Panels Delivery - 1&2 Bed Linear Apartments Buildings (Type L) - Second Floor - AP#16 | 4 | 2025-07-10 | 2025-07-14
R7S2-OFPR-SLSFAP17 | Precast Panels Delivery - 1&2 Bed Linear Apartments Buildings (Type L) - Second Floor - AP#17 | 4 | 2025-07-15 | 2025-07-19
R7S2-OFPR-SL-SFAP18 | Precast Panels Delivery - 1&2 Bed Linear Apartments Buildings (Type L) - Second Floor - AP#18 | 4 | 2025-07-20 | 2025-07-23
R7S2-OFPR-SL-SFAP19 | Precast Panels Delivery - 1&2 Bed Linear Apartments Buildings (Type M) - Second Floor - AP#19 | 4 | 2025-07-24 | 2025-07-28
R7S2-OFPR-SM-SFAP5 | Precast Panels Delivery - Linear Studios Apartments Buildings (Type M) - Second Floor - AP#05 | 4 | 2025-07-29 | 2025-08-02
R7S2-OFPR-SLSFAP14 | Precast Panels Delivery - 1&2 Bed Linear Apartments Buildings (Type L) - Second Floor - AP#14 | 4 | 2025-08-03 | 2025-08-06
R7S2-OFPR-SLSFAP15 | Precast Panels Delivery - 1&2 Bed Linear Apartments Buildings (Type L) - Second Floor - AP#15 | 4 | 2025-08-07 | 2025-08-11
R7S2-OFPR-M-HUB-EV16 | Precast Panels Delivery - EV16 | 2 | 2025-08-11 | 2025-08-12
POD WORKS - DUBAI |  | 86 | 2025-03-09 | 2025-06-02
R7S2-OFPW-SLGFAP16 | Pod Works - 1&2 Bed Linear Apartments Buildings (Type L) - Ground Floor - AP#16 | 11 | 2025-03-09 | 2025-03-20
R7S2-OFPW-SM-GFAP19 | Pod Works - 1&2 Bed Linear Apartments Buildings (Type M) - Ground Floor - AP#19 | 9 | 2025-03-18 | 2025-03-27
R7S2-OFPW-SL-GFAP18 | Pod Works - 1&2 Bed Linear Apartments Buildings (Type L) - Ground Floor - AP#18 | 11 | 2025-03-18 | 2025-03-30
R7S2-OFPW-SLGFAP17 | Pod Works - 1&2 Bed Linear Apartments Buildings (Type L) - Ground Floor - AP#17 | 15 | 2025-03-13 | 2025-03-30
R7S2-OFPW-SM-GFAP5 | Pod Works - Linear Studios Apartments Buildings (Type M) - Ground Floor - AP#05 | 23 | 2025-04-05 | 2025-04-30
R7S2-OFPW-SL-FFAP18 | Pod Works - 1&2 Bed Linear Apartments Buildings (Type L) - First Floor - AP#18 | 19 | 2025-04-09 | 2025-04-30
R7S2-OFPW-SLFFAP17 | Pod Works - 1&2 Bed Linear Apartments Buildings (Type L) - First Floor - AP#17 | 18 | 2025-04-10 | 2025-04-30
R7S2-OFPW-SLGFAP14 | Pod Works - 1&2 Bed Linear Apartments Buildings (Type L) - Ground Floor - AP#14 | 23 | 2025-04-05 | 2025-04-30
R7S2-OFPW-SLGFAP15 | Pod Works - 1&2 Bed Linear Apartments Buildings (Type L) - Ground Floor - AP#15 | 19 | 2025-04-09 | 2025-04-30
R7S2-OFPW-SM-FFAP5 | Pod Works - 1&2 Bed Linear Apartments Buildings (Type M) - First Floor - AP#05 | 29 | 2025-03-29 | 2025-05-05
R7S2-OFPW-SLFFAP14 | Pod Works - 1&2 Bed Linear Apartments Buildings (Type L) - First Floor - AP#14 | 25 | 2025-04-09 | 2025-05-07
R7S2-OFPW-SLFFAP15 | Pod Works - 1&2 Bed Linear Apartments Buildings (Type L) - First Floor - AP#15 | 25 | 2025-04-09 | 2025-05-07
R7S2-OFPW-SLFFAP16 | Pod Works - 1&2 Bed Linear Apartments Buildings (Type L) - First Floor - AP#16 | 25 | 2025-04-09 | 2025-05-07
R7S2-OFPW-SM-FFAP19 | Pod Works - 1&2 Bed Linear Apartments Buildings (Type M) - First Floor - AP#19 | 4 | 2025-05-05 | 2025-05-10
R7S2-OFPW-SLSFAP17 | Pod Works - 1&2 Bed Linear Apartments Buildings (Type L) - Second Floor - AP#17 | 36 | 2025-03-27 | 2025-05-12
R7S2-OFPW-SLSFAP16 | Pod Works - 1&2 Bed Linear Apartments Buildings (Type L) - Second Floor - AP#16 | 4 | 2025-05-10 | 2025-05-14
R7S2-OFPW-SL-SFAP18 | Pod Works - 1&2 Bed Linear Apartments Buildings (Type L) - Second Floor - AP#18 | 4 | 2025-05-14 | 2025-05-19
R7S2-OFPW-SM-SFAP5 | Pod Works - Linear Studios Apartments Buildings (Type M) - Second Floor - AP#05 | 43 | 2025-03-29 | 2025-05-21
R7S2-OFPW-SM-SFAP19 | Pod Works - 1&2 Bed Linear Apartments Buildings (Type M) - Second Floor - AP#19 | 4 | 2025-05-19 | 2025-05-24
R7S2-OFPW-SLSFAP14 | Pod Works - 1&2 Bed Linear Apartments Buildings (Type L) - Second Floor - AP#14 | 4 | 2025-05-24 | 2025-05-28
R7S2-OFPW-SLSFAP15 | Pod Works - 1&2 Bed Linear Apartments Buildings (Type L) - Second Floor - AP#15 | 4 | 2025-05-28 | 2025-06-02
POD (SHIPPING - DXB TO KSA) |  | 96 | 2025-03-18 | 2025-06-21
R7S2-OFPD-SM-GFAP19 | Pod Delivery to KSA - 1&2 Bed Linear Apartments Buildings (Type M) - Ground Floor - AP#19 | 5 | 2025-03-25 | 2025-03-30
R7S2-OFPD-SL-GFAP18 | Pod Delivery to KSA - 1&2 Bed Linear Apartments Buildings (Type L) - Ground Floor - AP#18 | 13 | 2025-03-23 | 2025-04-10
R7S2-OFPD-SLGFAP17 | Pod Delivery to KSA - 1&2 Bed Linear Apartments Buildings (Type L) - Ground Floor - AP#17 | 17 | 2025-03-18 | 2025-04-10
R7S2-OFPD-SLGFAP16 | Pod Delivery to KSA - 1&2 Bed Linear Apartments Buildings (Type L) - Ground Floor - AP#16 | 24 | 2025-03-24 | 2025-04-24
R7S2-OFPD-SM-GFAP5 | Pod Delivery to KSA - Linear Studios Apartments Buildings (Type M) - Ground Floor - AP#05 | 23 | 2025-04-05 | 2025-04-30
R7S2-OFPD-SLFFAP17 | Pod Delivery to KSA - 1&2 Bed Linear Apartments Buildings (Type L) - First Floor - AP#17 | 9 | 2025-04-21 | 2025-04-30
R7S2-OFPD-SLGFAP14 | Pod Delivery to KSA - 1&2 Bed Linear Apartments Buildings (Type L) - Ground Floor - AP#14 | 18 | 2025-04-10 | 2025-04-30
R7S2-OFPD-SLGFAP15 | Pod Delivery to KSA - 1&2 Bed Linear Apartments Buildings (Type L) - Ground Floor - AP#15 | 7 | 2025-04-23 | 2025-04-30
R7S2-OFPD-SLFFAP16 | Pod Delivery to KSA - 1&2 Bed Linear Apartments Buildings (Type L) - First Floor - AP#16 | 13 | 2025-04-23 | 2025-05-07
R7S2-OFPD-SL-FFAP18 | Pod Delivery to KSA - 1&2 Bed Linear Apartments Buildings (Type L) - First Floor - AP#18 | 12 | 2025-05-05 | 2025-05-19
R7S2-OFPD-SM-FFAP5 | Pod Delivery to KSA - 1&2 Bed Linear Apartments Buildings (Type M) - First Floor - AP#05 | 12 | 2025-05-10 | 2025-05-24
R7S2-OFPD-SM-FFAP19 | Pod Delivery to KSA - 1&2 Bed Linear Apartments Buildings (Type M) - First Floor - AP#19 | 12 | 2025-05-10 | 2025-05-24
R7S2-OFPD-SLFFAP14 | Pod Delivery to KSA - 1&2 Bed Linear Apartments Buildings (Type L) - First Floor - AP#14 | 12 | 2025-05-10 | 2025-05-24
R7S2-OFPD-SLFFAP15 | Pod Delivery to KSA - 1&2 Bed Linear Apartments Buildings (Type L) - First Floor - AP#15 | 12 | 2025-05-10 | 2025-05-24
R7S2-OFPD-SLSFAP17 | Pod Delivery to KSA - 1&2 Bed Linear Apartments Buildings (Type L) - Second Floor - AP#17 | 12 | 2025-05-14 | 2025-05-28
R7S2-OFPD-SLSFAP16 | Pod Delivery to KSA - 1&2 Bed Linear Apartments Buildings (Type L) - Second Floor - AP#16 | 12 | 2025-05-14 | 2025-05-28
R7S2-OFPD-SL-SFAP18 | Pod Delivery to KSA - 1&2 Bed Linear Apartments Buildings (Type L) - Second Floor - AP#18 | 12 | 2025-05-19 | 2025-06-02
R7S2-OFPD-SM-SFAP5 | Pod Delivery to KSA - Linear Studios Apartments Buildings (Type M) - Second Floor - AP#05 | 12 | 2025-05-24 | 2025-06-11
R7S2-OFPD-SM-SFAP19 | Pod Delivery to KSA - 1&2 Bed Linear Apartments Buildings (Type M) - Second Floor - AP#19 | 12 | 2025-05-24 | 2025-06-11
R7S2-OFPD-SLSFAP14 | Pod Delivery to KSA - 1&2 Bed Linear Apartments Buildings (Type L) - Second Floor - AP#14 | 12 | 2025-05-28 | 2025-06-16
R7S2-OFPD-SLSFAP15 | Pod Delivery to KSA - 1&2 Bed Linear Apartments Buildings (Type L) - Second Floor - AP#15 | 12 | 2025-06-02 | 2025-06-21
ASSEMBLY OF BOXES |  | 104 | 2025-04-13 | 2025-08-14
R7S2-OFAS-SLGFAP16 | Assembly of Boxes - 1&2 Bed Linear Apartments Buildings (Type L) - Ground Floor - AP#16 | 18 | 2025-04-13 | 2025-05-04
R7S2-OFAS-SLGFAP17 | Assembly of Boxes - 1&2 Bed Linear Apartments Buildings (Type L) - Ground Floor - AP#17 | 13 | 2025-04-22 | 2025-05-07
R7S2-OFAS-SL-GFAP18 | Assembly of Boxes - 1&2 Bed Linear Apartments Buildings (Type L) - Ground Floor - AP#18 | 16 | 2025-04-23 | 2025-05-12
R7S2-OFAS-SM-GFAP19 | Assembly of Boxes - 1&2 Bed Linear Apartments Buildings (Type M) - Ground Floor - AP#19 | 6 | 2025-05-19 | 2025-05-26
R7S2-OFAS-SM-GFAP5 | Assembly of Boxes - Linear Studios Apartments Buildings (Type M) - Ground Floor - AP#05 | 6 | 2025-05-21 | 2025-05-28
R7S2-OFAS-SLGFAP14 | Assembly of Boxes - 1&2 Bed Linear Apartments Buildings (Type L) - Ground Floor - AP#14 | 6 | 2025-05-24 | 2025-05-31
R7S2-OFAS-SLGFAP15 | Assembly of Boxes - 1&2 Bed Linear Apartments Buildings (Type L) - Ground Floor - AP#15 | 6 | 2025-05-28 | 2025-06-03
R7S2-OFAS-SLFFAP17 | Assembly of Boxes - 1&2 Bed Linear Apartments Buildings (Type L) - First Floor - AP#17 | 6 | 2025-06-03 | 2025-06-14
R7S2-OFAS-SL-FFAP18 | Assembly of Boxes - 1&2 Bed Linear Apartments Buildings (Type L) - First Floor - AP#18 | 6 | 2025-06-14 | 2025-06-19
R7S2-OFAS-SM-FFAP19 | Assembly of Boxes - 1&2 Bed Linear Apartments Buildings (Type M) - First Floor - AP#19 | 6 | 2025-06-19 | 2025-06-25
R7S2-OFAS-SM-FFAP5 | Assembly of Boxes - Linear Studios Apartments Buildings (Type M) - First Floor - AP#05 | 6 | 2025-06-25 | 2025-07-01
R7S2-OFAS-SLFFAP14 | Assembly of Boxes - 1&2 Bed Linear Apartments Buildings (Type L) - First Floor - AP#14 | 6 | 2025-07-01 | 2025-07-07
R7S2-OFAS-SLFFAP15 | Assembly of Boxes - 1&2 Bed Linear Apartments Buildings (Type L) - First Floor - AP#15 | 6 | 2025-07-07 | 2025-07-13
R7S2-OFAS-SLFFAP16 | Assembly of Boxes - 1&2 Bed Linear Apartments Buildings (Type L) - First Floor - AP#16 | 6 | 2025-07-12 | 2025-07-17
R7S2-OFAS-SLSFAP16 | Assembly of Boxes - 1&2 Bed Linear Apartments Buildings (Type L) - Second Floor - AP#16 | 5 | 2025-07-15 | 2025-07-20
R7S2-OFAS-SLSFAP17 | Assembly of Boxes - 1&2 Bed Linear Apartments Buildings (Type L) - Second Floor - AP#17 | 5 | 2025-07-17 | 2025-07-22
R7S2-OFAS-SL-SFAP18 | Assembly of Boxes - 1&2 Bed Linear Apartments Buildings (Type L) - Second Floor - AP#18 | 5 | 2025-07-21 | 2025-07-26
R7S2-OFAS-SM-SFAP19 | Assembly of Boxes - 1&2 Bed Linear Apartments Buildings (Type M) - Second Floor - AP#19 | 5 | 2025-07-26 | 2025-07-30
R7S2-OFAS-SM-SFAP5 | Assembly of Boxes - Linear Studios Apartments Buildings (Type M) - Second Floor - AP#05 | 5 | 2025-07-30 | 2025-08-04
R7S2-OFAS-SLSFAP14 | Assembly of Boxes - 1&2 Bed Linear Apartments Buildings (Type L) - Second Floor - AP#14 | 5 | 2025-08-04 | 2025-08-09
R7S2-OFAS-SLSFAP15 | Assembly of Boxes - 1&2 Bed Linear Apartments Buildings (Type L) - Second Floor - AP#15 | 5 | 2025-08-09 | 2025-08-13
R7S1-OFAS-HUB-EV16 | Assembly of Boxes - EV16 | 2 | 2025-08-13 | 2025-08-14
FINISHES/MEP WORKS |  | 113 | 2025-04-15 | 2025-08-24
R7S2-OFMF-SLGFAP16 | Finishes & MEP Works inside the Boxes - 1&2 Bed Linear Apartments Buildings (Type L) - Ground Floor - AP#16 | 18 | 2025-04-15 | 2025-05-05
R7S2-OFMF-SL-GFAP18 | Finishes & MEP Works inside the Boxes - 1&2 Bed Linear Apartments Buildings (Type L) - Ground Floor - AP#18 | 18 | 2025-04-21 | 2025-05-11
R7S2-OFMF-SLGFAP17 | Finishes & MEP Works inside the Boxes - 1&2 Bed Linear Apartments Buildings (Type L) - Ground Floor - AP#17 | 17 | 2025-05-01 | 2025-05-20
R7S2-OFMF-SM-GFAP19 | Finishes & MEP Works inside the Boxes - 1&2 Bed Linear Apartments Buildings (Type M) - Ground Floor - AP#19 | 17 | 2025-05-21 | 2025-06-15
R7S2-OFMF-SM-GFAP5 | Finishes & MEP Works inside the Boxes - Linear Studios Apartments Buildings (Type M) - Ground Floor - AP#05 | 17 | 2025-05-25 | 2025-06-18
R7S2-OFMF-SLGFAP14 | Finishes & MEP Works inside the Boxes - 1&2 Bed Linear Apartments Buildings (Type L) - Ground Floor - AP#14 | 17 | 2025-05-27 | 2025-06-21
R7S2-OFMF-SLGFAP15 | Finishes & MEP Works inside the Boxes - 1&2 Bed Linear Apartments Buildings (Type L) - Ground Floor - AP#15 | 17 | 2025-06-01 | 2025-06-24
R7S2-OFMF-SLFFAP17 | Finishes & MEP Works inside the Boxes - 1&2 Bed Linear Apartments Buildings (Type L) - First Floor - AP#17 | 16 | 2025-06-11 | 2025-06-29
R7S2-OFMF-SL-FFAP18 | Finishes & MEP Works inside the Boxes - 1&2 Bed Linear Apartments Buildings (Type L) - First Floor - AP#18 | 16 | 2025-06-17 | 2025-07-05
R7S2-OFMF-SM-FFAP19 | Finishes & MEP Works inside the Boxes - 1&2 Bed Linear Apartments Buildings (Type M) - First Floor - AP#19 | 16 | 2025-06-23 | 2025-07-10
R7S2-OFMF-SM-FFAP5 | Finishes & MEP Works inside the Boxes - Linear Studios Apartments Buildings (Type M) - First Floor - AP#05 | 16 | 2025-06-29 | 2025-07-16
R7S2-OFMF-SLFFAP14 | Finishes & MEP Works inside the Boxes - 1&2 Bed Linear Apartments Buildings (Type L) - First Floor - AP#14 | 16 | 2025-07-05 | 2025-07-22
R7S2-OFMF-SLFFAP15 | Finishes & MEP Works inside the Boxes - 1&2 Bed Linear Apartments Buildings (Type L) - First Floor - AP#15 | 16 | 2025-07-10 | 2025-07-28
R7S2-OFMF-SLFFAP16 | Finishes & MEP Works inside the Boxes - 1&2 Bed Linear Apartments Buildings (Type L) - First Floor - AP#16 | 15 | 2025-07-15 | 2025-07-31
R7S2-OFMF-SLSFAP16 | Finishes & MEP Works inside the Boxes - 1&2 Bed Linear Apartments Buildings (Type L) - Second Floor - AP#16 | 15 | 2025-07-19 | 2025-08-04
R7S2-OFMF-SLSFAP17 | Finishes & MEP Works inside the Boxes - 1&2 Bed Linear Apartments Buildings (Type L) - Second Floor - AP#17 | 15 | 2025-07-21 | 2025-08-06
R7S2-OFMF-SL-SFAP18 | Finishes & MEP Works inside the Boxes - 1&2 Bed Linear Apartments Buildings (Type L) - Second Floor - AP#18 | 15 | 2025-07-24 | 2025-08-10
R7S2-OFMF-SM-SFAP19 | Finishes & MEP Works inside the Boxes - 1&2 Bed Linear Apartments Buildings (Type M) - Second Floor - AP#19 | 15 | 2025-07-29 | 2025-08-14
R7S2-OFMF-SM-SFAP5 | Finishes & MEP Works inside the Boxes - Linear Studios Apartments Buildings (Type M) - Second Floor - AP#05 | 15 | 2025-08-02 | 2025-08-18
R7S2-OFMF-SLSFAP14 | Finishes & MEP Works inside the Boxes - 1&2 Bed Linear Apartments Buildings (Type L) - Second Floor - AP#14 | 14 | 2025-08-05 | 2025-08-20
R7S1-OFMF-HUB-EV16 | Finishes & MEP Works inside the Boxes - EV16 | 7 | 2025-08-16 | 2025-08-23
R7S2-OFMF-SLSFAP15 | Finishes & MEP Works inside the Boxes - 1&2 Bed Linear Apartments Buildings (Type L) - Second Floor - AP#15 | 13 | 2025-08-10 | 2025-08-24
ON-SITE WORKS |  | 407 | 2024-10-01 | 2025-12-22
MOBILIZATION |  | 51 | 2024-10-01 | 2024-11-28
R7-MOB-1000 | Mobilization For Main office & Laydown Area | 51 | 2024-10-01 | 2024-11-28
PRIORITY - 1 |  | 363 | 2024-11-10 | 2025-09-30
MANAGEMENT BUILDINGS |  | 290 | 2024-11-10 | 2025-09-30
BUILDING # AP03 (MGT BLDG) |  | 286 | 2024-11-13 | 2025-09-30
SUB-STRUCTURE |  | 39 | 2024-11-13 | 2024-12-28
R7S1-ONSB-AP03-215 | Site Setting Out Works - AP#03 | 1 | 2024-11-13 | 2024-11-13
R7S1-ONSB-AP03-212 | Site levelling & earthworks - AP#03 | 9 | 2024-11-16 | 2024-11-25
R7S1-ONSB-AP03-216 | Anti-termite & Polythene Sheet Works - AP#03 | 2 | 2024-12-02 | 2024-12-03
R7S1-ONSB-AP03-213 | Blinding PCC - AP#03 | 2 | 2024-12-03 | 2024-12-04
R7S1-ONSB-AP03-214 | Waterproofing for Blinding PCC (Bitumen Paint) - AP#03 | 1 | 2024-12-05 | 2024-12-05
R7S1-ONSB-AP03-217 | Foundations/Upstands - Rebar - AP#03 | 9 | 2024-12-05 | 2024-12-15
R7S1-ONSB-AP03-218 | Foundations/Upstands - Shuttering (Including dowel Works) - AP#03 | 9 | 2024-12-05 | 2024-12-15
R7S1-ONSB-AP03-221 | Installation of MEP U/G services below Boxes - AP#03 | 1 | 2024-12-15 | 2024-12-16
R7S1-ONSB-AP03-219 | Foundations/Upstands - Casting - AP#03 | 2 | 2024-12-16 | 2024-12-18
R7S1-ONSB-AP03-220 | Waterproofing For Foundations/Upstands - AP#03 | 0 | 2024-12-19 | 2024-12-19
R7S1-ONSB-AP03-222 | Backfilling & Compaction - AP#03 | 7 | 2024-12-21 | 2024-12-28
SLAB-ON-GRADE & UG MEP WORKS (in Corridor) |  | 62 | 2025-01-23 | 2025-04-10
LEFT SIDE |  | 53 | 2025-02-03 | 2025-04-10
R7S1-ONSG-AP03-256 | Block Work below Corridor area - AP#03 | 9 | 2025-02-03 | 2025-02-12
R7S1-ONSG-AP03-262 | Backfilling upto Pipe Level - AP#03 | 10 | 2025-02-04 | 2025-02-16
R7S1-ONSG-AP03-257 | UG MEP Works (Laying of Pipes) - AP#03 | 11 | 2025-02-05 | 2025-02-18
R7S1-ONSG-AP03-270 | Plaster Work for Blockwork - AP#03 | 11 | 2025-02-06 | 2025-02-18
R7S1-ONSG-AP03-258 | Backfilling Works after Pipe Laying - AP#03 | 13 | 2025-02-09 | 2025-02-24
R7S1-ONSG-AP03-259 | Antitermite Works - AP#03 | 12 | 2025-02-10 | 2025-02-24
R7S1-ONSG-AP03-260 | Polythene & Rebar Mesh Works - AP#03 | 9 | 2025-02-15 | 2025-02-25
R7S1-ONSG-AP03-261 | Pouring SOG Concrete - AP#03 | 9 | 2025-02-16 | 2025-02-26
R7S1-ONSG-AP03-280 | Backfilling & SOG (In Front of Lift Shaft) - AP#03 | 3 | 2025-04-07 | 2025-04-10
RIGHT SIDE |  | 28 | 2025-01-23 | 2025-02-25
R7S1-ONSG-AP03-263 | Block Work below Corridor area - AP#03 | 17 | 2025-01-23 | 2025-02-11
R7S1-ONSG-AP03-269 | Backfilling upto Pipe Level - AP#03 | 19 | 2025-01-25 | 2025-02-16
R7S1-ONSG-AP03-264 | UG MEP Works (Laying of Pipes) - AP#03 | 20 | 2025-01-26 | 2025-02-18
R7S1-ONSG-AP03-265 | Backfilling Works after Pipe Laying - AP#03 | 19 | 2025-01-29 | 2025-02-20
R7S1-ONSG-AP03-266 | Antitermite Works - AP#03 | 20 | 2025-01-30 | 2025-02-23
R7S1-ONSG-AP03-267 | Polythene & Rebar Mesh Works - AP#03 | 20 | 2025-02-01 | 2025-02-24
R7S1-ONSG-AP03-268 | Pouring SOG Concrete - AP#03 | 20 | 2025-02-02 | 2025-02-25
ERECTION WORKS |  | 88 | 2025-01-30 | 2025-05-18
GROUND FLOOR |  | 55 | 2025-01-30 | 2025-04-09
R7S1ONER-AP03GF157 | Erection of GF Boxes (Left Side) including Lift Box & Staircase - AP#03 | 14 | 2025-01-30 | 2025-02-15
R7S1ONER-AP03GF158 | Erection of GF Boxes (Right Side) - AP#03 | 14 | 2025-02-02 | 2025-02-17
R7S1ONER-AP03GF159 | Erection of GF MEP Modular Cages (Left Side) - AP#03 | 2 | 2025-02-16 | 2025-02-18
R7S1ONER-AP03GF160 | Erection of GF Corridor Slabs (Left Side) - AP#03 | 2 | 2025-02-17 | 2025-02-19
R7S1ONER-AP03GF161 | Erection of GF MEP Modular Cages (Right Side) - AP#03 | 22 | 2025-02-03 | 2025-03-01
R7S1ONER-AP03GF162 | Erection of GF Corridor Slabs Right Side) - AP#03 | 21 | 2025-02-05 | 2025-03-02
R7S1ONER-AP03GF172 | Erection of Columns/Beams Frame & Slab/Loose Elements (In Front of Lift Shaft) - AP#03 | 3 | 2025-04-06 | 2025-04-09
FIRST FLOOR |  | 39 | 2025-03-03 | 2025-04-22
R7S1ONER-AP03FF157 | Erection of FF Boxes (Left Side) - AP#03 | 7 | 2025-03-03 | 2025-03-11
R7S1ONER-AP03FF158 | Erection of FF Boxes (Right Side) - AP#03 | 3 | 2025-03-11 | 2025-03-13
R7S1ONER-AP03FF160 | Erection of FF Corridor Slabs (Left Side) - AP#03 | 6 | 2025-03-10 | 2025-03-16
R7S1ONER-AP03FF162 | Erection of FF Corridor Slabs Right Side) - AP#03 | 4 | 2025-03-13 | 2025-03-18
R7S1ONER-AP03FF159 | Erection of FF MEP Modular Cages (Left Side) - AP#03 | 12 | 2025-03-08 | 2025-03-20
R7S1ONER-AP03FF161 | Erection of FF MEP Modular Cages (Right Side) - AP#03 | 9 | 2025-03-11 | 2025-03-22
R7S1ONER-AP03FF182 | Erection of Columns/Beams Frame & Slab/Loose Elements (In Front of Lift Shaft) - AP#03 | 4 | 2025-04-19 | 2025-04-22
SECOND FLOOR |  | 15 | 2025-04-17 | 2025-05-04
R7S1ONER-AP03SF157 | Erection of SF Boxes (Left Side) - AP#03 | 3 | 2025-04-17 | 2025-04-20
R7S1ONER-AP03SF158 | Erection of SF Boxes (Right Side) - AP#03 | 3 | 2025-04-17 | 2025-04-21
R7S1ONER-AP03SF192 | Erection of Columns/Beams Frame & Slab/Loose Elements (In Front of Lift Shaft) - AP#03 | 2 | 2025-04-23 | 2025-04-24
R7S1ONER-AP03SF159 | Erection of SF MEP Modular Cages (Left Side) - AP#03 | 3 | 2025-04-26 | 2025-04-28
R7S1ONER-AP03SF160 | Erection of SF Corridor Slabs (Left Side) - AP#03 | 2 | 2025-04-29 | 2025-04-30
R7S1ONER-AP03SF161 | Erection of SF MEP Modular Cages (Right Side) - AP#03 | 2 | 2025-04-30 | 2025-05-01
R7S1ONER-AP03SF162 | Erection of SF Corridor Slabs Right Side) - AP#03 | 2 | 2025-05-03 | 2025-05-04
ROOF |  | 12 | 2025-05-05 | 2025-05-18
R7S1ONER-AP03RF102 | Erection of Loose Roof Parapets, Shaft Covers, MEP Foundation etc. - AP#03 Roof | 12 | 2025-05-05 | 2025-05-18
MEP WORKS & FINISHES |  | 198 | 2025-02-08 | 2025-09-30
GROUND FLOOR |  | 196 | 2025-02-08 | 2025-07-19
ARCH./ CIVIL WORKS |  | 190 | 2025-02-15 | 2025-07-19
CORRIDOR AREA |  | 139 | 2025-02-15 | 2025-07-19
R7S1ONAR-AP03GF74 | Flooring in Corridor - AP#03 (GF Corridor) | 58 | 2025-02-15 | 2025-04-28
R7S1ONAR-AP03GF72 | False Ceiling - 1st Fix - AP#03 (GF - Corridor) | 25 | 2025-04-07 | 2025-05-06
R7S1ONAR-AP03GF75 | Corridor Skirting - AP#03 (GF Corridor) | 55 | 2025-02-26 | 2025-05-06
R7S1ONAR-AP03GF73 | Gypsum Wall Cladding - 1st Fix (Shafts) - AP#03 (GF Corridor) | 85 | 2025-03-13 | 2025-06-30
R7S1ONAR-AP03GF76 | Gypsum Wall Cladding (Shafts) -2nd Fix - AP#03 (GF Corridor) | 57 | 2025-04-21 | 2025-06-30
R7S1ONAR-AP03GF80 | Fixing Architrave - AP#03 (GF Corridor) | 2 | 2025-07-01 | 2025-07-02
R7S1ONAR-AP03GF77 | False Ceiling - 2nd Fix (Closing the Ceiling) - AP#03 (GF Corridor) | 2 | 2025-07-03 | 2025-07-05
R7S1ONAR-AP03GF81 | Fixing Aluminium Doors - AP#03 (GF Corridor) | 2 | 2025-07-03 | 2025-07-05
R7S1ONAR-AP03GF78 | Painting - Surface Prep., Primer & 1st Coat - AP#03 (GF Corridor) | 8 | 2025-07-01 | 2025-07-09
R7S1ONAR-AP03GF102 | Painting - Surface Prep., Primer & 1st Coat for Ceiling - AP#03 (GF Corridor) | 4 | 2025-07-06 | 2025-07-09
R7S1ONAR-AP03GF79 | Painting - Final Coat (Ceiling + Walls) - AP#03 (GF Corridor) | 3 | 2025-07-16 | 2025-07-19
INSIDE BOXES |  | 20 | 2025-04-10 | 2025-05-03
R7S1ONAR-AP03GF82 | Fixing Thresholds (Joining the Room) - AP#03 (GF - inside Boxes) | 16 | 2025-04-10 | 2025-04-28
R7S1ONAR-AP03GF83 | Fixing Wooden Doors - AP#03 (GF - inside Boxes) | 4 | 2025-04-28 | 2025-05-03
R7S1ONAR-AP03GF84 | Fixing Aluminium Doors - AP#03 (GF - inside Boxes) | 7 | 2025-04-24 | 2025-05-03
IN FRONT OF LIFT SHAFT |  | 135 | 2025-04-26 | 2025-07-14
R7S1ONAR-AP03GF86 | Flooring - AP#03 (GF - Front of Lift Shaft) | 3 | 2025-04-26 | 2025-04-28
R7S1ONAR-AP03GF87 | Skirting & Thresholds - AP#03 (GF - Front of Lift Shaft) | 1 | 2025-04-28 | 2025-04-28
R7S1ONAR-AP03GF88 | Painting - Surface Prep., Primer & 1st Coat - AP#03 (GF - Front of Lift Shaft) | 4 | 2025-04-29 | 2025-05-03
R7S1ONAR-AP03GF85 | False Ceiling - 1st Fix - AP#03 (GF - Front of Lift Shaft) | 4 | 2025-05-04 | 2025-05-07
R7S1ONAR-AP03GF89 | False Ceiling - Final Fix - AP#03 (GF - Front of Lift Shaft) | 1 | 2025-05-08 | 2025-05-08
R7S1ONAR-AP03GF91 | Fixing Handrail - AP#03 (GF - Front of Lift Shaft) | 3 | 2025-06-30 | 2025-07-02
R7S1ONAR-AP03GF92 | Paint for Handrail - AP#03 (GF - Front of Lift Shaft) | 3 | 2025-07-03 | 2025-07-06
R7S1ONAR-AP03GF90 | Painting - Final Coat - AP#03 (GF - Front of Lift Shaft) | 3 | 2025-07-07 | 2025-07-09
R7S1ONAR-AP03GF94 | Fixing Wall Guard - AP#03 (GF - Front of Lift Shaft) | 2 | 2025-07-10 | 2025-07-12
R7S1ONAR-AP03GF93 | Fixing Floor Mat - AP#03 (GF - Front of Lift Shaft) | 2 | 2025-07-13 | 2025-07-14
GARBAGE ROOM |  | 2 | 2025-07-17 | 2025-07-19
R7S1ONAR-AP03GF95 | Paint Finishes and Touchups - Final Coat - AP#03 (GF - Garbage Room) | 2 | 2025-07-17 | 2025-07-19
BALCONIES |  | 140 | 2025-04-08 | 2025-07-14
R7S1ONAR-AP03GF96 | Wetarea Waterproofing - AP#03 (GF - Balconies) | 18 | 2025-04-08 | 2025-04-28
R7S1ONAR-AP03GF97 | Flooring - AP#03 (GF - Front of Lift Shaft) | 17 | 2025-04-13 | 2025-05-01
R7S1ONAR-AP03GF98 | Painting - Surface Prep., Primer & 1st Coat - AP#03 (GF - Front of Lift Shaft) | 6 | 2025-04-28 | 2025-05-05
R7S1ONAR-AP03GF100 | Fixing Handrail - AP#03 (GF - Front of Lift Shaft) | 6 | 2025-07-03 | 2025-07-09
R7S1ONAR-AP03GF101 | Paint for Handrail - AP#03 (GF - Front of Lift Shaft) | 2 | 2025-07-10 | 2025-07-12
R7S1ONAR-AP03GF99 | Painting - Final Coat - AP#03 (GF - Front of Lift Shaft) | 2 | 2025-07-13 | 2025-07-14
MEP WORKS |  | 129 | 2025-02-08 | 2025-07-10
MECHANICAL |  | 121 | 2025-02-08 | 2025-07-08
CHILLED WATER |  | 83 | 2025-02-08 | 2025-05-14
R7S1ONME-AP03GF392 | CHWP piping risers connections - AP#03 (GF - Corridor) | 19 | 2025-03-12 | 2025-04-08
R7S1ONME-AP03GF389 | Installation of Chilled water hanger and supports - AP#03 (GF - Corridor) | 48 | 2025-02-08 | 2025-04-10
R7S1ONME-AP03GF390 | Installation of CHWP piping (connection between modular cages & modular to apartment) - AP#03 (GF - Corridor) | 26 | 2025-03-08 | 2025-04-10
R7S1ONME-AP03GF391 | Installation of BTU Meter with valves - AP#03 (GF - Corridor) | 31 | 2025-03-10 | 2025-04-19
R7S1ONME-AP03GF393 | Pressure Testing of CHWP piping - AP#03 (GF - Corridor) | 20 | 2025-03-24 | 2025-04-20
R7S1ONME-AP03GF441 | Installation of CHWP connection for FCU with Valve package in Corridor, Electrical Room & ICT Room - AP#03 (GF) | 34 | 2025-03-12 | 2025-04-24
R7S1ONME-AP03GF456 | CHWP Installation/Connections and Insulation (In Front of Lift Shaft) - AP#03 | 4 | 2025-04-26 | 2025-04-29
R7S1ONME-AP03GF429 | CHWP Insulation - AP#03 (GF - Corridor) | 55 | 2025-03-06 | 2025-05-14
HVAC DUCTING |  | 100 | 2025-03-04 | 2025-07-07
R7S1ONME-AP03GF442 | Installation of Ducting and insulation (connection between modular cages) - AP#03 (GF - Corridor) | 19 | 2025-03-04 | 2025-03-26
R7S1ONME-AP03GF430 | Installation of Duct & Grill in Garbage Room - AP#03 (GF - Garbage Room) | 20 | 2025-03-15 | 2025-04-10
R7S1ONME-AP03GF394 | Duct Riser Continuation - AP#03 (GF - Corridor) | 33 | 2025-03-08 | 2025-04-19
R7S1ONME-AP03GF440 | Installation of FCU's & Duct Connection in Corridor, Electrical Room & ICT Room - AP#03 (GF) | 30 | 2025-03-17 | 2025-04-24
R7S1ONME-AP03GF395 | A/C drain & Copper pipe connection in ELV room - AP#03 (GF) | 19 | 2025-04-26 | 2025-05-17
R7S1ONME-AP03GF443 | Installation of Grilles in the Corridor - AP#03 (GF - Corridor) | 2 | 2025-07-06 | 2025-07-07
FIRE FIGHTING |  | 98 | 2025-03-08 | 2025-07-08
R7S1ONME-AP03GF396 | Riser Continuity in corridor - AP#03 (GF - Corridor) | 24 | 2025-03-08 | 2025-04-08
R7S1ONME-AP03GF397 | Continuitu of FF pipes & ZC Valves (connection between modular cages & modular to apartment) - AP#03 (GF - Corridor) | 38 | 2025-03-08 | 2025-04-24
R7S1ONME-AP03GF796 | Installation of F.F Pipes, Testing & Final Fixtures (In Front of Lift Shaft) - AP#03 | 3 | 2025-04-30 | 2025-05-03
R7S1ONME-AP03GF399 | Pressure Test for FF Piping in corridor - AP#03 (GF - Corridor) | 2 | 2025-05-04 | 2025-05-06
R7S1ONME-AP03GF398 | Installation of Sprinklers drops in corridor - AP#03 (GF - Corridor) | 4 | 2025-05-06 | 2025-05-11
R7S1ONME-AP03GF444 | FF Flushing network - AP#03 (GF - Corridor) | 1 | 2025-05-18 | 2025-05-19
R7S1ONME-AP03GF431 | Installation of Pipe & sprinkler in Garbage Room - AP#03 (GF - Garbage Room) | 87 | 2025-03-11 | 2025-06-30
R7S1ONME-AP03GF401 | Installation of Alarm check valve, Fire Extinguishers & Blanket - AP#03 (GF - Corridor) | 73 | 2025-04-07 | 2025-07-05
R7S1ONME-AP03GF400 | Installation of Sprinklers in corridor - AP#03 (GF - Corridor) | 3 | 2025-07-06 | 2025-07-08
WATER SUPPLY |  | 85 | 2025-02-08 | 2025-05-22
R7S1ONME-AP03GF403 | WS High Level Pipe continuation & Insulation works - AP#03 (GF - Corridor) | 32 | 2025-02-08 | 2025-03-17
R7S1ONME-AP03GF433 | Installation of Sanitary Fixtures in Janitor Room - AP#03 (GF - Janitor Room) | 33 | 2025-02-08 | 2025-03-18
R7S1ONME-AP03GF432 | Installation of WS Pipe in Garbage Room - AP#03 (GF - Garbage Room) | 37 | 2025-02-08 | 2025-03-23
R7S1ONME-AP03GF404 | Installation of Cold, Hot water line & Hot water return - AP#03 (GF - Corridor) | 39 | 2025-02-12 | 2025-03-30
R7S1ONME-AP03GF402 | Riser Continuity in Shafts - AP#03 (GF - Corridor) | 21 | 2025-04-06 | 2025-04-29
R7S1ONME-AP03GF405 | Water Meter Installation - AP#03 (GF - Corridor) | 4 | 2025-04-26 | 2025-04-29
R7S1ONME-AP03GF406 | Pressure Test for WS - AP#03 (GF - Corridor) | 4 | 2025-05-19 | 2025-05-22
R7S1ONME-AP03GF445 | Insulation for Hot water line & Hot water return - AP#03 (GF - Corridor) | 69 | 2025-02-27 | 2025-05-22
DRAINAGE |  | 83 | 2025-02-08 | 2025-05-20
R7S1ONME-AP03GF410 | Drainage Riser continuation in Shafts - AP#03 (GF - Corridor) | 25 | 2025-03-08 | 2025-04-09
R7S1ONME-AP03GF408 | Installation of Clean-outs, Floor drain in balcony - AP#03 (GF - Corridor) | 56 | 2025-02-08 | 2025-04-19
R7S1ONME-AP03GF409 | Rain Water Riser continuation in Shafts - AP#03 (GF - Corridor) | 13 | 2025-04-13 | 2025-04-28
R7S1ONME-AP03GF411 | Testing for Rain Water Riser - AP#03 (GF - Corridor) | 2 | 2025-05-19 | 2025-05-20
R7S1ONME-AP03GF412 | Testing for Drainage Riser1 - AP#03 (GF - Corridor) | 2 | 2025-05-19 | 2025-05-20
ELECTRICAL |  | 129 | 2025-02-08 | 2025-07-10
POWER & LIGHTING |  | 129 | 2025-02-08 | 2025-07-10
R7S1ONME-AP03GF413 | Contiuation of Cable Trays & apartment branches - AP#03 (GF - Corridor) | 30 | 2025-02-08 | 2025-03-15
R7S1ONME-AP03GF414 | Contiuation of Cable Trunking with Flexible conduits for Lights - AP#03 (GF - Corridor) | 30 | 2025-02-08 | 2025-03-15
R7S1ONME-AP03GF415 | Installation of EMT pipes - AP#03 (GF - Corridor) | 34 | 2025-02-08 | 2025-03-19
R7S1ONME-AP03GF416 | Installation of Busbar, Electrical Meter & Tap-off - AP#03 (GF - Corridor) | 12 | 2025-04-24 | 2025-05-07
R7S1ONME-AP03GF986 | Continuation of Cable Tray/Trunking with Flexible conduits for Lights (In Front of Lift Shaft) - AP#03 | 4 | 2025-05-04 | 2025-05-07
R7S1ONME-AP03GF417 | Corridor Wire Pulling - AP#03 (GF - Corridor) | 48 | 2025-03-10 | 2025-05-08
R7S1ONME-AP03GF439 | Termination of Tap-off with Electrical Meter in the apartments - AP#03 (GF - Corridor) | 3 | 2025-05-08 | 2025-05-11
R7S1ONME-AP03GF418 | Electrical Room - Installation of Cable trays, SMDB & Termination - AP#03 (GF - Corridor) | 62 | 2025-03-13 | 2025-05-29
R7S1ONME-AP03GF420 | Installation, Termination of Emergeny & Exit Lights with contiuity - AP#03 (GF - Corridor) | 2 | 2025-07-06 | 2025-07-07
R7S1ONME-AP03GF419 | Installation, Termination of Light Fixtures with continuity test - AP#03 (GF - Corridor & Balconies) | 3 | 2025-07-06 | 2025-07-08
R7S1ONME-AP03GF421 | Installation, Termination of PIR sensors with continuity test - AP#03 (GF - Corridor) | 2 | 2025-07-09 | 2025-07-10
LOW CURRENT SYSTEM |  | 118 | 2025-02-08 | 2025-07-09
R7S1ONME-AP03GF422 | Installation of Basket trays for BMS, CCTV, Access Control - AP#03 (GF - Corridor) | 30 | 2025-02-08 | 2025-03-15
R7S1ONME-AP03GF423 | Voice Evacuation cable installation - AP#03 (GF - Corridor) | 27 | 2025-02-11 | 2025-03-16
R7S1ONME-AP03GF424 | Fire alarm cable installation - AP#03 (GF - Corridor) | 29 | 2025-02-09 | 2025-03-16
R7S1ONME-AP03GF446 | CBS System cable installation - AP#03 (GF - Corridor) | 31 | 2025-02-08 | 2025-03-16
R7S1ONME-AP03GF426 | BMS, CCTV & Access control Cable installation - AP#03 (GF - Corridor) | 37 | 2025-03-26 | 2025-05-12
R7S1ONME-AP03GF1166 | Installation of Basket trays for Low Current, Cable Installation (In Front of Lift Shaft) - AP#03 | 4 | 2025-05-08 | 2025-05-12
R7S1ONME-AP03GF427 | Low Current Works including BMS Panel in ICT Room - AP#03 (GF - Corridor) | 73 | 2025-02-16 | 2025-05-17
R7S1ONME-AP03GF435 | Installation & Termination of Access control system for Electrical Room - AP#03 (GF) | 2 | 2025-05-17 | 2025-05-18
R7S1ONME-AP03GF425 | Fibre optic Cable pulling & Termination with OTO (in corridors to ONU) - AP#03 (GF - Corridor) | 2 | 2025-05-18 | 2025-05-19
R7S1ONME-AP03GF438 | Fluke test for CCTV & Fibre Optic Cable - AP#03 (GF - Corridor) (Ceiling 1st Fix) | 2 | 2025-05-20 | 2025-05-21
R7S1ONME-AP03GF428 | Installation & Termination of Fire alarm devices & Speakers - AP#03 (GF - Corridor) | 4 | 2025-07-01 | 2025-07-05
R7S1ONME-AP03GF434 | Installation & Termination of CCTV Cameras - AP#03 (GF - Corridor) | 2 | 2025-07-06 | 2025-07-07
R7S1ONME-AP03GF437 | Installation & Termination of Wireless Gateway & RF Node in corridors - AP#03 (GF - Corridor) | 2 | 2025-07-06 | 2025-07-07
R7S1ONME-AP03GF436 | Installation & Termination of Active Components & UPS installation in ICT Room - AP#03 (GF - Corridor) | 2 | 2025-07-08 | 2025-07-09
FIRST FLOOR |  | 167 | 2025-03-16 | 2025-08-24
ARCH./ CIVIL WORKS |  | 159 | 2025-03-25 | 2025-08-24
CORRIDOR AREA |  | 104 | 2025-04-12 | 2025-08-24
R7S1ONAR-AP03FF120 | Flooring in Corridor - AP#03 (FF - Corridor) | 15 | 2025-04-12 | 2025-04-28
R7S1ONAR-AP03FF121 | Corridor Skirting - AP#03 (FF - Corridor) | 2 | 2025-04-27 | 2025-04-29
R7S1ONAR-AP03FF118 | False Ceiling - 1st Fix - AP#03 (FF - Corridor) | 4 | 2025-04-29 | 2025-05-04
R7S1ONAR-AP03FF119 | Gypsum Wall Cladding (Shafts) - AP#03 (FF - Corridor) | 6 | 2025-07-01 | 2025-07-07
R7S1ONAR-AP03FF122 | Gypsum Wall Cladding (Shafts) -2nd Fix - AP#03 (FF Corridor) | 4 | 2025-07-08 | 2025-07-12
R7S1ONAR-AP03FF126 | Fixing Architrave - AP#03 (FF Corridor) | 2 | 2025-07-13 | 2025-07-14
R7S1ONAR-AP03FF127 | Fixing Aluminium Doors - AP#03 (FF Corridor) | 2 | 2025-07-15 | 2025-07-16
R7S1ONAR-AP03FF123 | False Ceiling - 2nd Fix (Closing the Ceiling) - AP#03 (FF Corridor) | 2 | 2025-07-17 | 2025-07-19
R7S1ONAR-AP03FF124 | Painting - Surface Prep., Primer & 1st Coat for Walls - AP#03 (FF Corridor) | 6 | 2025-07-13 | 2025-07-19
R7S1ONAR-AP03FF159 | Painting - Surface Prep., Primer & 1st Coat for Ceiling - AP#03 (FF Corridor) | 4 | 2025-07-20 | 2025-07-23
R7S1ONAR-AP03FF125 | Painting - Final Coat (Ceiling + Walls) - AP#03 (FF Corridor) | 3 | 2025-08-21 | 2025-08-24
INSIDE BOXES |  | 12 | 2025-04-30 | 2025-05-13
R7S1ONAR-AP03FF128 | Fixing Thresholds (Joining the Room) - AP#03 (FF - inside Boxes) | 4 | 2025-04-30 | 2025-05-04
R7S1ONAR-AP03FF129 | Fixing Wooden Doors - AP#03 (FF - inside Boxes) | 4 | 2025-05-05 | 2025-05-08
R7S1ONAR-AP03FF130 | Fixing Aluminium Doors (Next Floor) - AP#03 (FF - inside Boxes) | 4 | 2025-05-10 | 2025-05-13
IN FRONT OF LIFT SHAFT |  | 159 | 2025-03-25 | 2025-08-13
R7S1ONAR-AP03FF132 | Flooring - AP#03 (FF - Front of Lift Shaft) | 4 | 2025-07-20 | 2025-07-23
R7S1ONAR-AP03FF133 | Skirting & Thresholds - AP#03 (FF - Front of Lift Shaft) | 1 | 2025-07-23 | 2025-07-23
R7S1ONAR-AP03FF131 | False Ceiling - 1st Fix - AP#03 (FF - Front of Lift Shaft) | 99 | 2025-03-25 | 2025-07-28
R7S1ONAR-AP03FF134 | Painting - Surface Prep., Primer & 1st Coat - AP#03 (FF - Front of Lift Shaft) | 4 | 2025-07-24 | 2025-07-28
R7S1ONAR-AP03FF135 | False Ceiling - Final Fix - AP#03 (FF - Front of Lift Shaft) | 3 | 2025-07-29 | 2025-07-31
R7S1ONAR-AP03FF137 | Fixing Handrail - AP#03 (FF - Front of Lift Shaft) | 3 | 2025-08-02 | 2025-08-04
R7S1ONAR-AP03FF138 | Paint for Handrail - AP#03 (FF - Front of Lift Shaft) | 3 | 2025-08-05 | 2025-08-07
R7S1ONAR-AP03FF136 | Painting - 2nd Coat - AP#03 (FF - Front of Lift Shaft) | 3 | 2025-08-09 | 2025-08-11
R7S1ONAR-AP03FF139 | Fixing Floor Mat - AP#03 (FF - Front of Lift Shaft) | 2 | 2025-08-12 | 2025-08-13
R7S1ONAR-AP03FF140 | Fixing Wall Guard - AP#03 (FF - Front of Lift Shaft) | 2 | 2025-08-12 | 2025-08-13
GARBAGE ROOM |  | 10 | 2025-07-06 | 2025-07-16
R7S1ONAR-AP03FF141 | Installation of Dry Walls - First Fix - AP#03 (FF - Garbage Room) | 2 | 2025-07-06 | 2025-07-07
R7S1ONAR-AP03FF142 | Installation of Dry Walls - Final Fix - AP#03 (FF - Garbage Room) | 2 | 2025-07-07 | 2025-07-08
R7S1ONAR-AP03FF143 | Garbage Rooms - Wall Tile Finishes (One Side) - AP#03 (FF - Garbage Room) | 2 | 2025-07-08 | 2025-07-09
R7S1ONAR-AP03FF144 | Paint Works of Dry Walls - First Coat - AP#03 (FF - Garbage Room) | 2 | 2025-07-10 | 2025-07-12
R7S1ONAR-AP03FF145 | Installation of the Garbage Chute Door - AP#03 (FF - Garbage Room) | 2 | 2025-07-13 | 2025-07-14
R7S1ONAR-AP03FF146 | Paint Finishes and Touchups - Final Coat - AP#03 (FF - Garbage Room) | 2 | 2025-07-15 | 2025-07-16
BALCONIES |  | 128 | 2025-03-26 | 2025-08-20
R7S1ONAR-AP03FF147 | Wetarea Waterproofing - AP#03 (FF - Balconies) | 26 | 2025-03-26 | 2025-04-30
R7S1ONAR-AP03FF148 | Flooring - AP#03 (FF - Balconies) | 6 | 2025-04-26 | 2025-05-03
R7S1ONAR-AP03FF149 | Painting - Surface Prep., Primer & 1st Coat - AP#03 (FF - Balconies) | 8 | 2025-04-28 | 2025-05-07
R7S1ONAR-AP03FF151 | Fixing Handrail - AP#03 (FF - Balconies) | 6 | 2025-08-05 | 2025-08-11
R7S1ONAR-AP03FF152 | Paint for Handrail - AP#03 (FF - Balconies) | 4 | 2025-08-12 | 2025-08-16
R7S1ONAR-AP03FF150 | Painting - 2nd Coat - AP#03 (FF - Balconies) | 4 | 2025-08-17 | 2025-08-20
MEP WORKS |  | 103 | 2025-03-16 | 2025-07-24
MECHANICAL |  | 102 | 2025-03-16 | 2025-07-22
CHILLED WATER |  | 56 | 2025-03-16 | 2025-05-19
R7S1ONME-AP03FF126 | Installation of Chilled water hanger and supports - AP#03 (FF Corridor) | 25 | 2025-03-16 | 2025-04-19
R7S1ONME-AP03FF127 | Installation of CHWP piping (connection between modular cages & modular to apartment) - AP#03 -(FF Corridor) | 22 | 2025-03-20 | 2025-04-20
R7S1ONME-AP03FF128 | Installation of BTU Meter with valves - AP#03 (FF Corridor) | 2 | 2025-04-26 | 2025-04-27
R7S1ONME-AP03FF129 | CHWP piping risers connections - AP#03 (FF Corridor) | 14 | 2025-04-12 | 2025-04-27
R7S1ONME-AP03FF176 | Installation of CHWP connection for FCU with Valve package in Corridor, Electrical Room & ICT Room | 17 | 2025-04-09 | 2025-04-28
R7S1ONME-AP03FF130 | Pressure Testing of CHWP piping - AP#03 (FF Corridor) | 1 | 2025-04-28 | 2025-04-29
R7S1ONME-AP03FF466 | CHWP Installation/Connections and Insulation (In Front of Lift Shaft) - AP#03 | 4 | 2025-04-30 | 2025-05-04
R7S1ONME-AP03FF165 | CHWP Insulation - AP#03 (FF Corridor) | 4 | 2025-05-14 | 2025-05-19
HVAC DUCTING |  | 75 | 2025-03-24 | 2025-07-21
R7S1ONME-AP03FF131 | Duct Riser Continuation - AP#03 (FF Corridor) | 7 | 2025-04-19 | 2025-04-27
R7S1ONME-AP03FF132 | A/C drain & Copper pipe connection in ELV room - AP#03 (FF Corridor) | 2 | 2025-04-27 | 2025-04-29
R7S1ONME-AP03FF166 | Installation of Duct & Grill in Garbage Room - AP#03 (FF Corridor) | 5 | 2025-04-23 | 2025-04-29
R7S1ONME-AP03FF177 | Installation of FCU's & Duct Connection in Corridor, Electrical Room & ICT Room - AP#03 (FF Corridor) | 19 | 2025-04-09 | 2025-04-30
R7S1ONME-AP03FF178 | Installation of Ducting and insulation (connection between modular cages) - AP#03 (FF Corridor) | 29 | 2025-03-24 | 2025-04-30
R7S1ONME-AP03FF179 | Installation of Grilles in the Corridor - AP#03 (FF Corridor) | 2 | 2025-07-20 | 2025-07-21
FIRE FIGHTING |  | 84 | 2025-04-12 | 2025-07-22
R7S1ONME-AP03FF133 | Riser Continuity in corridor - AP#03 (FF Corridor) | 5 | 2025-04-12 | 2025-04-16
R7S1ONME-AP03FF134 | Continuation of FF pipes & ZC Valves (connection between modular cages & modular to apartment) - AP#03 (FF Corridor) | 4 | 2025-04-26 | 2025-04-29
R7S1ONME-AP03FF806 | Installation of F.F Pipes, Testing & Final Fixtures (In Front of Lift Shaft) - AP#03 | 3 | 2025-05-05 | 2025-05-07
R7S1ONME-AP03FF135 | Installation of Sprinklers drops in corridor - AP#03 (FF Corridor) | 4 | 2025-05-04 | 2025-05-08
R7S1ONME-AP03FF136 | Pressure Test for FF Piping in corridor - AP#03 (FF Corridor) | 2 | 2025-05-06 | 2025-05-08
R7S1ONME-AP03FF180 | FF Flushing network - AP#03 (FF Corridor) | 1 | 2025-05-18 | 2025-05-19
R7S1ONME-AP03FF167 | Installation of Pipe & sprinkler in Garbage Room - AP#03 (FF Corridor) | 59 | 2025-04-19 | 2025-06-30
R7S1ONME-AP03FF137 | Installation of Sprinklers in corridor - AP#03 (FF Corridor) | 3 | 2025-07-20 | 2025-07-22
R7S1ONME-AP03FF138 | Installation of Alarm check valve, Fire Extinguishers & Blanket (Last Stage of the Building) - AP#03 (FF Corridor) | 3 | 2025-07-20 | 2025-07-22
WATER SUPPLY |  | 54 | 2025-03-16 | 2025-05-22
R7S1ONME-AP03FF168 | Installation of WS Pipe in Garbage Room - AP#03 (FF Corridor) | 26 | 2025-03-16 | 2025-04-20
R7S1ONME-AP03FF169 | Installation of Sanitary Fixtures in Janitor Room - AP#03 (FF Corridor) | 26 | 2025-03-16 | 2025-04-20
R7S1ONME-AP03FF139 | Riser Continuity in Shafts - AP#03 (FF Corridor) | 4 | 2025-04-19 | 2025-04-22
R7S1ONME-AP03FF140 | WS High Level Pipe continuation & Insulation works in Corridor - AP#03 (FF Corridor) | 17 | 2025-04-06 | 2025-04-24
R7S1ONME-AP03FF141 | Installation of Cold, Hot water line & Hot water return in corridor - AP#03 (FF Corridor) | 17 | 2025-04-06 | 2025-04-24
R7S1ONME-AP03FF142 | Water Meter Installation in Corridor - AP#03 (FF Corridor) | 4 | 2025-04-26 | 2025-04-29
R7S1ONME-AP03FF143 | Pressure Test for WS - AP#03 (FF Corridor) | 2 | 2025-05-19 | 2025-05-20
R7S1ONME-AP03FF181 | Insulation for Hot water line & Hot water return in corridor - AP#03 (FF Corridor) | 28 | 2025-04-21 | 2025-05-22
DRAINAGE |  | 54 | 2025-03-16 | 2025-05-22
R7S1ONME-AP03FF144 | Installation of Clean-outs, Floor drain in balcony - AP#03 (FF Corridor) | 28 | 2025-03-16 | 2025-04-22
R7S1ONME-AP03FF145 | Rain Water Riser continuation in Shafts - AP#03 (FF Corridor) | 7 | 2025-04-19 | 2025-04-27
R7S1ONME-AP03FF146 | Drainage Riser continuation in Shafts - AP#03 (FF Corridor) | 7 | 2025-04-19 | 2025-04-27
R7S1ONME-AP03FF147 | Testing for Rain Water Riser - AP#03 (FF Corridor) | 4 | 2025-05-19 | 2025-05-22
R7S1ONME-AP03FF148 | Testing for Drainage Riser - AP#03 (FF Corridor) | 4 | 2025-05-19 | 2025-05-22
ELECTRICAL |  | 103 | 2025-03-16 | 2025-07-24
POWER & LIGHTING |  | 100 | 2025-03-16 | 2025-07-24
R7S1ONME-AP03FF151 | Installation of EMT pipes - AP#03 (FF Corridor) | 4 | 2025-03-19 | 2025-03-24
R7S1ONME-AP03FF149 | Contiuation of Cable Trays & apartment branches - AP#03 (FF Corridor) | 9 | 2025-03-16 | 2025-03-26
R7S1ONME-AP03FF150 | Contiuation of Cable Trunking with Flexible conduits for Lights - AP#03 (FF Corridor) | 9 | 2025-03-16 | 2025-03-26
R7S1ONME-AP03FF153 | Corridor Wire Pulling - AP#03 (FF Corridor) | 3 | 2025-03-25 | 2025-03-27
R7S1ONME-AP03FF996 | Continuation of Cable Tray/Trunking with Flexible conduits for Lights (In Front of Lift Shaft) - AP#03 | 4 | 2025-05-13 | 2025-05-17
R7S1ONME-AP03FF152 | Installation of Busbar, Electrical Meter & Tap-off - AP#03 (FF Corridor) | 35 | 2025-04-24 | 2025-06-04
R7S1ONME-AP03FF154 | Electrical Room - Installation of Cable trays, SMDB & Termination - AP#03 (FF Corridor) | 38 | 2025-04-21 | 2025-06-04
R7S1ONME-AP03FF175 | Termination of Tap-off with Electrical Meter in the apartments - AP#03 (FF Corridor) | 3 | 2025-06-04 | 2025-06-12
R7S1ONME-AP03FF156 | Installation, Termination of Emergeny & Exit Lights with contiuity - AP#03 (FF Corridor) | 2 | 2025-07-20 | 2025-07-21
R7S1ONME-AP03FF155 | Installation, Termination of Light Fixtures with continuity test - AP#03 (FF - Corridor & Balconies) | 3 | 2025-07-20 | 2025-07-22
R7S1ONME-AP03FF157 | Installation, Termination of PIR sensors with continuity test - AP#03 (FF Corridor) | 2 | 2025-07-23 | 2025-07-24
LOW CURRENT SYSTEM |  | 103 | 2025-03-16 | 2025-07-23
R7S1ONME-AP03FF158 | Installation of Basket trays for BMS, CCTV, Access Control - AP#03 (FF Corridor) | 9 | 2025-03-16 | 2025-03-26
R7S1ONME-AP03FF182 | CBS System cable installation - AP#03 (FF Corridor) | 10 | 2025-03-16 | 2025-03-27
R7S1ONME-AP03FF159 | Voice Evacuation cable installation - AP#03 (FF Corridor) | 15 | 2025-03-19 | 2025-04-10
R7S1ONME-AP03FF160 | Fire alarm cable installation - AP#03 (FF Corridor) | 17 | 2025-03-17 | 2025-04-10
R7S1ONME-AP03FF162 | BMS, CCTV & Access control Cable installation - AP#03 (FF Corridor) | 36 | 2025-04-10 | 2025-05-21
R7S1ONME-AP03FF1176 | Installation of Basket trays for Low Current, Cable Installation (In Front of Lift Shaft) - AP#03 | 4 | 2025-05-18 | 2025-05-21
R7S1ONME-AP03FF163 | Low Current Works including BMS Panel in ICT Room - AP#03 (FF Corridor) | 10 | 2025-05-13 | 2025-05-24
R7S1ONME-AP03FF161 | Fibre optic Cable pulling & Termination with OTO (in corridors to ONU) - AP#03 (FF Corridor) | 2 | 2025-05-25 | 2025-05-26
R7S1ONME-AP03FF174 | Fluke test for CCTV & Fibre Optic Cable - AP#03 (FF Corridor) | 2 | 2025-05-25 | 2025-05-26
R7S1ONME-AP03FF170 | Installation & Termination of CCTV Cameras - AP#03 (FF Corridor) | 2 | 2025-07-20 | 2025-07-21
R7S1ONME-AP03FF171 | Installation & Termination of Access control system for Electrical Room - AP#03 (FF Corridor) | 2 | 2025-07-20 | 2025-07-21
R7S1ONME-AP03FF173 | Installation & Termination of Wireless Gateway & RF Node - AP#03 (FF Corridor) | 2 | 2025-07-20 | 2025-07-21
R7S1ONME-AP03FF164 | Installation & Termination of Fire alarm devices & Speakers - AP#03 (FF Corridor) | 4 | 2025-07-20 | 2025-07-23
R7S1ONME-AP03FF172 | Installation & Termination of Active Components & UPS installation in ICT Room | 2 | 2025-07-22 | 2025-07-23
SECOND FLOOR |  | 122 | 2025-04-28 | 2025-09-30
ARCH./ CIVIL WORKS |  | 122 | 2025-04-28 | 2025-09-30
CORRIDOR AREA |  | 101 | 2025-04-28 | 2025-09-30
R7S1ONAR-AP03SF74 | Flooring in Corridor - AP#03 (SF Corridor) | 6 | 2025-04-28 | 2025-05-05
R7S1ONAR-AP03SF75 | Corridor Skirting - AP#03 (SF Corridor) | 2 | 2025-05-04 | 2025-05-06
R7S1ONAR-AP03SF72 | False Ceiling - 1st Fix - AP#03 (SF Corridor) | 4 | 2025-05-06 | 2025-05-11
R7S1ONAR-AP03SF73 | Gypsum Wall Cladding (Shafts) - AP#03 (SF Corridor) | 6 | 2025-08-07 | 2025-08-14
R7S1ONAR-AP03SF76 | Gypsum Wall Cladding (Shafts) -2nd Fix - AP#03 (SF Corridor) | 4 | 2025-08-14 | 2025-08-19
R7S1ONAR-AP03SF80 | Fixing Architrave - AP#03 (SF Corridor) | 2 | 2025-08-19 | 2025-08-21
R7S1ONAR-AP03SF81 | Fixing Aluminium Doors - AP#03 (SF Corridor) | 2 | 2025-08-21 | 2025-08-24
R7S1ONAR-AP03SF77 | False Ceiling - 2nd Fix (Closing the Ceiling) - AP#03 (SF Corridor) | 3 | 2025-08-24 | 2025-08-27
R7S1ONAR-AP03SF78 | Painting - Surface Prep., Primer & 1st Coat - AP#03 (SF Corridor) | 8 | 2025-08-19 | 2025-08-28
R7S1ONAR-AP03SF102 | Painting - Surface Prep., Primer & 1st Coat - AP#03 (SF Corridor) | 4 | 2025-08-27 | 2025-09-01
R7S1ONAR-AP03SF79 | Painting - Final Coat (Ceiling + Walls) - AP#03 (SF Corridor) | 4 | 2025-09-25 | 2025-09-30
INSIDE BOXES |  | 12 | 2025-05-05 | 2025-05-19
R7S1ONAR-AP03SF82 | Fixing Thresholds (Joining the Room) - AP#03 (SF - inside Boxes) | 4 | 2025-05-05 | 2025-05-10
R7S1ONAR-AP03SF83 | Fixing Wooden Doors - AP#03 (SF - inside Boxes) | 4 | 2025-05-10 | 2025-05-14
R7S1ONAR-AP03SF84 | Fixing Aluminium Doors (Next Floor) - AP#03 (SF - inside Boxes) | 4 | 2025-05-14 | 2025-05-19
IN FRONT OF LIFT SHAFT |  | 62 | 2025-08-28 | 2025-09-30
R7S1ONAR-AP03SF85 | False Ceiling - 1st Fix - AP#03 (SF - Front of Lift Shaft) | 4 | 2025-08-28 | 2025-09-02
R7S1ONAR-AP03SF86 | Flooring - AP#03 (SF - Front of Lift Shaft) | 4 | 2025-09-02 | 2025-09-07
R7S1ONAR-AP03SF87 | Skirting & Thresholds - AP#03 (SF - Front of Lift Shaft) | 2 | 2025-09-07 | 2025-09-09
R7S1ONAR-AP03SF88 | Painting - Surface Prep., Primer & 1st Coat - AP#03 (SF - Front of Lift Shaft) | 4 | 2025-09-09 | 2025-09-14
R7S1ONAR-AP03SF89 | False Ceiling - Final Fix - AP#03 (SF - Front of Lift Shaft) | 3 | 2025-09-14 | 2025-09-17
R7S1ONAR-AP03SF91 | Fixing Handrail - AP#03 (SF - Front of Lift Shaft) | 3 | 2025-09-17 | 2025-09-21
R7S1ONAR-AP03SF92 | Paint for Handrail - AP#03 (SF - Front of Lift Shaft) | 3 | 2025-09-21 | 2025-09-25
R7S1ONAR-AP03SF90 | Painting - 2nd Coat - AP#03 (SF - Front of Lift Shaft) | 3 | 2025-09-25 | 2025-09-29
R7S1ONAR-AP03SF93 | Fixing Floor Mat - AP#03 (SF - Front of Lift Shaft) | 2 | 2025-09-28 | 2025-09-30
R7S1ONAR-AP03SF94 | Fixing Wall Guard - AP#03 (SF - Front of Lift Shaft) | 2 | 2025-09-28 | 2025-09-30
GARBAGE ROOM |  | 45 | 2025-06-19 | 2025-09-02
R7S1ONAR-AP03SF101 | Installation of Garbage Chute Full System from GF to 2nd Floor - AP#03 (SF - Garbage Room) | 10 | 2025-06-19 | 2025-06-30
R7S1ONAR-AP03SF95 | Installation of Dry Walls - First Fix - AP#03 (SF - Garbage Room) | 2 | 2025-07-01 | 2025-07-02
R7S1ONAR-AP03SF96 | Installation of Dry Walls - Final Fix - AP#03 (SF - Garbage Room) | 2 | 2025-07-03 | 2025-07-05
R7S1ONAR-AP03SF97 | Garbage Rooms - Wall Tile Finishes (One Side) - AP#03 (SF - Garbage Room) | 2 | 2025-07-05 | 2025-07-06
R7S1ONAR-AP03SF98 | Paint Works of Dry Walls - First Coat - AP#03 (SF - Garbage Room) | 2 | 2025-07-07 | 2025-07-08
R7S1ONAR-AP03SF99 | Installation of the Garbage Chute Door - AP#03 (SF - Garbage Room) | 2 | 2025-07-09 | 2025-07-10
R7S1ONAR-AP03SF100 | Paint Finishes and Touchups - Final Coat - AP#03 (SF - Garbage Room) | 2 | 2025-08-31 | 2025-09-02
BALCONIES |  | 95 | 2025-05-05 | 2025-09-25
R7S1ONAR-AP03FF153 | Wetarea Waterproofing - AP#03 (SF - Balconies) | 8 | 2025-05-05 | 2025-05-14
R7S1ONAR-AP03FF154 | Flooring - AP#03 (SF - Balconies) | 6 | 2025-05-10 | 2025-05-17
R7S1ONAR-AP03FF155 | Painting - Surface Prep., Primer & 1st Coat - AP#03 (SF - Balconies) | 8 | 2025-05-12 | 2025-05-21
R7S1ONAR-AP03FF157 | Fixing Handrail - AP#03 (SF - Balconies) | 6 | 2025-09-14 | 2025-09-21
R7S1ONAR-AP03FF158 | Paint for Handrail - AP#03 (SF - Balconies) | 4 | 2025-09-16 | 2025-09-21
R7S1ONAR-AP03FF156 | Painting - 2nd Coat - AP#03 (SF - Balconies) | 4 | 2025-09-20 | 2025-09-25
MEP WORKS |  | 98 | 2025-05-05 | 2025-09-02
MECHANICAL |  | 97 | 2025-05-05 | 2025-09-01
CHILLED WATER |  | 22 | 2025-05-05 | 2025-05-21
R7S1ONME-AP03SF111 | Installation of Chilled water hanger and supports - AP#03 (SF Corridor) | 4 | 2025-05-05 | 2025-05-08
R7S1ONME-AP03SF161 | Installation of CHWP connection for FCU with Valve package in Corridor, Electrical Room & ICT Room | 4 | 2025-05-05 | 2025-05-08
R7S1ONME-AP03SF476 | CHWP Installation/Connections and Insulation (In Front of Lift Shaft) - AP#03 | 4 | 2025-05-05 | 2025-05-08
R7S1ONME-AP03SF113 | Installation of BTU Meter with valves - AP#03 (SF Corridor) | 2 | 2025-05-11 | 2025-05-12
R7S1ONME-AP03SF112 | Installation of CHWP piping (connection between modular cages & modular to apartment) - AP#03 (SF Corridor) | 4 | 2025-05-10 | 2025-05-13
R7S1ONME-AP03SF114 | CHWP piping risers connections - AP#03 (SF Corridor) | 3 | 2025-05-13 | 2025-05-15
R7S1ONME-AP03SF115 | Pressure Testing of CHWP piping - AP#03 (SF Corridor) | 1 | 2025-05-17 | 2025-05-17
R7S1ONME-AP03SF150 | CHWP Insulation - AP#03 (SF Corridor) | 4 | 2025-05-18 | 2025-05-21
HVAC DUCTING |  | 96 | 2025-05-05 | 2025-08-30
R7S1ONME-AP03SF116 | Duct Riser Continuation - AP#03 (SF Corridor) | 4 | 2025-05-05 | 2025-05-08
R7S1ONME-AP03SF162 | Installation of FCU's & Duct Connection in Corridor, Electrical Room & ICT Room - AP#03 (SF Corridor) | 4 | 2025-05-05 | 2025-05-08
R7S1ONME-AP03SF117 | A/C drain & Copper pipe connection in ELV room - AP#03 (SF Corridor) | 2 | 2025-05-10 | 2025-05-11
R7S1ONME-AP03SF163 | Installation of Ducting and insulation (connection between modular cages) - AP#03 (SF Corridor) | 3 | 2025-05-10 | 2025-05-12
R7S1ONME-AP03SF151 | Installation of Duct & Grill in Garbage Room - AP#03 (SF Corridor) | 2 | 2025-08-27 | 2025-08-30
R7S1ONME-AP03SF164 | Installation of Grilles in the Corridor - AP#03 (SF Corridor) | 2 | 2025-08-27 | 2025-08-30
FIRE FIGHTING |  | 97 | 2025-05-05 | 2025-09-01
R7S1ONME-AP03SF118 | Riser Continuity Succ - Closing of Gysum Boards on shaft - AP#03 (SF Corridor) | 4 | 2025-05-05 | 2025-05-08
R7S1ONME-AP03SF119 | FF Contiuation on High Level with Valves - AP#03 (SF Corridor) | 4 | 2025-05-05 | 2025-05-08
R7S1ONME-AP03SF816 | Installation of F.F Pipes, Testing & Final Fixtures (In Front of Lift Shaft) - AP#03 | 3 | 2025-05-10 | 2025-05-12
R7S1ONME-AP03SF120 | Installation of Sprinklers drops - AP#03 (SF Corridor) | 4 | 2025-05-11 | 2025-05-15
R7S1ONME-AP03SF121 | Pressure Test for FF Piping - AP#03 (SF Corridor) | 2 | 2025-05-15 | 2025-05-18
R7S1ONME-AP03SF123 | Installation of Fire Extinguishers - AP#03 (SF Corridor) | 3 | 2025-08-27 | 2025-08-31
R7S1ONME-AP03SF152 | Installation of Pipe & sprinkler in Garbage Room - AP#03 (SF Corridor) | 3 | 2025-08-27 | 2025-08-31
R7S1ONME-AP03SF122 | Installation of Sprinklers - AP#03 (SF Corridor) | 4 | 2025-08-27 | 2025-09-01
WATER SUPPLY |  | 22 | 2025-05-05 | 2025-05-29
R7S1ONME-AP03SF153 | Installation of WS Pipe in Garbage Room - AP#03 (SF Corridor) | 2 | 2025-05-05 | 2025-05-06
R7S1ONME-AP03SF154 | Installation of Sanitary Fixtures in Janitor Room - AP#03 (SF Corridor) | 2 | 2025-05-05 | 2025-05-06
R7S1ONME-AP03SF124 | Riser Continuity - AP#03 (SF Corridor) | 4 | 2025-05-05 | 2025-05-08
R7S1ONME-AP03SF125 | WS High Level Pipe continuation & Insulation works - AP#03 (SF Corridor) | 4 | 2025-05-05 | 2025-05-08
R7S1ONME-AP03SF126 | Instalation of Hot water line in corridor - AP#03 (SF Corridor) | 4 | 2025-05-10 | 2025-05-13
R7S1ONME-AP03SF127 | Water Meter Installation - AP#03 (SF Corridor) | 4 | 2025-05-14 | 2025-05-18
R7S1ONME-AP03SF128 | Pressure Test for WS - AP#03 (SF Corridor) | 4 | 2025-05-21 | 2025-05-25
R7S1ONME-AP03FF183 | Insulation for Hot water line & Hot water return in corridor - AP#03 (SF Corridor) | 4 | 2025-05-26 | 2025-05-29
DRAINAGE |  | 16 | 2025-05-05 | 2025-05-22
R7S1ONME-AP03SF129 | Installation of Clean-outs - AP#03 (SF Corridor) | 4 | 2025-05-05 | 2025-05-08
R7S1ONME-AP03SF130 | Rain Water Riser continuation - AP#03 (SF Corridor) | 4 | 2025-05-05 | 2025-05-08
R7S1ONME-AP03SF131 | Drainage Riser continuation - AP#03 (SF Corridor) | 4 | 2025-05-05 | 2025-05-08
R7S1ONME-AP03SF132 | Testing for Rain Water Riser - AP#03 (SF Corridor) | 4 | 2025-05-19 | 2025-05-22
R7S1ONME-AP03SF133 | Testing for Drainage Riser - AP#03 (SF Corridor) | 4 | 2025-05-19 | 2025-05-22
ELECTRICAL |  | 98 | 2025-05-05 | 2025-09-02
POWER & LIGHTING |  | 97 | 2025-05-05 | 2025-09-02
R7S1ONME-AP03SF134 | Contiuation of Cable Trays & apartment branches - AP#03 (SF Corridor) | 4 | 2025-05-05 | 2025-05-08
R7S1ONME-AP03SF135 | Contiuation of Cable Trunking with Flexible conduits for Lights - AP#03 (SF Corridor) | 4 | 2025-05-05 | 2025-05-08
R7S1ONME-AP03SF137 | Installation of Busbar, Electrical Meter & Tap-off in Corridor - AP#03 (SF Corridor) | 3 | 2025-05-06 | 2025-05-08
R7S1ONME-AP03SF136 | Installation of EMT pipes - AP#03 (SF Corridor) | 5 | 2025-05-05 | 2025-05-10
R7S1ONME-AP03SF160 | Termination of Tap-off with Electrical Meter in the apartments - AP#03 (SF Corridor) | 3 | 2025-05-10 | 2025-05-12
R7S1ONME-AP03SF1006 | Continuation of Cable Tray/Trunking with Flexible conduits for Lights (In Front of Lift Shaft) - AP#03 | 4 | 2025-05-08 | 2025-05-12
R7S1ONME-AP03SF138 | Corridor Wire Pulling - AP#03 (SF Corridor) | 6 | 2025-05-11 | 2025-05-17
R7S1ONME-AP03SF139 | Electrical Room - Installation of Cable trays, SMDB & Termination - AP#03 (SF Corridor) | 6 | 2025-07-01 | 2025-07-07
R7S1ONME-AP03SF141 | Installation, Termination of Emergeny & Exit Lights with contiuity - AP#03 (SF Corridor) | 2 | 2025-08-27 | 2025-08-30
R7S1ONME-AP03SF140 | Installation, Termination of Light Fixtures with continuity test - AP#03 (SF - Corridor & Balconies) | 3 | 2025-08-27 | 2025-08-31
R7S1ONME-AP03SF142 | Installation, Termination of PIR sensors with continuity test - AP#03 (SF Corridor) | 2 | 2025-08-31 | 2025-09-02
LOW CURRENT SYSTEM |  | 98 | 2025-05-05 | 2025-09-01
R7S1ONME-AP03SF165 | CBS System cable installation - AP#03 (SF Corridor) | 3 | 2025-05-05 | 2025-05-07
R7S1ONME-AP03SF143 | Installation of Basket trays for BMS, CCTV, Access Control - AP#03 (SF Corridor) | 4 | 2025-05-05 | 2025-05-08
R7S1ONME-AP03SF145 | Fire alarm cable installation - AP#03 (SF Corridor) | 3 | 2025-05-06 | 2025-05-08
R7S1ONME-AP03SF144 | Voice Evacuation cable installation - AP#03 (SF Corridor) | 3 | 2025-05-08 | 2025-05-11
R7S1ONME-AP03SF1186 | Installation of Basket trays for Low Current, Cable Installation (In Front of Lift Shaft) - AP#03 | 4 | 2025-05-18 | 2025-05-21
R7S1ONME-AP03SF147 | BMS, CCTV & Access control Cable installation - AP#03 (SF Corridor) | 2 | 2025-05-22 | 2025-05-24
R7S1ONME-AP03SF148 | Low Current Works including BMS Panel in ICT Room - AP#03 (SF Corridor) | 10 | 2025-07-24 | 2025-08-05
R7S1ONME-AP03SF159 | Fluke test for CCTV & Fibre Optic Cable - AP#03 (SF Corridor) | 2 | 2025-08-03 | 2025-08-05
R7S1ONME-AP03SF146 | Fibre optic Cable pulling & Termination with OTO (in corridors to ONU) - AP#03 (SF Corridor) | 2 | 2025-08-05 | 2025-08-07
R7S1ONME-AP03SF155 | Installation & Termination of CCTV Cameras - AP#03 (SF Corridor) | 2 | 2025-08-27 | 2025-08-30
R7S1ONME-AP03SF156 | Installation & Termination of Access control system for Electrical Room - AP#03 (SF Corridor) | 2 | 2025-08-27 | 2025-08-30
R7S1ONME-AP03SF158 | Installation & Termination of Wireless Gateway & RF Node in corridors - AP#03 (SF Corridor) | 2 | 2025-08-27 | 2025-08-30
R7S1ONME-AP03SF149 | Installation & Termination of Fire alarm devices & Speakers - AP#03 (SF Corridor) | 4 | 2025-08-27 | 2025-09-01
R7S1ONME-AP03SF157 | Installation & Termination of Active Components & UPS installation in ICT Room - AP#03 (SF Corridor) | 2 | 2025-08-30 | 2025-09-01
ROOF WORKS |  | 104 | 2025-05-19 | 2025-08-19
ARCH./ CIVIL WORKS |  | 104 | 2025-05-19 | 2025-08-19
R7S1ONAR-AP03RF19 | Roof Box Stiching (Concrete Works) - AP#03 (Roof) | 6 | 2025-05-19 | 2025-05-25
R7S1ONME-AP03RF161 | Installation of Roof Drains - AP#03 (Roof) | 2 | 2025-05-24 | 2025-05-25
R7S1ONAR-AP03RF20 | Roof Waterproofing Works with testing - AP#03 (Roof) | 20 | 2025-05-26 | 2025-06-22
R7S1ONAR-AP03RF21 | Laying of Gravel - AP#03 (Roof) | 2 | 2025-06-23 | 2025-06-24
R7S1ONAR-AP03RF22 | Surface Preparation & Primer for Parapets - AP#03 (Roof) | 6 | 2025-07-13 | 2025-07-19
R7S1ONAR-AP03RF23 | 1st Coat Paint for Parapets - AP#03 (Roof) | 2 | 2025-07-20 | 2025-07-21
R7S1ONAR-AP03RF24 | 2nd Coat Paint for Parapets - AP#03 (Roof) | 2 | 2025-07-22 | 2025-07-23
R7S1ONAR-AP03RF26 | Fixing Fall Arrest System - AP#03 (Roof) | 2 | 2025-08-09 | 2025-08-11
R7S1ONAR-AP03RF25 | Crossover Bridges Installation & application of Sealant on MEP penetrations - AP#03 (Roof) | 12 | 2025-08-06 | 2025-08-19
MECHANICAL |  | 70 | 2025-06-25 | 2025-08-14
HVAC |  | 37 | 2025-06-25 | 2025-08-11
R7S1ONME-AP03RF125 | Modular Installation - AP#03 (Roof) | 5 | 2025-06-25 | 2025-06-30
R7S1ONME-AP03RF126 | Continuation of Roof duct works/FAHU Connections - AP#03 (Roof) | 5 | 2025-06-28 | 2025-07-02
R7S1ONME-AP03RF128 | Insulations for ducts - AP#03 (Roof) | 5 | 2025-06-29 | 2025-07-03
R7S1ONME-AP03RF130 | Installation of FAHU - AP#03 (Roof) | 2 | 2025-08-03 | 2025-08-05
R7S1ONME-AP03RF135 | Installation of Outdoor VRF/DX Units - AP#03 (Roof) | 2 | 2025-08-04 | 2025-08-06
R7S1ONME-AP03RF136 | Installation & Insulation of the Condensation Drain - AP#03 (Roof) | 1 | 2025-08-05 | 2025-08-06
R7S1ONME-AP03RF138 | Installation of Ventilation Fans - AP#03 (Roof) | 3 | 2025-08-03 | 2025-08-06
R7S1ONME-AP03RF133 | Chilled Water System Continuation and Connections with Valve package of FAHU - AP#03 (Roof) | 4 | 2025-08-03 | 2025-08-07
R7S1ONME-AP03RF140 | Installation of Louvers - AP#03 (Roof) | 2 | 2025-08-06 | 2025-08-09
R7S1ONME-AP03RF143 | Installation & Testing of Copper Pipes - AP#03 (Roof) | 2 | 2025-08-06 | 2025-08-09
R7S1ONME-AP03RF144 | Miscellaneous Works for Mechanical Connections (Fire & Volume Dampers etc.) - AP#03 (Roof) | 2 | 2025-08-09 | 2025-08-11
WATERSUPPLY & DRAINAGE |  | 35 | 2025-07-01 | 2025-08-14
R7S1ONME-AP03RF124 | Testing for the Rain Water Risers - AP#03 (Roof) | 2 | 2025-07-03 | 2025-07-05
R7S1ONME-AP03RF127 | Installation & Continuation of Water supply pipes (connection between modular cages & modular to Shaft Riser) - AP#03 | 4 | 2025-07-01 | 2025-07-05
R7S1ONME-AP03RF134 | Installation of Rain Water outlet - AP#03 (Roof) | 3 | 2025-07-06 | 2025-07-08
R7S1ONME-AP03RF129 | Installation of Air Vent with Valve for Water Supply - AP#03 (Roof) | 4 | 2025-07-06 | 2025-07-09
R7S1ONME-AP03RF131 | Installation of Air Vent & Pressure Guage with Valves at Roof - AP#03 (Roof) | 4 | 2025-08-03 | 2025-08-07
R7S1ONME-AP03RF132 | Vertical Continuation of Vent Pipes To The Roof (Drainage) - AP#03 (Roof) | 4 | 2025-08-04 | 2025-08-09
R7S1ONME-AP03RF137 | Testing of Water Supply Pipes - AP#03 (Roof) | 2 | 2025-08-07 | 2025-08-10
R7S1ONME-AP03RF139 | Insulation of Roof Water Line - AP#03 (Roof) | 2 | 2025-08-09 | 2025-08-11
R7S1ONME-AP03RF141 | Testing for the Drainage Pipes Risers - AP#03 (Roof) | 2 | 2025-08-11 | 2025-08-13
R7S1ONME-AP03RF142 | Installation of Vent Cowl - AP#03 (Roof) | 1 | 2025-08-13 | 2025-08-14
SOLAR HEATER |  | 59 | 2025-07-06 | 2025-07-17
R7S1ONME-AP03RF156 | Installation of Solar water pumps and circulation pumps with valves(For Water Only) - AP#03 (Roof) | 2 | 2025-07-07 | 2025-07-08
R7S1ONME-AP03RF154 | Installation of Structure and Solar Panels (For Water Only) - AP#03 (Roof) | 5 | 2025-07-06 | 2025-07-10
R7S1ONME-AP03RF155 | Installation of Solar Calorifier Tank & Air cooler (For Water Only) - AP#03 (Roof) | 5 | 2025-07-07 | 2025-07-12
R7S1ONME-AP03RF157 | Installation of Solar Pipes Primary Loop - AP#03 (Roof) | 5 | 2025-07-07 | 2025-07-12
R7S1ONME-AP03RF158 | Testing of Solar Pipes Primary Loop - AP#03 (Roof) | 1 | 2025-07-13 | 2025-07-13
R7S1ONME-AP03RF159 | Insulation of Solar Pipes Primary Loop - AP#03 (Roof) | 1 | 2025-07-13 | 2025-07-13
R7S1ONME-AP03RF160 | Aluminum Cladding of Solar Pipes Primary Loop - AP#03 (Roof) | 4 | 2025-07-14 | 2025-07-17
ELECTRICAL |  | 37 | 2025-07-01 | 2025-08-18
POWER & LOW CURRENT |  | 37 | 2025-07-01 | 2025-08-18
R7S1ONME-AP03RF145 | Installation of Cables for Fire Alarm system - AP#03 (Roof) | 3 | 2025-07-01 | 2025-07-03
R7S1ONME-AP03RF146 | Installation of Cables for BMS - AP#03 (Roof) | 3 | 2025-07-01 | 2025-07-03
R7S1ONME-AP03RF147 | Installation of Fire Alarm Devices - AP#03 (Roof) | 3 | 2025-07-01 | 2025-07-03
R7S1ONME-AP03RF149 | Installation of Roof Light Fixtures - AP#03 (Roof) | 3 | 2025-07-01 | 2025-07-03
R7S1ONME-AP03RF121 | Installation of Electrical Containments for BMS - AP#03 (Roof) | 7 | 2025-07-01 | 2025-07-08
R7S1ONME-AP03RF163 | Termination of Primary & Secondary pump for Solar system - AP#03 (Roof) | 1 | 2025-07-09 | 2025-07-09
R7S1ONME-AP03RF162 | Installation & Termination of Solar System Panel - AP#03 (Roof) | 3 | 2025-07-19 | 2025-07-21
R7S1ONME-AP03RF119 | Lightening Protection & Earthing System - AP#03 (Roof) | 7 | 2025-07-24 | 2025-07-31
R7S1ONME-AP03RF148 | Installation of BMS Devices - AP#03 (Roof) | 4 | 2025-07-31 | 2025-08-05
R7S1ONME-AP03RF122 | Installation of Fire Alarm Containment for FAHU, Fans - AP#03 (Roof) | 4 | 2025-08-02 | 2025-08-05
R7S1ONME-AP03RF151 | Termination for BMS System - AP#03 (Roof) | 1 | 2025-08-05 | 2025-08-06
R7S1ONME-AP03RF152 | Termination for Fire Alarm Device - AP#03 (Roof) | 1 | 2025-08-06 | 2025-08-06
R7S1ONME-AP03RF123 | Installation of LV Power Cables for Roof Equipment - AP#03 (Roof) | 5 | 2025-08-06 | 2025-08-11
R7S1ONME-AP03RF120 | Installation of Isolators and Machine Connections - AP#03 (Roof) | 4 | 2025-08-11 | 2025-08-16
R7S1ONME-AP03RF150 | Termination for LV Cables - AP#03 (Roof) | 1 | 2025-08-16 | 2025-08-17
R7S1ONME-AP03RF153 | Megger Test for the Power Cables - AP#03 (Roof) | 1 | 2025-08-17 | 2025-08-18
STAIR CASE |  | 155 | 2025-04-21 | 2025-08-07
CIVIL WORKS |  | 125 | 2025-05-26 | 2025-08-03
STAIR CASE (MAIN WITH LIFT) |  | 96 | 2025-05-26 | 2025-07-19
R7S1ONST-AP03RG323 | Stair Flooring (Roof to GF) - AP#03 (Main Stair) | 7 | 2025-05-26 | 2025-06-02
R7S1ONST-AP03RG324 | Stair Hand Rails (Roof to GF) - AP#03 (Main Stair) | 6 | 2025-06-30 | 2025-07-06
R7S1ONST-AP03RG325 | Stair Paint - Primer & 1st Coat (Roof to GF)- AP#03 (Main Stair) | 7 | 2025-07-07 | 2025-07-14
R7S1ONST-AP03RG326 | Stair Paint - Final Coat (Roof to GF)- AP#03 (Main Stair) | 4 | 2025-07-15 | 2025-07-19
STAIR CASE (LEFT SIDE) |  | 93 | 2025-06-03 | 2025-07-23
R7S1ONST-AP03RG333 | Stair Flooring (Roof to GF) - AP#03 Left Side Stair | 7 | 2025-06-03 | 2025-06-15
R7S1ONST-AP03RG334 | Stair Hand Rails (Roof to GF) - AP#03 Left Side Stair | 6 | 2025-07-07 | 2025-07-13
R7S1ONST-AP03RG335 | Stair Paint - Primer & 1st Coat (Roof to GF) - AP#03 Left Side Stair | 6 | 2025-07-14 | 2025-07-20
R7S1ONST-AP03RG336 | Stair Paint - Final Coat (Roof to GF) - AP#03 Left Side Stair | 3 | 2025-07-21 | 2025-07-23
STAIR CASE (RIGHT SIDE) |  | 106 | 2025-06-16 | 2025-08-03
R7S1ONST-AP03RG337 | Stair Flooring (Roof to GF) - AP#03 Right Side Stair | 8 | 2025-06-16 | 2025-06-24
R7S1ONST-AP03RG338 | Stair Hand Rails (Roof to GF) - AP#03 Right Side Stair | 7 | 2025-07-14 | 2025-07-21
R7S1ONST-AP03RG339 | Stair Paint - Primer & 1st Coat (Roof to GF) - AP#03 Right Side Stair | 7 | 2025-07-22 | 2025-07-29
R7S1ONST-AP03RG340 | Stair Paint - Final Coat (Roof to GF) - AP#03 Right Side Stair | 4 | 2025-07-30 | 2025-08-03
MEP WORKS |  | 141 | 2025-04-21 | 2025-08-07
STAIR CASE (MAIN WITH LIFT) |  | 86 | 2025-05-19 | 2025-07-23
R7S1ONST-AP03RG322 | Main Staircase Wire Pulling - AP#03 (Main Stair) | 3 | 2025-05-19 | 2025-05-21
R7S1ONST-AP03RG341 | Final fix - Main Staircase Lights Fixtures & Motion Sensor - AP#03 (Main Stair) | 2 | 2025-07-20 | 2025-07-21
R7S1ONST-AP03RG342 | Final fix - Main Staircase Emergency Lights Fixtures - AP#03 (Main Stair) | 2 | 2025-07-22 | 2025-07-23
STAIR CASE (LEFT SIDE) |  | 134 | 2025-04-21 | 2025-07-28
R7S1ONST-AP03RG327 | Left Staircase Wire Pulling - AP#03 (Main Stair) | 27 | 2025-04-21 | 2025-05-22
R7S1ONST-AP03RG329 | Final fix - Left Staircase Lights Fixtures & Motion Sensor - AP#03 (Main Stair) | 2 | 2025-07-24 | 2025-07-26
R7S1ONST-AP03RG331 | Final fix - Left Staircase Emergency Lights Fixtures - AP#03 (Main Stair) | 2 | 2025-07-27 | 2025-07-28
STAIR CASE (RIGHT SIDE) |  | 141 | 2025-04-21 | 2025-08-07
R7S1ONST-AP03RG328 | Right Staircase Wire Pulling - AP#03 (Main Stair) | 27 | 2025-04-21 | 2025-05-22
R7S1ONST-AP03RG330 | Final fix - Right Staircase Lights Fixtures & Motion Sensor - AP#03 (Main Stair) | 2 | 2025-08-04 | 2025-08-05
R7S1ONST-AP03RG332 | Final fix - Right Staircase Emergency Lights Fixtures - AP#03 (Main Stair) | 2 | 2025-08-06 | 2025-08-07
ELEVATOR WORKS |  | 34 | 2025-07-26 | 2025-08-19
R7S1ONEL-AP03GR607 | Installation of Rails - AP#03 (Elevator Works) | 6 | 2025-07-26 | 2025-07-31
R7S1ONEL-AP03GR608 | Assembly of Cabin - AP#03 (Elevator Works) | 4 | 2025-08-02 | 2025-08-05
R7S1ONEL-AP03GR609 | Installation of Motor - AP#03 (Elevator Works) | 4 | 2025-08-06 | 2025-08-10
R7S1ONEL-AP03GR610 | Installation of Main Cables - AP#03 (Elevator Works) | 4 | 2025-08-11 | 2025-08-14
R7S1ONEL-AP03GR611 | Installation of Doors, Indicator, Push Button - AP#03 (Elevator Works) | 2 | 2025-08-16 | 2025-08-17
R7S1ONEL-AP03GR612 | Interior Finishes - AP#03 (Elevator Works) | 2 | 2025-08-18 | 2025-08-19
EXTERNAL ELEVATIONS |  | 84 | 2025-06-25 | 2025-08-07
ARCH./ CIVIL WORKS |  | 84 | 2025-06-25 | 2025-08-07
R7S1ONEE-AP03GR505 | External Selant Works - For Boxes - AP#03 (External Elevations) | 15 | 2025-06-25 | 2025-07-12
R7S1ONEE-AP03GR506 | Final Finishes & Touchups - AP#03 (External Elevations) | 15 | 2025-07-13 | 2025-07-29
R7S1ONME-AP03GF407 | Installation of rain water outlet - External façade - AP#03 (External Elevations) | 2 | 2025-07-30 | 2025-07-31
R7S1ONEE-AP03GR508 | Installation of External Signages - AP#03 (External Elevations) | 4 | 2025-08-02 | 2025-08-05
R7S1ONEE-AP03GR507 | Fixing Cage Ladder - AP#03 (External Elevations) | 2 | 2025-08-06 | 2025-08-07
EXTERNAL - CIVIL WORKS |  | 58 | 2025-05-15 | 2025-07-22
DRAINAGE |  | 27 | 2025-05-15 | 2025-05-28
R7S1ONECW-AP03-289 | Excavation Works & Sand Bedding - AP#03 (External Drainage) | 3 | 2025-05-15 | 2025-05-18
R7S1ONECW-AP03-290 | Drainage Manholes - AP#03 | 6 | 2025-05-15 | 2025-05-21
R7S1ONECW-AP03-291 | Drainage Backfilling - AP#03 | 2 | 2025-05-27 | 2025-05-28
WATERSUPPLY |  | 29 | 2025-05-19 | 2025-06-17
R7S1ONECW-AP03-292 | Excavation Works & Sand Bedding - Watersupply - AP#03 (External Watersupply Civil) | 3 | 2025-05-19 | 2025-05-21
R7S1ONECW-AP03-293 | Watersupply Manholes - AP#03 | 6 | 2025-05-22 | 2025-05-28
R7S1ONECW-AP03-294 | Watersupply Backfilling - AP#03 | 2 | 2025-06-16 | 2025-06-17
CHILLED WATER |  | 24 | 2025-05-22 | 2025-06-03
R7S1ONECW-AP03-298 | Excavation Works & Sand Bedding - AP#03 (External Chilled Water Civil) | 3 | 2025-05-22 | 2025-05-25
R7S1ONECW-AP03-299 | Chilled Water Manholes - AP#03 | 6 | 2025-05-26 | 2025-06-01
R7S1ONECW-AP03-300 | Chilled Water Backfilling - AP#03 | 2 | 2025-06-02 | 2025-06-03
FIRE FIGHTING |  | 23 | 2025-05-26 | 2025-06-17
R7S1ONECW-AP03-295 | Excavation Works & Sand Bedding - AP#03 (External Chilled Water Civil) | 3 | 2025-05-26 | 2025-05-28
R7S1ONECW-AP03-296 | Fire Fighting Manholes - AP#03 | 6 | 2025-05-29 | 2025-06-04
R7S1ONECW-AP03-297 | Fire Fighting Backfilling - AP#03 | 2 | 2025-06-16 | 2025-06-17
POWER |  | 25 | 2025-05-29 | 2025-07-22
R7S1ONECW-AP03-301 | Excavation Works & Sand Bedding - AP#03 (External Power Civil) | 3 | 2025-05-29 | 2025-06-01
R7S1ONECW-AP03-302 | Power Manholes - AP#03 | 3 | 2025-06-02 | 2025-06-04
R7S1ONECW-AP03-303 | Power Backfilling - AP#03 | 2 | 2025-07-21 | 2025-07-22
LOW CURRENT |  | 8 | 2025-06-02 | 2025-06-15
R7S1ONECW-AP03-304 | Excavation Works & Sand Bedding - AP#03 (External Low Current Civil) | 3 | 2025-06-02 | 2025-06-04
R7S1ONECW-AP03-305 | Low Current Manholes - AP#03 | 3 | 2025-06-10 | 2025-06-12
R7S1ONECW-AP03-306 | Low Current Backfilling - AP#03 | 2 | 2025-06-14 | 2025-06-15
EXTERNAL - MEP SERVICES |  | 52 | 2025-05-22 | 2025-07-20
DRAINAGE |  | 4 | 2025-05-22 | 2025-05-26
R7S1ONEME-AP03-201 | External Drainage Network - AP#03 (External Drainage MEP) | 4 | 2025-05-22 | 2025-05-26
WATERSUPPLY |  | 7 | 2025-05-29 | 2025-06-17
R7S1ONEME-AP03-202 | PRV statiuon assembly including meters- AP#03 (External WS MEP) | 4 | 2025-05-29 | 2025-06-02
R7S1ONEME-AP03-204 | Installation of valve station incl. BTU meter- AP#03 (External WS MEP) | 3 | 2025-06-15 | 2025-06-17
CHILLED WATER |  | 7 | 2025-06-03 | 2025-06-15
R7S1ONEME-AP03-203 | Installation of Chilled water line- AP#03 (External CWP MEP) | 6 | 2025-06-03 | 2025-06-14
R7S1ONEME-AP03-205 | Pressure Test for chilled water line- AP#03 (External CWP MEP) | 1 | 2025-06-15 | 2025-06-15
FIRE FIGHTING |  | 11 | 2025-05-29 | 2025-06-15
R7S1ONEME-AP03-206 | Installation of External FF network - AP#03 (External FF MEP) | 6 | 2025-05-29 | 2025-06-04
R7S1ONEME-AP03-207 | Installation of Alarm check valves- AP#03 (External FF MEP) | 3 | 2025-06-10 | 2025-06-12
R7S1ONEME-AP03-208 | Testing of External FF - AP#03 (External FF MEP) | 2 | 2025-06-14 | 2025-06-15
POWER |  | 2 | 2025-07-19 | 2025-07-20
R7S1ONEME-AP03-209 | Cable pulling from Manhole to the building MDB - AP#03 (External Power MEP) | 2 | 2025-07-19 | 2025-07-20
LOW CURRENT |  | 3 | 2025-06-10 | 2025-06-12
R7S1ONEME-AP03-210 | Low Current Cable pulling- AP#03 (External FF MEP) | 3 | 2025-06-10 | 2025-06-12
BUILDING # AP02 (MGT BLDG) |  | 287 | 2024-11-12 | 2025-09-30
SUB-STRUCTURE |  | 43 | 2024-11-12 | 2024-12-31
R7S1-ONSB-AP02-204 | Site Setting Out Works - AP#02 | 1 | 2024-11-12 | 2024-11-12
R7S1-ONSB-AP02-201 | Site levelling & earthworks - AP#02 | 6 | 2024-11-19 | 2024-11-26
R7S1-ONSB-AP02-205 | Anti-termite & Polythene Sheet Works - AP#02 | 1 | 2024-12-07 | 2024-12-07
R7S1-ONSB-AP02-202 | Blinding PCC - AP#02 | 4 | 2024-12-08 | 2024-12-11
R7S1-ONSB-AP02-203 | Waterproofing for Blinding PCC (Bitumen Paint) - AP#02 | 2 | 2024-12-11 | 2024-12-12
R7S1-ONSB-AP02-206 | Foundations/Upstands - Rebar - AP#02 | 5 | 2024-12-15 | 2024-12-21
R7S1-ONSB-AP02-207 | Foundations/Upstands - Shuttering (Including dowel Works) - AP#02 | 5 | 2024-12-16 | 2024-12-22
R7S1-ONSB-AP02-210 | Installation of MEP U/G services below Boxes - AP#02 | 2 | 2024-12-22 | 2024-12-24
R7S1-ONSB-AP02-208 | Foundations/Upstands - Casting - AP#02 | 2 | 2024-12-24 | 2024-12-26
R7S1-ONSB-AP02-209 | Waterproofing For Foundations/Upstands - AP#02 | 2 | 2024-12-28 | 2024-12-29
R7S1-ONSB-AP02-211 | Backfilling & Compaction - AP#02 | 2 | 2024-12-30 | 2024-12-31
SLAB-ON-GRADE & UG MEP WORKS (in Corridor) |  | 63 | 2025-02-04 | 2025-04-24
LEFT SIDE |  | 63 | 2025-02-04 | 2025-04-24
R7S1-ONSG-AP02-241 | Block Work below Corridor area - AP#02 | 5 | 2025-02-04 | 2025-02-10
R7S1-ONSG-AP02-242 | UG MEP Works (Laying of Pipes) - AP#02 | 1 | 2025-02-10 | 2025-02-11
R7S1-ONSG-AP02-243 | Backfilling Works after Pipe Laying - AP#02 | 1 | 2025-02-10 | 2025-02-11
R7S1-ONSG-AP02-244 | Antitermite Works - AP#02 | 1 | 2025-02-10 | 2025-02-11
R7S1-ONSG-AP02-247 | Backfilling upto Pipe Level - AP#02 | 5 | 2025-02-05 | 2025-02-11
R7S1-ONSG-AP02-255 | Plaster Work for Blockwork - AP#02 | 1 | 2025-02-10 | 2025-02-11
R7S1-ONSG-AP02-245 | Polythene & Rebar Mesh Works - AP#02 | 2 | 2025-02-10 | 2025-02-12
R7S1-ONSG-AP02-246 | Pouring SOG Concrete - AP#02 | 1 | 2025-02-15 | 2025-02-16
R7S1-ONSG-AP02-290 | Backfilling & SOG (In Front of Lift Shaft) - AP#02 | 4 | 2025-04-21 | 2025-04-24
RIGHT SIDE |  | 6 | 2025-02-11 | 2025-02-18
R7S1-ONSG-AP02-248 | Block Work below Corridor area - AP#02 | 2 | 2025-02-11 | 2025-02-13
R7S1-ONSG-AP02-249 | UG MEP Works (Laying of Pipes) - AP#02 | 2 | 2025-02-11 | 2025-02-13
R7S1-ONSG-AP02-250 | Backfilling Works after Pipe Laying - AP#02 | 2 | 2025-02-11 | 2025-02-13
R7S1-ONSG-AP02-251 | Antitermite Works - AP#02 | 2 | 2025-02-11 | 2025-02-13
R7S1-ONSG-AP02-254 | Backfilling upto Pipe Level - AP#02 | 2 | 2025-02-11 | 2025-02-13
R7S1-ONSG-AP02-252 | Polythene & Rebar Mesh Works - AP#02 | 4 | 2025-02-12 | 2025-02-17
R7S1-ONSG-AP02-253 | Pouring SOG Concrete - AP#02 | 1 | 2025-02-17 | 2025-02-18
ERECTION WORKS |  | 83 | 2025-02-04 | 2025-05-18
GROUND FLOOR |  | 63 | 2025-02-04 | 2025-04-24
R7S1ONER-AP02GF152 | Erection of GF Boxes (Right Side) - AP#02 | 4 | 2025-02-09 | 2025-02-13
R7S1ONER-AP02GF151 | Erection of GF Boxes (Left Side) including Lift Box & Staircase - AP#02 | 9 | 2025-02-04 | 2025-02-15
R7S1ONER-AP02GF153 | Erection of GF MEP Modular Cages (Left Side) - AP#02 | 2 | 2025-02-16 | 2025-02-18
R7S1ONER-AP02GF154 | Erection of GF Corridor Slabs (Left Side) - AP#02 | 1 | 2025-02-18 | 2025-02-19
R7S1ONER-AP02GF155 | Erection of GF MEP Modular Cages (Right Side) - AP#02 | 1 | 2025-02-18 | 2025-02-19
R7S1ONER-AP02GF156 | Erection of GF Corridor Slabs Right Side) - AP#02 | 1 | 2025-02-19 | 2025-02-20
R7S1ONER-AP02GF202 | Erection of Columns/Beams Frame & Slab/Loose Elements (In Front of Lift Shaft) - AP#02 | 1 | 2025-04-24 | 2025-04-24
FIRST FLOOR |  | 34 | 2025-03-11 | 2025-04-24
R7S1ONER-AP02FF151 | Erection of FF Boxes (Left Side) - AP#02 | 7 | 2025-03-11 | 2025-03-20
R7S1ONER-AP02FF152 | Erection of FF Boxes (Right Side) - AP#02 | 6 | 2025-03-16 | 2025-03-23
R7S1ONER-AP02FF153 | Erection of FF MEP Modular Cages (Left Side) - AP#02 | 13 | 2025-03-16 | 2025-03-30
R7S1ONER-AP02FF154 | Erection of FF Corridor Slabs (Left Side) - AP#02 | 11 | 2025-03-18 | 2025-03-30
R7S1ONER-AP02FF155 | Erection of FF MEP Modular Cages (Right Side) - AP#02 | 9 | 2025-03-19 | 2025-03-30
R7S1ONER-AP02FF156 | Erection of FF Corridor Slabs Right Side) - AP#02 | 7 | 2025-03-22 | 2025-03-30
R7S1ONER-AP02FF212 | Erection of Columns/Beams Frame & Slab/Loose Elements (In Front of Lift Shaft) - AP#02 | 2 | 2025-04-23 | 2025-04-24
SECOND FLOOR |  | 11 | 2025-04-22 | 2025-05-04
R7S1ONER-AP02SF151 | Erection of SF Boxes (Left Side) - AP#02 | 0 | 2025-04-23 | 2025-04-23
R7S1ONER-AP02SF152 | Erection of SF Boxes (Right Side) - AP#02 | 2 | 2025-04-22 | 2025-04-24
R7S1ONER-AP02SF222 | Erection of Columns/Beams Frame & Slab/Loose Elements (In Front of Lift Shaft) - AP#02 | 2 | 2025-04-23 | 2025-04-24
R7S1ONER-AP02SF153 | Erection of SF MEP Modular Cages (Left Side) - AP#02 | 3 | 2025-04-26 | 2025-04-28
R7S1ONER-AP02SF154 | Erection of SF Corridor Slabs (Left Side) - AP#02 | 2 | 2025-04-29 | 2025-04-30
R7S1ONER-AP02SF155 | Erection of SF MEP Modular Cages (Right Side) - AP#02 | 2 | 2025-04-30 | 2025-05-01
R7S1ONER-AP02SF156 | Erection of SF Corridor Slabs Right Side) - AP#02 | 2 | 2025-05-03 | 2025-05-04
ROOF |  | 12 | 2025-05-05 | 2025-05-18
R7S1ONER-AP02RF101 | Erection of Loose Roof Parapets, Shaft Covers, MEP Foundation etc. - AP#02 Roof | 12 | 2025-05-05 | 2025-05-18
MEP WORKS & FINISHES |  | 184 | 2025-02-23 | 2025-09-30
GROUND FLOOR |  | 179 | 2025-02-23 | 2025-07-29
ARCH./ CIVIL WORKS |  | 165 | 2025-03-10 | 2025-07-29
CORRIDOR AREA |  | 128 | 2025-03-10 | 2025-07-29
R7S1ONAR-AP02GF43 | Flooring in Corridor - AP#02 (GF Corridor) | 19 | 2025-04-07 | 2025-04-29
R7S1ONAR-AP02GF41 | False Ceiling - 1st Fix - AP#02 (GF - Corridor) | 22 | 2025-04-05 | 2025-04-30
R7S1ONAR-AP02GF44 | Corridor Skirting - AP#02 (GF Corridor) | 2 | 2025-04-28 | 2025-04-30
R7S1ONAR-AP02GF42 | Gypsum Wall Cladding - 1st Fix (Shafts) - AP#02 (GF Corridor) | 93 | 2025-03-10 | 2025-07-07
R7S1ONAR-AP02GF45 | Gypsum Wall Cladding (Shafts) -2nd Fix - AP#02 (GF Corridor) | 4 | 2025-07-07 | 2025-07-12
R7S1ONAR-AP02GF49 | Fixing Architrave - AP#02 (GF Corridor) | 2 | 2025-07-12 | 2025-07-14
R7S1ONAR-AP02GF50 | Fixing Aluminium Doors - AP#02 (GF Corridor) | 2 | 2025-07-14 | 2025-07-16
R7S1ONAR-AP02GF46 | False Ceiling - 2nd Fix (Closing the Ceiling) - AP#02 (GF Corridor) | 3 | 2025-07-16 | 2025-07-20
R7S1ONAR-AP02GF47 | Painting - Surface Prep., Primer & 1st Coat - AP#02 (GF Corridor) | 8 | 2025-07-12 | 2025-07-21
R7S1ONAR-AP02GF71 | Painting - Surface Prep., Primer & 1st Coat for Ceiling - AP#02 (GF Corridor) | 4 | 2025-07-20 | 2025-07-24
R7S1ONAR-AP02GF48 | Painting - Final Coat (Ceiling + Walls) - AP#02 (GF Corridor) | 3 | 2025-07-26 | 2025-07-29
INSIDE BOXES |  | 22 | 2025-04-09 | 2025-05-04
R7S1ONAR-AP02GF51 | Fixing Thresholds (Joining the Room) - AP#02 (GF - inside Boxes) | 18 | 2025-04-09 | 2025-04-29
R7S1ONAR-AP02GF52 | Fixing Wooden Doors - AP#02 (GF - inside Boxes) | 4 | 2025-04-29 | 2025-05-04
R7S1ONAR-AP02GF53 | Fixing Aluminium Doors - AP#02 (GF - inside Boxes) | 12 | 2025-04-21 | 2025-05-04
IN FRONT OF LIFT SHAFT |  | 128 | 2025-04-26 | 2025-07-17
R7S1ONAR-AP02GF55 | Flooring - AP#02 (GF - Front of Lift Shaft) | 3 | 2025-04-26 | 2025-04-28
R7S1ONAR-AP02GF56 | Skirting & Thresholds - AP#02 (GF - Front of Lift Shaft) | 1 | 2025-04-28 | 2025-04-28
R7S1ONAR-AP02GF57 | Painting - Surface Prep., Primer & 1st Coat - AP#02 (GF - Front of Lift Shaft) | 4 | 2025-04-29 | 2025-05-03
R7S1ONAR-AP02GF54 | False Ceiling - 1st Fix - AP#02 (GF - Front of Lift Shaft) | 4 | 2025-05-04 | 2025-05-07
R7S1ONAR-AP02GF58 | False Ceiling - Final Fix - AP#02 (GF - Front of Lift Shaft) | 3 | 2025-05-08 | 2025-05-11
R7S1ONAR-AP02GF60 | Fixing Handrail - AP#02 (GF - Front of Lift Shaft) | 3 | 2025-07-03 | 2025-07-06
R7S1ONAR-AP02GF61 | Paint for Handrail - AP#02 (GF - Front of Lift Shaft) | 3 | 2025-07-07 | 2025-07-09
R7S1ONAR-AP02GF59 | Painting - Final Coat - AP#02 (GF - Front of Lift Shaft) | 3 | 2025-07-10 | 2025-07-13
R7S1ONAR-AP02GF63 | Fixing Wall Guard - AP#02 (GF - Front of Lift Shaft) | 2 | 2025-07-14 | 2025-07-15
R7S1ONAR-AP02GF62 | Fixing Floor Mat - AP#02 (GF - Front of Lift Shaft) | 2 | 2025-07-16 | 2025-07-17
GARBAGE ROOM |  | 2 | 2025-07-23 | 2025-07-24
R7S1ONAR-AP02GF64 | Paint Finishes and Touchups - Final Coat - AP#02 (GF - Garbage Room) | 2 | 2025-07-23 | 2025-07-24
BALCONIES |  | 145 | 2025-04-08 | 2025-07-17
R7S1ONAR-AP02GF65 | Wetarea Waterproofing - AP#02 (GF - Balconies) | 19 | 2025-04-08 | 2025-04-29
R7S1ONAR-AP02GF66 | Flooring - AP#02 (GF - Front of Lift Shaft) | 19 | 2025-04-12 | 2025-05-03
R7S1ONAR-AP02GF67 | Painting - Surface Prep., Primer & 1st Coat - AP#02 (GF - Front of Lift Shaft) | 6 | 2025-04-30 | 2025-05-06
R7S1ONAR-AP02GF69 | Fixing Handrail - AP#02 (GF - Front of Lift Shaft) | 6 | 2025-07-07 | 2025-07-13
R7S1ONAR-AP02GF70 | Paint for Handrail - AP#02 (GF - Front of Lift Shaft) | 2 | 2025-07-14 | 2025-07-15
R7S1ONAR-AP02GF68 | Painting - Final Coat - AP#02 (GF - Front of Lift Shaft) | 2 | 2025-07-16 | 2025-07-17
MEP WORKS |  | 121 | 2025-02-23 | 2025-07-26
MECHANICAL |  | 114 | 2025-02-26 | 2025-07-23
CHILLED WATER |  | 74 | 2025-03-01 | 2025-05-10
R7S1ONME-AP02GF334 | CHWP piping risers connections - AP#02 (GF - Corridor) | 24 | 2025-03-03 | 2025-04-05
R7S1ONME-AP02GF331 | Installation of Chilled water hanger and supports - AP#02 (GF - Corridor) | 27 | 2025-03-01 | 2025-04-05
R7S1ONME-AP02GF332 | Installation of CHWP piping (connection between modular cages & modular to apartment) - AP#02 (GF - Corridor) | 33 | 2025-03-01 | 2025-04-13
R7S1ONME-AP02GF333 | Installation of BTU Meter with valves - AP#02 (GF - Corridor) | 32 | 2025-03-04 | 2025-04-15
R7S1ONME-AP02GF335 | Pressure Testing of CHWP piping - AP#02 (GF - Corridor) | 22 | 2025-03-19 | 2025-04-17
R7S1ONME-AP02GF383 | Installation of CHWP connection for FCU with Valve package in Corridor, Electrical Room & ICT Room - AP#02 (GF) | 32 | 2025-03-15 | 2025-04-24
R7S1ONME-AP02GF486 | CHWP Installation/Connections and Insulation (In Front of Lift Shaft) - AP#02 | 4 | 2025-05-05 | 2025-05-08
R7S1ONME-AP02GF371 | CHWP Insulation - AP#02 (GF - Corridor) | 41 | 2025-03-18 | 2025-05-10
HVAC DUCTING |  | 106 | 2025-03-01 | 2025-07-22
R7S1ONME-AP02GF336 | Duct Riser Continuation - AP#02 (GF - Corridor) | 28 | 2025-03-25 | 2025-04-30
R7S1ONME-AP02GF337 | A/C drain & Copper pipe connection in ELV room - AP#02 (GF) | 32 | 2025-03-20 | 2025-04-30
R7S1ONME-AP02GF372 | Installation of Duct & Grill in Garbage Room - AP#02 (GF - Garbage Room) | 30 | 2025-03-23 | 2025-04-30
R7S1ONME-AP02GF382 | Installation of FCU's & Duct Connection in Corridor, Electrical Room & ICT Room - AP#02 (GF) | 53 | 2025-03-01 | 2025-05-05
R7S1ONME-AP02GF384 | Installation of Ducting and insulation (connection between modular cages) - AP#02 (GF - Corridor) | 51 | 2025-03-03 | 2025-05-05
R7S1ONME-AP02GF385 | Installation of Grilles in the Corridor - AP#02 (GF - Corridor) | 2 | 2025-07-20 | 2025-07-22
FIRE FIGHTING |  | 113 | 2025-03-01 | 2025-07-23
R7S1ONME-AP02GF338 | Riser Continuity in corridor - AP#02 (GF - Corridor) | 15 | 2025-03-16 | 2025-04-06
R7S1ONME-AP02GF339 | Continuitu of FF pipes & ZC Valves (connection between modular cages & modular to apartment) - AP#02 (GF - Corridor) | 44 | 2025-03-01 | 2025-04-24
R7S1ONME-AP02GF340 | Installation of Sprinklers drops in corridor - AP#02 (GF - Corridor) | 4 | 2025-04-30 | 2025-05-05
R7S1ONME-AP02GF341 | Pressure Test for FF Piping in corridor - AP#02 (GF - Corridor) | 40 | 2025-03-15 | 2025-05-05
R7S1ONME-AP02GF826 | Installation of F.F Pipes, Testing & Final Fixtures (In Front of Lift Shaft) - AP#02 | 3 | 2025-05-10 | 2025-05-12
R7S1ONME-AP02GF386 | FF Flushing network - AP#02 (GF - Corridor) | 1 | 2025-05-15 | 2025-05-17
R7S1ONME-AP02GF373 | Installation of Pipe & sprinkler in Garbage Room - AP#02 (GF - Garbage Room) | 89 | 2025-03-16 | 2025-07-06
R7S1ONME-AP02GF343 | Installation of Alarm check valve, Fire Extinguishers & Blanket - AP#02 (GF - Corridor) | 86 | 2025-04-06 | 2025-07-20
R7S1ONME-AP02GF342 | Installation of Sprinklers in corridor - AP#02 (GF - Corridor) | 3 | 2025-07-20 | 2025-07-23
WATER SUPPLY |  | 69 | 2025-02-26 | 2025-05-22
R7S1ONME-AP02GF375 | Installation of Sanitary Fixtures in Janitor Room - AP#02 (GF - Janitor Room) | 1 | 2025-03-01 | 2025-03-01
R7S1ONME-AP02GF374 | Installation of WS Pipe in Garbage Room - AP#02 (GF - Garbage Room) | 7 | 2025-02-26 | 2025-03-06
R7S1ONME-AP02GF346 | Installation of Cold, Hot water line & Hot water return - AP#02 (GF - Corridor) | 6 | 2025-03-03 | 2025-03-09
R7S1ONME-AP02GF345 | WS High Level Pipe continuation & Insulation works - AP#02 (GF - Corridor) | 9 | 2025-03-01 | 2025-03-10
R7S1ONME-AP02GF344 | Riser Continuity in Shafts - AP#02 (GF - Corridor) | 24 | 2025-03-24 | 2025-04-24
R7S1ONME-AP02GF347 | Water Meter Installation - AP#02 (GF - Corridor) | 4 | 2025-04-26 | 2025-04-29
R7S1ONME-AP02GF348 | Pressure Test for WS - AP#02 (GF - Corridor) | 4 | 2025-05-19 | 2025-05-22
R7S1ONME-AP02GF387 | Insulation for Hot water line & Hot water return - AP#02 (GF - Corridor) | 53 | 2025-03-17 | 2025-05-22
DRAINAGE |  | 69 | 2025-02-26 | 2025-05-22
R7S1ONME-AP02GF352 | Drainage Riser continuation in Shafts - AP#02 (GF - Corridor) | 11 | 2025-03-16 | 2025-03-27
R7S1ONME-AP02GF351 | Rain Water Riser continuation in Shafts - AP#02 (GF - Corridor) | 26 | 2025-03-16 | 2025-04-19
R7S1ONME-AP02GF350 | Installation of Clean-outs, Floor drain in balcony - AP#02 (GF - Corridor) | 43 | 2025-02-26 | 2025-04-22
R7S1ONME-AP02GF353 | Testing for Rain Water Riser - AP#02 (GF - Corridor) | 4 | 2025-05-19 | 2025-05-22
R7S1ONME-AP02GF354 | Testing for Drainage Riser1 - AP#02 (GF - Corridor) | 4 | 2025-05-19 | 2025-05-22
ELECTRICAL |  | 121 | 2025-02-23 | 2025-07-26
POWER & LIGHTING |  | 117 | 2025-02-26 | 2025-07-26
R7S1ONME-AP02GF355 | Contiuation of Cable Trays & apartment branches - AP#02 (GF - Corridor) | 13 | 2025-03-01 | 2025-03-15
R7S1ONME-AP02GF356 | Contiuation of Cable Trunking with Flexible conduits for Lights - AP#02 (GF - Corridor) | 13 | 2025-03-01 | 2025-03-15
R7S1ONME-AP02GF357 | Installation of EMT pipes - AP#02 (GF - Corridor) | 18 | 2025-02-26 | 2025-03-19
R7S1ONME-AP02GF358 | Installation of Busbar, Electrical Meter & Tap-off - AP#02 (GF - Corridor) | 3 | 2025-05-08 | 2025-05-11
R7S1ONME-AP02GF359 | Corridor Wire Pulling - AP#02 (GF - Corridor) | 56 | 2025-03-04 | 2025-05-12
R7S1ONME-AP02GF360 | Electrical Room - Installation of Cable trays, SMDB & Termination - AP#02 (GF - Corridor) | 48 | 2025-03-13 | 2025-05-12
R7S1ONME-AP02GF381 | Termination of Tap-off with Electrical Meter in the apartments - AP#02 (GF - Corridor) | 3 | 2025-05-12 | 2025-05-14
R7S1ONME-AP02GF1016 | Continuation of Cable Tray/Trunking with Flexible conduits for Lights (In Front of Lift Shaft) - AP#02 | 4 | 2025-05-13 | 2025-05-17
R7S1ONME-AP02GF362 | Installation, Termination of Emergeny & Exit Lights with contiuity - AP#02 (GF - Corridor) | 2 | 2025-07-20 | 2025-07-22
R7S1ONME-AP02GF361 | Installation, Termination of Light Fixtures with continuity test - AP#02 (GF - Corridor & Balconies) | 3 | 2025-07-20 | 2025-07-23
R7S1ONME-AP02GF363 | Installation, Termination of PIR sensors with continuity test - AP#02 (GF - Corridor) | 2 | 2025-07-23 | 2025-07-26
LOW CURRENT SYSTEM |  | 121 | 2025-02-23 | 2025-07-24
R7S1ONME-AP02GF365 | Voice Evacuation cable installation - AP#02 (GF - Corridor) | 18 | 2025-02-23 | 2025-03-15
R7S1ONME-AP02GF366 | Fire alarm cable installation - AP#02 (GF - Corridor) | 18 | 2025-02-23 | 2025-03-15
R7S1ONME-AP02GF388 | CBS System cable installation - AP#02 (GF - Corridor) | 17 | 2025-02-24 | 2025-03-15
R7S1ONME-AP02GF364 | Installation of Basket trays for BMS, CCTV, Access Control - AP#02 (GF - Corridor) | 14 | 2025-02-27 | 2025-03-15
R7S1ONME-AP02GF368 | BMS, CCTV & Access control Cable installation - AP#02 (GF - Corridor) | 37 | 2025-04-05 | 2025-05-17
R7S1ONME-AP02GF1196 | Installation of Basket trays for Low Current, Cable Installation (In Front of Lift Shaft) - AP#02 | 4 | 2025-05-13 | 2025-05-17
R7S1ONME-AP02GF369 | Low Current Works including BMS Panel in ICT Room - AP#02 (GF - Corridor) | 10 | 2025-05-11 | 2025-05-21
R7S1ONME-AP02GF377 | Installation & Termination of Access control system for Electrical Room - AP#02 (GF) | 2 | 2025-05-21 | 2025-05-22
R7S1ONME-AP02GF367 | Fibre optic Cable pulling & Termination with OTO (in corridors to ONU) - AP#02 (GF - Corridor) | 2 | 2025-05-22 | 2025-05-24
R7S1ONME-AP02GF380 | Fluke test for CCTV & Fibre Optic Cable - AP#02 (GF - Corridor) (Ceiling 1st Fix) | 2 | 2025-05-25 | 2025-05-26
R7S1ONME-AP02GF376 | Installation & Termination of CCTV Cameras - AP#02 (GF - Corridor) | 2 | 2025-07-20 | 2025-07-22
R7S1ONME-AP02GF379 | Installation & Termination of Wireless Gateway & RF Node in corridors - AP#02 (GF - Corridor) | 2 | 2025-07-20 | 2025-07-22
R7S1ONME-AP02GF370 | Installation & Termination of Fire alarm devices & Speakers - AP#02 (GF - Corridor) | 4 | 2025-07-20 | 2025-07-24
R7S1ONME-AP02GF378 | Installation & Termination of Active Components & UPS installation in ICT Room - AP#02 (GF - Corridor) | 2 | 2025-07-22 | 2025-07-24
FIRST FLOOR |  | 149 | 2025-03-24 | 2025-09-29
ARCH./ CIVIL WORKS |  | 125 | 2025-04-26 | 2025-09-29
CORRIDOR AREA |  | 97 | 2025-04-26 | 2025-09-29
R7S1ONAR-AP02FF78 | Flooring in Corridor - AP#02 (FF - Corridor) | 4 | 2025-04-26 | 2025-04-29
R7S1ONAR-AP02FF79 | Corridor Skirting - AP#02 (FF - Corridor) | 2 | 2025-04-29 | 2025-04-30
R7S1ONAR-AP02FF76 | False Ceiling - 1st Fix - AP#02 (FF - Corridor) | 4 | 2025-05-01 | 2025-05-05
R7S1ONAR-AP02FF77 | Gypsum Wall Cladding (Shafts) - AP#02 (FF - Corridor) | 2 | 2025-08-12 | 2025-08-14
R7S1ONAR-AP02FF80 | Gypsum Wall Cladding (Shafts) -2nd Fix - AP#02 (FF Corridor) | 3 | 2025-08-14 | 2025-08-18
R7S1ONAR-AP02FF84 | Fixing Architrave - AP#02 (FF Corridor) | 1 | 2025-08-18 | 2025-08-19
R7S1ONAR-AP02FF85 | Fixing Aluminium Doors - AP#02 (FF Corridor) | 1 | 2025-08-19 | 2025-08-20
R7S1ONAR-AP02FF81 | False Ceiling - 2nd Fix (Closing the Ceiling) - AP#02 (FF Corridor) | 2 | 2025-08-20 | 2025-08-23
R7S1ONAR-AP02FF82 | Painting - Surface Prep., Primer & 1st Coat for Walls - AP#02 (FF Corridor) | 5 | 2025-08-18 | 2025-08-24
R7S1ONAR-AP02FF117 | Painting - Surface Prep., Primer & 1st Coat for Ceiling - AP#02 (FF Corridor) | 4 | 2025-08-23 | 2025-08-27
R7S1ONAR-AP02FF83 | Painting - Final Coat (Ceiling + Walls) - AP#02 (FF Corridor) | 3 | 2025-09-25 | 2025-09-29
INSIDE BOXES |  | 44 | 2025-04-30 | 2025-05-13
R7S1ONAR-AP02FF86 | Fixing Thresholds (Joining the Room) - AP#02 (FF - inside Boxes) | 4 | 2025-04-30 | 2025-05-04
R7S1ONAR-AP02FF87 | Fixing Wooden Doors - AP#02 (FF - inside Boxes) | 4 | 2025-05-05 | 2025-05-08
R7S1ONAR-AP02FF88 | Fixing Aluminium Doors (Next Floor) - AP#02 (FF - inside Boxes) | 4 | 2025-05-10 | 2025-05-13
IN FRONT OF LIFT SHAFT |  | 47 | 2025-08-24 | 2025-09-20
R7S1ONAR-AP02FF90 | Flooring - AP#02 (FF - Front of Lift Shaft) | 4 | 2025-08-24 | 2025-08-28
R7S1ONAR-AP02FF91 | Skirting & Thresholds - AP#02 (FF - Front of Lift Shaft) | 1 | 2025-08-27 | 2025-08-28
R7S1ONAR-AP02FF92 | Painting - Surface Prep., Primer & 1st Coat - AP#02 (FF - Front of Lift Shaft) | 4 | 2025-08-28 | 2025-09-02
R7S1ONAR-AP02FF89 | False Ceiling - 1st Fix - AP#02 (FF - Front of Lift Shaft) | 4 | 2025-09-02 | 2025-09-07
R7S1ONAR-AP02FF93 | False Ceiling - Final Fix - AP#02 (FF - Front of Lift Shaft) | 3 | 2025-09-07 | 2025-09-10
R7S1ONAR-AP02FF95 | Fixing Handrail - AP#02 (FF - Front of Lift Shaft) | 3 | 2025-09-07 | 2025-09-10
R7S1ONAR-AP02FF96 | Paint for Handrail - AP#02 (FF - Front of Lift Shaft) | 3 | 2025-09-10 | 2025-09-14
R7S1ONAR-AP02FF94 | Painting - 2nd Coat - AP#02 (FF - Front of Lift Shaft) | 3 | 2025-09-14 | 2025-09-17
R7S1ONAR-AP02FF97 | Fixing Floor Mat - AP#02 (FF - Front of Lift Shaft) | 2 | 2025-09-17 | 2025-09-20
R7S1ONAR-AP02FF98 | Fixing Wall Guard - AP#02 (FF - Front of Lift Shaft) | 2 | 2025-09-17 | 2025-09-20
GARBAGE ROOM |  | 13 | 2025-07-12 | 2025-07-22
R7S1ONAR-AP02FF99 | Installation of Dry Walls - First Fix - AP#02 (FF - Garbage Room) | 2 | 2025-07-12 | 2025-07-13
R7S1ONAR-AP02FF100 | Installation of Dry Walls - Final Fix - AP#02 (FF - Garbage Room) | 2 | 2025-07-13 | 2025-07-14
R7S1ONAR-AP02FF101 | Garbage Rooms - Wall Tile Finishes (One Side) - AP#02 (FF - Garbage Room) | 2 | 2025-07-14 | 2025-07-15
R7S1ONAR-AP02FF102 | Paint Works of Dry Walls - First Coat - AP#02 (FF - Garbage Room) | 2 | 2025-07-16 | 2025-07-17
R7S1ONAR-AP02FF103 | Installation of the Garbage Chute Door - AP#02 (FF - Garbage Room) | 2 | 2025-07-19 | 2025-07-20
R7S1ONAR-AP02FF104 | Paint Finishes and Touchups - Final Coat - AP#02 (FF - Garbage Room) | 2 | 2025-07-21 | 2025-07-22
BALCONIES |  | 108 | 2025-05-01 | 2025-09-28
R7S1ONAR-AP02FF105 | Wetarea Waterproofing - AP#02 (FF - Balconies) | 8 | 2025-05-01 | 2025-05-10
R7S1ONAR-AP02FF106 | Flooring - AP#02 (FF - Balconies) | 6 | 2025-05-06 | 2025-05-12
R7S1ONAR-AP02FF107 | Painting - Surface Prep., Primer & 1st Coat - AP#02 (FF - Balconies) | 8 | 2025-05-08 | 2025-05-17
R7S1ONAR-AP02FF109 | Fixing Handrail - AP#02 (FF - Balconies) | 6 | 2025-09-10 | 2025-09-17
R7S1ONAR-AP02FF110 | Paint for Handrail - AP#02 (FF - Balconies) | 4 | 2025-09-17 | 2025-09-22
R7S1ONAR-AP02FF108 | Painting - 2nd Coat - AP#02 (FF - Balconies) | 4 | 2025-09-22 | 2025-09-28
MEP WORKS |  | 126 | 2025-03-24 | 2025-08-28
MECHANICAL |  | 125 | 2025-03-24 | 2025-08-26
CHILLED WATER |  | 57 | 2025-03-24 | 2025-05-14
R7S1ONME-AP02FF69 | Installation of CHWP piping (connection between modular cages & modular to apartment) - AP#02 -(FF Corridor) | 12 | 2025-03-29 | 2025-04-16
R7S1ONME-AP02FF68 | Installation of Chilled water hanger and supports - AP#02 (FF Corridor) | 18 | 2025-03-24 | 2025-04-19
R7S1ONME-AP02FF118 | Installation of CHWP connection for FCU with Valve package in Corridor, Electrical Room & ICT Room | 11 | 2025-04-15 | 2025-04-27
R7S1ONME-AP02FF70 | Installation of BTU Meter with valves - AP#02 (FF Corridor) | 2 | 2025-04-26 | 2025-04-27
R7S1ONME-AP02FF71 | CHWP piping risers connections - AP#02 (FF Corridor) | 5 | 2025-04-22 | 2025-04-27
R7S1ONME-AP02FF72 | Pressure Testing of CHWP piping - AP#02 (FF Corridor) | 1 | 2025-04-28 | 2025-04-28
R7S1ONME-AP02FF496 | CHWP Installation/Connections and Insulation (In Front of Lift Shaft) - AP#02 | 4 | 2025-05-10 | 2025-05-13
R7S1ONME-AP02FF107 | CHWP Insulation - AP#02 (FF Corridor) | 4 | 2025-05-10 | 2025-05-14
HVAC DUCTING |  | 104 | 2025-03-24 | 2025-08-25
R7S1ONME-AP02FF73 | Duct Riser Continuation - AP#02 (FF Corridor) | 29 | 2025-03-24 | 2025-04-30
R7S1ONME-AP02FF119 | Installation of FCU's & Duct Connection in Corridor, Electrical Room & ICT Room - AP#02 (FF Corridor) | 19 | 2025-04-10 | 2025-05-01
R7S1ONME-AP02FF120 | Installation of Ducting and insulation (connection between modular cages) - AP#02 (FF Corridor) | 19 | 2025-04-10 | 2025-05-01
R7S1ONME-AP02FF74 | A/C drain & Copper pipe connection in ELV room - AP#02 (FF Corridor) | 2 | 2025-04-30 | 2025-05-03
R7S1ONME-AP02FF108 | Installation of Duct & Grill in Garbage Room - AP#02 (FF Corridor) | 10 | 2025-04-22 | 2025-05-03
R7S1ONME-AP02FF121 | Installation of Grilles in the Corridor - AP#02 (FF Corridor) | 2 | 2025-08-23 | 2025-08-25
FIRE FIGHTING |  | 112 | 2025-04-13 | 2025-08-26
R7S1ONME-AP02FF75 | Riser Continuity in corridor - AP#02 (FF Corridor) | 11 | 2025-04-13 | 2025-04-24
R7S1ONME-AP02FF76 | Continuation of FF pipes & ZC Valves (connection between modular cages & modular to apartment) - AP#02 (FF Corridor) | 12 | 2025-04-15 | 2025-04-29
R7S1ONME-AP02FF77 | Installation of Sprinklers drops in corridor - AP#02 (FF Corridor) | 4 | 2025-05-06 | 2025-05-10
R7S1ONME-AP02FF78 | Pressure Test for FF Piping in corridor - AP#02 (FF Corridor) | 4 | 2025-05-11 | 2025-05-14
R7S1ONME-AP02FF836 | Installation of F.F Pipes, Testing & Final Fixtures (In Front of Lift Shaft) - AP#02 | 3 | 2025-05-14 | 2025-05-17
R7S1ONME-AP02FF122 | FF Flushing network - AP#02 (FF Corridor) | 2 | 2025-05-15 | 2025-05-18
R7S1ONME-AP02FF109 | Installation of Pipe & sprinkler in Garbage Room - AP#02 (FF Corridor) | 64 | 2025-04-19 | 2025-07-06
R7S1ONME-AP02FF79 | Installation of Sprinklers in corridor - AP#02 (FF Corridor) | 3 | 2025-08-23 | 2025-08-26
R7S1ONME-AP02FF80 | Installation of Alarm check valve, Fire Extinguishers & Blanket (Last Stage of the Building) - AP#02 (FF Corridor) | 3 | 2025-08-23 | 2025-08-26
WATER SUPPLY |  | 47 | 2025-03-24 | 2025-05-22
R7S1ONME-AP02FF110 | Installation of WS Pipe in Garbage Room - AP#02 (FF Corridor) | 18 | 2025-03-24 | 2025-04-19
R7S1ONME-AP02FF111 | Installation of Sanitary Fixtures in Janitor Room - AP#02 (FF Corridor) | 18 | 2025-03-24 | 2025-04-19
R7S1ONME-AP02FF81 | Riser Continuity in Shafts - AP#02 (FF Corridor) | 6 | 2025-04-19 | 2025-04-24
R7S1ONME-AP02FF82 | WS High Level Pipe continuation & Insulation works in Corridor - AP#02 (FF Corridor) | 22 | 2025-04-05 | 2025-04-29
R7S1ONME-AP02FF83 | Installation of Cold, Hot water line & Hot water return in corridor - AP#02 (FF Corridor) | 15 | 2025-04-13 | 2025-04-29
R7S1ONME-AP02FF84 | Water Meter Installation in Corridor - AP#02 (FF Corridor) | 2 | 2025-04-29 | 2025-05-01
R7S1ONME-AP02FF85 | Pressure Test for WS - AP#02 (FF Corridor) | 2 | 2025-05-19 | 2025-05-20
R7S1ONME-AP02FF123 | Insulation for Hot water line & Hot water return in corridor - AP#02 (FF Corridor) | 28 | 2025-04-21 | 2025-05-22
DRAINAGE |  | 45 | 2025-03-24 | 2025-05-20
R7S1ONME-AP02FF86 | Installation of Clean-outs, Floor drain in balcony - AP#02 (FF Corridor) | 19 | 2025-03-24 | 2025-04-20
R7S1ONME-AP02FF87 | Rain Water Riser continuation in Shafts - AP#02 (FF Corridor) | 2 | 2025-04-26 | 2025-04-27
R7S1ONME-AP02FF88 | Drainage Riser continuation in Shafts - AP#02 (FF Corridor) | 2 | 2025-04-26 | 2025-04-27
R7S1ONME-AP02FF89 | Testing for Rain Water Riser - AP#02 (FF Corridor) | 2 | 2025-05-19 | 2025-05-20
R7S1ONME-AP02FF90 | Testing for Drainage Riser - AP#02 (FF Corridor) | 2 | 2025-05-19 | 2025-05-20
ELECTRICAL |  | 126 | 2025-03-24 | 2025-08-28
POWER & LIGHTING |  | 125 | 2025-03-24 | 2025-08-28
R7S1ONME-AP02FF91 | Contiuation of Cable Trays & apartment branches - AP#02 (FF Corridor) | 4 | 2025-03-24 | 2025-03-27
R7S1ONME-AP02FF92 | Contiuation of Cable Trunking with Flexible conduits for Lights - AP#02 (FF Corridor) | 3 | 2025-03-25 | 2025-03-27
R7S1ONME-AP02FF93 | Installation of EMT pipes - AP#02 (FF Corridor) | 2 | 2025-03-27 | 2025-03-29
R7S1ONME-AP02FF94 | Installation of Busbar, Electrical Meter & Tap-off - AP#02 (FF Corridor) | 3 | 2025-05-12 | 2025-05-14
R7S1ONME-AP02FF95 | Corridor Wire Pulling - AP#02 (FF Corridor) | 37 | 2025-03-30 | 2025-05-15
R7S1ONME-AP02FF96 | Electrical Room - Installation of Cable trays, SMDB & Termination - AP#02 (FF Corridor) | 28 | 2025-04-14 | 2025-05-15
R7S1ONME-AP02FF117 | Termination of Tap-off with Electrical Meter in the apartments - AP#02 (FF Corridor) | 3 | 2025-05-15 | 2025-05-18
R7S1ONME-AP02FF1026 | Continuation of Cable Tray/Trunking with Flexible conduits for Lights (In Front of Lift Shaft) - AP#02 | 4 | 2025-05-18 | 2025-05-21
R7S1ONME-AP02FF98 | Installation, Termination of Emergeny & Exit Lights with contiuity - AP#02 (FF Corridor) | 2 | 2025-08-23 | 2025-08-25
R7S1ONME-AP02FF97 | Installation, Termination of Light Fixtures with continuity test - AP#02 (FF - Corridor & Balconies) | 3 | 2025-08-23 | 2025-08-26
R7S1ONME-AP02FF99 | Installation, Termination of PIR sensors with continuity test - AP#02 (FF Corridor) | 2 | 2025-08-26 | 2025-08-28
LOW CURRENT SYSTEM |  | 126 | 2025-03-24 | 2025-08-27
R7S1ONME-AP02FF100 | Installation of Basket trays for BMS, CCTV, Access Control - AP#02 (FF Corridor) | 4 | 2025-03-24 | 2025-03-27
R7S1ONME-AP02FF124 | CBS System cable installation - AP#02 (FF Corridor) | 2 | 2025-03-26 | 2025-03-27
R7S1ONME-AP02FF101 | Voice Evacuation cable installation - AP#02 (FF Corridor) | 1 | 2025-03-29 | 2025-03-29
R7S1ONME-AP02FF102 | Fire alarm cable installation - AP#02 (FF Corridor) | 1 | 2025-03-29 | 2025-03-29
R7S1ONME-AP02FF104 | BMS, CCTV & Access control Cable installation - AP#02 (FF Corridor) | 13 | 2025-04-10 | 2025-04-24
R7S1ONME-AP02FF1206 | Installation of Basket trays for Low Current, Cable Installation (In Front of Lift Shaft) - AP#02 | 4 | 2025-05-22 | 2025-05-26
R7S1ONME-AP02FF105 | Low Current Works including BMS Panel in ICT Room - AP#02 (FF Corridor) | 10 | 2025-05-18 | 2025-05-28
R7S1ONME-AP02FF103 | Fibre optic Cable pulling & Termination with OTO (in corridors to ONU) - AP#02 (FF Corridor) | 2 | 2025-05-29 | 2025-05-31
R7S1ONME-AP02FF116 | Fluke test for CCTV & Fibre Optic Cable - AP#02 (FF Corridor) | 2 | 2025-05-29 | 2025-05-31
R7S1ONME-AP02FF112 | Installation & Termination of CCTV Cameras - AP#02 (FF Corridor) | 2 | 2025-08-23 | 2025-08-25
R7S1ONME-AP02FF113 | Installation & Termination of Access control system for Electrical Room - AP#02 (FF Corridor) | 2 | 2025-08-23 | 2025-08-25
R7S1ONME-AP02FF115 | Installation & Termination of Wireless Gateway & RF Node - AP#02 (FF Corridor) | 2 | 2025-08-23 | 2025-08-25
R7S1ONME-AP02FF106 | Installation & Termination of Fire alarm devices & Speakers - AP#02 (FF Corridor) | 4 | 2025-08-23 | 2025-08-27
R7S1ONME-AP02FF114 | Installation & Termination of Active Components & UPS installation in ICT Room | 2 | 2025-08-25 | 2025-08-27
SECOND FLOOR |  | 130 | 2025-04-30 | 2025-09-30
ARCH./ CIVIL WORKS |  | 130 | 2025-04-30 | 2025-09-30
CORRIDOR AREA |  | 93 | 2025-04-30 | 2025-09-30
R7S1ONAR-AP02SF43 | Flooring in Corridor - AP#02 (SF Corridor) | 4 | 2025-04-30 | 2025-05-05
R7S1ONAR-AP02SF44 | Corridor Skirting - AP#02 (SF Corridor) | 2 | 2025-05-04 | 2025-05-06
R7S1ONAR-AP02SF41 | False Ceiling - 1st Fix - AP#02 (SF Corridor) | 4 | 2025-05-06 | 2025-05-11
R7S1ONAR-AP02SF42 | Gypsum Wall Cladding (Shafts) - AP#02 (SF Corridor) | 2 | 2025-07-17 | 2025-07-19
R7S1ONAR-AP02SF45 | Gypsum Wall Cladding (Shafts) -2nd Fix - AP#02 (SF Corridor) | 3 | 2025-07-20 | 2025-07-22
R7S1ONAR-AP02SF49 | Fixing Architrave - AP#02 (SF Corridor) | 1 | 2025-07-23 | 2025-07-23
R7S1ONAR-AP02SF50 | Fixing Aluminium Doors - AP#02 (SF Corridor) | 1 | 2025-07-24 | 2025-07-24
R7S1ONAR-AP02SF46 | False Ceiling - 2nd Fix (Closing the Ceiling) - AP#02 (SF Corridor) | 2 | 2025-07-26 | 2025-07-27
R7S1ONAR-AP02SF47 | Painting - Surface Prep., Primer & 1st Coat - AP#02 (SF Corridor) | 5 | 2025-07-23 | 2025-07-28
R7S1ONAR-AP02SF71 | Painting - Surface Prep., Primer & 1st Coat - AP#02 (SF Corridor) | 4 | 2025-07-28 | 2025-07-31
R7S1ONAR-AP02SF48 | Painting - Final Coat (Ceiling + Walls) - AP#02 (SF Corridor) | 3 | 2025-09-27 | 2025-09-30
INSIDE BOXES |  | 12 | 2025-05-05 | 2025-05-14
R7S1ONAR-AP02SF51 | Fixing Thresholds (Joining the Room) - AP#02 (SF - inside Boxes) | 4 | 2025-05-05 | 2025-05-10
R7S1ONAR-AP02SF52 | Fixing Wooden Doors - AP#02 (SF - inside Boxes) | 2 | 2025-05-10 | 2025-05-12
R7S1ONAR-AP02SF53 | Fixing Aluminium Doors (Next Floor) - AP#02 (SF - inside Boxes) | 2 | 2025-05-12 | 2025-05-14
IN FRONT OF LIFT SHAFT |  | 73 | 2025-07-29 | 2025-09-18
R7S1ONAR-AP02SF54 | False Ceiling - 1st Fix - AP#02 (SF - Front of Lift Shaft) | 3 | 2025-07-29 | 2025-07-31
R7S1ONAR-AP02SF55 | Flooring - AP#02 (SF - Front of Lift Shaft) | 4 | 2025-08-02 | 2025-08-05
R7S1ONAR-AP02SF56 | Skirting & Thresholds - AP#02 (SF - Front of Lift Shaft) | 2 | 2025-08-06 | 2025-08-07
R7S1ONAR-AP02SF57 | Painting - Surface Prep., Primer & 1st Coat - AP#02 (SF - Front of Lift Shaft) | 2 | 2025-08-09 | 2025-08-10
R7S1ONAR-AP02SF58 | False Ceiling - Final Fix - AP#02 (SF - Front of Lift Shaft) | 1 | 2025-08-11 | 2025-08-11
R7S1ONAR-AP02SF60 | Fixing Handrail - AP#02 (SF - Front of Lift Shaft) | 3 | 2025-09-10 | 2025-09-14
R7S1ONAR-AP02SF61 | Paint for Handrail - AP#02 (SF - Front of Lift Shaft) | 1 | 2025-09-14 | 2025-09-15
R7S1ONAR-AP02SF59 | Painting - 2nd Coat - AP#02 (SF - Front of Lift Shaft) | 1 | 2025-09-15 | 2025-09-16
R7S1ONAR-AP02SF62 | Fixing Floor Mat - AP#02 (SF - Front of Lift Shaft) | 2 | 2025-09-16 | 2025-09-18
R7S1ONAR-AP02SF63 | Fixing Wall Guard - AP#02 (SF - Front of Lift Shaft) | 2 | 2025-09-16 | 2025-09-18
GARBAGE ROOM |  | 38 | 2025-06-25 | 2025-07-30
R7S1ONAR-AP02SF70 | Installation of Garbage Chute Full System from GF to 2nd Floor - AP#02 (SF - Garbage Room) | 10 | 2025-06-25 | 2025-07-06
R7S1ONAR-AP02SF64 | Installation of Dry Walls - First Fix - AP#02 (SF - Garbage Room) | 2 | 2025-07-07 | 2025-07-08
R7S1ONAR-AP02SF65 | Installation of Dry Walls - Final Fix - AP#02 (SF - Garbage Room) | 2 | 2025-07-09 | 2025-07-10
R7S1ONAR-AP02SF66 | Garbage Rooms - Wall Tile Finishes (One Side) - AP#02 (SF - Garbage Room) | 2 | 2025-07-10 | 2025-07-12
R7S1ONAR-AP02SF67 | Paint Works of Dry Walls - First Coat - AP#02 (SF - Garbage Room) | 2 | 2025-07-13 | 2025-07-14
R7S1ONAR-AP02SF68 | Installation of the Garbage Chute Door - AP#02 (SF - Garbage Room) | 2 | 2025-07-15 | 2025-07-16
R7S1ONAR-AP02SF69 | Paint Finishes and Touchups - Final Coat - AP#02 (SF - Garbage Room) | 2 | 2025-07-29 | 2025-07-30
BALCONIES |  | 107 | 2025-05-05 | 2025-09-28
R7S1ONAR-AP02FF111 | Wetarea Waterproofing - AP#02 (SF - Balconies) | 8 | 2025-05-05 | 2025-05-14
R7S1ONAR-AP02FF112 | Flooring - AP#02 (SF - Balconies) | 6 | 2025-05-10 | 2025-05-17
R7S1ONAR-AP02FF113 | Painting - Surface Prep., Primer & 1st Coat - AP#02 (SF - Balconies) | 8 | 2025-05-12 | 2025-05-21
R7S1ONAR-AP02FF115 | Fixing Handrail - AP#02 (SF - Balconies) | 6 | 2025-09-14 | 2025-09-21
R7S1ONAR-AP02FF116 | Paint for Handrail - AP#02 (SF - Balconies) | 4 | 2025-09-21 | 2025-09-27
R7S1ONAR-AP02FF114 | Painting - 2nd Coat - AP#02 (SF - Balconies) | 4 | 2025-09-22 | 2025-09-28
MEP WORKS |  | 77 | 2025-05-05 | 2025-08-31
MECHANICAL |  | 77 | 2025-05-05 | 2025-08-28
CHILLED WATER |  | 30 | 2025-05-05 | 2025-05-20
R7S1ONME-AP02SF56 | Installation of Chilled water hanger and supports - AP#02 (SF Corridor) | 3 | 2025-05-05 | 2025-05-07
R7S1ONME-AP02SF106 | Installation of CHWP connection for FCU with Valve package in Corridor, Electrical Room & ICT Room | 3 | 2025-05-05 | 2025-05-07
R7S1ONME-AP02SF57 | Installation of CHWP piping (connection between modular cages & modular to apartment) - AP#02 (SF Corridor) | 3 | 2025-05-08 | 2025-05-11
R7S1ONME-AP02SF58 | Installation of BTU Meter with valves - AP#02 (SF Corridor) | 2 | 2025-05-10 | 2025-05-11
R7S1ONME-AP02SF59 | CHWP piping risers connections - AP#02 (SF Corridor) | 3 | 2025-05-12 | 2025-05-14
R7S1ONME-AP02SF60 | Pressure Testing of CHWP piping - AP#02 (SF Corridor) | 1 | 2025-05-15 | 2025-05-15
R7S1ONME-AP02SF506 | CHWP Installation/Connections and Insulation (In Front of Lift Shaft) - AP#02 | 4 | 2025-05-14 | 2025-05-18
R7S1ONME-AP02SF95 | CHWP Insulation - AP#02 (SF Corridor) | 4 | 2025-05-17 | 2025-05-20
HVAC DUCTING |  | 69 | 2025-05-05 | 2025-07-28
R7S1ONME-AP02SF61 | Duct Riser Continuation - AP#02 (SF Corridor) | 3 | 2025-05-05 | 2025-05-07
R7S1ONME-AP02SF107 | Installation of FCU's & Duct Connection in Corridor, Electrical Room & ICT Room - AP#02 (SF Corridor) | 3 | 2025-05-05 | 2025-05-07
R7S1ONME-AP02SF62 | A/C drain & Copper pipe connection in ELV room - AP#02 (SF Corridor) | 1 | 2025-05-08 | 2025-05-08
R7S1ONME-AP02SF108 | Installation of Ducting and insulation (connection between modular cages) - AP#02 (SF Corridor) | 3 | 2025-05-08 | 2025-05-11
R7S1ONME-AP02SF96 | Installation of Duct & Grill in Garbage Room - AP#02 (SF Corridor) | 1 | 2025-07-28 | 2025-07-28
R7S1ONME-AP02SF109 | Installation of Grilles in the Corridor - AP#02 (SF Corridor) | 1 | 2025-07-28 | 2025-07-28
FIRE FIGHTING |  | 77 | 2025-05-05 | 2025-08-28
R7S1ONME-AP02SF63 | Riser Continuity Succ - Closing of Gysum Boards on shaft - AP#02 (SF Corridor) | 2 | 2025-05-05 | 2025-05-06
R7S1ONME-AP02SF64 | FF Contiuation on High Level with Valves - AP#02 (SF Corridor) | 2 | 2025-05-05 | 2025-05-06
R7S1ONME-AP02SF65 | Installation of Sprinklers drops - AP#02 (SF Corridor) | 2 | 2025-05-11 | 2025-05-13
R7S1ONME-AP02SF66 | Pressure Test for FF Piping - AP#02 (SF Corridor) | 2 | 2025-05-13 | 2025-05-15
R7S1ONME-AP02SF856 | Installation of F.F Pipes, Testing & Final Fixtures (In Front of Lift Shaft) - AP#02 | 3 | 2025-05-19 | 2025-05-21
R7S1ONME-AP02SF97 | Installation of Pipe & sprinkler in Garbage Room - AP#02 (SF Corridor) | 1 | 2025-07-28 | 2025-07-28
R7S1ONME-AP02SF67 | Installation of Sprinklers - AP#02 (SF Corridor) | 2 | 2025-07-28 | 2025-07-29
R7S1ONME-AP02SF68 | Installation of Fire Extinguishers - AP#02 (SF Corridor) | 2 | 2025-08-26 | 2025-08-28
WATER SUPPLY |  | 18 | 2025-05-05 | 2025-05-25
R7S1ONME-AP02SF98 | Installation of WS Pipe in Garbage Room - AP#02 (SF Corridor) | 1 | 2025-05-05 | 2025-05-05
R7S1ONME-AP02SF99 | Installation of Sanitary Fixtures in Janitor Room - AP#02 (SF Corridor) | 1 | 2025-05-05 | 2025-05-05
R7S1ONME-AP02SF69 | Riser Continuity - AP#02 (SF Corridor) | 2 | 2025-05-05 | 2025-05-06
R7S1ONME-AP02SF70 | WS High Level Pipe continuation & Insulation works - AP#02 (SF Corridor) | 2 | 2025-05-05 | 2025-05-06
R7S1ONME-AP02SF71 | Instalation of Hot water line in corridor - AP#02 (SF Corridor) | 2 | 2025-05-07 | 2025-05-08
R7S1ONME-AP02SF72 | Water Meter Installation - AP#02 (SF Corridor) | 2 | 2025-05-10 | 2025-05-11
R7S1ONME-AP02SF73 | Pressure Test for WS - AP#02 (SF Corridor) | 2 | 2025-05-21 | 2025-05-22
R7S1ONME-AP02FF125 | Insulation for Hot water line & Hot water return in corridor - AP#02 (SF Corridor) | 2 | 2025-05-24 | 2025-05-25
DRAINAGE |  | 14 | 2025-05-05 | 2025-05-20
R7S1ONME-AP02SF74 | Installation of Clean-outs - AP#02 (SF Corridor) | 2 | 2025-05-05 | 2025-05-06
R7S1ONME-AP02SF75 | Rain Water Riser continuation - AP#02 (SF Corridor) | 2 | 2025-05-05 | 2025-05-06
R7S1ONME-AP02SF76 | Drainage Riser continuation - AP#02 (SF Corridor) | 2 | 2025-05-05 | 2025-05-06
R7S1ONME-AP02SF77 | Testing for Rain Water Riser - AP#02 (SF Corridor) | 2 | 2025-05-19 | 2025-05-20
R7S1ONME-AP02SF78 | Testing for Drainage Riser - AP#02 (SF Corridor) | 2 | 2025-05-19 | 2025-05-20
ELECTRICAL |  | 72 | 2025-05-05 | 2025-08-31
POWER & LIGHTING |  | 71 | 2025-05-05 | 2025-08-31
R7S1ONME-AP02SF79 | Contiuation of Cable Trays & apartment branches - AP#02 (SF Corridor) | 4 | 2025-05-05 | 2025-05-08
R7S1ONME-AP02SF80 | Contiuation of Cable Trunking with Flexible conduits for Lights - AP#02 (SF Corridor) | 4 | 2025-05-05 | 2025-05-08
R7S1ONME-AP02SF81 | Installation of EMT pipes - AP#02 (SF Corridor) | 5 | 2025-05-05 | 2025-05-10
R7S1ONME-AP02SF82 | Installation of Busbar, Electrical Meter & Tap-off in Corridor - AP#02 (SF Corridor) | 3 | 2025-05-15 | 2025-05-18
R7S1ONME-AP02SF105 | Termination of Tap-off with Electrical Meter in the apartments - AP#02 (SF Corridor) | 3 | 2025-05-19 | 2025-05-21
R7S1ONME-AP02SF1036 | Continuation of Cable Tray/Trunking with Flexible conduits for Lights (In Front of Lift Shaft) - AP#02 | 4 | 2025-05-18 | 2025-05-21
R7S1ONME-AP02SF83 | Corridor Wire Pulling - AP#02 (SF Corridor) | 6 | 2025-05-17 | 2025-05-22
R7S1ONME-AP02SF84 | Electrical Room - Installation of Cable trays, SMDB & Termination - AP#02 (SF Corridor) | 6 | 2025-07-09 | 2025-07-15
R7S1ONME-AP02SF86 | Installation, Termination of Emergeny & Exit Lights with contiuity - AP#02 (SF Corridor) | 2 | 2025-07-28 | 2025-07-29
R7S1ONME-AP02SF85 | Installation, Termination of Light Fixtures with continuity test - AP#02 (SF - Corridor & Balconies) | 3 | 2025-07-28 | 2025-07-30
R7S1ONME-AP02SF87 | Installation, Termination of PIR sensors with continuity test - AP#02 (SF Corridor) | 2 | 2025-08-28 | 2025-08-31
LOW CURRENT SYSTEM |  | 72 | 2025-05-05 | 2025-07-31
R7S1ONME-AP02SF110 | CBS System cable installation - AP#02 (SF Corridor) | 3 | 2025-05-05 | 2025-05-07
R7S1ONME-AP02SF88 | Installation of Basket trays for BMS, CCTV, Access Control - AP#02 (SF Corridor) | 4 | 2025-05-05 | 2025-05-08
R7S1ONME-AP02SF90 | Fire alarm cable installation - AP#02 (SF Corridor) | 3 | 2025-05-06 | 2025-05-08
R7S1ONME-AP02SF89 | Voice Evacuation cable installation - AP#02 (SF Corridor) | 3 | 2025-05-08 | 2025-05-11
R7S1ONME-AP02SF92 | BMS, CCTV & Access control Cable installation - AP#02 (SF Corridor) | 2 | 2025-05-25 | 2025-05-26
R7S1ONME-AP02SF1216 | Installation of Basket trays for Low Current, Cable Installation (In Front of Lift Shaft) - AP#02 | 4 | 2025-05-27 | 2025-05-31
R7S1ONME-AP02SF93 | Low Current Works including BMS Panel in ICT Room - AP#02 (SF Corridor) | 10 | 2025-07-03 | 2025-07-14
R7S1ONME-AP02SF104 | Fluke test for CCTV & Fibre Optic Cable - AP#02 (SF Corridor) | 2 | 2025-07-13 | 2025-07-14
R7S1ONME-AP02SF91 | Fibre optic Cable pulling & Termination with OTO (in corridors to ONU) - AP#02 (SF Corridor) | 2 | 2025-07-15 | 2025-07-16
R7S1ONME-AP02SF100 | Installation & Termination of CCTV Cameras - AP#02 (SF Corridor) | 2 | 2025-07-28 | 2025-07-29
R7S1ONME-AP02SF101 | Installation & Termination of Access control system for Electrical Room - AP#02 (SF Corridor) | 2 | 2025-07-28 | 2025-07-29
R7S1ONME-AP02SF103 | Installation & Termination of Wireless Gateway & RF Node in corridors - AP#02 (SF Corridor) | 2 | 2025-07-28 | 2025-07-29
R7S1ONME-AP02SF94 | Installation & Termination of Fire alarm devices & Speakers - AP#02 (SF Corridor) | 4 | 2025-07-28 | 2025-07-31
R7S1ONME-AP02SF102 | Installation & Termination of Active Components & UPS installation in ICT Room - AP#02 (SF Corridor) | 2 | 2025-07-30 | 2025-07-31
ROOF WORKS |  | 96 | 2025-05-19 | 2025-08-27
ARCH./ CIVIL WORKS |  | 96 | 2025-05-19 | 2025-08-27
R7S1ONAR-AP02RF11 | Roof Box Stiching (Concrete Works) - AP#02 (Roof) | 6 | 2025-05-19 | 2025-05-25
R7S1ONME-AP02RF116 | Installation of Roof Drains - AP#02 (Roof) | 2 | 2025-05-24 | 2025-05-25
R7S1ONAR-AP02RF12 | Roof Waterproofing Works with testing - AP#02 (Roof) | 20 | 2025-06-03 | 2025-06-30
R7S1ONAR-AP02RF13 | Laying of Gravel - AP#02 (Roof) | 2 | 2025-07-01 | 2025-07-02
R7S1ONAR-AP02RF14 | Surface Preparation & Primer for Parapets - AP#02 (Roof) | 6 | 2025-07-21 | 2025-07-27
R7S1ONAR-AP02RF15 | 1st Coat Paint for Parapets - AP#02 (Roof) | 2 | 2025-07-28 | 2025-07-29
R7S1ONAR-AP02RF16 | 2nd Coat Paint for Parapets - AP#02 (Roof) | 2 | 2025-07-30 | 2025-07-31
R7S1ONAR-AP02RF18 | Fixing Fall Arrest System - AP#02 (Roof) | 2 | 2025-08-02 | 2025-08-03
R7S1ONAR-AP02RF17 | Crossover Bridges Installation & application of Sealant on MEP penetrations - AP#02 (Roof) | 12 | 2025-08-14 | 2025-08-27
MECHANICAL |  | 58 | 2025-07-03 | 2025-07-26
HVAC |  | 31 | 2025-07-03 | 2025-07-19
R7S1ONME-AP02RF80 | Modular Installation - AP#02 (Roof) | 5 | 2025-07-03 | 2025-07-08
R7S1ONME-AP02RF81 | Continuation of Roof duct works/FAHU Connections - AP#02 (Roof) | 5 | 2025-07-06 | 2025-07-10
R7S1ONME-AP02RF83 | Insulations for ducts - AP#02 (Roof) | 5 | 2025-07-07 | 2025-07-12
R7S1ONME-AP02RF85 | Installation of FAHU - AP#02 (Roof) | 2 | 2025-07-12 | 2025-07-13
R7S1ONME-AP02RF90 | Installation of Outdoor VRF/DX Units - AP#02 (Roof) | 2 | 2025-07-13 | 2025-07-14
R7S1ONME-AP02RF91 | Installation & Insulation of the Condensation Drain - AP#02 (Roof) | 1 | 2025-07-14 | 2025-07-14
R7S1ONME-AP02RF93 | Installation of Ventilation Fans - AP#02 (Roof) | 3 | 2025-07-12 | 2025-07-14
R7S1ONME-AP02RF88 | Chilled Water System Continuation and Connections with Valve package of FAHU - AP#02 (Roof) | 4 | 2025-07-12 | 2025-07-15
R7S1ONME-AP02RF95 | Installation of Louvers - AP#02 (Roof) | 2 | 2025-07-15 | 2025-07-16
R7S1ONME-AP02RF98 | Installation & Testing of Copper Pipes - AP#02 (Roof) | 2 | 2025-07-15 | 2025-07-16
R7S1ONME-AP02RF99 | Miscellaneous Works for Mechanical Connections (Fire & Volume Dampers etc.) - AP#02 (Roof) | 2 | 2025-07-17 | 2025-07-19
WATERSUPPLY & DRAINAGE |  | 42 | 2025-07-09 | 2025-07-24
R7S1ONME-AP02RF79 | Testing for the Rain Water Risers - AP#02 (Roof) | 2 | 2025-07-12 | 2025-07-13
R7S1ONME-AP02RF82 | Installation & Continuation of Water supply pipes (connection between modular cages & modular to Shaft Riser) - AP#02 | 4 | 2025-07-09 | 2025-07-13
R7S1ONME-AP02RF86 | Installation of Air Vent & Pressure Guage with Valves at Roof - AP#02 (Roof) | 4 | 2025-07-12 | 2025-07-15
R7S1ONME-AP02RF87 | Vertical Continuation of Vent Pipes To The Roof (Drainage) - AP#02 (Roof) | 4 | 2025-07-13 | 2025-07-16
R7S1ONME-AP02RF89 | Installation of Rain Water outlet - AP#02 (Roof) | 3 | 2025-07-14 | 2025-07-16
R7S1ONME-AP02RF84 | Installation of Air Vent with Valve for Water Supply - AP#02 (Roof) | 4 | 2025-07-14 | 2025-07-17
R7S1ONME-AP02RF92 | Testing of Water Supply Pipes - AP#02 (Roof) | 2 | 2025-07-19 | 2025-07-20
R7S1ONME-AP02RF94 | Insulation of Roof Water Line - AP#02 (Roof) | 2 | 2025-07-20 | 2025-07-21
R7S1ONME-AP02RF96 | Testing for the Drainage Pipes Risers - AP#02 (Roof) | 2 | 2025-07-22 | 2025-07-23
R7S1ONME-AP02RF97 | Installation of Vent Cowl - AP#02 (Roof) | 1 | 2025-07-24 | 2025-07-24
SOLAR HEATER |  | 49 | 2025-07-14 | 2025-07-26
R7S1ONME-AP02RF111 | Installation of Solar water pumps and circulation pumps with valves(For Water Only) - AP#02 (Roof) | 2 | 2025-07-15 | 2025-07-16
R7S1ONME-AP02RF109 | Installation of Structure and Solar Panels (For Water Only) - AP#02 (Roof) | 5 | 2025-07-14 | 2025-07-19
R7S1ONME-AP02RF110 | Installation of Solar Calorifier Tank & Air cooler (For Water Only) - AP#02 (Roof) | 5 | 2025-07-15 | 2025-07-20
R7S1ONME-AP02RF112 | Installation of Solar Pipes Primary Loop - AP#02 (Roof) | 5 | 2025-07-15 | 2025-07-20
R7S1ONME-AP02RF113 | Testing of Solar Pipes Primary Loop - AP#02 (Roof) | 1 | 2025-07-21 | 2025-07-21
R7S1ONME-AP02RF114 | Insulation of Solar Pipes Primary Loop - AP#02 (Roof) | 1 | 2025-07-21 | 2025-07-21
R7S1ONME-AP02RF115 | Aluminum Cladding of Solar Pipes Primary Loop - AP#02 (Roof) | 4 | 2025-07-22 | 2025-07-26
ELECTRICAL |  | 36 | 2025-07-09 | 2025-08-21
POWER & LOW CURRENT |  | 36 | 2025-07-09 | 2025-08-21
R7S1ONME-AP02RF100 | Installation of Cables for Fire Alarm system - AP#02 (Roof) | 3 | 2025-07-09 | 2025-07-12
R7S1ONME-AP02RF101 | Installation of Cables for BMS - AP#02 (Roof) | 3 | 2025-07-09 | 2025-07-12
R7S1ONME-AP02RF102 | Installation of Fire Alarm Devices - AP#02 (Roof) | 3 | 2025-07-09 | 2025-07-12
R7S1ONME-AP02RF104 | Installation of Roof Light Fixtures - AP#02 (Roof) | 3 | 2025-07-09 | 2025-07-12
R7S1ONME-AP02RF103 | Installation of BMS Devices - AP#02 (Roof) | 4 | 2025-07-10 | 2025-07-14
R7S1ONME-AP02RF76 | Installation of Electrical Containments for BMS - AP#02 (Roof) | 7 | 2025-07-09 | 2025-07-16
R7S1ONME-AP02RF106 | Termination for BMS System - AP#02 (Roof) | 1 | 2025-07-17 | 2025-07-17
R7S1ONME-AP02RF118 | Termination of Primary & Secondary pump for Solar system - AP#02 (Roof) | 1 | 2025-07-17 | 2025-07-17
R7S1ONME-AP02RF117 | Installation & Termination of Solar System Panel - AP#02 (Roof) | 3 | 2025-07-27 | 2025-07-29
R7S1ONME-AP02RF75 | Installation of Isolators and Machine Connections - AP#02 (Roof) | 4 | 2025-08-04 | 2025-08-07
R7S1ONME-AP02RF74 | Lightening Protection & Earthing System - AP#02 (Roof) | 7 | 2025-08-02 | 2025-08-09
R7S1ONME-AP02RF77 | Installation of Fire Alarm Containment for FAHU, Fans - AP#02 (Roof) | 4 | 2025-08-10 | 2025-08-13
R7S1ONME-AP02RF107 | Termination for Fire Alarm Device - AP#02 (Roof) | 1 | 2025-08-14 | 2025-08-14
R7S1ONME-AP02RF78 | Installation of LV Power Cables for Roof Equipment - AP#02 (Roof) | 5 | 2025-08-14 | 2025-08-19
R7S1ONME-AP02RF105 | Termination for LV Cables - AP#02 (Roof) | 1 | 2025-08-20 | 2025-08-20
R7S1ONME-AP02RF108 | Megger Test for the Power Cables - AP#02 (Roof) | 1 | 2025-08-21 | 2025-08-21
STAIR CASE |  | 155 | 2025-04-21 | 2025-07-20
CIVIL WORKS |  | 125 | 2025-05-26 | 2025-07-15
STAIR CASE (MAIN WITH LIFT) |  | 113 | 2025-05-26 | 2025-06-26
R7S1ONST-AP02RG302 | Stair Flooring (Roof to GF) - AP#02 (Main Stair) | 7 | 2025-05-26 | 2025-06-02
R7S1ONST-AP02RG303 | Stair Hand Rails (Roof to GF) - AP#02 (Main Stair) | 6 | 2025-06-03 | 2025-06-14
R7S1ONST-AP02RG304 | Stair Paint - Primer & 1st Coat (Roof to GF)- AP#02 (Main Stair) | 7 | 2025-06-15 | 2025-06-22
R7S1ONST-AP02RG305 | Stair Paint - Final Coat (Roof to GF)- AP#02 (Main Stair) | 4 | 2025-06-23 | 2025-06-26
STAIR CASE (LEFT SIDE) |  | 113 | 2025-06-03 | 2025-07-02
R7S1ONST-AP02RG312 | Stair Flooring (Roof to GF) - AP#02 Left Side Stair | 7 | 2025-06-03 | 2025-06-15
R7S1ONST-AP02RG313 | Stair Hand Rails (Roof to GF) - AP#02 Left Side Stair | 6 | 2025-06-16 | 2025-06-22
R7S1ONST-AP02RG314 | Stair Paint - Primer & 1st Coat (Roof to GF) - AP#02 Left Side Stair | 6 | 2025-06-23 | 2025-06-29
R7S1ONST-AP02RG315 | Stair Paint - Final Coat (Roof to GF) - AP#02 Left Side Stair | 3 | 2025-06-30 | 2025-07-02
STAIR CASE (RIGHT SIDE) |  | 59 | 2025-06-16 | 2025-07-15
R7S1ONST-AP02RG316 | Stair Flooring (Roof to GF) - AP#02 Right Side Stair | 8 | 2025-06-16 | 2025-06-24
R7S1ONST-AP02RG317 | Stair Hand Rails (Roof to GF) - AP#02 Right Side Stair | 7 | 2025-06-25 | 2025-07-02
R7S1ONST-AP02RG318 | Stair Paint - Primer & 1st Coat (Roof to GF) - AP#02 Right Side Stair | 7 | 2025-07-03 | 2025-07-10
R7S1ONST-AP02RG319 | Stair Paint - Final Coat (Roof to GF) - AP#02 Right Side Stair | 4 | 2025-07-12 | 2025-07-15
MEP WORKS |  | 98 | 2025-04-21 | 2025-07-20
STAIR CASE (MAIN WITH LIFT) |  | 62 | 2025-05-19 | 2025-07-01
R7S1ONST-AP02RG301 | Main Staircase Wire Pulling - AP#02 (Main Stair) | 3 | 2025-05-19 | 2025-05-21
R7S1ONST-AP02RG320 | Final fix - Main Staircase Lights Fixtures & Motion Sensor - AP#02 (Main Stair) | 2 | 2025-06-28 | 2025-06-29
R7S1ONST-AP02RG321 | Final fix - Main Staircase Emergency Lights Fixtures - AP#02 (Main Stair) | 2 | 2025-06-30 | 2025-07-01
STAIR CASE (LEFT SIDE) |  | 92 | 2025-04-21 | 2025-07-07
R7S1ONST-AP02RG306 | Left Staircase Wire Pulling - AP#02 (Main Stair) | 27 | 2025-04-21 | 2025-05-22
R7S1ONST-AP02RG308 | Final fix - Left Staircase Lights Fixtures & Motion Sensor - AP#02 (Main Stair) | 2 | 2025-07-03 | 2025-07-05
R7S1ONST-AP02RG310 | Final fix - Left Staircase Emergency Lights Fixtures - AP#02 (Main Stair) | 2 | 2025-07-06 | 2025-07-07
STAIR CASE (RIGHT SIDE) |  | 98 | 2025-04-21 | 2025-07-20
R7S1ONST-AP02RG307 | Right Staircase Wire Pulling - AP#02 (Main Stair) | 27 | 2025-04-21 | 2025-05-22
R7S1ONST-AP02RG309 | Final fix - Right Staircase Lights Fixtures & Motion Sensor - AP#02 (Main Stair) | 2 | 2025-07-16 | 2025-07-17
R7S1ONST-AP02RG311 | Final fix - Right Staircase Emergency Lights Fixtures - AP#02 (Main Stair) | 2 | 2025-07-19 | 2025-07-20
ELEVATOR WORKS |  | 20 | 2025-06-01 | 2025-07-01
R7S1ONEL-AP02GR601 | Installation of Rails - AP#02 (Elevator Works) | 6 | 2025-06-01 | 2025-06-12
R7S1ONEL-AP02GR602 | Assembly of Cabin - AP#02 (Elevator Works) | 4 | 2025-06-12 | 2025-06-17
R7S1ONEL-AP02GR603 | Installation of Motor - AP#02 (Elevator Works) | 4 | 2025-06-17 | 2025-06-22
R7S1ONEL-AP02GR604 | Installation of Main Cables - AP#02 (Elevator Works) | 4 | 2025-06-22 | 2025-06-26
R7S1ONEL-AP02GR605 | Installation of Doors, Indicator, Push Button - AP#02 (Elevator Works) | 2 | 2025-06-26 | 2025-06-29
R7S1ONEL-AP02GR606 | Interior Finishes - AP#02 (Elevator Works) | 2 | 2025-06-29 | 2025-07-01
EXTERNAL ELEVATIONS |  | 79 | 2025-07-03 | 2025-08-21
ARCH./ CIVIL WORKS |  | 79 | 2025-07-03 | 2025-08-21
R7S1ONEE-AP02GR501 | External Selant Works - For Boxes - AP#02 (External Elevations) | 15 | 2025-07-03 | 2025-07-20
R7S1ONEE-AP02GR502 | Final Finishes & Touchups - AP#02 (External Elevations) | 20 | 2025-07-21 | 2025-08-12
R7S1ONME-AP02GF349 | Installation of rain water outlet - External façade - AP#02 (External Elevations) | 2 | 2025-08-13 | 2025-08-14
R7S1ONEE-AP02GR504 | Installation of External Signages - AP#02 (External Elevations) | 4 | 2025-08-16 | 2025-08-19
R7S1ONEE-AP02GR503 | Fixing Cage Ladder - AP#02 (External Elevations) | 2 | 2025-08-20 | 2025-08-21
EXTERNAL - CIVIL WORKS |  | 48 | 2025-05-29 | 2025-07-24
DRAINAGE |  | 23 | 2025-05-29 | 2025-06-16
R7S1ONECW-AP02-271 | Excavation Works & Sand Bedding - AP#02 (External Drainage) | 3 | 2025-05-29 | 2025-06-01
R7S1ONECW-AP02-272 | Drainage Manholes - AP#02 | 6 | 2025-05-29 | 2025-06-04
R7S1ONECW-AP02-273 | Drainage Backfilling - AP#02 | 2 | 2025-06-15 | 2025-06-16
WATERSUPPLY |  | 31 | 2025-06-02 | 2025-07-01
R7S1ONECW-AP02-274 | Excavation Works & Sand Bedding - Watersupply - AP#02 (External Watersupply Civil) | 3 | 2025-06-02 | 2025-06-04
R7S1ONECW-AP02-275 | Watersupply Manholes - AP#02 | 6 | 2025-06-10 | 2025-06-16
R7S1ONECW-AP02-276 | Watersupply Backfilling - AP#02 | 2 | 2025-06-30 | 2025-07-01
CHILLED WATER |  | 19 | 2025-06-10 | 2025-06-22
R7S1ONECW-AP02-280 | Excavation Works & Sand Bedding - AP#02 (External Chilled Water Civil) | 3 | 2025-06-10 | 2025-06-12
R7S1ONECW-AP02-281 | Chilled Water Manholes - AP#02 | 6 | 2025-06-14 | 2025-06-19
R7S1ONECW-AP02-282 | Chilled Water Backfilling - AP#02 | 2 | 2025-06-21 | 2025-06-22
FIRE FIGHTING |  | 22 | 2025-06-14 | 2025-07-01
R7S1ONECW-AP02-277 | Excavation Works & Sand Bedding - AP#02 (External Chilled Water Civil) | 3 | 2025-06-14 | 2025-06-16
R7S1ONECW-AP02-278 | Fire Fighting Manholes - AP#02 | 6 | 2025-06-17 | 2025-06-23
R7S1ONECW-AP02-279 | Fire Fighting Backfilling - AP#02 | 2 | 2025-06-30 | 2025-07-01
POWER |  | 25 | 2025-06-17 | 2025-07-24
R7S1ONECW-AP02-283 | Excavation Works & Sand Bedding - AP#02 (External Power Civil) | 3 | 2025-06-17 | 2025-06-19
R7S1ONECW-AP02-284 | Power Manholes - AP#02 | 3 | 2025-06-21 | 2025-06-23
R7S1ONECW-AP02-285 | Power Backfilling - AP#02 | 2 | 2025-07-23 | 2025-07-24
LOW CURRENT |  | 8 | 2025-06-21 | 2025-06-29
R7S1ONECW-AP02-286 | Excavation Works & Sand Bedding - AP#02 (External Low Current Civil) | 3 | 2025-06-21 | 2025-06-23
R7S1ONECW-AP02-287 | Low Current Manholes - AP#02 | 3 | 2025-06-24 | 2025-06-26
R7S1ONECW-AP02-288 | Low Current Backfilling - AP#02 | 2 | 2025-06-28 | 2025-06-29
EXTERNAL - MEP SERVICES |  | 44 | 2025-06-10 | 2025-07-22
DRAINAGE |  | 4 | 2025-06-10 | 2025-06-14
R7S1ONEME-AP02-191 | External Drainage Network - AP#02 (External Drainage MEP) | 4 | 2025-06-10 | 2025-06-14
WATERSUPPLY |  | 13 | 2025-06-17 | 2025-07-01
R7S1ONEME-AP02-192 | PRV statiuon assembly including meters- AP#02 (External WS MEP) | 4 | 2025-06-17 | 2025-06-21
R7S1ONEME-AP02-194 | Installation of valve station incl. BTU meter- AP#02 (External WS MEP) | 3 | 2025-06-29 | 2025-07-01
CHILLED WATER |  | 7 | 2025-06-22 | 2025-06-29
R7S1ONEME-AP02-193 | Installation of Chilled water line- AP#02 (External CWP MEP) | 6 | 2025-06-22 | 2025-06-28
R7S1ONEME-AP02-195 | Pressure Test for chilled water line- AP#02 (External CWP MEP) | 1 | 2025-06-29 | 2025-06-29
FIRE FIGHTING |  | 9 | 2025-06-17 | 2025-06-29
R7S1ONEME-AP02-196 | Installation of External FF network - AP#02 (External FF MEP) | 6 | 2025-06-17 | 2025-06-23
R7S1ONEME-AP02-197 | Installation of Alarm check valves- AP#02 (External FF MEP) | 3 | 2025-06-24 | 2025-06-26
R7S1ONEME-AP02-198 | Testing of External FF - AP#02 (External FF MEP) | 2 | 2025-06-28 | 2025-06-29
POWER |  | 2 | 2025-07-21 | 2025-07-22
R7S1ONEME-AP02-199 | Cable pulling from Manhole to the building MDB - AP#02 (External Power MEP) | 2 | 2025-07-21 | 2025-07-22
LOW CURRENT |  | 3 | 2025-06-24 | 2025-06-26
R7S1ONEME-AP02-200 | Low Current Cable pulling- AP#02 (External FF MEP) | 3 | 2025-06-24 | 2025-06-26
BUILDING # AP01 (MGT BLDG) |  | 290 | 2024-11-10 | 2025-09-30
SUB-STRUCTURE |  | 42 | 2024-11-10 | 2024-12-28
R7S1-ONSB-AP01-100 | Site Setting Out Works - AP#01 | 1 | 2024-11-10 | 2024-11-10
R7S1-ONSB-AP01-110 | Site levelling & earthworks - AP#01 | 8 | 2024-11-12 | 2024-11-20
R7S1-ONSB-AP01-120 | Anti-termite & Polythene Sheet Works - AP#01 | 2 | 2024-12-02 | 2024-12-03
R7S1-ONSB-AP01-130 | Blinding PCC - AP#01 | 2 | 2024-12-03 | 2024-12-04
R7S1-ONSB-AP01-140 | Waterproofing for Blinding PCC (Bitumen Paint) - AP#01 | 1 | 2024-12-05 | 2024-12-05
R7S1-ONSB-AP01-150 | Foundations/Upstands - Rebar - AP#01 | 3 | 2024-12-07 | 2024-12-09
R7S1-ONSB-AP01-160 | Foundations/Upstands - Shuttering (Including dowel Works) - AP#01 | 6 | 2024-12-05 | 2024-12-11
R7S1-ONSB-AP01-170 | Installation of MEP U/G services below Boxes - AP#01 | 1 | 2024-12-14 | 2024-12-15
R7S1-ONSB-AP01-180 | Foundations/Upstands - Casting - AP#01 | 1 | 2024-12-15 | 2024-12-16
R7S1-ONSB-AP01-190 | Waterproofing For Foundations/Upstands - AP#01 | 3 | 2024-12-16 | 2024-12-19
R7S1-ONSB-AP01-200 | Backfilling & Compaction - AP#01 | 8 | 2024-12-19 | 2024-12-28
SLAB-ON-GRADE & UG MEP WORKS (in Corridor) |  | 66 | 2025-02-02 | 2025-04-24
LEFT SIDE |  | 66 | 2025-02-02 | 2025-04-24
R7S1-ONSG-AP01-100 | Block Work below Corridor area - AP#01 | 2 | 2025-02-02 | 2025-02-03
R7S1-ONSG-AP01-120 | UG MEP Works (Laying of Pipes) - AP#01 | 2 | 2025-02-02 | 2025-02-03
R7S1-ONSG-AP01-140 | Backfilling Works after Pipe Laying - AP#01 | 2 | 2025-02-02 | 2025-02-03
R7S1-ONSG-AP01-110 | Backfilling upto Pipe Level - AP#01 | 2 | 2025-02-02 | 2025-02-03
R7S1-ONSG-AP01-130 | Plaster Work for Blockwork - AP#01 | 2 | 2025-02-02 | 2025-02-03
R7S1-ONSG-AP01-150 | Antitermite Works - AP#01 | 1 | 2025-02-04 | 2025-02-04
R7S1-ONSG-AP01-160 | Polythene & Rebar Mesh Works - AP#01 | 2 | 2025-02-04 | 2025-02-05
R7S1-ONSG-AP01-170 | Pouring SOG Concrete - AP#01 | 1 | 2025-02-06 | 2025-02-06
R7S1-ONSG-AP01-300 | Backfilling & SOG (In Front of Lift Shaft) - AP#01 | 4 | 2025-04-21 | 2025-04-24
RIGHT SIDE |  | 5 | 2025-02-05 | 2025-02-11
R7S1-ONSG-AP01-180 | Block Work below Corridor area - AP#01 | 2 | 2025-02-05 | 2025-02-06
R7S1-ONSG-AP01-190 | Backfilling upto Pipe Level - AP#01 | 2 | 2025-02-05 | 2025-02-06
R7S1-ONSG-AP01-200 | UG MEP Works (Laying of Pipes) - AP#01 | 1 | 2025-02-06 | 2025-02-08
R7S1-ONSG-AP01-210 | Backfilling Works after Pipe Laying - AP#01 | 1 | 2025-02-08 | 2025-02-09
R7S1-ONSG-AP01-220 | Antitermite Works - AP#01 | 1 | 2025-02-09 | 2025-02-10
R7S1-ONSG-AP01-230 | Polythene & Rebar Mesh Works - AP#01 | 1 | 2025-02-09 | 2025-02-10
R7S1-ONSG-AP01-240 | Pouring SOG Concrete - AP#01 | 1 | 2025-02-10 | 2025-02-11
ERECTION WORKS |  | 82 | 2025-02-06 | 2025-05-18
GROUND FLOOR |  | 62 | 2025-02-06 | 2025-04-24
R7S1ONER-AP01GF110 | Erection of GF Boxes (Right Side) - AP#01 | 3 | 2025-02-06 | 2025-02-09
R7S1ONER-AP01GF120 | Erection of GF MEP Modular Cages (Left Side) - AP#01 | 3 | 2025-02-09 | 2025-02-11
R7S1ONER-AP01GF100 | Erection of GF Boxes (Left Side) including Lift Box & Staircase - AP#01 | 2 | 2025-02-10 | 2025-02-12
R7S1ONER-AP01GF130 | Erection of GF Corridor Slabs (Left Side) - AP#01 | 4 | 2025-02-09 | 2025-02-12
R7S1ONER-AP01GF140 | Erection of GF MEP Modular Cages (Right Side) - AP#01 | 1 | 2025-02-15 | 2025-02-15
R7S1ONER-AP01GF150 | Erection of GF Corridor Slabs Right Side) - AP#01 | 2 | 2025-02-16 | 2025-02-17
R7S1ONER-AP01GF232 | Erection of Columns/Beams Frame & Slab/Loose Elements (In Front of Lift Shaft) - AP#01 | 4 | 2025-04-21 | 2025-04-24
FIRST FLOOR |  | 34 | 2025-03-11 | 2025-04-24
R7S1ONER-AP01FF100 | Erection of FF Boxes (Left Side) - AP#01 | 3 | 2025-03-11 | 2025-03-15
R7S1ONER-AP01FF110 | Erection of FF Boxes (Right Side) - AP#01 | 3 | 2025-03-15 | 2025-03-18
R7S1ONER-AP01FF120 | Erection of FF MEP Modular Cages (Left Side) - AP#01 | 2 | 2025-03-16 | 2025-03-18
R7S1ONER-AP01FF130 | Erection of FF Corridor Slabs (Left Side) - AP#01 | 1 | 2025-03-18 | 2025-03-19
R7S1ONER-AP01FF140 | Erection of FF MEP Modular Cages (Right Side) - AP#01 | 1 | 2025-03-18 | 2025-03-19
R7S1ONER-AP01FF150 | Erection of FF Corridor Slabs Right Side) - AP#01 | 1 | 2025-03-20 | 2025-03-22
R7S1ONER-AP01FF242 | Erection of Columns/Beams Frame & Slab/Loose Elements (In Front of Lift Shaft) - AP#01 | 4 | 2025-04-21 | 2025-04-24
SECOND FLOOR |  | 12 | 2025-04-21 | 2025-05-04
R7S1ONER-AP01SF252 | Erection of Columns/Beams Frame & Slab/Loose Elements (In Front of Lift Shaft) - AP#01 | 4 | 2025-04-21 | 2025-04-24
R7S1ONER-AP01SF100 | Erection of SF Boxes (Left Side) - AP#01 | 2 | 2025-04-26 | 2025-04-27
R7S1ONER-AP01SF110 | Erection of SF Boxes (Right Side) - AP#01 | 2 | 2025-04-27 | 2025-04-29
R7S1ONER-AP01SF120 | Erection of SF MEP Modular Cages (Left Side) - AP#01 | 3 | 2025-04-27 | 2025-04-30
R7S1ONER-AP01SF130 | Erection of SF Corridor Slabs (Left Side) - AP#01 | 2 | 2025-04-28 | 2025-04-30
R7S1ONER-AP01SF140 | Erection of SF MEP Modular Cages (Right Side) - AP#01 | 2 | 2025-04-29 | 2025-05-01
R7S1ONER-AP01SF150 | Erection of SF Corridor Slabs Right Side) - AP#01 | 2 | 2025-05-01 | 2025-05-04
ROOF |  | 12 | 2025-05-04 | 2025-05-18
R7S1ONER-AP01RF100 | Erection of Loose Roof Parapets, Shaft Covers, MEP Foundation etc. - AP#01 Roof | 12 | 2025-05-04 | 2025-05-18
MEP WORKS & FINISHES |  | 189 | 2025-02-16 | 2025-09-30
GROUND FLOOR |  | 189 | 2025-02-16 | 2025-08-07
ARCH./ CIVIL WORKS |  | 189 | 2025-02-16 | 2025-08-07
CORRIDOR AREA |  | 149 | 2025-02-16 | 2025-08-07
R7S1ONAR-AP01GF1 | False Ceiling - 1st Fix - AP#01 (GF - Corridor) | 19 | 2025-04-07 | 2025-04-29
R7S1ONAR-AP01GF2 | Gypsum Wall Cladding - 1st Fix (Shafts) - AP#01 (GF Corridor) | 84 | 2025-04-08 | 2025-07-20
R7S1ONAR-AP01GF8 | Gypsum Wall Cladding (Shafts) -2nd Fix - AP#01 (GF Corridor) | 72 | 2025-04-23 | 2025-07-20
R7S1ONAR-AP01GF3 | Flooring in Corridor - AP#01 (GF Corridor) | 88 | 2025-04-05 | 2025-07-21
R7S1ONAR-AP01GF4 | Corridor Skirting - AP#01 (GF Corridor) | 125 | 2025-02-16 | 2025-07-22
R7S1ONAR-AP01GF5 | Fixing Architrave - AP#01 (GF Corridor) | 2 | 2025-07-20 | 2025-07-22
R7S1ONAR-AP01GF9 | False Ceiling - 2nd Fix (Closing the Ceiling) - AP#01 (GF Corridor) | 3 | 2025-07-21 | 2025-07-24
R7S1ONAR-AP01GF7 | Fixing Aluminium Doors - AP#01 (GF Corridor) | 2 | 2025-07-22 | 2025-07-24
R7S1ONAR-AP01GF6 | Painting - Surface Prep., Primer & 1st Coat - AP#01 (GF Corridor) | 8 | 2025-07-20 | 2025-07-29
R7S1ONAR-AP01GF40 | Painting - Surface Prep., Primer & 1st Coat for Ceiling - AP#01 (GF Corridor) | 4 | 2025-07-24 | 2025-07-29
R7S1ONAR-AP01GF10 | Painting - Final Coat (Ceiling + Walls) - AP#01 (GF Corridor) | 3 | 2025-08-04 | 2025-08-07
INSIDE BOXES |  | 83 | 2025-04-10 | 2025-07-21
R7S1ONAR-AP01GF11 | Fixing Thresholds (Joining the Room) - AP#01 (GF - inside Boxes) | 83 | 2025-04-10 | 2025-07-21
R7S1ONAR-AP01GF16 | Fixing Wooden Doors - AP#01 (GF - inside Boxes) | 4 | 2025-07-16 | 2025-07-21
R7S1ONAR-AP01GF17 | Fixing Aluminium Doors - AP#01 (GF - inside Boxes) | 75 | 2025-04-20 | 2025-07-21
IN FRONT OF LIFT SHAFT |  | 140 | 2025-04-20 | 2025-07-21
R7S1ONAR-AP01GF13 | Flooring - AP#01 (GF - Front of Lift Shaft) | 5 | 2025-04-20 | 2025-04-24
R7S1ONAR-AP01GF14 | Skirting & Thresholds - AP#01 (GF - Front of Lift Shaft) | 1 | 2025-04-26 | 2025-04-26
R7S1ONAR-AP01GF15 | Painting - Surface Prep., Primer & 1st Coat - AP#01 (GF - Front of Lift Shaft) | 4 | 2025-04-26 | 2025-04-29
R7S1ONAR-AP01GF12 | False Ceiling - 1st Fix - AP#01 (GF - Front of Lift Shaft) | 4 | 2025-04-30 | 2025-05-04
R7S1ONAR-AP01GF18 | False Ceiling - Final Fix - AP#01 (GF - Front of Lift Shaft) | 3 | 2025-05-05 | 2025-05-07
R7S1ONAR-AP01GF19 | Fixing Handrail - AP#01 (GF - Front of Lift Shaft) | 3 | 2025-07-07 | 2025-07-09
R7S1ONAR-AP01GF20 | Paint for Handrail - AP#01 (GF - Front of Lift Shaft) | 3 | 2025-07-10 | 2025-07-13
R7S1ONAR-AP01GF21 | Painting - Final Coat - AP#01 (GF - Front of Lift Shaft) | 3 | 2025-07-14 | 2025-07-16
R7S1ONAR-AP01GF22 | Fixing Wall Guard - AP#01 (GF - Front of Lift Shaft) | 2 | 2025-07-17 | 2025-07-19
R7S1ONAR-AP01GF23 | Fixing Floor Mat - AP#01 (GF - Front of Lift Shaft) | 2 | 2025-07-20 | 2025-07-21
GARBAGE ROOM |  | 2 | 2025-07-29 | 2025-07-30
R7S1ONAR-AP01GF24 | Paint Finishes and Touchups - Final Coat - AP#01 (GF - Garbage Room) | 2 | 2025-07-29 | 2025-07-30
BALCONIES |  | 150 | 2025-04-08 | 2025-08-04
R7S1ONAR-AP01GF25 | Wetarea Waterproofing - AP#01 (GF - Balconies) | 85 | 2025-04-08 | 2025-07-21
R7S1ONAR-AP01GF26 | Flooring - AP#01 (GF - Front of Lift Shaft) | 80 | 2025-04-17 | 2025-07-24
R7S1ONAR-AP01GF27 | Painting - Surface Prep., Primer & 1st Coat - AP#01 (GF - Front of Lift Shaft) | 8 | 2025-07-19 | 2025-07-28
R7S1ONAR-AP01GF28 | Fixing Handrail - AP#01 (GF - Front of Lift Shaft) | 8 | 2025-07-21 | 2025-07-30
R7S1ONAR-AP01GF29 | Paint for Handrail - AP#01 (GF - Front of Lift Shaft) | 2 | 2025-07-30 | 2025-08-02
R7S1ONAR-AP01GF30 | Painting - Final Coat - AP#01 (GF - Front of Lift Shaft) | 2 | 2025-08-02 | 2025-08-04
MEP WORKS |  | 130 | 2025-02-23 | 2025-07-30
MECHANICAL |  | 122 | 2025-02-24 | 2025-07-28
CHILLED WATER |  | 78 | 2025-03-04 | 2025-05-18
R7S1ONME-AP01GF35 | CHWP piping risers connections - AP#01 (GF - Corridor) | 10 | 2025-03-24 | 2025-04-08
R7S1ONME-AP01GF1 | Installation of Chilled water hanger and supports - AP#01 (GF - Corridor) | 30 | 2025-03-04 | 2025-04-13
R7S1ONME-AP01GF25 | Installation of CHWP piping (connection between modular cages & modular to apartment) - AP#01 (GF - Corridor) | 31 | 2025-03-08 | 2025-04-16
R7S1ONME-AP01GF28 | Installation of BTU Meter with valves - AP#01 (GF - Corridor) | 29 | 2025-03-10 | 2025-04-17
R7S1ONME-AP01GF43 | Pressure Testing of CHWP piping - AP#01 (GF - Corridor) | 7 | 2025-04-17 | 2025-04-24
R7S1ONME-AP01GF45 | CHWP Insulation - AP#01 (GF - Corridor) | 7 | 2025-04-17 | 2025-04-24
R7S1ONME-AP01GF17 | Installation of CHWP connection for FCU with Valve package in Corridor, Electrical Room & ICT Room - AP#01 (GF) | 34 | 2025-03-12 | 2025-04-24
R7S1ONME-AP01GF516 | CHWP Installation/Connections and Insulation (In Front of Lift Shaft) - AP#01 | 4 | 2025-05-14 | 2025-05-18
HVAC DUCTING |  | 108 | 2025-03-04 | 2025-07-27
R7S1ONME-AP01GF27 | Installation of Ducting and insulation (connection between modular cages) - AP#01 (GF - Corridor) | 20 | 2025-03-04 | 2025-03-26
R7S1ONME-AP01GF16 | Installation of FCU's & Duct Connection in Corridor, Electrical Room & ICT Room - AP#01 (GF) | 30 | 2025-03-17 | 2025-04-24
R7S1ONME-AP01GF2 | Duct Riser Continuation - AP#01 (GF - Corridor) | 26 | 2025-03-26 | 2025-04-30
R7S1ONME-AP01GF26 | A/C drain & Copper pipe connection in ELV room - AP#01 (GF) | 24 | 2025-03-29 | 2025-04-30
R7S1ONME-AP01GF32 | Installation of Duct & Grill in Garbage Room - AP#01 (GF - Garbage Room) | 22 | 2025-04-05 | 2025-04-30
R7S1ONME-AP01GF52 | Installation of Grilles in the Corridor - AP#01 (GF - Corridor) | 2 | 2025-07-24 | 2025-07-27
FIRE FIGHTING |  | 98 | 2025-03-24 | 2025-07-28
R7S1ONME-AP01GF3 | Riser Continuity in corridor - AP#01 (GF - Corridor) | 10 | 2025-03-24 | 2025-04-08
R7S1ONME-AP01GF4 | Continuitu of FF pipes & ZC Valves (connection between modular cages & modular to apartment) - AP#01 (GF - Corridor) | 15 | 2025-04-08 | 2025-04-24
R7S1ONME-AP01GF33 | Installation of Sprinklers drops in corridor - AP#01 (GF - Corridor) | 4 | 2025-04-29 | 2025-05-04
R7S1ONME-AP01GF38 | Pressure Test for FF Piping in corridor - AP#01 (GF - Corridor) | 14 | 2025-04-17 | 2025-05-04
R7S1ONME-AP01GF44 | FF Flushing network - AP#01 (GF - Corridor) | 1 | 2025-05-20 | 2025-05-21
R7S1ONME-AP01GF866 | Installation of F.F Pipes, Testing & Final Fixtures (In Front of Lift Shaft) - AP#01 | 3 | 2025-05-19 | 2025-05-21
R7S1ONME-AP01GF13 | Installation of Pipe & sprinkler in Garbage Room - AP#01 (GF - Garbage Room) | 83 | 2025-03-27 | 2025-07-13
R7S1ONME-AP01GF54 | Installation of Alarm check valve, Fire Extinguishers & Blanket - AP#01 (GF - Corridor) | 3 | 2025-07-21 | 2025-07-24
R7S1ONME-AP01GF48 | Installation of Sprinklers in corridor - AP#01 (GF - Corridor) | 3 | 2025-07-24 | 2025-07-28
WATER SUPPLY |  | 72 | 2025-02-24 | 2025-05-22
R7S1ONME-AP01GF15 | Installation of Sanitary Fixtures in Janitor Room - AP#01 (GF - Janitor Room) | 2 | 2025-03-01 | 2025-03-02
R7S1ONME-AP01GF20 | Installation of Cold, Hot water line & Hot water return - AP#01 (GF - Corridor) | 11 | 2025-02-24 | 2025-03-09
R7S1ONME-AP01GF5 | Riser Continuity in Shafts - AP#01 (GF - Corridor) | 14 | 2025-03-24 | 2025-04-13
R7S1ONME-AP01GF6 | WS High Level Pipe continuation & Insulation works - AP#01 (GF - Corridor) | 35 | 2025-03-04 | 2025-04-19
R7S1ONME-AP01GF14 | Installation of WS Pipe in Garbage Room - AP#01 (GF - Garbage Room) | 36 | 2025-03-04 | 2025-04-20
R7S1ONME-AP01GF29 | Water Meter Installation - AP#01 (GF - Corridor) | 4 | 2025-04-26 | 2025-04-29
R7S1ONME-AP01GF36 | Pressure Test for WS - AP#01 (GF - Corridor) | 4 | 2025-05-18 | 2025-05-22
R7S1ONME-AP01GF42 | Insulation for Hot water line & Hot water return - AP#01 (GF - Corridor) | 48 | 2025-03-23 | 2025-05-22
DRAINAGE |  | 64 | 2025-03-04 | 2025-05-22
R7S1ONME-AP01GF9 | Drainage Riser continuation in Shafts - AP#01 (GF - Corridor) | 11 | 2025-03-24 | 2025-04-09
R7S1ONME-AP01GF7 | Installation of Clean-outs, Floor drain in balcony - AP#01 (GF - Corridor) | 36 | 2025-03-04 | 2025-04-20
R7S1ONME-AP01GF8 | Rain Water Riser continuation in Shafts - AP#01 (GF - Corridor) | 22 | 2025-03-24 | 2025-04-22
R7S1ONME-AP01GF21 | Testing for Rain Water Riser - AP#01 (GF - Corridor) | 4 | 2025-05-18 | 2025-05-22
R7S1ONME-AP01GF22 | Testing for Drainage Riser1 - AP#01 (GF - Corridor) | 4 | 2025-05-18 | 2025-05-22
ELECTRICAL |  | 130 | 2025-02-23 | 2025-07-30
POWER & LIGHTING |  | 122 | 2025-02-23 | 2025-07-30
R7S1ONME-AP01GF10 | Contiuation of Cable Trays & apartment branches - AP#01 (GF - Corridor) | 13 | 2025-03-01 | 2025-03-15
R7S1ONME-AP01GF11 | Contiuation of Cable Trunking with Flexible conduits for Lights - AP#01 (GF - Corridor) | 18 | 2025-02-23 | 2025-03-15
R7S1ONME-AP01GF12 | Installation of EMT pipes - AP#01 (GF - Corridor) | 13 | 2025-03-04 | 2025-03-19
R7S1ONME-AP01GF30 | Installation of Busbar, Electrical Meter & Tap-off - AP#01 (GF - Corridor) | 3 | 2025-05-19 | 2025-05-21
R7S1ONME-AP01GF34 | Corridor Wire Pulling - AP#01 (GF - Corridor) | 73 | 2025-02-23 | 2025-05-22
R7S1ONME-AP01GF46 | Electrical Room - Installation of Cable trays, SMDB & Termination - AP#01 (GF - Corridor) | 58 | 2025-03-12 | 2025-05-22
R7S1ONME-AP01GF40 | Termination of Tap-off with Electrical Meter in the apartments - AP#01 (GF - Corridor) | 3 | 2025-05-22 | 2025-05-25
R7S1ONME-AP01GF1046 | Continuation of Cable Tray/Trunking with Flexible conduits for Lights (In Front of Lift Shaft) - AP#01 | 4 | 2025-05-22 | 2025-05-26
R7S1ONME-AP01GF56 | Installation, Termination of Emergeny & Exit Lights with contiuity - AP#01 (GF - Corridor) | 2 | 2025-07-24 | 2025-07-27
R7S1ONME-AP01GF55 | Installation, Termination of Light Fixtures with continuity test - AP#01 (GF - Corridor & Balconies) | 3 | 2025-07-24 | 2025-07-28
R7S1ONME-AP01GF57 | Installation, Termination of PIR sensors with continuity test - AP#01 (GF - Corridor) | 2 | 2025-07-28 | 2025-07-30
LOW CURRENT SYSTEM |  | 130 | 2025-02-23 | 2025-07-29
R7S1ONME-AP01GF31 | Voice Evacuation cable installation - AP#01 (GF - Corridor) | 18 | 2025-02-23 | 2025-03-15
R7S1ONME-AP01GF23 | Fire alarm cable installation - AP#01 (GF - Corridor) | 18 | 2025-02-23 | 2025-03-15
R7S1ONME-AP01GF18 | CBS System cable installation - AP#01 (GF - Corridor) | 18 | 2025-02-23 | 2025-03-15
R7S1ONME-AP01GF19 | Installation of Basket trays for BMS, CCTV, Access Control - AP#01 (GF - Corridor) | 18 | 2025-02-23 | 2025-03-15
R7S1ONME-AP01GF37 | BMS, CCTV & Access control Cable installation - AP#01 (GF - Corridor) | 33 | 2025-04-05 | 2025-05-13
R7S1ONME-AP01GF39 | Low Current Works including BMS Panel in ICT Room - AP#01 (GF - Corridor) | 10 | 2025-05-06 | 2025-05-18
R7S1ONME-AP01GF47 | Installation & Termination of Access control system for Electrical Room - AP#01 (GF) | 2 | 2025-05-17 | 2025-05-19
R7S1ONME-AP01GF24 | Fibre optic Cable pulling & Termination with OTO (in corridors to ONU) - AP#01 (GF - Corridor) | 2 | 2025-05-18 | 2025-05-20
R7S1ONME-AP01GF41 | Fluke test for CCTV & Fibre Optic Cable - AP#01 (GF - Corridor) (Ceiling 1st Fix) | 2 | 2025-05-20 | 2025-05-22
R7S1ONME-AP01GF1226 | Installation of Basket trays for Low Current, Cable Installation (In Front of Lift Shaft) - AP#01 | 4 | 2025-06-01 | 2025-06-04
R7S1ONME-AP01GF50 | Installation & Termination of CCTV Cameras - AP#01 (GF - Corridor) | 2 | 2025-07-24 | 2025-07-27
R7S1ONME-AP01GF51 | Installation & Termination of Wireless Gateway & RF Node in corridors - AP#01 (GF - Corridor) | 2 | 2025-07-24 | 2025-07-27
R7S1ONME-AP01GF49 | Installation & Termination of Fire alarm devices & Speakers - AP#01 (GF - Corridor) | 4 | 2025-07-24 | 2025-07-29
R7S1ONME-AP01GF53 | Installation & Termination of Active Components & UPS installation in ICT Room - AP#01 (GF - Corridor) | 2 | 2025-07-27 | 2025-07-29
FIRST FLOOR |  | 152 | 2025-03-30 | 2025-09-21
ARCH./ CIVIL WORKS |  | 139 | 2025-04-20 | 2025-09-21
CORRIDOR AREA |  | 100 | 2025-04-26 | 2025-09-21
R7S1ONAR-AP01FF3 | Flooring in Corridor - AP#01 (FF - Corridor) | 6 | 2025-04-26 | 2025-05-01
R7S1ONAR-AP01FF4 | Corridor Skirting - AP#01 (FF - Corridor) | 2 | 2025-07-22 | 2025-07-24
R7S1ONAR-AP01FF1 | False Ceiling - 1st Fix - AP#01 (FF - Corridor) | 4 | 2025-07-24 | 2025-07-29
R7S1ONAR-AP01FF2 | Gypsum Wall Cladding (Shafts) - AP#01 (FF - Corridor) | 6 | 2025-08-05 | 2025-08-12
R7S1ONAR-AP01FF8 | Gypsum Wall Cladding (Shafts) -2nd Fix - AP#01 (FF Corridor) | 4 | 2025-08-12 | 2025-08-17
R7S1ONAR-AP01FF5 | Fixing Architrave - AP#01 (FF Corridor) | 2 | 2025-08-17 | 2025-08-19
R7S1ONAR-AP01FF7 | Fixing Aluminium Doors - AP#01 (FF Corridor) | 2 | 2025-08-19 | 2025-08-21
R7S1ONAR-AP01FF9 | False Ceiling - 2nd Fix (Closing the Ceiling) - AP#01 (FF Corridor) | 3 | 2025-08-21 | 2025-08-25
R7S1ONAR-AP01FF6 | Painting - Surface Prep., Primer & 1st Coat for Walls - AP#01 (FF Corridor) | 8 | 2025-08-17 | 2025-08-26
R7S1ONAR-AP01FF75 | Painting - Surface Prep., Primer & 1st Coat for Ceiling - AP#01 (FF Corridor) | 4 | 2025-08-25 | 2025-08-30
R7S1ONAR-AP01FF10 | Painting - Final Coat (Ceiling + Walls) - AP#01 (FF Corridor) | 3 | 2025-09-17 | 2025-09-21
INSIDE BOXES |  | 19 | 2025-04-29 | 2025-05-13
R7S1ONAR-AP01FF11 | Fixing Thresholds (Joining the Room) - AP#01 (FF - inside Boxes) | 4 | 2025-04-29 | 2025-05-04
R7S1ONAR-AP01FF13 | Fixing Wooden Doors - AP#01 (FF - inside Boxes) | 4 | 2025-05-04 | 2025-05-08
R7S1ONAR-AP01FF14 | Fixing Aluminium Doors (Next Floor) - AP#01 (FF - inside Boxes) | 4 | 2025-05-08 | 2025-05-13
IN FRONT OF LIFT SHAFT |  | 139 | 2025-04-20 | 2025-09-17
R7S1ONAR-AP01FF15 | Flooring - AP#01 (FF - Front of Lift Shaft) | 106 | 2025-04-20 | 2025-08-26
R7S1ONAR-AP01FF18 | Skirting & Thresholds - AP#01 (FF - Front of Lift Shaft) | 1 | 2025-08-25 | 2025-08-26
R7S1ONAR-AP01FF20 | Painting - Surface Prep., Primer & 1st Coat - AP#01 (FF - Front of Lift Shaft) | 4 | 2025-08-26 | 2025-08-31
R7S1ONAR-AP01FF12 | False Ceiling - 1st Fix - AP#01 (FF - Front of Lift Shaft) | 4 | 2025-08-31 | 2025-09-04
R7S1ONAR-AP01FF23 | False Ceiling - Final Fix - AP#01 (FF - Front of Lift Shaft) | 3 | 2025-09-04 | 2025-09-08
R7S1ONAR-AP01FF25 | Fixing Handrail - AP#01 (FF - Front of Lift Shaft) | 3 | 2025-09-04 | 2025-09-08
R7S1ONAR-AP01FF27 | Paint for Handrail - AP#01 (FF - Front of Lift Shaft) | 3 | 2025-09-08 | 2025-09-11
R7S1ONAR-AP01FF28 | Painting - 2nd Coat - AP#01 (FF - Front of Lift Shaft) | 3 | 2025-09-11 | 2025-09-15
R7S1ONAR-AP01FF29 | Fixing Floor Mat - AP#01 (FF - Front of Lift Shaft) | 2 | 2025-09-15 | 2025-09-17
R7S1ONAR-AP01FF30 | Fixing Wall Guard - AP#01 (FF - Front of Lift Shaft) | 2 | 2025-09-15 | 2025-09-17
GARBAGE ROOM |  | 40 | 2025-07-17 | 2025-07-28
R7S1ONAR-AP01FF17 | Installation of Dry Walls - First Fix - AP#01 (FF - Garbage Room) | 2 | 2025-07-17 | 2025-07-19
R7S1ONAR-AP01FF19 | Installation of Dry Walls - Final Fix - AP#01 (FF - Garbage Room) | 1 | 2025-07-20 | 2025-07-20
R7S1ONAR-AP01FF21 | Garbage Rooms - Wall Tile Finishes (One Side) - AP#01 (FF - Garbage Room) | 2 | 2025-07-21 | 2025-07-22
R7S1ONAR-AP01FF22 | Paint Works of Dry Walls - First Coat - AP#01 (FF - Garbage Room) | 2 | 2025-07-23 | 2025-07-24
R7S1ONAR-AP01FF24 | Installation of the Garbage Chute Door - AP#01 (FF - Garbage Room) | 1 | 2025-07-26 | 2025-07-26
R7S1ONAR-AP01FF26 | Paint Finishes and Touchups - Final Coat - AP#01 (FF - Garbage Room) | 2 | 2025-07-27 | 2025-07-28
BALCONIES |  | 70 | 2025-07-24 | 2025-08-21
R7S1ONAR-AP01FF60 | Wetarea Waterproofing - AP#01 (FF - Balconies) | 8 | 2025-07-24 | 2025-08-03
R7S1ONAR-AP01FF61 | Flooring - AP#01 (FF - Balconies) | 6 | 2025-07-29 | 2025-08-05
R7S1ONAR-AP01FF62 | Painting - Surface Prep., Primer & 1st Coat - AP#01 (FF - Balconies) | 8 | 2025-07-31 | 2025-08-10
R7S1ONAR-AP01FF63 | Fixing Handrail - AP#01 (FF - Balconies) | 6 | 2025-08-05 | 2025-08-12
R7S1ONAR-AP01FF64 | Paint for Handrail - AP#01 (FF - Balconies) | 4 | 2025-08-12 | 2025-08-17
R7S1ONAR-AP01FF65 | Painting - 2nd Coat - AP#01 (FF - Balconies) | 4 | 2025-08-17 | 2025-08-21
MEP WORKS |  | 122 | 2025-03-30 | 2025-09-01
MECHANICAL |  | 120 | 2025-03-30 | 2025-08-27
CHILLED WATER |  | 60 | 2025-04-05 | 2025-05-22
R7S1ONME-AP01FF2 | Installation of CHWP connection for FCU with Valve package in Corridor, Electrical Room & ICT Room | 7 | 2025-04-19 | 2025-04-26
R7S1ONME-AP01FF1 | Installation of Chilled water hanger and supports - AP#01 (FF Corridor) | 20 | 2025-04-05 | 2025-04-27
R7S1ONME-AP01FF3 | Installation of CHWP piping (connection between modular cages & modular to apartment) - AP#01 - AP#01 (FF Corridor) | 16 | 2025-04-08 | 2025-04-27
R7S1ONME-AP01FF4 | Installation of BTU Meter with valves - AP#01 (FF Corridor) | 16 | 2025-04-09 | 2025-04-28
R7S1ONME-AP01FF35 | CHWP piping risers connections - AP#01 (FF Corridor) | 5 | 2025-04-23 | 2025-04-28
R7S1ONME-AP01FF43 | Pressure Testing of CHWP piping - AP#01 (FF Corridor) | 4 | 2025-04-24 | 2025-04-28
R7S1ONME-AP01FF45 | CHWP Insulation - AP#01 (FF Corridor) | 4 | 2025-04-28 | 2025-05-03
R7S1ONME-AP01FF526 | CHWP Installation/Connections and Insulation (In Front of Lift Shaft) - AP#01 | 4 | 2025-05-19 | 2025-05-22
HVAC DUCTING |  | 78 | 2025-04-19 | 2025-08-27
R7S1ONME-AP01FF5 | Duct Riser Continuation - AP#01 (FF Corridor) | 8 | 2025-04-19 | 2025-04-27
R7S1ONME-AP01FF27 | A/C drain & Copper pipe connection in ELV room - AP#01 (FF Corridor) | 2 | 2025-04-27 | 2025-04-29
R7S1ONME-AP01FF19 | Installation of FCU's & Duct Connection in Corridor, Electrical Room & ICT Room - AP#01 (FF Corridor) | 4 | 2025-04-26 | 2025-04-29
R7S1ONME-AP01FF32 | Installation of Duct & Grill in Garbage Room - AP#01 (FF Corridor) | 7 | 2025-04-23 | 2025-04-30
R7S1ONME-AP01FF28 | Installation of Ducting and insulation (connection between modular cages) - AP#01 (FF Corridor) | 3 | 2025-04-30 | 2025-05-03
R7S1ONME-AP01FF52 | Installation of Grilles in the Corridor - AP#01 (FF Corridor) | 2 | 2025-08-25 | 2025-08-27
FIRE FIGHTING |  | 120 | 2025-04-05 | 2025-08-27
R7S1ONME-AP01FF6 | Riser Continuity in corridor - AP#01 (FF Corridor) | 20 | 2025-04-05 | 2025-04-27
R7S1ONME-AP01FF7 | Continuation of FF pipes & ZC Valves (connection between modular cages & modular to apartment) - AP#01 (FF Corridor) | 19 | 2025-04-06 | 2025-04-27
R7S1ONME-AP01FF876 | Installation of F.F Pipes, Testing & Final Fixtures (In Front of Lift Shaft) - AP#01 | 3 | 2025-05-24 | 2025-05-26
R7S1ONME-AP01FF16 | Installation of Pipe & sprinkler in Garbage Room - AP#01 (FF Corridor) | 81 | 2025-04-05 | 2025-07-13
R7S1ONME-AP01FF33 | Installation of Sprinklers drops in corridor - AP#01 (FF Corridor) | 4 | 2025-07-29 | 2025-08-03
R7S1ONME-AP01FF38 | Pressure Test for FF Piping in corridor - AP#01 (FF Corridor) | 2 | 2025-07-31 | 2025-08-03
R7S1ONME-AP01FF44 | FF Flushing network - AP#01 (FF Corridor) | 2 | 2025-08-03 | 2025-08-05
R7S1ONME-AP01FF48 | Installation of Sprinklers in corridor - AP#01 (FF Corridor) | 2 | 2025-08-25 | 2025-08-27
R7S1ONME-AP01FF54 | Installation of Alarm check valve, Fire Extinguishers & Blanket (Last Stage of the Building) - AP#01 (FF Corridor) | 2 | 2025-08-25 | 2025-08-27
WATER SUPPLY |  | 42 | 2025-03-30 | 2025-05-22
R7S1ONME-AP01FF8 | Riser Continuity in Shafts - AP#01 (FF Corridor) | 8 | 2025-04-19 | 2025-04-27
R7S1ONME-AP01FF17 | Installation of WS Pipe in Garbage Room - AP#01 (FF Corridor) | 20 | 2025-03-30 | 2025-04-27
R7S1ONME-AP01FF18 | Installation of Sanitary Fixtures in Janitor Room - AP#01 (FF Corridor) | 20 | 2025-03-30 | 2025-04-27
R7S1ONME-AP01FF9 | WS High Level Pipe continuation & Insulation works in Corridor - AP#01 (FF Corridor) | 16 | 2025-04-12 | 2025-04-29
R7S1ONME-AP01FF22 | Installation of Cold, Hot water line & Hot water return in corridor - AP#01 (FF Corridor) | 14 | 2025-04-14 | 2025-04-29
R7S1ONME-AP01FF29 | Water Meter Installation in Corridor - AP#01 (FF Corridor) | 4 | 2025-04-29 | 2025-05-04
R7S1ONME-AP01FF36 | Pressure Test for WS - AP#01 (FF Corridor) | 4 | 2025-05-18 | 2025-05-22
R7S1ONME-AP01FF42 | Insulation for Hot water line & Hot water return in corridor - AP#01 (FF Corridor) | 27 | 2025-04-22 | 2025-05-22
DRAINAGE |  | 44 | 2025-03-30 | 2025-05-22
R7S1ONME-AP01FF10 | Installation of Clean-outs, Floor drain in balcony - AP#01 (FF Corridor) | 19 | 2025-03-30 | 2025-04-26
R7S1ONME-AP01FF11 | Rain Water Riser continuation in Shafts - AP#01 (FF Corridor) | 8 | 2025-04-19 | 2025-04-27
R7S1ONME-AP01FF12 | Drainage Riser continuation in Shafts - AP#01 (FF Corridor) | 20 | 2025-04-05 | 2025-04-27
R7S1ONME-AP01FF23 | Testing for Rain Water Riser - AP#01 (FF Corridor) | 4 | 2025-05-18 | 2025-05-22
R7S1ONME-AP01FF24 | Testing for Drainage Riser - AP#01 (FF Corridor) | 4 | 2025-05-18 | 2025-05-22
ELECTRICAL |  | 122 | 2025-03-30 | 2025-09-01
POWER & LIGHTING |  | 97 | 2025-03-30 | 2025-08-31
R7S1ONME-AP01FF13 | Contiuation of Cable Trays & apartment branches - AP#01 (FF Corridor) | 7 | 2025-03-30 | 2025-04-12
R7S1ONME-AP01FF14 | Contiuation of Cable Trunking with Flexible conduits for Lights - AP#01 (FF Corridor) | 7 | 2025-03-30 | 2025-04-12
R7S1ONME-AP01FF15 | Installation of EMT pipes - AP#01 (FF Corridor) | 9 | 2025-03-30 | 2025-04-14
R7S1ONME-AP01FF30 | Installation of Busbar, Electrical Meter & Tap-off - AP#01 (FF Corridor) | 3 | 2025-05-22 | 2025-05-25
R7S1ONME-AP01FF34 | Corridor Wire Pulling - AP#01 (FF Corridor) | 39 | 2025-04-12 | 2025-05-26
R7S1ONME-AP01FF46 | Electrical Room - Installation of Cable trays, SMDB & Termination - AP#01 (FF Corridor) | 39 | 2025-04-12 | 2025-05-26
R7S1ONME-AP01FF40 | Termination of Tap-off with Electrical Meter in the apartments - AP#01 (FF Corridor) | 3 | 2025-05-26 | 2025-05-28
R7S1ONME-AP01FF1056 | Continuation of Cable Tray/Trunking with Flexible conduits for Lights (In Front of Lift Shaft) - AP#01 | 4 | 2025-05-27 | 2025-05-31
R7S1ONME-AP01FF56 | Installation, Termination of Emergeny & Exit Lights with contiuity - AP#01 (FF Corridor) | 2 | 2025-08-25 | 2025-08-27
R7S1ONME-AP01FF55 | Installation, Termination of Light Fixtures with continuity test - AP#01 (FF - Corridor & Balconies) | 3 | 2025-08-25 | 2025-08-28
R7S1ONME-AP01FF57 | Installation, Termination of PIR sensors with continuity test - AP#01 (FF Corridor) | 2 | 2025-08-28 | 2025-08-31
LOW CURRENT SYSTEM |  | 122 | 2025-03-30 | 2025-09-01
R7S1ONME-AP01FF21 | Installation of Basket trays for BMS, CCTV, Access Control - AP#01 (FF Corridor) | 7 | 2025-03-30 | 2025-04-12
R7S1ONME-AP01FF20 | CBS System cable installation - AP#01 (FF Corridor) | 7 | 2025-03-30 | 2025-04-12
R7S1ONME-AP01FF31 | Voice Evacuation cable installation - AP#01 (FF Corridor) | 12 | 2025-04-07 | 2025-04-21
R7S1ONME-AP01FF25 | Fire alarm cable installation - AP#01 (FF Corridor) | 14 | 2025-04-05 | 2025-04-21
R7S1ONME-AP01FF37 | BMS, CCTV & Access control Cable installation - AP#01 (FF Corridor) | 27 | 2025-04-16 | 2025-05-17
R7S1ONME-AP01FF39 | Low Current Works including BMS Panel in ICT Room - AP#01 (FF Corridor) | 10 | 2025-05-11 | 2025-05-21
R7S1ONME-AP01FF26 | Fibre optic Cable pulling & Termination with OTO (in corridors to ONU) - AP#01 (FF Corridor) | 2 | 2025-05-22 | 2025-05-24
R7S1ONME-AP01FF41 | Fluke test for CCTV & Fibre Optic Cable - AP#01 (FF Corridor) | 2 | 2025-05-22 | 2025-05-24
R7S1ONME-AP01FF1236 | Installation of Basket trays for Low Current, Cable Installation (In Front of Lift Shaft) - AP#01 | 4 | 2025-06-01 | 2025-06-04
R7S1ONME-AP01FF50 | Installation & Termination of CCTV Cameras - AP#01 (FF Corridor) | 2 | 2025-08-25 | 2025-08-27
R7S1ONME-AP01FF47 | Installation & Termination of Access control system for Electrical Room - AP#01 (FF Corridor) | 2 | 2025-08-25 | 2025-08-27
R7S1ONME-AP01FF51 | Installation & Termination of Wireless Gateway & RF Node - AP#01 (FF Corridor) | 2 | 2025-08-25 | 2025-08-27
R7S1ONME-AP01FF49 | Installation & Termination of Fire alarm devices & Speakers - AP#01 (FF Corridor) | 4 | 2025-08-25 | 2025-08-30
R7S1ONME-AP01FF53 | Installation & Termination of Active Components & UPS installation in ICT Room | 4 | 2025-08-27 | 2025-09-01
SECOND FLOOR |  | 137 | 2025-04-23 | 2025-09-30
ARCH./ CIVIL WORKS |  | 134 | 2025-04-26 | 2025-09-30
CORRIDOR AREA |  | 100 | 2025-04-28 | 2025-09-30
R7S1ONAR-AP01SF3 | Flooring in Corridor - AP#01 (SF Corridor) | 6 | 2025-04-28 | 2025-05-05
R7S1ONAR-AP01SF4 | Corridor Skirting - AP#01 (SF Corridor) | 2 | 2025-05-04 | 2025-05-06
R7S1ONAR-AP01SF1 | False Ceiling - 1st Fix - AP#01 (SF Corridor) | 4 | 2025-05-06 | 2025-05-11
R7S1ONAR-AP01SF2 | Gypsum Wall Cladding (Shafts) - AP#01 (SF Corridor) | 6 | 2025-07-26 | 2025-07-31
R7S1ONAR-AP01SF8 | Gypsum Wall Cladding (Shafts) -2nd Fix - AP#01 (SF Corridor) | 4 | 2025-08-02 | 2025-08-05
R7S1ONAR-AP01SF5 | Fixing Architrave - AP#01 (SF Corridor) | 2 | 2025-08-06 | 2025-08-07
R7S1ONAR-AP01SF7 | Fixing Aluminium Doors - AP#01 (SF Corridor) | 2 | 2025-08-09 | 2025-08-10
R7S1ONAR-AP01SF9 | False Ceiling - 2nd Fix (Closing the Ceiling) - AP#01 (SF Corridor) | 2 | 2025-08-11 | 2025-08-12
R7S1ONAR-AP01SF6 | Painting - Surface Prep., Primer & 1st Coat - AP#01 (SF Corridor) | 8 | 2025-08-06 | 2025-08-14
R7S1ONAR-AP01SF40 | Painting - Surface Prep., Primer & 1st Coat - AP#01 (SF Corridor) | 4 | 2025-08-13 | 2025-08-17
R7S1ONAR-AP01SF10 | Painting - Final Coat (Ceiling + Walls) - AP#01 (SF Corridor) | 3 | 2025-09-27 | 2025-09-30
INSIDE BOXES |  | 39 | 2025-05-04 | 2025-05-18
R7S1ONAR-AP01SF11 | Fixing Thresholds (Joining the Room) - AP#01 (SF - inside Boxes) | 4 | 2025-05-04 | 2025-05-08
R7S1ONAR-AP01SF12 | Fixing Wooden Doors - AP#01 (SF - inside Boxes) | 4 | 2025-05-08 | 2025-05-13
R7S1ONAR-AP01SF13 | Fixing Aluminium Doors (Next Floor) - AP#01 (SF - inside Boxes) | 4 | 2025-05-13 | 2025-05-18
IN FRONT OF LIFT SHAFT |  | 128 | 2025-05-03 | 2025-09-21
R7S1ONAR-AP01SF14 | False Ceiling - 1st Fix - AP#01 (SF - Front of Lift Shaft) | 3 | 2025-05-04 | 2025-05-07
R7S1ONAR-AP01SF15 | Flooring - AP#01 (SF - Front of Lift Shaft) | 4 | 2025-05-03 | 2025-05-07
R7S1ONAR-AP01SF16 | Skirting & Thresholds - AP#01 (SF - Front of Lift Shaft) | 2 | 2025-05-07 | 2025-05-10
R7S1ONAR-AP01SF17 | Painting - Surface Prep., Primer & 1st Coat - AP#01 (SF - Front of Lift Shaft) | 4 | 2025-05-10 | 2025-05-14
R7S1ONAR-AP01SF18 | False Ceiling - Final Fix - AP#01 (SF - Front of Lift Shaft) | 3 | 2025-05-20 | 2025-05-24
R7S1ONAR-AP01SF19 | Fixing Handrail - AP#01 (SF - Front of Lift Shaft) | 3 | 2025-09-08 | 2025-09-11
R7S1ONAR-AP01SF20 | Paint for Handrail - AP#01 (SF - Front of Lift Shaft) | 3 | 2025-09-11 | 2025-09-15
R7S1ONAR-AP01SF21 | Painting - 2nd Coat - AP#01 (SF - Front of Lift Shaft) | 3 | 2025-09-15 | 2025-09-18
R7S1ONAR-AP01SF22 | Fixing Floor Mat - AP#01 (SF - Front of Lift Shaft) | 2 | 2025-09-18 | 2025-09-21
R7S1ONAR-AP01SF23 | Fixing Wall Guard - AP#01 (SF - Front of Lift Shaft) | 2 | 2025-09-18 | 2025-09-21
GARBAGE ROOM |  | 45 | 2025-07-01 | 2025-08-17
R7S1ONAR-AP01SF24 | Installation of Garbage Chute Full System from GF to 2nd Floor - AP#01 (SF - Garbage Room) | 10 | 2025-07-01 | 2025-07-12
R7S1ONAR-AP01SF25 | Installation of Dry Walls - First Fix - AP#01 (SF - Garbage Room) | 2 | 2025-07-13 | 2025-07-14
R7S1ONAR-AP01SF26 | Installation of Dry Walls - Final Fix - AP#01 (SF - Garbage Room) | 2 | 2025-07-15 | 2025-07-16
R7S1ONAR-AP01SF27 | Garbage Rooms - Wall Tile Finishes (One Side) - AP#01 (SF - Garbage Room) | 2 | 2025-07-16 | 2025-07-17
R7S1ONAR-AP01SF28 | Paint Works of Dry Walls - First Coat - AP#01 (SF - Garbage Room) | 2 | 2025-07-19 | 2025-07-20
R7S1ONAR-AP01SF29 | Installation of the Garbage Chute Door - AP#01 (SF - Garbage Room) | 2 | 2025-07-21 | 2025-07-22
R7S1ONAR-AP01SF30 | Paint Finishes and Touchups - Final Coat - AP#01 (SF - Garbage Room) | 2 | 2025-08-16 | 2025-08-17
BALCONIES |  | 115 | 2025-04-26 | 2025-09-29
R7S1ONAR-AP01FF31 | Wetarea Waterproofing - AP#01 (SF - Balconies) | 8 | 2025-04-26 | 2025-05-05
R7S1ONAR-AP01FF32 | Flooring - AP#01 (SF - Balconies) | 6 | 2025-04-30 | 2025-05-07
R7S1ONAR-AP01FF33 | Painting - Surface Prep., Primer & 1st Coat - AP#01 (SF - Balconies) | 8 | 2025-05-03 | 2025-05-12
R7S1ONAR-AP01FF34 | Fixing Handrail - AP#01 (SF - Balconies) | 6 | 2025-09-11 | 2025-09-18
R7S1ONAR-AP01FF35 | Paint for Handrail - AP#01 (SF - Balconies) | 4 | 2025-09-18 | 2025-09-24
R7S1ONAR-AP01FF36 | Painting - 2nd Coat - AP#01 (SF - Balconies) | 4 | 2025-09-24 | 2025-09-29
MEP WORKS |  | 94 | 2025-04-23 | 2025-09-02
MECHANICAL |  | 94 | 2025-04-23 | 2025-08-30
CHILLED WATER |  | 42 | 2025-04-29 | 2025-05-27
R7S1ONME-AP01SF1 | Installation of Chilled water hanger and supports - AP#01 (SF Corridor) | 4 | 2025-04-29 | 2025-05-04
R7S1ONME-AP01SF2 | Installation of CHWP connection for FCU with Valve package in Corridor, Electrical Room & ICT Room | 4 | 2025-04-29 | 2025-05-04
R7S1ONME-AP01SF4 | Installation of BTU Meter with valves - AP#01 (SF Corridor) | 2 | 2025-05-05 | 2025-05-07
R7S1ONME-AP01SF3 | Installation of CHWP piping (connection between modular cages & modular to apartment) - AP#01 (SF Corridor) | 4 | 2025-05-04 | 2025-05-08
R7S1ONME-AP01SF5 | CHWP piping risers connections - AP#01 (SF Corridor) | 3 | 2025-05-07 | 2025-05-11
R7S1ONME-AP01SF6 | Pressure Testing of CHWP piping - AP#01 (SF Corridor) | 1 | 2025-05-11 | 2025-05-12
R7S1ONME-AP01SF7 | CHWP Insulation - AP#01 (SF Corridor) | 4 | 2025-05-12 | 2025-05-17
R7S1ONME-AP01SF536 | CHWP Installation/Connections and Insulation (In Front of Lift Shaft) - AP#01 | 4 | 2025-05-24 | 2025-05-27
HVAC DUCTING |  | 88 | 2025-04-29 | 2025-08-14
R7S1ONME-AP01SF8 | Duct Riser Continuation - AP#01 (SF Corridor) | 4 | 2025-04-29 | 2025-05-04
R7S1ONME-AP01SF9 | Installation of FCU's & Duct Connection in Corridor, Electrical Room & ICT Room - AP#01 (SF Corridor) | 4 | 2025-04-29 | 2025-05-04
R7S1ONME-AP01SF11 | Installation of Ducting and insulation (connection between modular cages) - AP#01 (SF Corridor) | 3 | 2025-04-30 | 2025-05-04
R7S1ONME-AP01SF10 | A/C drain & Copper pipe connection in ELV room - AP#01 (SF Corridor) | 2 | 2025-05-04 | 2025-05-06
R7S1ONME-AP01SF12 | Installation of Duct & Grill in Garbage Room - AP#01 (SF Corridor) | 2 | 2025-08-13 | 2025-08-14
R7S1ONME-AP01SF13 | Installation of Grilles in the Corridor - AP#01 (SF Corridor) | 2 | 2025-08-13 | 2025-08-14
FIRE FIGHTING |  | 83 | 2025-05-04 | 2025-08-30
R7S1ONME-AP01SF14 | Riser Continuity Succ - Closing of Gysum Boards on shaft - AP#01 (SF Corridor) | 4 | 2025-05-04 | 2025-05-08
R7S1ONME-AP01SF15 | FF Contiuation on High Level with Valves - AP#01 (SF Corridor) | 4 | 2025-05-04 | 2025-05-08
R7S1ONME-AP01SF16 | Installation of Sprinklers drops - AP#01 (SF Corridor) | 4 | 2025-05-11 | 2025-05-15
R7S1ONME-AP01SF17 | Pressure Test for FF Piping - AP#01 (SF Corridor) | 4 | 2025-05-15 | 2025-05-20
R7S1ONME-AP01SF886 | Installation of F.F Pipes, Testing & Final Fixtures (In Front of Lift Shaft) - AP#01 | 3 | 2025-05-24 | 2025-05-26
R7S1ONME-AP01SF18 | Installation of Pipe & sprinkler in Garbage Room - AP#01 (SF Corridor) | 1 | 2025-08-13 | 2025-08-13
R7S1ONME-AP01SF19 | Installation of Sprinklers - AP#01 (SF Corridor) | 4 | 2025-08-13 | 2025-08-17
R7S1ONME-AP01SF20 | Installation of Fire Extinguishers - AP#01 (SF Corridor) | 2 | 2025-08-27 | 2025-08-30
WATER SUPPLY |  | 28 | 2025-04-29 | 2025-06-01
R7S1ONME-AP01SF21 | Riser Continuity - AP#01 (SF Corridor) | 4 | 2025-04-29 | 2025-05-04
R7S1ONME-AP01SF22 | WS High Level Pipe continuation & Insulation works - AP#01 (SF Corridor) | 4 | 2025-04-29 | 2025-05-04
R7S1ONME-AP01SF23 | Installation of WS Pipe in Garbage Room - AP#01 (SF Corridor) | 2 | 2025-05-01 | 2025-05-04
R7S1ONME-AP01SF25 | Instalation of Hot water line in corridor - AP#01 (SF Corridor) | 4 | 2025-05-04 | 2025-05-08
R7S1ONME-AP01SF24 | Installation of Sanitary Fixtures in Janitor Room - AP#01 (SF Corridor) | 4 | 2025-05-04 | 2025-05-08
R7S1ONME-AP01SF26 | Water Meter Installation - AP#01 (SF Corridor) | 4 | 2025-05-08 | 2025-05-13
R7S1ONME-AP01SF27 | Pressure Test for WS - AP#01 (SF Corridor) | 4 | 2025-05-22 | 2025-05-27
R7S1ONME-AP01FF67 | Insulation for Hot water line & Hot water return in corridor - AP#01 (SF Corridor) | 4 | 2025-05-27 | 2025-06-01
DRAINAGE |  | 26 | 2025-04-23 | 2025-05-22
R7S1ONME-AP01SF28 | Installation of Clean-outs - AP#01 (SF Corridor) | 10 | 2025-04-23 | 2025-05-04
R7S1ONME-AP01SF29 | Rain Water Riser continuation - AP#01 (SF Corridor) | 4 | 2025-04-29 | 2025-05-04
R7S1ONME-AP01SF30 | Drainage Riser continuation - AP#01 (SF Corridor) | 4 | 2025-04-29 | 2025-05-04
R7S1ONME-AP01SF31 | Testing for Rain Water Riser - AP#01 (SF Corridor) | 4 | 2025-05-18 | 2025-05-22
R7S1ONME-AP01SF32 | Testing for Drainage Riser - AP#01 (SF Corridor) | 4 | 2025-05-18 | 2025-05-22
ELECTRICAL |  | 74 | 2025-05-04 | 2025-09-02
POWER & LIGHTING |  | 74 | 2025-05-04 | 2025-09-02
R7S1ONME-AP01SF33 | Contiuation of Cable Trays & apartment branches - AP#01 (SF Corridor) | 4 | 2025-05-04 | 2025-05-08
R7S1ONME-AP01SF34 | Contiuation of Cable Trunking with Flexible conduits for Lights - AP#01 (SF Corridor) | 4 | 2025-05-04 | 2025-05-08
R7S1ONME-AP01SF35 | Installation of EMT pipes - AP#01 (SF Corridor) | 5 | 2025-05-04 | 2025-05-10
R7S1ONME-AP01SF36 | Installation of Busbar, Electrical Meter & Tap-off in Corridor - AP#01 (SF Corridor) | 3 | 2025-05-26 | 2025-05-28
R7S1ONME-AP01SF1066 | Continuation of Cable Tray/Trunking with Flexible conduits for Lights (In Front of Lift Shaft) - AP#01 | 4 | 2025-05-27 | 2025-05-31
R7S1ONME-AP01SF38 | Termination of Tap-off with Electrical Meter in the apartments - AP#01 (SF Corridor) | 3 | 2025-05-29 | 2025-06-01
R7S1ONME-AP01SF37 | Corridor Wire Pulling - AP#01 (SF Corridor) | 6 | 2025-05-27 | 2025-06-02
R7S1ONME-AP01SF39 | Electrical Room - Installation of Cable trays, SMDB & Termination - AP#01 (SF Corridor) | 6 | 2025-07-17 | 2025-07-23
R7S1ONME-AP01SF41 | Installation, Termination of Emergeny & Exit Lights with contiuity - AP#01 (SF Corridor) | 2 | 2025-08-13 | 2025-08-14
R7S1ONME-AP01SF40 | Installation, Termination of Light Fixtures with continuity test - AP#01 (SF - Corridor & Balconies) | 3 | 2025-08-13 | 2025-08-16
R7S1ONME-AP01SF42 | Installation, Termination of PIR sensors with continuity test - AP#01 (SF Corridor) | 2 | 2025-08-31 | 2025-09-02
LOW CURRENT SYSTEM |  | 72 | 2025-05-04 | 2025-08-17
R7S1ONME-AP01SF43 | CBS System cable installation - AP#01 (SF Corridor) | 3 | 2025-05-04 | 2025-05-07
R7S1ONME-AP01SF44 | Installation of Basket trays for BMS, CCTV, Access Control - AP#01 (SF Corridor) | 4 | 2025-05-04 | 2025-05-08
R7S1ONME-AP01SF45 | Fire alarm cable installation - AP#01 (SF Corridor) | 3 | 2025-05-05 | 2025-05-08
R7S1ONME-AP01SF47 | Voice Evacuation cable installation - AP#01 (SF Corridor) | 3 | 2025-05-07 | 2025-05-11
R7S1ONME-AP01SF48 | BMS, CCTV & Access control Cable installation - AP#01 (SF Corridor) | 2 | 2025-06-12 | 2025-06-14
R7S1ONME-AP01SF1246 | Installation of Basket trays for Low Current, Cable Installation (In Front of Lift Shaft) - AP#01 | 4 | 2025-06-10 | 2025-06-14
R7S1ONME-AP01SF49 | Low Current Works including BMS Panel in ICT Room - AP#01 (SF Corridor) | 10 | 2025-07-12 | 2025-07-22
R7S1ONME-AP01SF50 | Fluke test for CCTV & Fibre Optic Cable - AP#01 (SF Corridor) | 2 | 2025-07-21 | 2025-07-22
R7S1ONME-AP01SF46 | Fibre optic Cable pulling & Termination with OTO (in corridors to ONU) - AP#01 (SF Corridor) | 2 | 2025-07-23 | 2025-07-24
R7S1ONME-AP01SF53 | Installation & Termination of CCTV Cameras - AP#01 (SF Corridor) | 2 | 2025-08-13 | 2025-08-14
R7S1ONME-AP01SF51 | Installation & Termination of Access control system for Electrical Room - AP#01 (SF Corridor) | 2 | 2025-08-13 | 2025-08-14
R7S1ONME-AP01SF54 | Installation & Termination of Wireless Gateway & RF Node in corridors - AP#01 (SF Corridor) | 2 | 2025-08-13 | 2025-08-14
R7S1ONME-AP01SF52 | Installation & Termination of Fire alarm devices & Speakers - AP#01 (SF Corridor) | 4 | 2025-08-13 | 2025-08-17
R7S1ONME-AP01SF55 | Installation & Termination of Active Components & UPS installation in ICT Room - AP#01 (SF Corridor) | 2 | 2025-08-16 | 2025-08-17
ROOF WORKS |  | 97 | 2025-05-18 | 2025-09-02
ARCH./ CIVIL WORKS |  | 97 | 2025-05-18 | 2025-09-02
R7S1ONAR-AP01RF1 | Roof Box Stiching (Concrete Works) - AP#01 (Roof) | 6 | 2025-05-18 | 2025-05-25
R7S1ONME-AP01RF53 | Installation of Roof Drains - AP#01 (Roof) | 2 | 2025-05-22 | 2025-05-25
R7S1ONAR-AP01RF2 | Roof Waterproofing Works with testing - AP#01 (Roof) | 20 | 2025-06-16 | 2025-07-08
R7S1ONAR-AP01RF3 | Laying of Gravel - AP#01 (Roof) | 2 | 2025-07-09 | 2025-07-10
R7S1ONAR-AP01RF5 | Surface Preparation & Primer for Parapets - AP#01 (Roof) | 4 | 2025-07-29 | 2025-08-02
R7S1ONAR-AP01RF6 | 1st Coat Paint for Parapets - AP#01 (Roof) | 2 | 2025-08-03 | 2025-08-04
R7S1ONAR-AP01RF10 | 2nd Coat Paint for Parapets - AP#01 (Roof) | 2 | 2025-08-05 | 2025-08-06
R7S1ONAR-AP01RF8 | Fixing Fall Arrest System - AP#01 (Roof) | 2 | 2025-08-07 | 2025-08-09
R7S1ONAR-AP01RF9 | Crossover Bridges Installation & application of Sealant on MEP penetrations - AP#01 (Roof) | 12 | 2025-08-20 | 2025-09-02
MECHANICAL |  | 58 | 2025-07-12 | 2025-08-03
HVAC |  | 24 | 2025-07-12 | 2025-07-27
R7S1ONME-AP01RF1 | Modular Installation - AP#01 (Roof) | 5 | 2025-07-12 | 2025-07-16
R7S1ONME-AP01RF2 | Continuation of Roof duct works/FAHU Connections - AP#01 (Roof) | 5 | 2025-07-14 | 2025-07-19
R7S1ONME-AP01RF4 | Insulations for ducts - AP#01 (Roof) | 5 | 2025-07-15 | 2025-07-20
R7S1ONME-AP01RF5 | Installation of FAHU - AP#01 (Roof) | 2 | 2025-07-20 | 2025-07-21
R7S1ONME-AP01RF7 | Installation of Outdoor VRF/DX Units - AP#01 (Roof) | 2 | 2025-07-21 | 2025-07-22
R7S1ONME-AP01RF9 | Installation & Insulation of the Condensation Drain - AP#01 (Roof) | 1 | 2025-07-22 | 2025-07-22
R7S1ONME-AP01RF8 | Installation of Ventilation Fans - AP#01 (Roof) | 3 | 2025-07-20 | 2025-07-22
R7S1ONME-AP01RF6 | Chilled Water System Continuation and Connections with Valve package of FAHU - AP#01 (Roof) | 4 | 2025-07-20 | 2025-07-23
R7S1ONME-AP01RF20 | Installation of Louvers - AP#01 (Roof) | 2 | 2025-07-23 | 2025-07-24
R7S1ONME-AP01RF21 | Installation & Testing of Copper Pipes - AP#01 (Roof) | 2 | 2025-07-23 | 2025-07-24
R7S1ONME-AP01RF22 | Miscellaneous Works for Mechanical Connections (Fire & Volume Dampers etc.) - AP#01 (Roof) | 2 | 2025-07-26 | 2025-07-27
WATERSUPPLY & DRAINAGE |  | 27 | 2025-07-17 | 2025-08-02
R7S1ONME-AP01RF11 | Testing for the Rain Water Risers - AP#01 (Roof) | 2 | 2025-07-20 | 2025-07-21
R7S1ONME-AP01RF10 | Installation & Continuation of Water supply pipes (connection between modular cages & modular to Shaft Riser) - AP#01 | 4 | 2025-07-17 | 2025-07-21
R7S1ONME-AP01RF12 | Installation of Air Vent & Pressure Guage with Valves at Roof - AP#01 (Roof) | 4 | 2025-07-20 | 2025-07-23
R7S1ONME-AP01RF13 | Vertical Continuation of Vent Pipes To The Roof (Drainage) - AP#01 (Roof) | 4 | 2025-07-21 | 2025-07-24
R7S1ONME-AP01RF15 | Installation of Rain Water outlet - AP#01 (Roof) | 3 | 2025-07-22 | 2025-07-24
R7S1ONME-AP01RF14 | Installation of Air Vent with Valve for Water Supply - AP#01 (Roof) | 4 | 2025-07-22 | 2025-07-26
R7S1ONME-AP01RF16 | Testing of Water Supply Pipes - AP#01 (Roof) | 2 | 2025-07-27 | 2025-07-28
R7S1ONME-AP01RF17 | Insulation of Roof Water Line - AP#01 (Roof) | 2 | 2025-07-28 | 2025-07-29
R7S1ONME-AP01RF18 | Testing for the Drainage Pipes Risers - AP#01 (Roof) | 2 | 2025-07-30 | 2025-07-31
R7S1ONME-AP01RF19 | Installation of Vent Cowl - AP#01 (Roof) | 1 | 2025-08-02 | 2025-08-02
SOLAR HEATER |  | 54 | 2025-07-22 | 2025-08-03
R7S1ONME-AP01RF25 | Installation of Solar water pumps and circulation pumps with valves(For Water Only) - AP#01 (Roof) | 2 | 2025-07-23 | 2025-07-24
R7S1ONME-AP01RF23 | Installation of Structure and Solar Panels (For Water Only) - AP#01 (Roof) | 5 | 2025-07-22 | 2025-07-27
R7S1ONME-AP01RF24 | Installation of Solar Calorifier Tank & Air cooler (For Water Only) - AP#01 (Roof) | 5 | 2025-07-23 | 2025-07-28
R7S1ONME-AP01RF26 | Installation of Solar Pipes Primary Loop - AP#01 (Roof) | 5 | 2025-07-23 | 2025-07-28
R7S1ONME-AP01RF27 | Testing of Solar Pipes Primary Loop - AP#01 (Roof) | 1 | 2025-07-29 | 2025-07-29
R7S1ONME-AP01RF28 | Insulation of Solar Pipes Primary Loop - AP#01 (Roof) | 1 | 2025-07-29 | 2025-07-29
R7S1ONME-AP01RF29 | Aluminum Cladding of Solar Pipes Primary Loop - AP#01 (Roof) | 4 | 2025-07-30 | 2025-08-03
ELECTRICAL |  | 49 | 2025-07-17 | 2025-08-27
POWER & LOW CURRENT |  | 49 | 2025-07-17 | 2025-08-27
R7S1ONME-AP01RF32 | Installation of Cables for Fire Alarm system - AP#01 (Roof) | 3 | 2025-07-17 | 2025-07-20
R7S1ONME-AP01RF33 | Installation of Cables for BMS - AP#01 (Roof) | 3 | 2025-07-17 | 2025-07-20
R7S1ONME-AP01RF34 | Installation of Fire Alarm Devices - AP#01 (Roof) | 3 | 2025-07-17 | 2025-07-20
R7S1ONME-AP01RF35 | Installation of Roof Light Fixtures - AP#01 (Roof) | 3 | 2025-07-17 | 2025-07-20
R7S1ONME-AP01RF36 | Installation of BMS Devices - AP#01 (Roof) | 4 | 2025-07-19 | 2025-07-22
R7S1ONME-AP01RF31 | Installation of Electrical Containments for BMS - AP#01 (Roof) | 7 | 2025-07-17 | 2025-07-24
R7S1ONME-AP01RF38 | Termination for BMS System - AP#01 (Roof) | 1 | 2025-07-26 | 2025-07-26
R7S1ONME-AP01RF73 | Termination of Primary & Secondary pump for Solar system - AP#01 (Roof) | 1 | 2025-07-26 | 2025-07-26
R7S1ONME-AP01RF63 | Installation & Termination of Solar System Panel - AP#01 (Roof) | 3 | 2025-08-04 | 2025-08-06
R7S1ONME-AP01RF39 | Installation of Isolators and Machine Connections - AP#01 (Roof) | 4 | 2025-08-10 | 2025-08-13
R7S1ONME-AP01RF30 | Lightening Protection & Earthing System - AP#01 (Roof) | 7 | 2025-08-07 | 2025-08-14
R7S1ONME-AP01RF37 | Installation of Fire Alarm Containment for FAHU, Fans - AP#01 (Roof) | 4 | 2025-08-16 | 2025-08-19
R7S1ONME-AP01RF41 | Termination for Fire Alarm Device - AP#01 (Roof) | 1 | 2025-08-20 | 2025-08-20
R7S1ONME-AP01RF40 | Installation of LV Power Cables for Roof Equipment - AP#01 (Roof) | 5 | 2025-08-20 | 2025-08-25
R7S1ONME-AP01RF42 | Termination for LV Cables - AP#01 (Roof) | 1 | 2025-08-26 | 2025-08-26
R7S1ONME-AP01RF43 | Megger Test for the Power Cables - AP#01 (Roof) | 1 | 2025-08-27 | 2025-08-27
STAIR CASE |  | 156 | 2025-04-21 | 2025-07-20
CIVIL WORKS |  | 126 | 2025-05-25 | 2025-07-15
STAIR CASE (MAIN WITH LIFT) |  | 113 | 2025-05-25 | 2025-06-26
R7S1ONST-AP01RG100 | Stair Flooring (Roof to GF) - AP#01 (Main Stair) | 7 | 2025-05-25 | 2025-06-02
R7S1ONST-AP01RG110 | Stair Hand Rails (Roof to GF) - AP#01 (Main Stair) | 6 | 2025-06-02 | 2025-06-14
R7S1ONST-AP01RG120 | Stair Paint - Primer & 1st Coat (Roof to GF)- AP#01 (Main Stair) | 7 | 2025-06-14 | 2025-06-22
R7S1ONST-AP01RG130 | Stair Paint - Final Coat (Roof to GF)- AP#01 (Main Stair) | 4 | 2025-06-22 | 2025-06-26
STAIR CASE (LEFT SIDE) |  | 112 | 2025-06-02 | 2025-07-02
R7S1ONST-AP01RG140 | Stair Flooring (Roof to GF) - AP#01 Left Side Stair | 7 | 2025-06-02 | 2025-06-15
R7S1ONST-AP01RG150 | Stair Hand Rails (Roof to GF) - AP#01 Left Side Stair | 6 | 2025-06-15 | 2025-06-22
R7S1ONST-AP01RG160 | Stair Paint - Primer & 1st Coat (Roof to GF) - AP#01 Left Side Stair | 6 | 2025-06-22 | 2025-06-29
R7S1ONST-AP01RG170 | Stair Paint - Final Coat (Roof to GF) - AP#01 Left Side Stair | 3 | 2025-06-29 | 2025-07-02
STAIR CASE (RIGHT SIDE) |  | 106 | 2025-06-15 | 2025-07-15
R7S1ONST-AP01RG180 | Stair Flooring (Roof to GF) - AP#01 Right Side Stair | 8 | 2025-06-15 | 2025-06-24
R7S1ONST-AP01RG190 | Stair Hand Rails (Roof to GF) - AP#01 Right Side Stair | 7 | 2025-06-24 | 2025-07-02
R7S1ONST-AP01RG200 | Stair Paint - Primer & 1st Coat (Roof to GF) - AP#01 Right Side Stair | 7 | 2025-07-02 | 2025-07-10
R7S1ONST-AP01RG210 | Stair Paint - Final Coat (Roof to GF) - AP#01 Right Side Stair | 4 | 2025-07-10 | 2025-07-15
MEP WORKS |  | 95 | 2025-04-21 | 2025-07-20
STAIR CASE (MAIN WITH LIFT) |  | 85 | 2025-04-21 | 2025-07-01
R7S1ONST-AP01RG220 | Main Staircase Wire Pulling - AP#01 (Main Stair) | 28 | 2025-04-21 | 2025-05-22
R7S1ONST-AP01RG230 | Final fix - Main Staircase Lights Fixtures & Motion Sensor - AP#01 (Main Stair) | 2 | 2025-06-26 | 2025-06-29
R7S1ONST-AP01RG240 | Final fix - Main Staircase Emergency Lights Fixtures - AP#01 (Main Stair) | 2 | 2025-06-29 | 2025-07-01
STAIR CASE (LEFT SIDE) |  | 65 | 2025-05-24 | 2025-07-07
R7S1ONST-AP01RG250 | Left Staircase Wire Pulling - AP#01 (Main Stair) | 3 | 2025-05-24 | 2025-05-26
R7S1ONST-AP01RG260 | Final fix - Left Staircase Lights Fixtures & Motion Sensor - AP#01 (Main Stair) | 2 | 2025-07-02 | 2025-07-05
R7S1ONST-AP01RG270 | Final fix - Left Staircase Emergency Lights Fixtures - AP#01 (Main Stair) | 2 | 2025-07-05 | 2025-07-07
STAIR CASE (RIGHT SIDE) |  | 95 | 2025-04-21 | 2025-07-20
R7S1ONST-AP01RG280 | Right Staircase Wire Pulling - AP#01 (Main Stair) | 31 | 2025-04-21 | 2025-05-26
R7S1ONST-AP01RG290 | Final fix - Right Staircase Lights Fixtures & Motion Sensor - AP#01 (Main Stair) | 2 | 2025-07-15 | 2025-07-17
R7S1ONST-AP01RG300 | Final fix - Right Staircase Emergency Lights Fixtures - AP#01 (Main Stair) | 2 | 2025-07-17 | 2025-07-20
ELEVATOR WORKS |  | 26 | 2025-05-25 | 2025-06-24
R7S1ONEL-AP01GR100 | Installation of Rails - AP#01 (Elevator Works) | 6 | 2025-05-25 | 2025-06-01
R7S1ONEL-AP01GR200 | Assembly of Cabin - AP#01 (Elevator Works) | 4 | 2025-06-01 | 2025-06-10
R7S1ONEL-AP01GR300 | Installation of Motor - AP#01 (Elevator Works) | 4 | 2025-06-10 | 2025-06-15
R7S1ONEL-AP01GR400 | Installation of Main Cables - AP#01 (Elevator Works) | 4 | 2025-06-15 | 2025-06-19
R7S1ONEL-AP01GR500 | Installation of Doors, Indicator, Push Button - AP#01 (Elevator Works) | 2 | 2025-06-19 | 2025-06-22
R7S1ONEL-AP01GR600 | Interior Finishes - AP#01 (Elevator Works) | 2 | 2025-06-22 | 2025-06-24
EXTERNAL ELEVATIONS |  | 53 | 2025-07-12 | 2025-08-30
ARCH./ CIVIL WORKS |  | 53 | 2025-07-12 | 2025-08-30
R7S1ONEE-AP01GR200 | External Selant Works - For Boxes - AP#01 (External Elevations) | 15 | 2025-07-12 | 2025-07-28
R7S1ONEE-AP01GR300 | Final Finishes & Touchups - AP#01 (External Elevations) | 20 | 2025-07-29 | 2025-08-20
R7S1ONME-AP01GF330 | Installation of rain water outlet - External façade - AP#01 (External Elevations) | 2 | 2025-08-21 | 2025-08-23
R7S1ONEE-AP01GR400 | Installation of External Signages - AP#01 (External Elevations) | 4 | 2025-08-24 | 2025-08-27
R7S1ONEE-AP01GR500 | Fixing Cage Ladder - AP#01 (External Elevations) | 2 | 2025-08-28 | 2025-08-30
EXTERNAL - CIVIL WORKS |  | 38 | 2025-06-17 | 2025-07-27
DRAINAGE |  | 15 | 2025-06-17 | 2025-06-30
R7S1ONECW-AP01-100 | Excavation Works & Sand Bedding - AP#01 (External Drainage) | 3 | 2025-06-17 | 2025-06-19
R7S1ONECW-AP01-110 | Drainage Manholes - AP#01 | 6 | 2025-06-17 | 2025-06-23
R7S1ONECW-AP01-120 | Drainage Backfilling - AP#01 | 2 | 2025-06-29 | 2025-06-30
WATERSUPPLY |  | 25 | 2025-06-21 | 2025-07-15
R7S1ONECW-AP01-130 | Excavation Works & Sand Bedding - Watersupply - AP#01 (External Watersupply Civil) | 3 | 2025-06-21 | 2025-06-23
R7S1ONECW-AP01-140 | Watersupply Manholes - AP#01 | 6 | 2025-06-24 | 2025-06-30
R7S1ONECW-AP01-150 | Watersupply Backfilling - AP#01 | 2 | 2025-07-14 | 2025-07-15
CHILLED WATER |  | 13 | 2025-06-24 | 2025-07-06
R7S1ONECW-AP01-160 | Excavation Works & Sand Bedding - AP#01 (External Chilled Water Civil) | 3 | 2025-06-24 | 2025-06-26
R7S1ONECW-AP01-170 | Chilled Water Manholes - AP#01 | 6 | 2025-06-28 | 2025-07-03
R7S1ONECW-AP01-180 | Chilled Water Backfilling - AP#01 | 2 | 2025-07-05 | 2025-07-06
FIRE FIGHTING |  | 18 | 2025-06-28 | 2025-07-15
R7S1ONECW-AP01-190 | Excavation Works & Sand Bedding - AP#01 (External Chilled Water Civil) | 3 | 2025-06-28 | 2025-06-30
R7S1ONECW-AP01-200 | Fire Fighting Manholes - AP#01 | 6 | 2025-07-01 | 2025-07-07
R7S1ONECW-AP01-210 | Fire Fighting Backfilling - AP#01 | 2 | 2025-07-14 | 2025-07-15
POWER |  | 25 | 2025-07-01 | 2025-07-27
R7S1ONECW-AP01-220 | Excavation Works & Sand Bedding - AP#01 (External Power Civil) | 3 | 2025-07-01 | 2025-07-03
R7S1ONECW-AP01-230 | Power Manholes - AP#01 | 3 | 2025-07-05 | 2025-07-07
R7S1ONECW-AP01-240 | Power Backfilling - AP#01 | 2 | 2025-07-26 | 2025-07-27
LOW CURRENT |  | 8 | 2025-07-05 | 2025-07-13
R7S1ONECW-AP01-250 | Excavation Works & Sand Bedding - AP#01 (External Low Current Civil) | 3 | 2025-07-05 | 2025-07-07
R7S1ONECW-AP01-260 | Low Current Manholes - AP#01 | 3 | 2025-07-08 | 2025-07-10
R7S1ONECW-AP01-270 | Low Current Backfilling - AP#01 | 2 | 2025-07-12 | 2025-07-13
EXTERNAL - MEP SERVICES |  | 36 | 2025-06-24 | 2025-07-24
DRAINAGE |  | 4 | 2025-06-24 | 2025-06-28
R7S1ONEME-AP01-100 | External Drainage Network - AP#01 (External Drainage MEP) | 4 | 2025-06-24 | 2025-06-28
WATERSUPPLY |  | 7 | 2025-07-01 | 2025-07-15
R7S1ONEME-AP01-110 | PRV statiuon assembly including meters- AP#01 (External WS MEP) | 4 | 2025-07-01 | 2025-07-05
R7S1ONEME-AP01-120 | Installation of valve station incl. BTU meter- AP#01 (External WS MEP) | 3 | 2025-07-13 | 2025-07-15
CHILLED WATER |  | 8 | 2025-07-06 | 2025-07-13
R7S1ONEME-AP01-130 | Installation of Chilled water line- AP#01 (External CWP MEP) | 6 | 2025-07-06 | 2025-07-12
R7S1ONEME-AP01-140 | Pressure Test for chilled water line- AP#01 (External CWP MEP) | 1 | 2025-07-13 | 2025-07-13
FIRE FIGHTING |  | 11 | 2025-07-01 | 2025-07-13
R7S1ONEME-AP01-150 | Installation of External FF network - AP#01 (External FF MEP) | 6 | 2025-07-01 | 2025-07-07
R7S1ONEME-AP01-160 | Installation of Alarm check valves- AP#01 (External FF MEP) | 3 | 2025-07-08 | 2025-07-10
R7S1ONEME-AP01-170 | Testing of External FF - AP#01 (External FF MEP) | 2 | 2025-07-12 | 2025-07-13
POWER |  | 2 | 2025-07-23 | 2025-07-24
R7S1ONEME-AP01-180 | Cable pulling from Manhole to the building MDB - AP#01 (External Power MEP) | 2 | 2025-07-23 | 2025-07-24
LOW CURRENT |  | 3 | 2025-07-08 | 2025-07-10
R7S1ONEME-AP01-190 | Low Current Cable pulling- AP#01 (External FF MEP) | 3 | 2025-07-08 | 2025-07-10
BUILDING # AP04 (MGT BLDG) |  | 286 | 2024-11-14 | 2025-09-21
SUB-STRUCTURE |  | 48 | 2024-11-14 | 2025-01-08
R7S1-ONSB-AP04-226 | Site Setting Out Works - AP#04 | 1 | 2024-11-14 | 2024-11-14
R7S1-ONSB-AP04-223 | Site levelling & earthworks - AP#04 | 9 | 2024-11-18 | 2024-11-27
R7S1-ONSB-AP04-227 | Anti-termite & Polythene Sheet Works - AP#04 | 1 | 2024-12-11 | 2024-12-11
R7S1-ONSB-AP04-224 | Blinding PCC - AP#04 | 3 | 2024-12-15 | 2024-12-17
R7S1-ONSB-AP04-225 | Waterproofing for Blinding PCC (Bitumen Paint) - AP#04 | 3 | 2024-12-18 | 2024-12-21
R7S1-ONSB-AP04-228 | Foundations/Upstands - Rebar - AP#04 | 9 | 2024-12-22 | 2025-01-01
R7S1-ONSB-AP04-229 | Foundations/Upstands - Shuttering (Including dowel Works) - AP#04 | 9 | 2024-12-22 | 2025-01-01
R7S1-ONSB-AP04-232 | Installation of MEP U/G services below Boxes - AP#04 | 9 | 2024-12-22 | 2025-01-01
R7S1-ONSB-AP04-230 | Foundations/Upstands - Casting - AP#04 | 27 | 2024-12-02 | 2025-01-02
R7S1-ONSB-AP04-231 | Waterproofing For Foundations/Upstands - AP#04 | 2 | 2025-01-05 | 2025-01-06
R7S1-ONSB-AP04-233 | Backfilling & Compaction - AP#04 | 3 | 2025-01-06 | 2025-01-08
SLAB-ON-GRADE & UG MEP WORKS (in Corridor) |  | 63 | 2025-02-05 | 2025-04-24
LEFT SIDE |  | 49 | 2025-02-23 | 2025-04-24
R7S1-ONSG-AP04-271 | Block Work below Corridor area - AP#04 | 3 | 2025-02-23 | 2025-02-25
R7S1-ONSG-AP04-277 | Backfilling upto Pipe Level - AP#04 | 3 | 2025-02-23 | 2025-02-25
R7S1-ONSG-AP04-272 | UG MEP Works (Laying of Pipes) - AP#04 | 3 | 2025-02-24 | 2025-02-26
R7S1-ONSG-AP04-285 | Plaster Work for Blockwork - AP#04 | 4 | 2025-02-24 | 2025-02-27
R7S1-ONSG-AP04-273 | Backfilling Works after Pipe Laying - AP#04 | 2 | 2025-02-26 | 2025-03-01
R7S1-ONSG-AP04-274 | Antitermite Works - AP#04 | 2 | 2025-02-26 | 2025-03-01
R7S1-ONSG-AP04-275 | Polythene & Rebar Mesh Works - AP#04 | 2 | 2025-02-27 | 2025-03-02
R7S1-ONSG-AP04-276 | Pouring SOG Concrete - AP#04 | 2 | 2025-03-01 | 2025-03-03
R7S1-ONSG-AP04-310 | Backfilling & SOG (In Front of Lift Shaft) - AP#04 | 4 | 2025-04-21 | 2025-04-24
RIGHT SIDE |  | 25 | 2025-02-05 | 2025-03-06
R7S1-ONSG-AP04-278 | Block Work below Corridor area - AP#04 | 22 | 2025-02-05 | 2025-03-03
R7S1-ONSG-AP04-279 | UG MEP Works (Laying of Pipes) - AP#04 | 20 | 2025-02-08 | 2025-03-03
R7S1-ONSG-AP04-280 | Backfilling Works after Pipe Laying - AP#04 | 18 | 2025-02-11 | 2025-03-04
R7S1-ONSG-AP04-281 | Antitermite Works - AP#04 | 17 | 2025-02-12 | 2025-03-04
R7S1-ONSG-AP04-284 | Backfilling upto Pipe Level - AP#04 | 22 | 2025-02-06 | 2025-03-04
R7S1-ONSG-AP04-282 | Polythene & Rebar Mesh Works - AP#04 | 17 | 2025-02-13 | 2025-03-05
R7S1-ONSG-AP04-283 | Pouring SOG Concrete - AP#04 | 17 | 2025-02-15 | 2025-03-06
ERECTION WORKS |  | 81 | 2025-02-15 | 2025-05-26
GROUND FLOOR |  | 54 | 2025-02-15 | 2025-04-24
R7S1ONER-AP04GF163 | Erection of GF Boxes (Left Side) including Lift Box & Staircase - AP#04 | 7 | 2025-02-15 | 2025-02-24
R7S1ONER-AP04GF164 | Erection of GF Boxes (Right Side) - AP#04 | 7 | 2025-02-17 | 2025-02-26
R7S1ONER-AP04GF165 | Erection of GF MEP Modular Cages (Left Side) - AP#04 | 1 | 2025-03-04 | 2025-03-04
R7S1ONER-AP04GF166 | Erection of GF Corridor Slabs (Left Side) - AP#04 | 2 | 2025-03-04 | 2025-03-05
R7S1ONER-AP04GF167 | Erection of GF MEP Modular Cages (Right Side) - AP#04 | 16 | 2025-02-16 | 2025-03-06
R7S1ONER-AP04GF168 | Erection of GF Corridor Slabs Right Side) - AP#04 | 16 | 2025-02-18 | 2025-03-09
R7S1ONER-AP04GF262 | Erection of Columns/Beams Frame & Slab/Loose Elements (In Front of Lift Shaft) - AP#04 | 3 | 2025-04-22 | 2025-04-24
FIRST FLOOR |  | 44 | 2025-03-24 | 2025-04-27
R7S1ONER-AP04FF163 | Erection of FF Boxes (Left Side) - AP#04 | 3 | 2025-03-24 | 2025-03-26
R7S1ONER-AP04FF164 | Erection of FF Boxes (Right Side) - AP#04 | 3 | 2025-03-26 | 2025-03-29
R7S1ONER-AP04FF166 | Erection of FF Corridor Slabs (Left Side) - AP#04 | 2 | 2025-03-30 | 2025-04-05
R7S1ONER-AP04FF167 | Erection of FF MEP Modular Cages (Right Side) - AP#04 | 2 | 2025-03-30 | 2025-04-05
R7S1ONER-AP04FF168 | Erection of FF Corridor Slabs Right Side) - AP#04 | 2 | 2025-04-06 | 2025-04-07
R7S1ONER-AP04FF165 | Erection of FF MEP Modular Cages (Left Side) - AP#04 | 11 | 2025-04-06 | 2025-04-17
R7S1ONER-AP04FF272 | Erection of Columns/Beams Frame & Slab/Loose Elements (In Front of Lift Shaft) - AP#04 | 2 | 2025-04-26 | 2025-04-27
SECOND FLOOR |  | 18 | 2025-04-28 | 2025-05-12
R7S1ONER-AP04SF282 | Erection of Columns/Beams Frame & Slab/Loose Elements (In Front of Lift Shaft) - AP#04 | 2 | 2025-04-28 | 2025-04-29
R7S1ONER-AP04SF163 | Erection of SF Boxes (Left Side) - AP#04 | 2 | 2025-04-30 | 2025-05-03
R7S1ONER-AP04SF164 | Erection of SF Boxes (Right Side) - AP#04 | 2 | 2025-05-03 | 2025-05-05
R7S1ONER-AP04SF165 | Erection of SF MEP Modular Cages (Left Side) - AP#04 | 3 | 2025-05-03 | 2025-05-06
R7S1ONER-AP04SF166 | Erection of SF Corridor Slabs (Left Side) - AP#04 | 2 | 2025-05-06 | 2025-05-08
R7S1ONER-AP04SF167 | Erection of SF MEP Modular Cages (Right Side) - AP#04 | 2 | 2025-05-07 | 2025-05-10
R7S1ONER-AP04SF168 | Erection of SF Corridor Slabs Right Side) - AP#04 | 2 | 2025-05-10 | 2025-05-12
ROOF |  | 12 | 2025-05-12 | 2025-05-26
R7S1ONER-AP04RF103 | Erection of Loose Roof Parapets, Shaft Covers, MEP Foundation etc. - AP#04 Roof | 12 | 2025-05-12 | 2025-05-26
MEP WORKS & FINISHES |  | 191 | 2025-02-20 | 2025-09-21
GROUND FLOOR |  | 191 | 2025-02-20 | 2025-08-19
ARCH./ CIVIL WORKS |  | 162 | 2025-03-27 | 2025-08-19
CORRIDOR AREA |  | 126 | 2025-03-27 | 2025-08-19
R7S1ONAR-AP04GF105 | Flooring in Corridor - AP#04 (GF Corridor) | 91 | 2025-03-27 | 2025-07-21
R7S1ONAR-AP04GF103 | False Ceiling - 1st Fix - AP#04 (GF - Corridor) | 73 | 2025-04-23 | 2025-07-22
R7S1ONAR-AP04GF106 | Corridor Skirting - AP#04 (GF Corridor) | 2 | 2025-07-20 | 2025-07-22
R7S1ONAR-AP04GF104 | Gypsum Wall Cladding - 1st Fix (Shafts) - AP#04 (GF Corridor) | 90 | 2025-04-09 | 2025-07-28
R7S1ONAR-AP04GF107 | Gypsum Wall Cladding (Shafts) -2nd Fix - AP#04 (GF Corridor) | 4 | 2025-07-28 | 2025-08-02
R7S1ONAR-AP04GF111 | Fixing Architrave - AP#04 (GF Corridor) | 2 | 2025-08-02 | 2025-08-04
R7S1ONAR-AP04GF112 | Fixing Aluminium Doors - AP#04 (GF Corridor) | 2 | 2025-08-04 | 2025-08-06
R7S1ONAR-AP04GF108 | False Ceiling - 2nd Fix (Closing the Ceiling) - AP#04 (GF Corridor) | 3 | 2025-08-06 | 2025-08-10
R7S1ONAR-AP04GF109 | Painting - Surface Prep., Primer & 1st Coat - AP#04 (GF Corridor) | 8 | 2025-08-02 | 2025-08-11
R7S1ONAR-AP04GF133 | Painting - Surface Prep., Primer & 1st Coat for Ceiling - AP#04 (GF Corridor) | 4 | 2025-08-10 | 2025-08-14
R7S1ONAR-AP04GF110 | Painting - Final Coat (Ceiling + Walls) - AP#04 (GF Corridor) | 3 | 2025-08-16 | 2025-08-19
INSIDE BOXES |  | 96 | 2025-04-05 | 2025-07-30
R7S1ONAR-AP04GF113 | Fixing Thresholds (Joining the Room) - AP#04 (GF - inside Boxes) | 88 | 2025-04-05 | 2025-07-21
R7S1ONAR-AP04GF114 | Fixing Wooden Doors - AP#04 (GF - inside Boxes) | 4 | 2025-07-21 | 2025-07-26
R7S1ONAR-AP04GF115 | Fixing Aluminium Doors - AP#04 (GF - inside Boxes) | 4 | 2025-07-26 | 2025-07-30
IN FRONT OF LIFT SHAFT |  | 123 | 2025-04-26 | 2025-07-24
R7S1ONAR-AP04GF117 | Flooring - AP#04 (GF - Front of Lift Shaft) | 3 | 2025-04-26 | 2025-04-28
R7S1ONAR-AP04GF118 | Skirting & Thresholds - AP#04 (GF - Front of Lift Shaft) | 1 | 2025-04-28 | 2025-04-28
R7S1ONAR-AP04GF119 | Painting - Surface Prep., Primer & 1st Coat - AP#04 (GF - Front of Lift Shaft) | 4 | 2025-04-29 | 2025-05-03
R7S1ONAR-AP04GF116 | False Ceiling - 1st Fix - AP#04 (GF - Front of Lift Shaft) | 4 | 2025-05-04 | 2025-05-07
R7S1ONAR-AP04GF120 | False Ceiling - Final Fix - AP#04 (GF - Front of Lift Shaft) | 3 | 2025-05-08 | 2025-05-11
R7S1ONAR-AP04GF122 | Fixing Handrail - AP#04 (GF - Front of Lift Shaft) | 3 | 2025-07-10 | 2025-07-13
R7S1ONAR-AP04GF123 | Paint for Handrail - AP#04 (GF - Front of Lift Shaft) | 3 | 2025-07-14 | 2025-07-16
R7S1ONAR-AP04GF121 | Painting - Final Coat - AP#04 (GF - Front of Lift Shaft) | 3 | 2025-07-17 | 2025-07-20
R7S1ONAR-AP04GF125 | Fixing Wall Guard - AP#04 (GF - Front of Lift Shaft) | 2 | 2025-07-21 | 2025-07-22
R7S1ONAR-AP04GF124 | Fixing Floor Mat - AP#04 (GF - Front of Lift Shaft) | 2 | 2025-07-23 | 2025-07-24
GARBAGE ROOM |  | 2 | 2025-08-04 | 2025-08-05
R7S1ONAR-AP04GF126 | Paint Finishes and Touchups - Final Coat - AP#04 (GF - Garbage Room) | 2 | 2025-08-04 | 2025-08-05
BALCONIES |  | 153 | 2025-04-09 | 2025-08-04
R7S1ONAR-AP04GF127 | Wetarea Waterproofing - AP#04 (GF - Balconies) | 84 | 2025-04-09 | 2025-07-21
R7S1ONAR-AP04GF128 | Flooring - AP#04 (GF - Front of Lift Shaft) | 77 | 2025-04-21 | 2025-07-24
R7S1ONAR-AP04GF129 | Painting - Surface Prep., Primer & 1st Coat - AP#04 (GF - Front of Lift Shaft) | 6 | 2025-07-21 | 2025-07-28
R7S1ONAR-AP04GF131 | Fixing Handrail - AP#04 (GF - Front of Lift Shaft) | 6 | 2025-07-23 | 2025-07-30
R7S1ONAR-AP04GF132 | Paint for Handrail - AP#04 (GF - Front of Lift Shaft) | 2 | 2025-07-30 | 2025-08-02
R7S1ONAR-AP04GF130 | Painting - Final Coat - AP#04 (GF - Front of Lift Shaft) | 2 | 2025-08-02 | 2025-08-04
MEP WORKS |  | 137 | 2025-02-20 | 2025-08-16
MECHANICAL |  | 137 | 2025-02-20 | 2025-08-13
CHILLED WATER |  | 100 | 2025-02-20 | 2025-06-01
R7S1ONME-AP04GF447 | Installation of Chilled water hanger and supports - AP#04 (GF - Corridor) | 46 | 2025-02-20 | 2025-04-20
R7S1ONME-AP04GF448 | Installation of CHWP piping (connection between modular cages & modular to apartment) - AP#04 (GF - Corridor) | 28 | 2025-03-19 | 2025-04-24
R7S1ONME-AP04GF499 | Installation of CHWP connection for FCU with Valve package in Corridor, Electrical Room & ICT Room - AP#04 (GF) | 27 | 2025-03-20 | 2025-04-24
R7S1ONME-AP04GF449 | Installation of BTU Meter with valves - AP#04 (GF - Corridor) | 3 | 2025-04-26 | 2025-04-28
R7S1ONME-AP04GF450 | CHWP piping risers connections - AP#04 (GF - Corridor) | 20 | 2025-04-06 | 2025-04-28
R7S1ONME-AP04GF451 | Pressure Testing of CHWP piping - AP#04 (GF - Corridor) | 24 | 2025-03-27 | 2025-04-28
R7S1ONME-AP04GF487 | CHWP Insulation - AP#04 (GF - Corridor) | 26 | 2025-03-26 | 2025-04-30
R7S1ONME-AP04GF546 | CHWP Installation/Connections and Insulation (In Front of Lift Shaft) - AP#04 | 4 | 2025-05-28 | 2025-06-01
HVAC DUCTING |  | 131 | 2025-02-26 | 2025-08-12
R7S1ONME-AP04GF452 | Duct Riser Continuation - AP#04 (GF - Corridor) | 10 | 2025-04-16 | 2025-04-27
R7S1ONME-AP04GF453 | A/C drain & Copper pipe connection in ELV room - AP#04 (GF) | 17 | 2025-04-08 | 2025-04-27
R7S1ONME-AP04GF488 | Installation of Duct & Grill in Garbage Room - AP#04 (GF - Garbage Room) | 11 | 2025-04-15 | 2025-04-27
R7S1ONME-AP04GF498 | Installation of FCU's & Duct Connection in Corridor, Electrical Room & ICT Room - AP#04 (GF) | 39 | 2025-03-15 | 2025-05-03
R7S1ONME-AP04GF500 | Installation of Ducting and insulation (connection between modular cages) - AP#04 (GF - Corridor) | 53 | 2025-02-26 | 2025-05-03
R7S1ONME-AP04GF501 | Installation of Grilles in the Corridor - AP#04 (GF - Corridor) | 2 | 2025-08-10 | 2025-08-12
FIRE FIGHTING |  | 119 | 2025-03-15 | 2025-08-13
R7S1ONME-AP04GF454 | Riser Continuity in corridor - AP#04 (GF - Corridor) | 11 | 2025-04-06 | 2025-04-17
R7S1ONME-AP04GF455 | Continuitu of FF pipes & ZC Valves (connection between modular cages & modular to apartment) - AP#04 (GF - Corridor) | 32 | 2025-03-15 | 2025-04-24
R7S1ONME-AP04GF896 | Installation of F.F Pipes, Testing & Final Fixtures (In Front of Lift Shaft) - AP#04 | 3 | 2025-06-02 | 2025-06-04
R7S1ONME-AP04GF489 | Installation of Pipe & sprinkler in Garbage Room - AP#04 (GF - Garbage Room) | 81 | 2025-04-09 | 2025-07-17
R7S1ONME-AP04GF456 | Installation of Sprinklers drops in corridor - AP#04 (GF - Corridor) | 4 | 2025-07-22 | 2025-07-27
R7S1ONME-AP04GF457 | Pressure Test for FF Piping in corridor - AP#04 (GF - Corridor) | 86 | 2025-04-13 | 2025-07-27
R7S1ONME-AP04GF502 | FF Flushing network - AP#04 (GF - Corridor) | 1 | 2025-07-27 | 2025-07-28
R7S1ONME-AP04GF459 | Installation of Alarm check valve, Fire Extinguishers & Blanket - AP#04 (GF - Corridor) | 100 | 2025-04-10 | 2025-08-10
R7S1ONME-AP04GF458 | Installation of Sprinklers in corridor - AP#04 (GF - Corridor) | 3 | 2025-08-10 | 2025-08-13
WATER SUPPLY |  | 83 | 2025-02-20 | 2025-05-31
R7S1ONME-AP04GF491 | Installation of Sanitary Fixtures in Janitor Room - AP#04 (GF - Janitor Room) | 16 | 2025-02-20 | 2025-03-11
R7S1ONME-AP04GF490 | Installation of WS Pipe in Garbage Room - AP#04 (GF - Garbage Room) | 38 | 2025-02-20 | 2025-04-10
R7S1ONME-AP04GF460 | Riser Continuity in Shafts - AP#04 (GF - Corridor) | 12 | 2025-04-06 | 2025-04-19
R7S1ONME-AP04GF461 | WS High Level Pipe continuation & Insulation works - AP#04 (GF - Corridor) | 36 | 2025-03-10 | 2025-04-24
R7S1ONME-AP04GF462 | Installation of Cold, Hot water line & Hot water return - AP#04 (GF - Corridor) | 35 | 2025-03-18 | 2025-05-01
R7S1ONME-AP04GF463 | Water Meter Installation - AP#04 (GF - Corridor) | 4 | 2025-05-01 | 2025-05-06
R7S1ONME-AP04GF464 | Pressure Test for WS - AP#04 (GF - Corridor) | 4 | 2025-05-26 | 2025-05-31
R7S1ONME-AP04GF503 | Insulation for Hot water line & Hot water return - AP#04 (GF - Corridor) | 43 | 2025-04-10 | 2025-05-31
DRAINAGE |  | 83 | 2025-02-20 | 2025-05-31
R7S1ONME-AP04GF468 | Drainage Riser continuation in Shafts - AP#04 (GF - Corridor) | 11 | 2025-04-08 | 2025-04-20
R7S1ONME-AP04GF466 | Installation of Clean-outs, Floor drain in balcony - AP#04 (GF - Corridor) | 48 | 2025-02-20 | 2025-04-22
R7S1ONME-AP04GF467 | Rain Water Riser continuation in Shafts - AP#04 (GF - Corridor) | 15 | 2025-04-06 | 2025-04-22
R7S1ONME-AP04GF469 | Testing for Rain Water Riser - AP#04 (GF - Corridor) | 4 | 2025-05-26 | 2025-05-31
R7S1ONME-AP04GF470 | Testing for Drainage Riser1 - AP#04 (GF - Corridor) | 4 | 2025-05-26 | 2025-05-31
ELECTRICAL |  | 137 | 2025-02-20 | 2025-08-16
POWER & LIGHTING |  | 124 | 2025-02-20 | 2025-08-16
R7S1ONME-AP04GF471 | Contiuation of Cable Trays & apartment branches - AP#04 (GF - Corridor) | 19 | 2025-02-20 | 2025-03-15
R7S1ONME-AP04GF472 | Contiuation of Cable Trunking with Flexible conduits for Lights - AP#04 (GF - Corridor) | 19 | 2025-02-20 | 2025-03-15
R7S1ONME-AP04GF473 | Installation of EMT pipes - AP#04 (GF - Corridor) | 23 | 2025-02-20 | 2025-03-19
R7S1ONME-AP04GF474 | Installation of Busbar, Electrical Meter & Tap-off - AP#04 (GF - Corridor) | 3 | 2025-05-29 | 2025-06-01
R7S1ONME-AP04GF475 | Corridor Wire Pulling - AP#04 (GF - Corridor) | 67 | 2025-03-12 | 2025-06-02
R7S1ONME-AP04GF476 | Electrical Room - Installation of Cable trays, SMDB & Termination - AP#04 (GF - Corridor) | 47 | 2025-04-09 | 2025-06-02
R7S1ONME-AP04GF497 | Termination of Tap-off with Electrical Meter in the apartments - AP#04 (GF - Corridor) | 3 | 2025-06-02 | 2025-06-04
R7S1ONME-AP04GF1076 | Continuation of Cable Tray/Trunking with Flexible conduits for Lights (In Front of Lift Shaft) - AP#04 | 4 | 2025-06-02 | 2025-06-10
R7S1ONME-AP04GF478 | Installation, Termination of Emergeny & Exit Lights with contiuity - AP#04 (GF - Corridor) | 2 | 2025-08-10 | 2025-08-12
R7S1ONME-AP04GF477 | Installation, Termination of Light Fixtures with continuity test - AP#04 (GF - Corridor & Balconies) | 3 | 2025-08-10 | 2025-08-13
R7S1ONME-AP04GF479 | Installation, Termination of PIR sensors with continuity test - AP#04 (GF - Corridor) | 2 | 2025-08-13 | 2025-08-16
LOW CURRENT SYSTEM |  | 137 | 2025-02-20 | 2025-08-14
R7S1ONME-AP04GF480 | Installation of Basket trays for BMS, CCTV, Access Control - AP#04 (GF - Corridor) | 19 | 2025-02-20 | 2025-03-15
R7S1ONME-AP04GF504 | CBS System cable installation - AP#04 (GF - Corridor) | 21 | 2025-02-20 | 2025-03-17
R7S1ONME-AP04GF481 | Voice Evacuation cable installation - AP#04 (GF - Corridor) | 21 | 2025-02-25 | 2025-03-20
R7S1ONME-AP04GF482 | Fire alarm cable installation - AP#04 (GF - Corridor) | 23 | 2025-02-23 | 2025-03-20
R7S1ONME-AP04GF484 | BMS, CCTV & Access control Cable installation - AP#04 (GF - Corridor) | 57 | 2025-04-06 | 2025-06-15
R7S1ONME-AP04GF1256 | Installation of Basket trays for Low Current, Cable Installation (In Front of Lift Shaft) - AP#04 | 4 | 2025-06-11 | 2025-06-15
R7S1ONME-AP04GF485 | Low Current Works including BMS Panel in ICT Room - AP#04 (GF - Corridor) | 10 | 2025-06-04 | 2025-06-19
R7S1ONME-AP04GF493 | Installation & Termination of Access control system for Electrical Room - AP#04 (GF) | 2 | 2025-06-19 | 2025-06-21
R7S1ONME-AP04GF483 | Fibre optic Cable pulling & Termination with OTO (in corridors to ONU) - AP#04 (GF - Corridor) | 2 | 2025-06-21 | 2025-06-22
R7S1ONME-AP04GF496 | Fluke test for CCTV & Fibre Optic Cable - AP#04 (GF - Corridor) (Ceiling 1st Fix) | 2 | 2025-06-23 | 2025-06-24
R7S1ONME-AP04GF492 | Installation & Termination of CCTV Cameras - AP#04 (GF - Corridor) | 2 | 2025-08-10 | 2025-08-12
R7S1ONME-AP04GF495 | Installation & Termination of Wireless Gateway & RF Node in corridors - AP#04 (GF - Corridor) | 2 | 2025-08-10 | 2025-08-12
R7S1ONME-AP04GF486 | Installation & Termination of Fire alarm devices & Speakers - AP#04 (GF - Corridor) | 4 | 2025-08-10 | 2025-08-14
R7S1ONME-AP04GF494 | Installation & Termination of Active Components & UPS installation in ICT Room - AP#04 (GF - Corridor) | 2 | 2025-08-12 | 2025-08-14
FIRST FLOOR |  | 154 | 2025-04-08 | 2025-09-17
ARCH./ CIVIL WORKS |  | 143 | 2025-04-21 | 2025-09-17
CORRIDOR AREA |  | 116 | 2025-04-21 | 2025-09-17
R7S1ONAR-AP04FF162 | Flooring in Corridor - AP#04 (FF - Corridor) | 10 | 2025-04-21 | 2025-05-01
R7S1ONAR-AP04FF163 | Corridor Skirting - AP#04 (FF - Corridor) | 2 | 2025-05-01 | 2025-05-03
R7S1ONAR-AP04FF160 | False Ceiling - 1st Fix - AP#04 (FF - Corridor) | 4 | 2025-05-04 | 2025-05-07
R7S1ONAR-AP04FF161 | Gypsum Wall Cladding (Shafts) - AP#04 (FF - Corridor) | 6 | 2025-07-19 | 2025-07-24
R7S1ONAR-AP04FF164 | Gypsum Wall Cladding (Shafts) -2nd Fix - AP#04 (FF Corridor) | 4 | 2025-07-26 | 2025-07-29
R7S1ONAR-AP04FF168 | Fixing Architrave - AP#04 (FF Corridor) | 2 | 2025-07-30 | 2025-07-31
R7S1ONAR-AP04FF169 | Fixing Aluminium Doors - AP#04 (FF Corridor) | 2 | 2025-08-02 | 2025-08-03
R7S1ONAR-AP04FF165 | False Ceiling - 2nd Fix (Closing the Ceiling) - AP#04 (FF Corridor) | 3 | 2025-08-04 | 2025-08-06
R7S1ONAR-AP04FF166 | Painting - Surface Prep., Primer & 1st Coat for Walls - AP#04 (FF Corridor) | 8 | 2025-07-30 | 2025-08-07
R7S1ONAR-AP04FF201 | Painting - Surface Prep., Primer & 1st Coat for Ceiling - AP#04 (FF Corridor) | 4 | 2025-08-07 | 2025-08-11
R7S1ONAR-AP04FF167 | Painting - Final Coat (Ceiling + Walls) - AP#04 (FF Corridor) | 3 | 2025-09-15 | 2025-09-17
INSIDE BOXES |  | 32 | 2025-05-12 | 2025-05-26
R7S1ONAR-AP04FF170 | Fixing Thresholds (Joining the Room) - AP#04 (FF - inside Boxes) | 4 | 2025-05-12 | 2025-05-17
R7S1ONAR-AP04FF171 | Fixing Wooden Doors - AP#04 (FF - inside Boxes) | 4 | 2025-05-17 | 2025-05-21
R7S1ONAR-AP04FF172 | Fixing Aluminium Doors (Next Floor) - AP#04 (FF - inside Boxes) | 4 | 2025-05-21 | 2025-05-26
IN FRONT OF LIFT SHAFT |  | 59 | 2025-08-09 | 2025-09-07
R7S1ONAR-AP04FF174 | Flooring - AP#04 (FF - Front of Lift Shaft) | 4 | 2025-08-09 | 2025-08-12
R7S1ONAR-AP04FF175 | Skirting & Thresholds - AP#04 (FF - Front of Lift Shaft) | 1 | 2025-08-12 | 2025-08-12
R7S1ONAR-AP04FF176 | Painting - Surface Prep., Primer & 1st Coat - AP#04 (FF - Front of Lift Shaft) | 4 | 2025-08-13 | 2025-08-17
R7S1ONAR-AP04FF173 | False Ceiling - 1st Fix - AP#04 (FF - Front of Lift Shaft) | 4 | 2025-08-18 | 2025-08-21
R7S1ONAR-AP04FF177 | False Ceiling - Final Fix - AP#04 (FF - Front of Lift Shaft) | 3 | 2025-08-23 | 2025-08-25
R7S1ONAR-AP04FF179 | Fixing Handrail - AP#04 (FF - Front of Lift Shaft) | 3 | 2025-08-26 | 2025-08-28
R7S1ONAR-AP04FF180 | Paint for Handrail - AP#04 (FF - Front of Lift Shaft) | 3 | 2025-08-30 | 2025-09-01
R7S1ONAR-AP04FF178 | Painting - 2nd Coat - AP#04 (FF - Front of Lift Shaft) | 3 | 2025-09-02 | 2025-09-04
R7S1ONAR-AP04FF181 | Fixing Floor Mat - AP#04 (FF - Front of Lift Shaft) | 2 | 2025-09-06 | 2025-09-07
R7S1ONAR-AP04FF182 | Fixing Wall Guard - AP#04 (FF - Front of Lift Shaft) | 2 | 2025-09-06 | 2025-09-07
GARBAGE ROOM |  | 37 | 2025-07-23 | 2025-08-03
R7S1ONAR-AP04FF183 | Installation of Dry Walls - First Fix - AP#04 (FF - Garbage Room) | 2 | 2025-07-23 | 2025-07-24
R7S1ONAR-AP04FF184 | Installation of Dry Walls - Final Fix - AP#04 (FF - Garbage Room) | 2 | 2025-07-24 | 2025-07-26
R7S1ONAR-AP04FF185 | Garbage Rooms - Wall Tile Finishes (One Side) - AP#04 (FF - Garbage Room) | 2 | 2025-07-26 | 2025-07-27
R7S1ONAR-AP04FF186 | Paint Works of Dry Walls - First Coat - AP#04 (FF - Garbage Room) | 2 | 2025-07-28 | 2025-07-29
R7S1ONAR-AP04FF187 | Installation of the Garbage Chute Door - AP#04 (FF - Garbage Room) | 2 | 2025-07-30 | 2025-07-31
R7S1ONAR-AP04FF188 | Paint Finishes and Touchups - Final Coat - AP#04 (FF - Garbage Room) | 2 | 2025-08-02 | 2025-08-03
BALCONIES |  | 132 | 2025-05-04 | 2025-09-14
R7S1ONAR-AP04FF189 | Wetarea Waterproofing - AP#04 (FF - Balconies) | 8 | 2025-05-04 | 2025-05-12
R7S1ONAR-AP04FF190 | Flooring - AP#04 (FF - Balconies) | 6 | 2025-05-08 | 2025-05-14
R7S1ONAR-AP04FF191 | Painting - Surface Prep., Primer & 1st Coat - AP#04 (FF - Balconies) | 8 | 2025-05-11 | 2025-05-19
R7S1ONAR-AP04FF193 | Fixing Handrail - AP#04 (FF - Balconies) | 6 | 2025-08-30 | 2025-09-04
R7S1ONAR-AP04FF194 | Paint for Handrail - AP#04 (FF - Balconies) | 4 | 2025-09-06 | 2025-09-09
R7S1ONAR-AP04FF192 | Painting - 2nd Coat - AP#04 (FF - Balconies) | 4 | 2025-09-10 | 2025-09-14
MEP WORKS |  | 104 | 2025-04-08 | 2025-08-18
MECHANICAL |  | 96 | 2025-04-14 | 2025-08-12
CHILLED WATER |  | 54 | 2025-04-26 | 2025-06-10
R7S1ONME-AP04FF184 | Installation of Chilled water hanger and supports - AP#04 (FF Corridor) | 4 | 2025-04-26 | 2025-04-29
R7S1ONME-AP04FF234 | Installation of CHWP connection for FCU with Valve package in Corridor, Electrical Room & ICT Room | 4 | 2025-04-26 | 2025-04-29
R7S1ONME-AP04FF185 | Installation of CHWP piping (connection between modular cages & modular to apartment) - AP#04 -(FF Corridor) | 4 | 2025-04-30 | 2025-05-04
R7S1ONME-AP04FF186 | Installation of BTU Meter with valves - AP#04 (FF Corridor) | 4 | 2025-05-01 | 2025-05-05
R7S1ONME-AP04FF187 | CHWP piping risers connections - AP#04 (FF Corridor) | 3 | 2025-05-06 | 2025-05-08
R7S1ONME-AP04FF188 | Pressure Testing of CHWP piping - AP#04 (FF Corridor) | 1 | 2025-05-10 | 2025-05-10
R7S1ONME-AP04FF223 | CHWP Insulation - AP#04 (FF Corridor) | 4 | 2025-05-11 | 2025-05-14
R7S1ONME-AP04FF556 | CHWP Installation/Connections and Insulation (In Front of Lift Shaft) - AP#04 | 4 | 2025-06-02 | 2025-06-10
HVAC DUCTING |  | 87 | 2025-04-26 | 2025-08-09
R7S1ONME-AP04FF235 | Installation of FCU's & Duct Connection in Corridor, Electrical Room & ICT Room - AP#04 (FF Corridor) | 4 | 2025-04-26 | 2025-04-29
R7S1ONME-AP04FF189 | Duct Riser Continuation - AP#04 (FF Corridor) | 4 | 2025-05-03 | 2025-05-07
R7S1ONME-AP04FF190 | A/C drain & Copper pipe connection in ELV room - AP#04 (FF Corridor) | 4 | 2025-05-07 | 2025-05-12
R7S1ONME-AP04FF236 | Installation of Ducting and insulation (connection between modular cages) - AP#04 (FF Corridor) | 4 | 2025-05-07 | 2025-05-12
R7S1ONME-AP04FF224 | Installation of Duct & Grill in Garbage Room - AP#04 (FF Corridor) | 2 | 2025-05-12 | 2025-05-14
R7S1ONME-AP04FF237 | Installation of Grilles in the Corridor - AP#04 (FF Corridor) | 2 | 2025-08-07 | 2025-08-09
FIRE FIGHTING |  | 93 | 2025-04-19 | 2025-08-12
R7S1ONME-AP04FF191 | Riser Continuity in corridor - AP#04 (FF Corridor) | 4 | 2025-05-03 | 2025-05-07
R7S1ONME-AP04FF192 | Continuation of FF pipes & ZC Valves (connection between modular cages & modular to apartment) - AP#04 (FF Corridor) | 4 | 2025-05-03 | 2025-05-07
R7S1ONME-AP04FF193 | Installation of Sprinklers drops in corridor - AP#04 (FF Corridor) | 4 | 2025-05-08 | 2025-05-12
R7S1ONME-AP04FF194 | Pressure Test for FF Piping in corridor - AP#04 (FF Corridor) | 2 | 2025-05-13 | 2025-05-14
R7S1ONME-AP04FF238 | FF Flushing network - AP#04 (FF Corridor) | 2 | 2025-05-24 | 2025-05-26
R7S1ONME-AP04FF906 | Installation of F.F Pipes, Testing & Final Fixtures (In Front of Lift Shaft) - AP#04 | 3 | 2025-06-11 | 2025-06-14
R7S1ONME-AP04FF225 | Installation of Pipe & sprinkler in Garbage Room - AP#04 (FF Corridor) | 74 | 2025-04-19 | 2025-07-17
R7S1ONME-AP04FF195 | Installation of Sprinklers in corridor - AP#04 (FF Corridor) | 2 | 2025-08-07 | 2025-08-09
R7S1ONME-AP04FF196 | Installation of Alarm check valve, Fire Extinguishers & Blanket (Last Stage of the Building) - AP#04 (FF Corridor) | 2 | 2025-08-10 | 2025-08-12
WATER SUPPLY |  | 42 | 2025-04-14 | 2025-05-31
R7S1ONME-AP04FF226 | Installation of WS Pipe in Garbage Room - AP#04 (FF Corridor) | 5 | 2025-04-14 | 2025-04-20
R7S1ONME-AP04FF227 | Installation of Sanitary Fixtures in Janitor Room - AP#04 (FF Corridor) | 5 | 2025-04-14 | 2025-04-20
R7S1ONME-AP04FF198 | WS High Level Pipe continuation & Insulation works in Corridor - AP#04 (FF Corridor) | 4 | 2025-04-17 | 2025-04-21
R7S1ONME-AP04FF199 | Installation of Cold, Hot water line & Hot water return in corridor - AP#04 (FF Corridor) | 3 | 2025-04-22 | 2025-04-24
R7S1ONME-AP04FF200 | Water Meter Installation in Corridor - AP#04 (FF Corridor) | 4 | 2025-04-26 | 2025-04-29
R7S1ONME-AP04FF197 | Riser Continuity in Shafts - AP#04 (FF Corridor) | 12 | 2025-04-19 | 2025-05-03
R7S1ONME-AP04FF201 | Pressure Test for WS - AP#04 (FF Corridor) | 4 | 2025-05-26 | 2025-05-31
R7S1ONME-AP04FF239 | Insulation for Hot water line & Hot water return in corridor - AP#04 (FF Corridor) | 34 | 2025-04-21 | 2025-05-31
DRAINAGE |  | 39 | 2025-04-19 | 2025-05-31
R7S1ONME-AP04FF202 | Installation of Clean-outs, Floor drain in balcony - AP#04 (FF Corridor) | 4 | 2025-04-19 | 2025-04-22
R7S1ONME-AP04FF204 | Drainage Riser continuation in Shafts - AP#04 (FF Corridor) | 12 | 2025-04-19 | 2025-05-03
R7S1ONME-AP04FF203 | Rain Water Riser continuation in Shafts - AP#04 (FF Corridor) | 4 | 2025-05-03 | 2025-05-07
R7S1ONME-AP04FF205 | Testing for Rain Water Riser - AP#04 (FF Corridor) | 4 | 2025-05-26 | 2025-05-31
R7S1ONME-AP04FF206 | Testing for Drainage Riser - AP#04 (FF Corridor) | 4 | 2025-05-26 | 2025-05-31
ELECTRICAL |  | 104 | 2025-04-08 | 2025-08-18
POWER & LIGHTING |  | 95 | 2025-04-08 | 2025-08-18
R7S1ONME-AP04FF209 | Installation of EMT pipes - AP#04 (FF Corridor) | 5 | 2025-04-08 | 2025-04-13
R7S1ONME-AP04FF207 | Contiuation of Cable Trays & apartment branches - AP#04 (FF Corridor) | 4 | 2025-04-26 | 2025-04-29
R7S1ONME-AP04FF208 | Contiuation of Cable Trunking with Flexible conduits for Lights - AP#04 (FF Corridor) | 4 | 2025-04-26 | 2025-04-29
R7S1ONME-AP04FF210 | Installation of Busbar, Electrical Meter & Tap-off - AP#04 (FF Corridor) | 3 | 2025-06-02 | 2025-06-04
R7S1ONME-AP04FF233 | Termination of Tap-off with Electrical Meter in the apartments - AP#04 (FF Corridor) | 3 | 2025-06-10 | 2025-06-12
R7S1ONME-AP04FF211 | Corridor Wire Pulling - AP#04 (FF Corridor) | 6 | 2025-06-03 | 2025-06-14
R7S1ONME-AP04FF1086 | Continuation of Cable Tray/Trunking with Flexible conduits for Lights (In Front of Lift Shaft) - AP#04 | 4 | 2025-06-11 | 2025-06-15
R7S1ONME-AP04FF212 | Electrical Room - Installation of Cable trays, SMDB & Termination - AP#04 (FF Corridor) | 6 | 2025-06-15 | 2025-06-21
R7S1ONME-AP04FF214 | Installation, Termination of Emergeny & Exit Lights with contiuity - AP#04 (FF Corridor) | 2 | 2025-08-07 | 2025-08-09
R7S1ONME-AP04FF213 | Installation, Termination of Light Fixtures with continuity test - AP#04 (FF - Corridor & Balconies) | 3 | 2025-08-07 | 2025-08-10
R7S1ONME-AP04FF215 | Installation, Termination of PIR sensors with continuity test - AP#04 (FF Corridor) | 2 | 2025-08-16 | 2025-08-18
LOW CURRENT SYSTEM |  | 89 | 2025-04-26 | 2025-08-11
R7S1ONME-AP04FF240 | CBS System cable installation - AP#04 (FF Corridor) | 3 | 2025-04-26 | 2025-04-28
R7S1ONME-AP04FF216 | Installation of Basket trays for BMS, CCTV, Access Control - AP#04 (FF Corridor) | 4 | 2025-04-26 | 2025-04-29
R7S1ONME-AP04FF218 | Fire alarm cable installation - AP#04 (FF Corridor) | 3 | 2025-04-27 | 2025-04-29
R7S1ONME-AP04FF217 | Voice Evacuation cable installation - AP#04 (FF Corridor) | 3 | 2025-04-29 | 2025-05-01
R7S1ONME-AP04FF220 | BMS, CCTV & Access control Cable installation - AP#04 (FF Corridor) | 2 | 2025-06-18 | 2025-06-19
R7S1ONME-AP04FF1266 | Installation of Basket trays for Low Current, Cable Installation (In Front of Lift Shaft) - AP#04 | 4 | 2025-06-16 | 2025-06-19
R7S1ONME-AP04FF221 | Low Current Works including BMS Panel in ICT Room - AP#04 (FF Corridor) | 10 | 2025-06-14 | 2025-06-24
R7S1ONME-AP04FF219 | Fibre optic Cable pulling & Termination with OTO (in corridors to ONU) - AP#04 (FF Corridor) | 2 | 2025-06-25 | 2025-06-26
R7S1ONME-AP04FF232 | Fluke test for CCTV & Fibre Optic Cable - AP#04 (FF Corridor) | 2 | 2025-06-25 | 2025-06-26
R7S1ONME-AP04FF228 | Installation & Termination of CCTV Cameras - AP#04 (FF Corridor) | 2 | 2025-08-07 | 2025-08-09
R7S1ONME-AP04FF229 | Installation & Termination of Access control system for Electrical Room - AP#04 (FF Corridor) | 2 | 2025-08-07 | 2025-08-09
R7S1ONME-AP04FF231 | Installation & Termination of Wireless Gateway & RF Node - AP#04 (FF Corridor) | 2 | 2025-08-07 | 2025-08-09
R7S1ONME-AP04FF222 | Installation & Termination of Fire alarm devices & Speakers - AP#04 (FF Corridor) | 4 | 2025-08-07 | 2025-08-11
R7S1ONME-AP04FF230 | Installation & Termination of Active Components & UPS installation in ICT Room | 2 | 2025-08-10 | 2025-08-11
SECOND FLOOR |  | 130 | 2025-04-28 | 2025-09-21
ARCH./ CIVIL WORKS |  | 130 | 2025-04-28 | 2025-09-21
CORRIDOR AREA |  | 97 | 2025-04-28 | 2025-09-21
R7S1ONAR-AP04SF105 | Flooring in Corridor - AP#04 (SF Corridor) | 6 | 2025-04-28 | 2025-05-05
R7S1ONAR-AP04SF106 | Corridor Skirting - AP#04 (SF Corridor) | 2 | 2025-05-04 | 2025-05-06
R7S1ONAR-AP04SF103 | False Ceiling - 1st Fix - AP#04 (SF Corridor) | 4 | 2025-05-06 | 2025-05-11
R7S1ONAR-AP04SF104 | Gypsum Wall Cladding (Shafts) - AP#04 (SF Corridor) | 6 | 2025-08-02 | 2025-08-09
R7S1ONAR-AP04SF107 | Gypsum Wall Cladding (Shafts) -2nd Fix - AP#04 (SF Corridor) | 4 | 2025-08-09 | 2025-08-13
R7S1ONAR-AP04SF111 | Fixing Architrave - AP#04 (SF Corridor) | 2 | 2025-08-13 | 2025-08-16
R7S1ONAR-AP04SF112 | Fixing Aluminium Doors - AP#04 (SF Corridor) | 2 | 2025-08-16 | 2025-08-18
R7S1ONAR-AP04SF108 | False Ceiling - 2nd Fix (Closing the Ceiling) - AP#04 (SF Corridor) | 3 | 2025-08-18 | 2025-08-21
R7S1ONAR-AP04SF109 | Painting - Surface Prep., Primer & 1st Coat - AP#04 (SF Corridor) | 8 | 2025-08-13 | 2025-08-23
R7S1ONAR-AP04SF133 | Painting - Surface Prep., Primer & 1st Coat - AP#04 (SF Corridor) | 4 | 2025-08-21 | 2025-08-26
R7S1ONAR-AP04SF110 | Painting - Final Coat (Ceiling + Walls) - AP#04 (SF Corridor) | 3 | 2025-09-18 | 2025-09-21
INSIDE BOXES |  | 30 | 2025-05-12 | 2025-05-26
R7S1ONAR-AP04SF113 | Fixing Thresholds (Joining the Room) - AP#04 (SF - inside Boxes) | 4 | 2025-05-12 | 2025-05-17
R7S1ONAR-AP04SF114 | Fixing Wooden Doors - AP#04 (SF - inside Boxes) | 4 | 2025-05-17 | 2025-05-21
R7S1ONAR-AP04SF115 | Fixing Aluminium Doors (Next Floor) - AP#04 (SF - inside Boxes) | 4 | 2025-05-21 | 2025-05-26
IN FRONT OF LIFT SHAFT |  | 114 | 2025-05-12 | 2025-09-07
R7S1ONAR-AP04SF116 | False Ceiling - 1st Fix - AP#04 (SF - Front of Lift Shaft) | 3 | 2025-05-12 | 2025-05-15
R7S1ONAR-AP04SF117 | Flooring - AP#04 (SF - Front of Lift Shaft) | 4 | 2025-05-15 | 2025-05-20
R7S1ONAR-AP04SF118 | Skirting & Thresholds - AP#04 (SF - Front of Lift Shaft) | 2 | 2025-05-20 | 2025-05-22
R7S1ONAR-AP04SF119 | Painting - Surface Prep., Primer & 1st Coat - AP#04 (SF - Front of Lift Shaft) | 4 | 2025-05-22 | 2025-05-27
R7S1ONAR-AP04SF120 | False Ceiling - Final Fix - AP#04 (SF - Front of Lift Shaft) | 3 | 2025-05-27 | 2025-05-31
R7S1ONAR-AP04SF122 | Fixing Handrail - AP#04 (SF - Front of Lift Shaft) | 3 | 2025-08-26 | 2025-08-28
R7S1ONAR-AP04SF123 | Paint for Handrail - AP#04 (SF - Front of Lift Shaft) | 3 | 2025-08-30 | 2025-09-01
R7S1ONAR-AP04SF121 | Painting - 2nd Coat - AP#04 (SF - Front of Lift Shaft) | 3 | 2025-09-02 | 2025-09-04
R7S1ONAR-AP04SF124 | Fixing Floor Mat - AP#04 (SF - Front of Lift Shaft) | 2 | 2025-09-06 | 2025-09-07
R7S1ONAR-AP04SF125 | Fixing Wall Guard - AP#04 (SF - Front of Lift Shaft) | 2 | 2025-09-06 | 2025-09-07
GARBAGE ROOM |  | 49 | 2025-07-07 | 2025-08-26
R7S1ONAR-AP04SF132 | Installation of Garbage Chute Full System from GF to 2nd Floor - AP#04 (SF - Garbage Room) | 10 | 2025-07-07 | 2025-07-17
R7S1ONAR-AP04SF126 | Installation of Dry Walls - First Fix - AP#04 (SF - Garbage Room) | 2 | 2025-07-19 | 2025-07-20
R7S1ONAR-AP04SF127 | Installation of Dry Walls - Final Fix - AP#04 (SF - Garbage Room) | 2 | 2025-07-21 | 2025-07-22
R7S1ONAR-AP04SF128 | Garbage Rooms - Wall Tile Finishes (One Side) - AP#04 (SF - Garbage Room) | 2 | 2025-07-22 | 2025-07-23
R7S1ONAR-AP04SF129 | Paint Works of Dry Walls - First Coat - AP#04 (SF - Garbage Room) | 2 | 2025-07-24 | 2025-07-26
R7S1ONAR-AP04SF130 | Installation of the Garbage Chute Door - AP#04 (SF - Garbage Room) | 2 | 2025-07-27 | 2025-07-28
R7S1ONAR-AP04SF131 | Paint Finishes and Touchups - Final Coat - AP#04 (SF - Garbage Room) | 2 | 2025-08-24 | 2025-08-26
BALCONIES |  | 130 | 2025-05-05 | 2025-09-14
R7S1ONAR-AP04FF195 | Wetarea Waterproofing - AP#04 (SF - Balconies) | 8 | 2025-05-05 | 2025-05-14
R7S1ONAR-AP04FF196 | Flooring - AP#04 (SF - Balconies) | 6 | 2025-05-10 | 2025-05-17
R7S1ONAR-AP04FF197 | Painting - Surface Prep., Primer & 1st Coat - AP#04 (SF - Balconies) | 8 | 2025-05-12 | 2025-05-21
R7S1ONAR-AP04FF199 | Fixing Handrail - AP#04 (SF - Balconies) | 6 | 2025-08-30 | 2025-09-04
R7S1ONAR-AP04FF200 | Paint for Handrail - AP#04 (SF - Balconies) | 4 | 2025-09-06 | 2025-09-09
R7S1ONAR-AP04FF198 | Painting - 2nd Coat - AP#04 (SF - Balconies) | 4 | 2025-09-10 | 2025-09-14
MEP WORKS |  | 98 | 2025-05-12 | 2025-08-27
MECHANICAL |  | 98 | 2025-05-12 | 2025-08-25
CHILLED WATER |  | 44 | 2025-05-12 | 2025-06-15
R7S1ONME-AP04SF166 | Installation of Chilled water hanger and supports - AP#04 (SF Corridor) | 4 | 2025-05-12 | 2025-05-17
R7S1ONME-AP04SF216 | Installation of CHWP connection for FCU with Valve package in Corridor, Electrical Room & ICT Room | 4 | 2025-05-12 | 2025-05-17
R7S1ONME-AP04SF167 | Installation of CHWP piping (connection between modular cages & modular to apartment) - AP#04 (SF Corridor) | 4 | 2025-05-17 | 2025-05-21
R7S1ONME-AP04SF168 | Installation of BTU Meter with valves - AP#04 (SF Corridor) | 4 | 2025-05-18 | 2025-05-22
R7S1ONME-AP04SF169 | CHWP piping risers connections - AP#04 (SF Corridor) | 3 | 2025-05-22 | 2025-05-26
R7S1ONME-AP04SF170 | Pressure Testing of CHWP piping - AP#04 (SF Corridor) | 2 | 2025-05-26 | 2025-05-28
R7S1ONME-AP04SF205 | CHWP Insulation - AP#04 (SF Corridor) | 4 | 2025-05-28 | 2025-06-02
R7S1ONME-AP04SF566 | CHWP Installation/Connections and Insulation (In Front of Lift Shaft) - AP#04 | 4 | 2025-06-11 | 2025-06-15
HVAC DUCTING |  | 73 | 2025-05-12 | 2025-08-24
R7S1ONME-AP04SF171 | Duct Riser Continuation - AP#04 (SF Corridor) | 4 | 2025-05-12 | 2025-05-17
R7S1ONME-AP04SF217 | Installation of FCU's & Duct Connection in Corridor, Electrical Room & ICT Room - AP#04 (SF Corridor) | 4 | 2025-05-12 | 2025-05-17
R7S1ONME-AP04SF172 | A/C drain & Copper pipe connection in ELV room - AP#04 (SF Corridor) | 4 | 2025-05-17 | 2025-05-21
R7S1ONME-AP04SF218 | Installation of Ducting and insulation (connection between modular cages) - AP#04 (SF Corridor) | 4 | 2025-05-17 | 2025-05-21
R7S1ONME-AP04SF206 | Installation of Duct & Grill in Garbage Room - AP#04 (SF Corridor) | 2 | 2025-08-21 | 2025-08-24
R7S1ONME-AP04SF219 | Installation of Grilles in the Corridor - AP#04 (SF Corridor) | 2 | 2025-08-21 | 2025-08-24
FIRE FIGHTING |  | 98 | 2025-05-12 | 2025-08-25
R7S1ONME-AP04SF173 | Riser Continuity Succ - Closing of Gysum Boards on shaft - AP#04 (SF Corridor) | 4 | 2025-05-12 | 2025-05-17
R7S1ONME-AP04SF174 | FF Contiuation on High Level with Valves - AP#04 (SF Corridor) | 4 | 2025-05-12 | 2025-05-17
R7S1ONME-AP04SF175 | Installation of Sprinklers drops - AP#04 (SF Corridor) | 4 | 2025-05-17 | 2025-05-21
R7S1ONME-AP04SF176 | Pressure Test for FF Piping - AP#04 (SF Corridor) | 2 | 2025-05-21 | 2025-05-24
R7S1ONME-AP04SF916 | Installation of F.F Pipes, Testing & Final Fixtures (In Front of Lift Shaft) - AP#04 | 3 | 2025-06-16 | 2025-06-18
R7S1ONME-AP04SF207 | Installation of Pipe & sprinkler in Garbage Room - AP#04 (SF Corridor) | 1 | 2025-08-21 | 2025-08-23
R7S1ONME-AP04SF177 | Installation of Sprinklers - AP#04 (SF Corridor) | 3 | 2025-08-21 | 2025-08-25
R7S1ONME-AP04SF178 | Installation of Fire Extinguishers - AP#04 (SF Corridor) | 3 | 2025-08-21 | 2025-08-25
WATER SUPPLY |  | 23 | 2025-05-12 | 2025-06-11
R7S1ONME-AP04SF208 | Installation of WS Pipe in Garbage Room - AP#04 (SF Corridor) | 2 | 2025-05-12 | 2025-05-14
R7S1ONME-AP04SF179 | Riser Continuity - AP#04 (SF Corridor) | 4 | 2025-05-12 | 2025-05-17
R7S1ONME-AP04SF180 | WS High Level Pipe continuation & Insulation works - AP#04 (SF Corridor) | 4 | 2025-05-12 | 2025-05-17
R7S1ONME-AP04SF209 | Installation of Sanitary Fixtures in Janitor Room - AP#04 (SF Corridor) | 4 | 2025-05-12 | 2025-05-17
R7S1ONME-AP04SF181 | Instalation of Hot water line in corridor - AP#04 (SF Corridor) | 4 | 2025-05-17 | 2025-05-21
R7S1ONME-AP04SF182 | Water Meter Installation - AP#04 (SF Corridor) | 4 | 2025-05-21 | 2025-05-26
R7S1ONME-AP04SF183 | Pressure Test for WS - AP#04 (SF Corridor) | 4 | 2025-05-31 | 2025-06-04
R7S1ONME-AP04FF241 | Insulation for Hot water line & Hot water return in corridor - AP#04 (SF Corridor) | 2 | 2025-06-04 | 2025-06-11
DRAINAGE |  | 19 | 2025-05-12 | 2025-05-31
R7S1ONME-AP04SF184 | Installation of Clean-outs - AP#04 (SF Corridor) | 4 | 2025-05-12 | 2025-05-17
R7S1ONME-AP04SF185 | Rain Water Riser continuation - AP#04 (SF Corridor) | 4 | 2025-05-12 | 2025-05-17
R7S1ONME-AP04SF186 | Drainage Riser continuation - AP#04 (SF Corridor) | 4 | 2025-05-12 | 2025-05-17
R7S1ONME-AP04SF187 | Testing for Rain Water Riser - AP#04 (SF Corridor) | 4 | 2025-05-26 | 2025-05-31
R7S1ONME-AP04SF188 | Testing for Drainage Riser - AP#04 (SF Corridor) | 4 | 2025-05-26 | 2025-05-31
ELECTRICAL |  | 73 | 2025-05-12 | 2025-08-27
POWER & LIGHTING |  | 73 | 2025-05-12 | 2025-08-27
R7S1ONME-AP04SF189 | Contiuation of Cable Trays & apartment branches - AP#04 (SF Corridor) | 4 | 2025-05-12 | 2025-05-17
R7S1ONME-AP04SF190 | Contiuation of Cable Trunking with Flexible conduits for Lights - AP#04 (SF Corridor) | 4 | 2025-05-12 | 2025-05-17
R7S1ONME-AP04SF191 | Installation of EMT pipes - AP#04 (SF Corridor) | 5 | 2025-05-12 | 2025-05-18
R7S1ONME-AP04SF192 | Installation of Busbar, Electrical Meter & Tap-off in Corridor - AP#04 (SF Corridor) | 3 | 2025-06-10 | 2025-06-12
R7S1ONME-AP04SF215 | Termination of Tap-off with Electrical Meter in the apartments - AP#04 (SF Corridor) | 3 | 2025-06-14 | 2025-06-16
R7S1ONME-AP04SF193 | Corridor Wire Pulling - AP#04 (SF Corridor) | 6 | 2025-06-11 | 2025-06-17
R7S1ONME-AP04SF1096 | Continuation of Cable Tray/Trunking with Flexible conduits for Lights (In Front of Lift Shaft) - AP#04 | 4 | 2025-06-16 | 2025-06-19
R7S1ONME-AP04SF194 | Electrical Room - Installation of Cable trays, SMDB & Termination - AP#04 (SF Corridor) | 6 | 2025-07-24 | 2025-07-31
R7S1ONME-AP04SF196 | Installation, Termination of Emergeny & Exit Lights with contiuity - AP#04 (SF Corridor) | 2 | 2025-08-21 | 2025-08-24
R7S1ONME-AP04SF195 | Installation, Termination of Light Fixtures with continuity test - AP#04 (SF - Corridor & Balconies) | 3 | 2025-08-21 | 2025-08-25
R7S1ONME-AP04SF197 | Installation, Termination of PIR sensors with continuity test - AP#04 (SF Corridor) | 2 | 2025-08-25 | 2025-08-27
LOW CURRENT SYSTEM |  | 73 | 2025-05-12 | 2025-08-26
R7S1ONME-AP04SF220 | CBS System cable installation - AP#04 (SF Corridor) | 3 | 2025-05-12 | 2025-05-15
R7S1ONME-AP04SF198 | Installation of Basket trays for BMS, CCTV, Access Control - AP#04 (SF Corridor) | 4 | 2025-05-12 | 2025-05-17
R7S1ONME-AP04SF200 | Fire alarm cable installation - AP#04 (SF Corridor) | 3 | 2025-05-13 | 2025-05-17
R7S1ONME-AP04SF199 | Voice Evacuation cable installation - AP#04 (SF Corridor) | 3 | 2025-05-15 | 2025-05-19
R7S1ONME-AP04SF202 | BMS, CCTV & Access control Cable installation - AP#04 (SF Corridor) | 2 | 2025-06-21 | 2025-06-22
R7S1ONME-AP04SF1276 | Installation of Basket trays for Low Current, Cable Installation (In Front of Lift Shaft) - AP#04 | 4 | 2025-06-21 | 2025-06-24
R7S1ONME-AP04SF203 | Low Current Works including BMS Panel in ICT Room - AP#04 (SF Corridor) | 10 | 2025-07-19 | 2025-07-30
R7S1ONME-AP04SF214 | Fluke test for CCTV & Fibre Optic Cable - AP#04 (SF Corridor) | 2 | 2025-07-28 | 2025-07-30
R7S1ONME-AP04SF201 | Fibre optic Cable pulling & Termination with OTO (in corridors to ONU) - AP#04 (SF Corridor) | 2 | 2025-07-30 | 2025-08-02
R7S1ONME-AP04SF210 | Installation & Termination of CCTV Cameras - AP#04 (SF Corridor) | 2 | 2025-08-21 | 2025-08-24
R7S1ONME-AP04SF211 | Installation & Termination of Access control system for Electrical Room - AP#04 (SF Corridor) | 2 | 2025-08-21 | 2025-08-24
R7S1ONME-AP04SF213 | Installation & Termination of Wireless Gateway & RF Node in corridors - AP#04 (SF Corridor) | 2 | 2025-08-21 | 2025-08-24
R7S1ONME-AP04SF204 | Installation & Termination of Fire alarm devices & Speakers - AP#04 (SF Corridor) | 4 | 2025-08-21 | 2025-08-26
R7S1ONME-AP04SF212 | Installation & Termination of Active Components & UPS installation in ICT Room - AP#04 (SF Corridor) | 2 | 2025-08-24 | 2025-08-26
ROOF WORKS |  | 96 | 2025-05-26 | 2025-09-07
ARCH./ CIVIL WORKS |  | 96 | 2025-05-26 | 2025-09-06
R7S1ONAR-AP04RF27 | Roof Box Stiching (Concrete Works) - AP#04 (Roof) | 6 | 2025-05-26 | 2025-06-02
R7S1ONME-AP04RF206 | Installation of Roof Drains - AP#04 (Roof) | 2 | 2025-05-31 | 2025-06-02
R7S1ONAR-AP04RF28 | Roof Waterproofing Works with testing - AP#04 (Roof) | 20 | 2025-06-23 | 2025-07-16
R7S1ONAR-AP04RF29 | Laying of Gravel - AP#04 (Roof) | 2 | 2025-07-16 | 2025-07-19
R7S1ONAR-AP04RF30 | Surface Preparation & Primer for Parapets - AP#04 (Roof) | 6 | 2025-08-05 | 2025-08-12
R7S1ONAR-AP04RF31 | 1st Coat Paint for Parapets - AP#04 (Roof) | 2 | 2025-08-12 | 2025-08-14
R7S1ONAR-AP04RF32 | 2nd Coat Paint for Parapets - AP#04 (Roof) | 2 | 2025-08-14 | 2025-08-17
R7S1ONAR-AP04RF34 | Fixing Fall Arrest System - AP#04 (Roof) | 2 | 2025-08-17 | 2025-08-19
R7S1ONAR-AP04RF33 | Crossover Bridges Installation & application of Sealant on MEP penetrations - AP#04 (Roof) | 6 | 2025-08-30 | 2025-09-06
MECHANICAL |  | 65 | 2025-07-19 | 2025-08-11
HVAC |  | 29 | 2025-07-19 | 2025-08-04
R7S1ONME-AP04RF170 | Modular Installation - AP#04 (Roof) | 5 | 2025-07-19 | 2025-07-24
R7S1ONME-AP04RF171 | Continuation of Roof duct works/FAHU Connections - AP#04 (Roof) | 5 | 2025-07-21 | 2025-07-27
R7S1ONME-AP04RF173 | Insulations for ducts - AP#04 (Roof) | 5 | 2025-07-22 | 2025-07-28
R7S1ONME-AP04RF175 | Installation of FAHU - AP#04 (Roof) | 2 | 2025-07-27 | 2025-07-29
R7S1ONME-AP04RF180 | Installation of Outdoor VRF/DX Units - AP#04 (Roof) | 2 | 2025-07-28 | 2025-07-30
R7S1ONME-AP04RF181 | Installation & Insulation of the Condensation Drain - AP#04 (Roof) | 1 | 2025-07-29 | 2025-07-30
R7S1ONME-AP04RF183 | Installation of Ventilation Fans - AP#04 (Roof) | 3 | 2025-07-27 | 2025-07-30
R7S1ONME-AP04RF178 | Chilled Water System Continuation and Connections with Valve package of FAHU - AP#04 (Roof) | 4 | 2025-07-27 | 2025-07-31
R7S1ONME-AP04RF185 | Installation of Louvers - AP#04 (Roof) | 2 | 2025-07-30 | 2025-08-02
R7S1ONME-AP04RF188 | Installation & Testing of Copper Pipes - AP#04 (Roof) | 2 | 2025-07-30 | 2025-08-02
R7S1ONME-AP04RF189 | Miscellaneous Works for Mechanical Connections (Fire & Volume Dampers etc.) - AP#04 (Roof) | 2 | 2025-08-02 | 2025-08-04
WATERSUPPLY & DRAINAGE |  | 39 | 2025-07-24 | 2025-08-10
R7S1ONME-AP04RF169 | Testing for the Rain Water Risers - AP#04 (Roof) | 2 | 2025-07-27 | 2025-07-29
R7S1ONME-AP04RF172 | Installation & Continuation of Water supply pipes (connection between modular cages & modular to Shaft Riser) - AP#04 | 4 | 2025-07-24 | 2025-07-29
R7S1ONME-AP04RF176 | Installation of Air Vent & Pressure Guage with Valves at Roof - AP#04 (Roof) | 4 | 2025-07-27 | 2025-07-31
R7S1ONME-AP04RF177 | Vertical Continuation of Vent Pipes To The Roof (Drainage) - AP#04 (Roof) | 4 | 2025-07-28 | 2025-08-02
R7S1ONME-AP04RF179 | Installation of Rain Water outlet - AP#04 (Roof) | 3 | 2025-07-29 | 2025-08-02
R7S1ONME-AP04RF174 | Installation of Air Vent with Valve for Water Supply - AP#04 (Roof) | 4 | 2025-07-29 | 2025-08-03
R7S1ONME-AP04RF182 | Testing of Water Supply Pipes - AP#04 (Roof) | 2 | 2025-08-03 | 2025-08-05
R7S1ONME-AP04RF184 | Insulation of Roof Water Line - AP#04 (Roof) | 2 | 2025-08-04 | 2025-08-06
R7S1ONME-AP04RF186 | Testing for the Drainage Pipes Risers - AP#04 (Roof) | 2 | 2025-08-06 | 2025-08-09
R7S1ONME-AP04RF187 | Installation of Vent Cowl - AP#04 (Roof) | 1 | 2025-08-09 | 2025-08-10
SOLAR HEATER |  | 59 | 2025-07-29 | 2025-08-11
R7S1ONME-AP04RF201 | Installation of Solar water pumps and circulation pumps with valves(For Water Only) - AP#04 (Roof) | 2 | 2025-07-30 | 2025-08-02
R7S1ONME-AP04RF199 | Installation of Structure and Solar Panels (For Water Only) - AP#04 (Roof) | 5 | 2025-07-29 | 2025-08-04
R7S1ONME-AP04RF200 | Installation of Solar Calorifier Tank & Air cooler (For Water Only) - AP#04 (Roof) | 5 | 2025-07-30 | 2025-08-05
R7S1ONME-AP04RF202 | Installation of Solar Pipes Primary Loop - AP#04 (Roof) | 5 | 2025-07-30 | 2025-08-05
R7S1ONME-AP04RF203 | Testing of Solar Pipes Primary Loop - AP#04 (Roof) | 1 | 2025-08-05 | 2025-08-06
R7S1ONME-AP04RF204 | Insulation of Solar Pipes Primary Loop - AP#04 (Roof) | 1 | 2025-08-05 | 2025-08-06
R7S1ONME-AP04RF205 | Aluminum Cladding of Solar Pipes Primary Loop - AP#04 (Roof) | 4 | 2025-08-06 | 2025-08-11
ELECTRICAL |  | 42 | 2025-07-24 | 2025-09-07
POWER & LOW CURRENT |  | 42 | 2025-07-24 | 2025-09-07
R7S1ONME-AP04RF190 | Installation of Cables for Fire Alarm system - AP#04 (Roof) | 3 | 2025-07-24 | 2025-07-28
R7S1ONME-AP04RF191 | Installation of Cables for BMS - AP#04 (Roof) | 3 | 2025-07-24 | 2025-07-28
R7S1ONME-AP04RF192 | Installation of Fire Alarm Devices - AP#04 (Roof) | 3 | 2025-07-24 | 2025-07-28
R7S1ONME-AP04RF194 | Installation of Roof Light Fixtures - AP#04 (Roof) | 3 | 2025-07-24 | 2025-07-28
R7S1ONME-AP04RF193 | Installation of BMS Devices - AP#04 (Roof) | 4 | 2025-07-26 | 2025-07-30
R7S1ONME-AP04RF166 | Installation of Electrical Containments for BMS - AP#04 (Roof) | 7 | 2025-07-24 | 2025-08-02
R7S1ONME-AP04RF196 | Termination for BMS System - AP#04 (Roof) | 1 | 2025-08-02 | 2025-08-03
R7S1ONME-AP04RF208 | Termination of Primary & Secondary pump for Solar system - AP#04 (Roof) | 1 | 2025-08-02 | 2025-08-03
R7S1ONME-AP04RF207 | Installation & Termination of Solar System Panel - AP#04 (Roof) | 3 | 2025-08-11 | 2025-08-14
R7S1ONME-AP04RF165 | Installation of Isolators and Machine Connections - AP#04 (Roof) | 4 | 2025-08-19 | 2025-08-24
R7S1ONME-AP04RF164 | Lightening Protection & Earthing System - AP#04 (Roof) | 7 | 2025-08-17 | 2025-08-25
R7S1ONME-AP04RF167 | Installation of Fire Alarm Containment for FAHU, Fans - AP#04 (Roof) | 4 | 2025-08-25 | 2025-08-30
R7S1ONME-AP04RF197 | Termination for Fire Alarm Device - AP#04 (Roof) | 1 | 2025-08-30 | 2025-08-31
R7S1ONME-AP04RF168 | Installation of LV Power Cables for Roof Equipment - AP#04 (Roof) | 5 | 2025-08-30 | 2025-09-04
R7S1ONME-AP04RF195 | Termination for LV Cables - AP#04 (Roof) | 1 | 2025-09-04 | 2025-09-06
R7S1ONME-AP04RF198 | Megger Test for the Power Cables - AP#04 (Roof) | 1 | 2025-09-06 | 2025-09-07
STAIR CASE |  | 156 | 2025-04-21 | 2025-07-28
CIVIL WORKS |  | 102 | 2025-06-02 | 2025-07-23
STAIR CASE (MAIN WITH LIFT) |  | 101 | 2025-06-02 | 2025-07-05
R7S1ONST-AP04RG344 | Stair Flooring (Roof to GF) - AP#04 (Main Stair) | 7 | 2025-06-02 | 2025-06-15
R7S1ONST-AP04RG345 | Stair Hand Rails (Roof to GF) - AP#04 (Main Stair) | 6 | 2025-06-15 | 2025-06-22
R7S1ONST-AP04RG346 | Stair Paint - Primer & 1st Coat (Roof to GF)- AP#04 (Main Stair) | 7 | 2025-06-22 | 2025-06-30
R7S1ONST-AP04RG347 | Stair Paint - Final Coat (Roof to GF)- AP#04 (Main Stair) | 4 | 2025-06-30 | 2025-07-05
STAIR CASE (LEFT SIDE) |  | 89 | 2025-06-15 | 2025-07-10
R7S1ONST-AP04RG354 | Stair Flooring (Roof to GF) - AP#04 Left Side Stair | 7 | 2025-06-15 | 2025-06-23
R7S1ONST-AP04RG355 | Stair Hand Rails (Roof to GF) - AP#04 Left Side Stair | 6 | 2025-06-23 | 2025-06-30
R7S1ONST-AP04RG356 | Stair Paint - Primer & 1st Coat (Roof to GF) - AP#04 Left Side Stair | 6 | 2025-06-30 | 2025-07-07
R7S1ONST-AP04RG357 | Stair Paint - Final Coat (Roof to GF) - AP#04 Left Side Stair | 3 | 2025-07-07 | 2025-07-10
STAIR CASE (RIGHT SIDE) |  | 83 | 2025-06-23 | 2025-07-23
R7S1ONST-AP04RG358 | Stair Flooring (Roof to GF) - AP#04 Right Side Stair | 8 | 2025-06-23 | 2025-07-02
R7S1ONST-AP04RG359 | Stair Hand Rails (Roof to GF) - AP#04 Right Side Stair | 7 | 2025-07-02 | 2025-07-10
R7S1ONST-AP04RG360 | Stair Paint - Primer & 1st Coat (Roof to GF) - AP#04 Right Side Stair | 7 | 2025-07-10 | 2025-07-19
R7S1ONST-AP04RG361 | Stair Paint - Final Coat (Roof to GF) - AP#04 Right Side Stair | 4 | 2025-07-19 | 2025-07-23
MEP WORKS |  | 129 | 2025-04-21 | 2025-07-28
STAIR CASE (MAIN WITH LIFT) |  | 84 | 2025-06-03 | 2025-07-09
R7S1ONST-AP04RG343 | Main Staircase Wire Pulling - AP#04 (Main Stair) | 3 | 2025-06-03 | 2025-06-10
R7S1ONST-AP04RG362 | Final fix - Main Staircase Lights Fixtures & Motion Sensor - AP#04 (Main Stair) | 2 | 2025-07-05 | 2025-07-07
R7S1ONST-AP04RG363 | Final fix - Main Staircase Emergency Lights Fixtures - AP#04 (Main Stair) | 2 | 2025-07-07 | 2025-07-09
STAIR CASE (LEFT SIDE) |  | 120 | 2025-04-21 | 2025-07-15
R7S1ONST-AP04RG348 | Left Staircase Wire Pulling - AP#04 (Main Stair) | 40 | 2025-04-21 | 2025-06-10
R7S1ONST-AP04RG350 | Final fix - Left Staircase Lights Fixtures & Motion Sensor - AP#04 (Main Stair) | 2 | 2025-07-10 | 2025-07-13
R7S1ONST-AP04RG352 | Final fix - Left Staircase Emergency Lights Fixtures - AP#04 (Main Stair) | 2 | 2025-07-13 | 2025-07-15
STAIR CASE (RIGHT SIDE) |  | 129 | 2025-04-21 | 2025-07-28
R7S1ONST-AP04RG349 | Right Staircase Wire Pulling - AP#04 (Main Stair) | 40 | 2025-04-21 | 2025-06-10
R7S1ONST-AP04RG351 | Final fix - Right Staircase Lights Fixtures & Motion Sensor - AP#04 (Main Stair) | 2 | 2025-07-23 | 2025-07-26
R7S1ONST-AP04RG353 | Final fix - Right Staircase Emergency Lights Fixtures - AP#04 (Main Stair) | 2 | 2025-07-26 | 2025-07-28
ELEVATOR WORKS |  | 23 | 2025-08-02 | 2025-08-26
R7S1ONEL-AP04GR613 | Installation of Rails - AP#04 (Elevator Works) | 6 | 2025-08-02 | 2025-08-07
R7S1ONEL-AP04GR614 | Assembly of Cabin - AP#04 (Elevator Works) | 4 | 2025-08-09 | 2025-08-12
R7S1ONEL-AP04GR615 | Installation of Motor - AP#04 (Elevator Works) | 4 | 2025-08-13 | 2025-08-17
R7S1ONEL-AP04GR616 | Installation of Main Cables - AP#04 (Elevator Works) | 4 | 2025-08-18 | 2025-08-21
R7S1ONEL-AP04GR617 | Installation of Doors, Indicator, Push Button - AP#04 (Elevator Works) | 2 | 2025-08-23 | 2025-08-24
R7S1ONEL-AP04GR618 | Interior Finishes - AP#04 (Elevator Works) | 2 | 2025-08-25 | 2025-08-26
EXTERNAL ELEVATIONS |  | 58 | 2025-07-19 | 2025-09-07
ARCH./ CIVIL WORKS |  | 58 | 2025-07-19 | 2025-09-07
R7S1ONEE-AP04GR509 | External Selant Works - For Boxes - AP#04 (External Elevations) | 15 | 2025-07-19 | 2025-08-05
R7S1ONEE-AP04GR510 | Final Finishes & Touchups - AP#04 (External Elevations) | 20 | 2025-08-05 | 2025-08-28
R7S1ONME-AP04GF465 | Installation of rain water outlet - External façade - AP#04 (External Elevations) | 2 | 2025-08-28 | 2025-08-31
R7S1ONEE-AP04GR512 | Installation of External Signages - AP#04 (External Elevations) | 4 | 2025-08-31 | 2025-09-04
R7S1ONEE-AP04GR511 | Fixing Cage Ladder - AP#04 (External Elevations) | 2 | 2025-09-04 | 2025-09-07
EXTERNAL - CIVIL WORKS |  | 61 | 2025-06-29 | 2025-07-28
DRAINAGE |  | 11 | 2025-06-29 | 2025-07-12
R7S1ONECW-AP04-307 | Excavation Works & Sand Bedding - AP#04 (External Drainage) | 3 | 2025-06-29 | 2025-07-01
R7S1ONECW-AP04-308 | Drainage Manholes - AP#04 | 6 | 2025-06-29 | 2025-07-05
R7S1ONECW-AP04-309 | Drainage Backfilling - AP#04 | 2 | 2025-07-10 | 2025-07-12
WATERSUPPLY |  | 14 | 2025-07-02 | 2025-07-27
R7S1ONECW-AP04-310 | Excavation Works & Sand Bedding - Watersupply - AP#04 (External Watersupply Civil) | 3 | 2025-07-02 | 2025-07-05
R7S1ONECW-AP04-311 | Watersupply Manholes - AP#04 | 6 | 2025-07-06 | 2025-07-12
R7S1ONECW-AP04-312 | Watersupply Backfilling - AP#04 | 2 | 2025-07-26 | 2025-07-27
CHILLED WATER |  | 11 | 2025-07-06 | 2025-07-17
R7S1ONECW-AP04-316 | Excavation Works & Sand Bedding - AP#04 (External Chilled Water Civil) | 3 | 2025-07-06 | 2025-07-08
R7S1ONECW-AP04-317 | Chilled Water Manholes - AP#04 | 6 | 2025-07-09 | 2025-07-15
R7S1ONECW-AP04-318 | Chilled Water Backfilling - AP#04 | 2 | 2025-07-16 | 2025-07-17
FIRE FIGHTING |  | 16 | 2025-07-09 | 2025-07-27
R7S1ONECW-AP04-313 | Excavation Works & Sand Bedding - AP#04 (External Chilled Water Civil) | 3 | 2025-07-09 | 2025-07-12
R7S1ONECW-AP04-314 | Fire Fighting Manholes - AP#04 | 6 | 2025-07-13 | 2025-07-19
R7S1ONECW-AP04-315 | Fire Fighting Backfilling - AP#04 | 2 | 2025-07-26 | 2025-07-27
POWER |  | 46 | 2025-07-13 | 2025-07-28
R7S1ONECW-AP04-319 | Excavation Works & Sand Bedding - AP#04 (External Power Civil) | 3 | 2025-07-13 | 2025-07-15
R7S1ONECW-AP04-320 | Power Manholes - AP#04 | 3 | 2025-07-16 | 2025-07-19
R7S1ONECW-AP04-321 | Power Backfilling - AP#04 | 2 | 2025-07-27 | 2025-07-28
LOW CURRENT |  | 16 | 2025-07-16 | 2025-07-24
R7S1ONECW-AP04-322 | Excavation Works & Sand Bedding - AP#04 (External Low Current Civil) | 3 | 2025-07-16 | 2025-07-19
R7S1ONECW-AP04-323 | Low Current Manholes - AP#04 | 3 | 2025-07-20 | 2025-07-22
R7S1ONECW-AP04-324 | Low Current Backfilling - AP#04 | 2 | 2025-07-23 | 2025-07-24
EXTERNAL - MEP SERVICES |  | 62 | 2025-07-06 | 2025-07-27
DRAINAGE |  | 4 | 2025-07-06 | 2025-07-09
R7S1ONEME-AP04-211 | External Drainage Network - AP#04 (External Drainage MEP) | 4 | 2025-07-06 | 2025-07-09
WATERSUPPLY |  | 51 | 2025-07-13 | 2025-07-27
R7S1ONEME-AP04-212 | PRV statiuon assembly including meters- AP#04 (External WS MEP) | 4 | 2025-07-13 | 2025-07-16
R7S1ONEME-AP04-214 | Installation of valve station incl. BTU meter- AP#04 (External WS MEP) | 3 | 2025-07-24 | 2025-07-27
CHILLED WATER |  | 8 | 2025-07-17 | 2025-07-24
R7S1ONEME-AP04-213 | Installation of Chilled water line- AP#04 (External CWP MEP) | 6 | 2025-07-17 | 2025-07-23
R7S1ONEME-AP04-215 | Pressure Test for chilled water line- AP#04 (External CWP MEP) | 1 | 2025-07-24 | 2025-07-24
FIRE FIGHTING |  | 11 | 2025-07-13 | 2025-07-24
R7S1ONEME-AP04-216 | Installation of External FF network - AP#04 (External FF MEP) | 6 | 2025-07-13 | 2025-07-19
R7S1ONEME-AP04-217 | Installation of Alarm check valves- AP#04 (External FF MEP) | 3 | 2025-07-20 | 2025-07-22
R7S1ONEME-AP04-218 | Testing of External FF - AP#04 (External FF MEP) | 2 | 2025-07-23 | 2025-07-24
POWER |  | 1 | 2025-07-26 | 2025-07-26
R7S1ONEME-AP04-219 | Cable pulling from Manhole to the building MDB - AP#04 (External Power MEP) | 1 | 2025-07-26 | 2025-07-26
LOW CURRENT |  | 3 | 2025-07-20 | 2025-07-22
R7S1ONEME-AP04-220 | Low Current Cable pulling- AP#04 (External FF MEP) | 3 | 2025-07-20 | 2025-07-22
BUILDING # AP06 (MGT BLDG) |  | 277 | 2024-11-24 | 2025-09-24
SUB-STRUCTURE |  | 40 | 2024-11-24 | 2025-01-09
R7S1-ONSB-AP06-237 | Site Setting Out Works - AP#06 | 1 | 2024-11-24 | 2024-11-25
R7S1-ONSB-AP06-234 | Site levelling & earthworks - AP#06 | 4 | 2024-11-25 | 2024-11-30
R7S1-ONSB-AP06-238 | Anti-termite & Polythene Sheet Works - AP#06 | 2 | 2024-12-21 | 2024-12-22
R7S1-ONSB-AP06-235 | Blinding PCC - AP#06 | 4 | 2024-12-22 | 2024-12-25
R7S1-ONSB-AP06-236 | Waterproofing for Blinding PCC (Bitumen Paint) - AP#06 | 2 | 2024-12-25 | 2024-12-26
R7S1-ONSB-AP06-240 | Foundations/Upstands - Shuttering (Including dowel Works) - AP#06 | 6 | 2024-12-28 | 2025-01-02
R7S1-ONSB-AP06-239 | Foundations/Upstands - Rebar - AP#06 | 6 | 2024-12-28 | 2025-01-04
R7S1-ONSB-AP06-243 | Installation of MEP U/G services below Boxes - AP#06 | 1 | 2025-01-05 | 2025-01-05
R7S1-ONSB-AP06-241 | Foundations/Upstands - Casting - AP#06 | 1 | 2025-01-07 | 2025-01-07
R7S1-ONSB-AP06-242 | Waterproofing For Foundations/Upstands - AP#06 | 1 | 2025-01-08 | 2025-01-08
R7S1-ONSB-AP06-244 | Backfilling & Compaction - AP#06 | 2 | 2025-01-08 | 2025-01-09
SLAB-ON-GRADE & UG MEP WORKS (in Corridor) |  | 46 | 2025-02-26 | 2025-04-24
LEFT SIDE |  | 46 | 2025-02-26 | 2025-04-24
R7S1-ONSG-AP06-286 | Block Work below Corridor area - AP#06 | 2 | 2025-02-26 | 2025-02-27
R7S1-ONSG-AP06-292 | Backfilling upto Pipe Level - AP#06 | 3 | 2025-02-27 | 2025-03-02
R7S1-ONSG-AP06-300 | Plaster Work for Blockwork - AP#06 | 3 | 2025-03-03 | 2025-03-06
R7S1-ONSG-AP06-287 | UG MEP Works (Laying of Pipes) - AP#06 | 7 | 2025-02-26 | 2025-03-06
R7S1-ONSG-AP06-288 | Backfilling Works after Pipe Laying - AP#06 | 5 | 2025-03-02 | 2025-03-08
R7S1-ONSG-AP06-289 | Antitermite Works - AP#06 | 4 | 2025-03-03 | 2025-03-08
R7S1-ONSG-AP06-290 | Polythene & Rebar Mesh Works - AP#06 | 4 | 2025-03-04 | 2025-03-09
R7S1-ONSG-AP06-291 | Pouring SOG Concrete - AP#06 | 4 | 2025-03-05 | 2025-03-10
R7S1-ONSG-AP06-320 | Backfilling & SOG (In Front of Lift Shaft) - AP#06 | 4 | 2025-04-21 | 2025-04-24
RIGHT SIDE |  | 13 | 2025-02-26 | 2025-03-13
R7S1-ONSG-AP06-293 | Block Work below Corridor area - AP#06 | 8 | 2025-02-26 | 2025-03-08
R7S1-ONSG-AP06-299 | Backfilling upto Pipe Level - AP#06 | 8 | 2025-02-27 | 2025-03-09
R7S1-ONSG-AP06-294 | UG MEP Works (Laying of Pipes) - AP#06 | 8 | 2025-03-01 | 2025-03-10
R7S1-ONSG-AP06-295 | Backfilling Works after Pipe Laying - AP#06 | 6 | 2025-03-04 | 2025-03-11
R7S1-ONSG-AP06-296 | Antitermite Works - AP#06 | 6 | 2025-03-05 | 2025-03-12
R7S1-ONSG-AP06-297 | Polythene & Rebar Mesh Works - AP#06 | 5 | 2025-03-06 | 2025-03-12
R7S1-ONSG-AP06-298 | Pouring SOG Concrete - AP#06 | 5 | 2025-03-08 | 2025-03-13
ERECTION WORKS |  | 80 | 2025-02-19 | 2025-05-31
GROUND FLOOR |  | 74 | 2025-02-19 | 2025-05-01
R7S1ONER-AP06GF169 | Erection of GF Boxes (Left Side) including Lift Box & Staircase - AP#06 | 9 | 2025-02-19 | 2025-03-03
R7S1ONER-AP06GF170 | Erection of GF Boxes (Right Side) - AP#06 | 9 | 2025-02-23 | 2025-03-05
R7S1ONER-AP06GF171 | Erection of GF MEP Modular Cages (Left Side) - AP#06 | 8 | 2025-03-06 | 2025-03-16
R7S1ONER-AP06GF173 | Erection of GF MEP Modular Cages (Right Side) - AP#06 | 6 | 2025-03-09 | 2025-03-16
R7S1ONER-AP06GF172 | Erection of GF Corridor Slabs (Left Side) - AP#06 | 8 | 2025-03-09 | 2025-03-18
R7S1ONER-AP06GF174 | Erection of GF Corridor Slabs Right Side) - AP#06 | 6 | 2025-03-11 | 2025-03-18
R7S1ONER-AP06GF292 | Erection of Columns/Beams Frame & Slab/Loose Elements (In Front of Lift Shaft) - AP#06 | 2 | 2025-04-30 | 2025-05-01
FIRST FLOOR |  | 46 | 2025-03-29 | 2025-05-04
R7S1ONER-AP06FF169 | Erection of FF Boxes (Left Side) - AP#06 | 3 | 2025-03-29 | 2025-04-05
R7S1ONER-AP06FF170 | Erection of FF Boxes (Right Side) - AP#06 | 6 | 2025-04-05 | 2025-04-10
R7S1ONER-AP06FF171 | Erection of FF MEP Modular Cages (Left Side) - AP#06 | 8 | 2025-04-12 | 2025-04-20
R7S1ONER-AP06FF173 | Erection of FF MEP Modular Cages (Right Side) - AP#06 | 6 | 2025-04-14 | 2025-04-20
R7S1ONER-AP06FF172 | Erection of FF Corridor Slabs (Left Side) - AP#06 | 8 | 2025-04-14 | 2025-04-22
R7S1ONER-AP06FF174 | Erection of FF Corridor Slabs Right Side) - AP#06 | 6 | 2025-04-16 | 2025-04-22
R7S1ONER-AP06FF302 | Erection of Columns/Beams Frame & Slab/Loose Elements (In Front of Lift Shaft) - AP#06 | 2 | 2025-05-03 | 2025-05-04
SECOND FLOOR |  | 20 | 2025-05-05 | 2025-05-17
R7S1ONER-AP06SF312 | Erection of Columns/Beams Frame & Slab/Loose Elements (In Front of Lift Shaft) - AP#06 | 2 | 2025-05-05 | 2025-05-06
R7S1ONER-AP06SF169 | Erection of SF Boxes (Left Side) - AP#06 | 2 | 2025-05-05 | 2025-05-07
R7S1ONER-AP06SF170 | Erection of SF Boxes (Right Side) - AP#06 | 2 | 2025-05-07 | 2025-05-10
R7S1ONER-AP06SF171 | Erection of SF MEP Modular Cages (Left Side) - AP#06 | 3 | 2025-05-07 | 2025-05-11
R7S1ONER-AP06SF172 | Erection of SF Corridor Slabs (Left Side) - AP#06 | 2 | 2025-05-11 | 2025-05-13
R7S1ONER-AP06SF173 | Erection of SF MEP Modular Cages (Right Side) - AP#06 | 2 | 2025-05-12 | 2025-05-14
R7S1ONER-AP06SF174 | Erection of SF Corridor Slabs Right Side) - AP#06 | 2 | 2025-05-14 | 2025-05-17
ROOF |  | 12 | 2025-05-17 | 2025-05-31
R7S1ONER-AP06RF104 | Erection of Loose Roof Parapets, Shaft Covers, MEP Foundation etc. - AP#06 Roof | 12 | 2025-05-17 | 2025-05-31
MEP WORKS & FINISHES |  | 176 | 2025-03-13 | 2025-09-24
GROUND FLOOR |  | 176 | 2025-03-13 | 2025-09-16
ARCH./ CIVIL WORKS |  | 148 | 2025-04-21 | 2025-09-16
CORRIDOR AREA |  | 115 | 2025-04-21 | 2025-09-16
R7S1ONAR-AP06GF136 | Flooring in Corridor - AP#06 (GF Corridor) | 74 | 2025-04-21 | 2025-07-21
R7S1ONAR-AP06GF137 | Corridor Skirting - AP#06 (GF Corridor) | 2 | 2025-07-20 | 2025-07-22
R7S1ONAR-AP06GF134 | False Ceiling - 1st Fix - AP#06 (GF - Corridor) | 4 | 2025-07-22 | 2025-07-27
R7S1ONAR-AP06GF135 | Gypsum Wall Cladding - 1st Fix (Shafts) - AP#06 (GF Corridor) | 6 | 2025-08-04 | 2025-08-11
R7S1ONAR-AP06GF138 | Gypsum Wall Cladding (Shafts) -2nd Fix - AP#06 (GF Corridor) | 3 | 2025-08-11 | 2025-08-14
R7S1ONAR-AP06GF142 | Fixing Architrave - AP#06 (GF Corridor) | 2 | 2025-08-14 | 2025-08-17
R7S1ONAR-AP06GF143 | Fixing Aluminium Doors - AP#06 (GF Corridor) | 2 | 2025-08-17 | 2025-08-19
R7S1ONAR-AP06GF139 | False Ceiling - 2nd Fix (Closing the Ceiling) - AP#06 (GF Corridor) | 4 | 2025-08-19 | 2025-08-24
R7S1ONAR-AP06GF140 | Painting - Surface Prep., Primer & 1st Coat - AP#06 (GF Corridor) | 8 | 2025-08-14 | 2025-08-24
R7S1ONAR-AP06GF164 | Painting - Surface Prep., Primer & 1st Coat for Ceiling - AP#06 (GF Corridor) | 4 | 2025-08-24 | 2025-08-28
R7S1ONAR-AP06GF141 | Painting - Final Coat (Ceiling + Walls) - AP#06 (GF Corridor) | 3 | 2025-09-14 | 2025-09-16
INSIDE BOXES |  | 75 | 2025-04-21 | 2025-07-30
R7S1ONAR-AP06GF144 | Fixing Thresholds (Joining the Room) - AP#06 (GF - inside Boxes) | 74 | 2025-04-21 | 2025-07-21
R7S1ONAR-AP06GF145 | Fixing Wooden Doors - AP#06 (GF - inside Boxes) | 4 | 2025-07-21 | 2025-07-26
R7S1ONAR-AP06GF146 | Fixing Aluminium Doors - AP#06 (GF - inside Boxes) | 4 | 2025-07-26 | 2025-07-30
IN FRONT OF LIFT SHAFT |  | 136 | 2025-04-26 | 2025-09-13
R7S1ONAR-AP06GF148 | Flooring - AP#06 (GF - Front of Lift Shaft) | 3 | 2025-04-26 | 2025-04-28
R7S1ONAR-AP06GF149 | Skirting & Thresholds - AP#06 (GF - Front of Lift Shaft) | 1 | 2025-04-28 | 2025-04-28
R7S1ONAR-AP06GF150 | Painting - Surface Prep., Primer & 1st Coat - AP#06 (GF - Front of Lift Shaft) | 4 | 2025-04-29 | 2025-05-03
R7S1ONAR-AP06GF147 | False Ceiling - 1st Fix - AP#06 (GF - Front of Lift Shaft) | 4 | 2025-05-04 | 2025-05-07
R7S1ONAR-AP06GF151 | False Ceiling - Final Fix - AP#06 (GF - Front of Lift Shaft) | 3 | 2025-05-08 | 2025-05-11
R7S1ONAR-AP06GF153 | Fixing Handrail - AP#06 (GF - Front of Lift Shaft) | 3 | 2025-08-30 | 2025-09-01
R7S1ONAR-AP06GF154 | Paint for Handrail - AP#06 (GF - Front of Lift Shaft) | 3 | 2025-09-02 | 2025-09-04
R7S1ONAR-AP06GF152 | Painting - Final Coat - AP#06 (GF - Front of Lift Shaft) | 3 | 2025-09-06 | 2025-09-08
R7S1ONAR-AP06GF156 | Fixing Wall Guard - AP#06 (GF - Front of Lift Shaft) | 2 | 2025-09-09 | 2025-09-10
R7S1ONAR-AP06GF155 | Fixing Floor Mat - AP#06 (GF - Front of Lift Shaft) | 2 | 2025-09-11 | 2025-09-13
GARBAGE ROOM |  | 2 | 2025-08-04 | 2025-08-05
R7S1ONAR-AP06GF157 | Paint Finishes and Touchups - Final Coat - AP#06 (GF - Garbage Room) | 2 | 2025-08-04 | 2025-08-05
BALCONIES |  | 74 | 2025-07-21 | 2025-09-13
R7S1ONAR-AP06GF158 | Wetarea Waterproofing - AP#06 (GF - Balconies) | 6 | 2025-07-21 | 2025-07-28
R7S1ONAR-AP06GF159 | Flooring - AP#06 (GF - Front of Lift Shaft) | 6 | 2025-07-24 | 2025-07-31
R7S1ONAR-AP06GF160 | Painting - Surface Prep., Primer & 1st Coat - AP#06 (GF - Front of Lift Shaft) | 6 | 2025-07-28 | 2025-08-04
R7S1ONAR-AP06GF162 | Fixing Handrail - AP#06 (GF - Front of Lift Shaft) | 6 | 2025-09-02 | 2025-09-08
R7S1ONAR-AP06GF163 | Paint for Handrail - AP#06 (GF - Front of Lift Shaft) | 2 | 2025-09-09 | 2025-09-10
R7S1ONAR-AP06GF161 | Painting - Final Coat - AP#06 (GF - Front of Lift Shaft) | 2 | 2025-09-11 | 2025-09-13
MEP WORKS |  | 131 | 2025-03-13 | 2025-08-30
MECHANICAL |  | 131 | 2025-03-13 | 2025-08-27
CHILLED WATER |  | 94 | 2025-03-13 | 2025-06-19
R7S1ONME-AP06GF505 | Installation of Chilled water hanger and supports - AP#06 (GF - Corridor) | 27 | 2025-03-13 | 2025-04-19
R7S1ONME-AP06GF506 | Installation of CHWP piping (connection between modular cages & modular to apartment) - AP#06 (GF - Corridor) | 24 | 2025-03-18 | 2025-04-20
R7S1ONME-AP06GF557 | Installation of CHWP connection for FCU with Valve package in Corridor, Electrical Room & ICT Room - AP#06 (GF) | 18 | 2025-04-05 | 2025-04-24
R7S1ONME-AP06GF507 | Installation of BTU Meter with valves - AP#06 (GF - Corridor) | 31 | 2025-03-22 | 2025-05-01
R7S1ONME-AP06GF508 | CHWP piping risers connections - AP#06 (GF - Corridor) | 17 | 2025-04-12 | 2025-05-01
R7S1ONME-AP06GF509 | Pressure Testing of CHWP piping - AP#06 (GF - Corridor) | 2 | 2025-05-01 | 2025-05-04
R7S1ONME-AP06GF545 | CHWP Insulation - AP#06 (GF - Corridor) | 26 | 2025-04-05 | 2025-05-04
R7S1ONME-AP06GF576 | CHWP Installation/Connections and Insulation (In Front of Lift Shaft) - AP#06 | 4 | 2025-06-16 | 2025-06-19
HVAC DUCTING |  | 109 | 2025-03-19 | 2025-08-26
R7S1ONME-AP06GF510 | Duct Riser Continuation - AP#06 (GF - Corridor) | 6 | 2025-04-19 | 2025-04-24
R7S1ONME-AP06GF511 | A/C drain & Copper pipe connection in ELV room - AP#06 (GF) | 8 | 2025-04-16 | 2025-04-24
R7S1ONME-AP06GF546 | Installation of Duct & Grill in Garbage Room - AP#06 (GF - Garbage Room) | 6 | 2025-04-19 | 2025-04-24
R7S1ONME-AP06GF556 | Installation of FCU's & Duct Connection in Corridor, Electrical Room & ICT Room - AP#06 (GF) | 34 | 2025-03-19 | 2025-05-01
R7S1ONME-AP06GF558 | Installation of Ducting and insulation (connection between modular cages) - AP#06 (GF - Corridor) | 34 | 2025-03-19 | 2025-05-01
R7S1ONME-AP06GF559 | Installation of Grilles in the Corridor - AP#06 (GF - Corridor) | 2 | 2025-08-24 | 2025-08-26
FIRE FIGHTING |  | 114 | 2025-04-08 | 2025-08-27
R7S1ONME-AP06GF512 | Riser Continuity in corridor - AP#06 (GF - Corridor) | 10 | 2025-04-12 | 2025-04-22
R7S1ONME-AP06GF513 | Continuitu of FF pipes & ZC Valves (connection between modular cages & modular to apartment) - AP#06 (GF - Corridor) | 15 | 2025-04-08 | 2025-04-24
R7S1ONME-AP06GF926 | Installation of F.F Pipes, Testing & Final Fixtures (In Front of Lift Shaft) - AP#06 | 3 | 2025-06-21 | 2025-06-23
R7S1ONME-AP06GF547 | Installation of Pipe & sprinkler in Garbage Room - AP#06 (GF - Garbage Room) | 79 | 2025-04-19 | 2025-07-24
R7S1ONME-AP06GF514 | Installation of Sprinklers drops in corridor - AP#06 (GF - Corridor) | 4 | 2025-07-27 | 2025-07-31
R7S1ONME-AP06GF515 | Pressure Test for FF Piping in corridor - AP#06 (GF - Corridor) | 2 | 2025-07-31 | 2025-08-03
R7S1ONME-AP06GF560 | FF Flushing network - AP#06 (GF - Corridor) | 1 | 2025-08-03 | 2025-08-04
R7S1ONME-AP06GF517 | Installation of Alarm check valve, Fire Extinguishers & Blanket - AP#06 (GF - Corridor) | 103 | 2025-04-21 | 2025-08-24
R7S1ONME-AP06GF516 | Installation of Sprinklers in corridor - AP#06 (GF - Corridor) | 3 | 2025-08-24 | 2025-08-27
WATER SUPPLY |  | 67 | 2025-03-13 | 2025-06-04
R7S1ONME-AP06GF549 | Installation of Sanitary Fixtures in Janitor Room - AP#06 (GF - Janitor Room) | 6 | 2025-03-13 | 2025-03-20
R7S1ONME-AP06GF548 | Installation of WS Pipe in Garbage Room - AP#06 (GF - Garbage Room) | 28 | 2025-03-13 | 2025-04-20
R7S1ONME-AP06GF518 | Riser Continuity in Shafts - AP#06 (GF - Corridor) | 10 | 2025-04-12 | 2025-04-22
R7S1ONME-AP06GF519 | WS High Level Pipe continuation & Insulation works - AP#06 (GF - Corridor) | 34 | 2025-03-19 | 2025-05-01
R7S1ONME-AP06GF520 | Installation of Cold, Hot water line & Hot water return - AP#06 (GF - Corridor) | 34 | 2025-03-19 | 2025-05-01
R7S1ONME-AP06GF521 | Water Meter Installation - AP#06 (GF - Corridor) | 4 | 2025-05-01 | 2025-05-06
R7S1ONME-AP06GF522 | Pressure Test for WS - AP#06 (GF - Corridor) | 4 | 2025-05-31 | 2025-06-04
R7S1ONME-AP06GF561 | Insulation for Hot water line & Hot water return - AP#06 (GF - Corridor) | 38 | 2025-04-21 | 2025-06-04
DRAINAGE |  | 67 | 2025-03-13 | 2025-06-04
R7S1ONME-AP06GF524 | Installation of Clean-outs, Floor drain in balcony - AP#06 (GF - Corridor) | 30 | 2025-03-13 | 2025-04-22
R7S1ONME-AP06GF525 | Rain Water Riser continuation in Shafts - AP#06 (GF - Corridor) | 4 | 2025-04-26 | 2025-04-29
R7S1ONME-AP06GF526 | Drainage Riser continuation in Shafts - AP#06 (GF - Corridor) | 4 | 2025-04-26 | 2025-04-29
R7S1ONME-AP06GF527 | Testing for Rain Water Riser - AP#06 (GF - Corridor) | 4 | 2025-05-31 | 2025-06-04
R7S1ONME-AP06GF528 | Testing for Drainage Riser1 - AP#06 (GF - Corridor) | 4 | 2025-05-31 | 2025-06-04
ELECTRICAL |  | 120 | 2025-03-13 | 2025-08-30
POWER & LIGHTING |  | 114 | 2025-03-13 | 2025-08-30
R7S1ONME-AP06GF529 | Contiuation of Cable Trays & apartment branches - AP#06 (GF - Corridor) | 6 | 2025-03-13 | 2025-03-20
R7S1ONME-AP06GF530 | Contiuation of Cable Trunking with Flexible conduits for Lights - AP#06 (GF - Corridor) | 6 | 2025-03-13 | 2025-03-20
R7S1ONME-AP06GF531 | Installation of EMT pipes - AP#06 (GF - Corridor) | 2 | 2025-03-19 | 2025-03-20
R7S1ONME-AP06GF532 | Installation of Busbar, Electrical Meter & Tap-off - AP#06 (GF - Corridor) | 3 | 2025-06-14 | 2025-06-16
R7S1ONME-AP06GF533 | Corridor Wire Pulling - AP#06 (GF - Corridor) | 69 | 2025-03-20 | 2025-06-17
R7S1ONME-AP06GF534 | Electrical Room - Installation of Cable trays, SMDB & Termination - AP#06 (GF - Corridor) | 58 | 2025-04-07 | 2025-06-17
R7S1ONME-AP06GF555 | Termination of Tap-off with Electrical Meter in the apartments - AP#06 (GF - Corridor) | 3 | 2025-06-17 | 2025-06-19
R7S1ONME-AP06GF1106 | Continuation of Cable Tray/Trunking with Flexible conduits for Lights (In Front of Lift Shaft) - AP#06 | 4 | 2025-06-24 | 2025-06-28
R7S1ONME-AP06GF536 | Installation, Termination of Emergeny & Exit Lights with contiuity - AP#06 (GF - Corridor) | 2 | 2025-08-24 | 2025-08-26
R7S1ONME-AP06GF535 | Installation, Termination of Light Fixtures with continuity test - AP#06 (GF - Corridor & Balconies) | 3 | 2025-08-24 | 2025-08-27
R7S1ONME-AP06GF537 | Installation, Termination of PIR sensors with continuity test - AP#06 (GF - Corridor) | 2 | 2025-08-27 | 2025-08-30
LOW CURRENT SYSTEM |  | 120 | 2025-03-13 | 2025-08-28
R7S1ONME-AP06GF538 | Installation of Basket trays for BMS, CCTV, Access Control - AP#06 (GF - Corridor) | 6 | 2025-03-13 | 2025-03-20
R7S1ONME-AP06GF539 | Voice Evacuation cable installation - AP#06 (GF - Corridor) | 6 | 2025-03-17 | 2025-03-24
R7S1ONME-AP06GF540 | Fire alarm cable installation - AP#06 (GF - Corridor) | 8 | 2025-03-15 | 2025-03-24
R7S1ONME-AP06GF562 | CBS System cable installation - AP#06 (GF - Corridor) | 11 | 2025-03-13 | 2025-03-26
R7S1ONME-AP06GF542 | BMS, CCTV & Access control Cable installation - AP#06 (GF - Corridor) | 57 | 2025-04-19 | 2025-06-28
R7S1ONME-AP06GF543 | Low Current Works including BMS Panel in ICT Room - AP#06 (GF - Corridor) | 10 | 2025-06-22 | 2025-07-02
R7S1ONME-AP06GF1286 | Installation of Basket trays for Low Current, Cable Installation (In Front of Lift Shaft) - AP#06 | 4 | 2025-06-29 | 2025-07-02
R7S1ONME-AP06GF551 | Installation & Termination of Access control system for Electrical Room - AP#06 (GF) | 2 | 2025-07-02 | 2025-07-03
R7S1ONME-AP06GF541 | Fibre optic Cable pulling & Termination with OTO (in corridors to ONU) - AP#06 (GF - Corridor) | 2 | 2025-07-03 | 2025-07-05
R7S1ONME-AP06GF554 | Fluke test for CCTV & Fibre Optic Cable - AP#06 (GF - Corridor) (Ceiling 1st Fix) | 2 | 2025-07-06 | 2025-07-07
R7S1ONME-AP06GF550 | Installation & Termination of CCTV Cameras - AP#06 (GF - Corridor) | 2 | 2025-08-24 | 2025-08-26
R7S1ONME-AP06GF553 | Installation & Termination of Wireless Gateway & RF Node in corridors - AP#06 (GF - Corridor) | 2 | 2025-08-24 | 2025-08-26
R7S1ONME-AP06GF544 | Installation & Termination of Fire alarm devices & Speakers - AP#06 (GF - Corridor) | 4 | 2025-08-24 | 2025-08-28
R7S1ONME-AP06GF552 | Installation & Termination of Active Components & UPS installation in ICT Room - AP#06 (GF - Corridor) | 2 | 2025-08-26 | 2025-08-28
FIRST FLOOR |  | 148 | 2025-04-19 | 2025-09-21
ARCH./ CIVIL WORKS |  | 136 | 2025-04-26 | 2025-09-21
CORRIDOR AREA |  | 115 | 2025-05-03 | 2025-09-21
R7S1ONAR-AP06FF204 | Flooring in Corridor - AP#06 (FF - Corridor) | 6 | 2025-05-03 | 2025-05-08
R7S1ONAR-AP06FF205 | Corridor Skirting - AP#06 (FF - Corridor) | 2 | 2025-05-08 | 2025-05-10
R7S1ONAR-AP06FF202 | False Ceiling - 1st Fix - AP#06 (FF - Corridor) | 4 | 2025-05-11 | 2025-05-14
R7S1ONAR-AP06FF203 | Gypsum Wall Cladding (Shafts) - AP#06 (FF - Corridor) | 6 | 2025-07-24 | 2025-07-31
R7S1ONAR-AP06FF206 | Gypsum Wall Cladding (Shafts) -2nd Fix - AP#06 (FF Corridor) | 4 | 2025-07-31 | 2025-08-05
R7S1ONAR-AP06FF210 | Fixing Architrave - AP#06 (FF Corridor) | 2 | 2025-08-05 | 2025-08-07
R7S1ONAR-AP06FF211 | Fixing Aluminium Doors - AP#06 (FF Corridor) | 2 | 2025-08-07 | 2025-08-10
R7S1ONAR-AP06FF207 | False Ceiling - 2nd Fix (Closing the Ceiling) - AP#06 (FF Corridor) | 3 | 2025-08-10 | 2025-08-13
R7S1ONAR-AP06FF208 | Painting - Surface Prep., Primer & 1st Coat for Walls - AP#06 (FF Corridor) | 8 | 2025-08-05 | 2025-08-14
R7S1ONAR-AP06FF243 | Painting - Surface Prep., Primer & 1st Coat for Ceiling - AP#06 (FF Corridor) | 4 | 2025-08-13 | 2025-08-18
R7S1ONAR-AP06FF209 | Painting - Final Coat (Ceiling + Walls) - AP#06 (FF Corridor) | 3 | 2025-09-18 | 2025-09-21
INSIDE BOXES |  | 48 | 2025-05-17 | 2025-05-31
R7S1ONAR-AP06FF212 | Fixing Thresholds (Joining the Room) - AP#06 (FF - inside Boxes) | 4 | 2025-05-17 | 2025-05-21
R7S1ONAR-AP06FF213 | Fixing Wooden Doors - AP#06 (FF - inside Boxes) | 4 | 2025-05-21 | 2025-05-26
R7S1ONAR-AP06FF214 | Fixing Aluminium Doors (Next Floor) - AP#06 (FF - inside Boxes) | 4 | 2025-05-26 | 2025-05-31
IN FRONT OF LIFT SHAFT |  | 88 | 2025-04-26 | 2025-09-15
R7S1ONAR-AP06FF216 | Flooring - AP#06 (FF - Front of Lift Shaft) | 4 | 2025-04-26 | 2025-04-29
R7S1ONAR-AP06FF217 | Skirting & Thresholds - AP#06 (FF - Front of Lift Shaft) | 1 | 2025-04-29 | 2025-04-29
R7S1ONAR-AP06FF218 | Painting - Surface Prep., Primer & 1st Coat - AP#06 (FF - Front of Lift Shaft) | 2 | 2025-04-30 | 2025-05-01
R7S1ONAR-AP06FF215 | False Ceiling - 1st Fix - AP#06 (FF - Front of Lift Shaft) | 2 | 2025-05-03 | 2025-05-04
R7S1ONAR-AP06FF219 | False Ceiling - Final Fix - AP#06 (FF - Front of Lift Shaft) | 1 | 2025-05-22 | 2025-05-22
R7S1ONAR-AP06FF221 | Fixing Handrail - AP#06 (FF - Front of Lift Shaft) | 3 | 2025-08-30 | 2025-09-01
R7S1ONAR-AP06FF222 | Paint for Handrail - AP#06 (FF - Front of Lift Shaft) | 1 | 2025-09-02 | 2025-09-02
R7S1ONAR-AP06FF220 | Painting - 2nd Coat - AP#06 (FF - Front of Lift Shaft) | 1 | 2025-09-03 | 2025-09-03
R7S1ONAR-AP06FF224 | Fixing Wall Guard - AP#06 (FF - Front of Lift Shaft) | 2 | 2025-09-11 | 2025-09-13
R7S1ONAR-AP06FF223 | Fixing Floor Mat - AP#06 (FF - Front of Lift Shaft) | 2 | 2025-09-14 | 2025-09-15
GARBAGE ROOM |  | 44 | 2025-07-27 | 2025-08-03
R7S1ONAR-AP06FF225 | Installation of Dry Walls - First Fix - AP#06 (FF - Garbage Room) | 1 | 2025-07-27 | 2025-07-27
R7S1ONAR-AP06FF226 | Installation of Dry Walls - Final Fix - AP#06 (FF - Garbage Room) | 1 | 2025-07-28 | 2025-07-28
R7S1ONAR-AP06FF227 | Garbage Rooms - Wall Tile Finishes (One Side) - AP#06 (FF - Garbage Room) | 1 | 2025-07-29 | 2025-07-29
R7S1ONAR-AP06FF228 | Paint Works of Dry Walls - First Coat - AP#06 (FF - Garbage Room) | 1 | 2025-07-30 | 2025-07-30
R7S1ONAR-AP06FF229 | Installation of the Garbage Chute Door - AP#06 (FF - Garbage Room) | 1 | 2025-07-31 | 2025-07-31
R7S1ONAR-AP06FF230 | Paint Finishes and Touchups - Final Coat - AP#06 (FF - Garbage Room) | 2 | 2025-08-02 | 2025-08-03
BALCONIES |  | 129 | 2025-05-11 | 2025-09-17
R7S1ONAR-AP06FF231 | Wetarea Waterproofing - AP#06 (FF - Balconies) | 8 | 2025-05-11 | 2025-05-19
R7S1ONAR-AP06FF232 | Flooring - AP#06 (FF - Balconies) | 6 | 2025-05-15 | 2025-05-21
R7S1ONAR-AP06FF233 | Painting - Surface Prep., Primer & 1st Coat - AP#06 (FF - Balconies) | 8 | 2025-05-18 | 2025-05-26
R7S1ONAR-AP06FF235 | Fixing Handrail - AP#06 (FF - Balconies) | 6 | 2025-09-02 | 2025-09-08
R7S1ONAR-AP06FF236 | Paint for Handrail - AP#06 (FF - Balconies) | 4 | 2025-09-09 | 2025-09-13
R7S1ONAR-AP06FF234 | Painting - 2nd Coat - AP#06 (FF - Balconies) | 4 | 2025-09-14 | 2025-09-17
MEP WORKS |  | 115 | 2025-04-19 | 2025-09-01
MECHANICAL |  | 115 | 2025-04-19 | 2025-08-26
CHILLED WATER |  | 66 | 2025-04-26 | 2025-06-24
R7S1ONME-AP06FF242 | Installation of Chilled water hanger and supports - AP#06 (FF Corridor) | 4 | 2025-04-26 | 2025-04-29
R7S1ONME-AP06FF292 | Installation of CHWP connection for FCU with Valve package in Corridor, Electrical Room & ICT Room | 4 | 2025-04-26 | 2025-04-29
R7S1ONME-AP06FF244 | Installation of BTU Meter with valves - AP#06 (FF Corridor) | 2 | 2025-05-01 | 2025-05-03
R7S1ONME-AP06FF243 | Installation of CHWP piping (connection between modular cages & modular to apartment) - AP#06 -(FF Corridor) | 4 | 2025-04-30 | 2025-05-04
R7S1ONME-AP06FF245 | CHWP piping risers connections - AP#06 (FF Corridor) | 3 | 2025-05-07 | 2025-05-11
R7S1ONME-AP06FF246 | Pressure Testing of CHWP piping - AP#06 (FF Corridor) | 1 | 2025-05-11 | 2025-05-12
R7S1ONME-AP06FF281 | CHWP Insulation - AP#06 (FF Corridor) | 4 | 2025-05-12 | 2025-05-17
R7S1ONME-AP06FF586 | CHWP Installation/Connections and Insulation (In Front of Lift Shaft) - AP#06 | 4 | 2025-06-21 | 2025-06-24
HVAC DUCTING |  | 78 | 2025-04-26 | 2025-08-16
R7S1ONME-AP06FF293 | Installation of FCU's & Duct Connection in Corridor, Electrical Room & ICT Room - AP#06 (FF Corridor) | 4 | 2025-04-26 | 2025-04-29
R7S1ONME-AP06FF247 | Duct Riser Continuation - AP#06 (FF Corridor) | 4 | 2025-05-07 | 2025-05-12
R7S1ONME-AP06FF248 | A/C drain & Copper pipe connection in ELV room - AP#06 (FF Corridor) | 2 | 2025-05-12 | 2025-05-14
R7S1ONME-AP06FF294 | Installation of Ducting and insulation (connection between modular cages) - AP#06 (FF Corridor) | 3 | 2025-05-12 | 2025-05-15
R7S1ONME-AP06FF282 | Installation of Duct & Grill in Garbage Room - AP#06 (FF Corridor) | 2 | 2025-05-14 | 2025-05-17
R7S1ONME-AP06FF295 | Installation of Grilles in the Corridor - AP#06 (FF Corridor) | 2 | 2025-08-13 | 2025-08-16
FIRE FIGHTING |  | 115 | 2025-04-19 | 2025-08-26
R7S1ONME-AP06FF249 | Riser Continuity in corridor - AP#06 (FF Corridor) | 4 | 2025-05-07 | 2025-05-12
R7S1ONME-AP06FF250 | Continuation of FF pipes & ZC Valves (connection between modular cages & modular to apartment) - AP#06 (FF Corridor) | 4 | 2025-05-07 | 2025-05-12
R7S1ONME-AP06FF251 | Installation of Sprinklers drops in corridor - AP#06 (FF Corridor) | 4 | 2025-05-15 | 2025-05-19
R7S1ONME-AP06FF252 | Pressure Test for FF Piping in corridor - AP#06 (FF Corridor) | 2 | 2025-05-20 | 2025-05-21
R7S1ONME-AP06FF296 | FF Flushing network - AP#06 (FF Corridor) | 1 | 2025-05-28 | 2025-05-29
R7S1ONME-AP06FF936 | Installation of F.F Pipes, Testing & Final Fixtures (In Front of Lift Shaft) - AP#06 | 3 | 2025-06-25 | 2025-06-28
R7S1ONME-AP06FF283 | Installation of Pipe & sprinkler in Garbage Room - AP#06 (FF Corridor) | 79 | 2025-04-19 | 2025-07-24
R7S1ONME-AP06FF253 | Installation of Sprinklers in corridor - AP#06 (FF Corridor) | 3 | 2025-08-13 | 2025-08-17
R7S1ONME-AP06FF254 | Installation of Alarm check valve, Fire Extinguishers & Blanket (Last Stage of the Building) - AP#06 (FF Corridor) | 2 | 2025-08-24 | 2025-08-26
WATER SUPPLY |  | 38 | 2025-04-26 | 2025-06-14
R7S1ONME-AP06FF284 | Installation of WS Pipe in Garbage Room - AP#06 (FF Corridor) | 2 | 2025-04-26 | 2025-04-27
R7S1ONME-AP06FF285 | Installation of Sanitary Fixtures in Janitor Room - AP#06 (FF Corridor) | 2 | 2025-04-26 | 2025-04-27
R7S1ONME-AP06FF256 | WS High Level Pipe continuation & Insulation works in Corridor - AP#06 (FF Corridor) | 4 | 2025-04-26 | 2025-04-29
R7S1ONME-AP06FF257 | Installation of Cold, Hot water line & Hot water return in corridor - AP#06 (FF Corridor) | 4 | 2025-04-30 | 2025-05-04
R7S1ONME-AP06FF258 | Water Meter Installation in Corridor - AP#06 (FF Corridor) | 4 | 2025-05-05 | 2025-05-08
R7S1ONME-AP06FF255 | Riser Continuity in Shafts - AP#06 (FF Corridor) | 4 | 2025-05-07 | 2025-05-12
R7S1ONME-AP06FF259 | Pressure Test for WS - AP#06 (FF Corridor) | 4 | 2025-05-31 | 2025-06-04
R7S1ONME-AP06FF297 | Insulation for Hot water line & Hot water return in corridor - AP#06 (FF Corridor) | 4 | 2025-06-04 | 2025-06-14
DRAINAGE |  | 34 | 2025-04-23 | 2025-06-02
R7S1ONME-AP06FF260 | Installation of Clean-outs, Floor drain in balcony - AP#06 (FF Corridor) | 2 | 2025-04-23 | 2025-04-24
R7S1ONME-AP06FF261 | Rain Water Riser continuation in Shafts - AP#06 (FF Corridor) | 2 | 2025-05-07 | 2025-05-10
R7S1ONME-AP06FF262 | Drainage Riser continuation in Shafts - AP#06 (FF Corridor) | 2 | 2025-05-07 | 2025-05-10
R7S1ONME-AP06FF263 | Testing for Rain Water Riser - AP#06 (FF Corridor) | 2 | 2025-05-31 | 2025-06-02
R7S1ONME-AP06FF264 | Testing for Drainage Riser - AP#06 (FF Corridor) | 2 | 2025-05-31 | 2025-06-02
ELECTRICAL |  | 94 | 2025-04-26 | 2025-09-01
POWER & LIGHTING |  | 84 | 2025-04-26 | 2025-09-01
R7S1ONME-AP06FF265 | Contiuation of Cable Trays & apartment branches - AP#06 (FF Corridor) | 4 | 2025-04-26 | 2025-04-29
R7S1ONME-AP06FF266 | Contiuation of Cable Trunking with Flexible conduits for Lights - AP#06 (FF Corridor) | 4 | 2025-04-26 | 2025-04-29
R7S1ONME-AP06FF267 | Installation of EMT pipes - AP#06 (FF Corridor) | 5 | 2025-04-26 | 2025-04-30
R7S1ONME-AP06FF268 | Installation of Busbar, Electrical Meter & Tap-off - AP#06 (FF Corridor) | 3 | 2025-06-17 | 2025-06-19
R7S1ONME-AP06FF291 | Termination of Tap-off with Electrical Meter in the apartments - AP#06 (FF Corridor) | 3 | 2025-06-21 | 2025-06-23
R7S1ONME-AP06FF269 | Corridor Wire Pulling - AP#06 (FF Corridor) | 6 | 2025-06-18 | 2025-06-24
R7S1ONME-AP06FF270 | Electrical Room - Installation of Cable trays, SMDB & Termination - AP#06 (FF Corridor) | 6 | 2025-06-25 | 2025-07-01
R7S1ONME-AP06FF1116 | Continuation of Cable Tray/Trunking with Flexible conduits for Lights (In Front of Lift Shaft) - AP#06 | 4 | 2025-07-03 | 2025-07-07
R7S1ONME-AP06FF272 | Installation, Termination of Emergeny & Exit Lights with contiuity - AP#06 (FF Corridor) | 2 | 2025-08-13 | 2025-08-16
R7S1ONME-AP06FF271 | Installation, Termination of Light Fixtures with continuity test - AP#06 (FF - Corridor & Balconies) | 3 | 2025-08-13 | 2025-08-17
R7S1ONME-AP06FF273 | Installation, Termination of PIR sensors with continuity test - AP#06 (FF Corridor) | 2 | 2025-08-30 | 2025-09-01
LOW CURRENT SYSTEM |  | 94 | 2025-04-26 | 2025-08-18
R7S1ONME-AP06FF298 | CBS System cable installation - AP#06 (FF Corridor) | 3 | 2025-04-26 | 2025-04-28
R7S1ONME-AP06FF274 | Installation of Basket trays for BMS, CCTV, Access Control - AP#06 (FF Corridor) | 4 | 2025-04-26 | 2025-04-29
R7S1ONME-AP06FF276 | Fire alarm cable installation - AP#06 (FF Corridor) | 3 | 2025-04-27 | 2025-04-29
R7S1ONME-AP06FF275 | Voice Evacuation cable installation - AP#06 (FF Corridor) | 3 | 2025-04-29 | 2025-05-01
R7S1ONME-AP06FF278 | BMS, CCTV & Access control Cable installation - AP#06 (FF Corridor) | 2 | 2025-07-03 | 2025-07-05
R7S1ONME-AP06FF1296 | Installation of Basket trays for Low Current, Cable Installation (In Front of Lift Shaft) - AP#06 | 4 | 2025-07-03 | 2025-07-07
R7S1ONME-AP06FF279 | Low Current Works including BMS Panel in ICT Room - AP#06 (FF Corridor) | 10 | 2025-06-29 | 2025-07-09
R7S1ONME-AP06FF277 | Fibre optic Cable pulling & Termination with OTO (in corridors to ONU) - AP#06 (FF Corridor) | 2 | 2025-07-10 | 2025-07-12
R7S1ONME-AP06FF290 | Fluke test for CCTV & Fibre Optic Cable - AP#06 (FF Corridor) | 2 | 2025-07-10 | 2025-07-12
R7S1ONME-AP06FF286 | Installation & Termination of CCTV Cameras - AP#06 (FF Corridor) | 2 | 2025-08-13 | 2025-08-16
R7S1ONME-AP06FF287 | Installation & Termination of Access control system for Electrical Room - AP#06 (FF Corridor) | 2 | 2025-08-13 | 2025-08-16
R7S1ONME-AP06FF289 | Installation & Termination of Wireless Gateway & RF Node - AP#06 (FF Corridor) | 2 | 2025-08-13 | 2025-08-16
R7S1ONME-AP06FF280 | Installation & Termination of Fire alarm devices & Speakers - AP#06 (FF Corridor) | 4 | 2025-08-13 | 2025-08-18
R7S1ONME-AP06FF288 | Installation & Termination of Active Components & UPS installation in ICT Room | 2 | 2025-08-16 | 2025-08-18
SECOND FLOOR |  | 123 | 2025-04-28 | 2025-09-24
ARCH./ CIVIL WORKS |  | 123 | 2025-04-28 | 2025-09-24
CORRIDOR AREA |  | 110 | 2025-04-28 | 2025-09-24
R7S1ONAR-AP06SF136 | Flooring in Corridor - AP#06 (SF Corridor) | 6 | 2025-04-28 | 2025-05-05
R7S1ONAR-AP06SF137 | Corridor Skirting - AP#06 (SF Corridor) | 2 | 2025-05-04 | 2025-05-06
R7S1ONAR-AP06SF134 | False Ceiling - 1st Fix - AP#06 (SF Corridor) | 4 | 2025-05-06 | 2025-05-11
R7S1ONAR-AP06SF135 | Gypsum Wall Cladding (Shafts) - AP#06 (SF Corridor) | 6 | 2025-08-07 | 2025-08-14
R7S1ONAR-AP06SF138 | Gypsum Wall Cladding (Shafts) -2nd Fix - AP#06 (SF Corridor) | 4 | 2025-08-14 | 2025-08-19
R7S1ONAR-AP06SF142 | Fixing Architrave - AP#06 (SF Corridor) | 2 | 2025-08-19 | 2025-08-21
R7S1ONAR-AP06SF143 | Fixing Aluminium Doors - AP#06 (SF Corridor) | 2 | 2025-08-21 | 2025-08-24
R7S1ONAR-AP06SF139 | False Ceiling - 2nd Fix (Closing the Ceiling) - AP#06 (SF Corridor) | 3 | 2025-08-24 | 2025-08-27
R7S1ONAR-AP06SF140 | Painting - Surface Prep., Primer & 1st Coat - AP#06 (SF Corridor) | 8 | 2025-08-19 | 2025-08-28
R7S1ONAR-AP06SF164 | Painting - Surface Prep., Primer & 1st Coat - AP#06 (SF Corridor) | 4 | 2025-08-27 | 2025-09-01
R7S1ONAR-AP06SF141 | Painting - Final Coat (Ceiling + Walls) - AP#06 (SF Corridor) | 3 | 2025-09-21 | 2025-09-24
INSIDE BOXES |  | 6 | 2025-05-17 | 2025-05-26
R7S1ONAR-AP06SF144 | Fixing Thresholds (Joining the Room) - AP#06 (SF - inside Boxes) | 4 | 2025-05-17 | 2025-05-21
R7S1ONAR-AP06SF145 | Fixing Wooden Doors - AP#06 (SF - inside Boxes) | 2 | 2025-05-21 | 2025-05-24
R7S1ONAR-AP06SF146 | Fixing Aluminium Doors (Next Floor) - AP#06 (SF - inside Boxes) | 2 | 2025-05-24 | 2025-05-26
IN FRONT OF LIFT SHAFT |  | 85 | 2025-05-17 | 2025-09-06
R7S1ONAR-AP06SF147 | False Ceiling - 1st Fix - AP#06 (SF - Front of Lift Shaft) | 3 | 2025-05-17 | 2025-05-20
R7S1ONAR-AP06SF148 | Flooring - AP#06 (SF - Front of Lift Shaft) | 4 | 2025-05-20 | 2025-05-25
R7S1ONAR-AP06SF149 | Skirting & Thresholds - AP#06 (SF - Front of Lift Shaft) | 2 | 2025-05-25 | 2025-05-27
R7S1ONAR-AP06SF150 | Painting - Surface Prep., Primer & 1st Coat - AP#06 (SF - Front of Lift Shaft) | 2 | 2025-05-27 | 2025-05-29
R7S1ONAR-AP06SF151 | False Ceiling - Final Fix - AP#06 (SF - Front of Lift Shaft) | 1 | 2025-05-29 | 2025-05-31
R7S1ONAR-AP06SF153 | Fixing Handrail - AP#06 (SF - Front of Lift Shaft) | 3 | 2025-08-30 | 2025-09-01
R7S1ONAR-AP06SF154 | Paint for Handrail - AP#06 (SF - Front of Lift Shaft) | 1 | 2025-09-02 | 2025-09-02
R7S1ONAR-AP06SF152 | Painting - 2nd Coat - AP#06 (SF - Front of Lift Shaft) | 1 | 2025-09-03 | 2025-09-03
R7S1ONAR-AP06SF155 | Fixing Floor Mat - AP#06 (SF - Front of Lift Shaft) | 2 | 2025-09-04 | 2025-09-06
R7S1ONAR-AP06SF156 | Fixing Wall Guard - AP#06 (SF - Front of Lift Shaft) | 2 | 2025-09-04 | 2025-09-06
GARBAGE ROOM |  | 58 | 2025-07-13 | 2025-09-02
R7S1ONAR-AP06SF163 | Installation of Garbage Chute Full System from GF to 2nd Floor - AP#06 (SF - Garbage Room) | 10 | 2025-07-13 | 2025-07-23
R7S1ONAR-AP06SF157 | Installation of Dry Walls - First Fix - AP#06 (SF - Garbage Room) | 1 | 2025-07-24 | 2025-07-24
R7S1ONAR-AP06SF158 | Installation of Dry Walls - Final Fix - AP#06 (SF - Garbage Room) | 1 | 2025-07-26 | 2025-07-26
R7S1ONAR-AP06SF159 | Garbage Rooms - Wall Tile Finishes (One Side) - AP#06 (SF - Garbage Room) | 1 | 2025-07-27 | 2025-07-27
R7S1ONAR-AP06SF160 | Paint Works of Dry Walls - First Coat - AP#06 (SF - Garbage Room) | 1 | 2025-07-28 | 2025-07-28
R7S1ONAR-AP06SF161 | Installation of the Garbage Chute Door - AP#06 (SF - Garbage Room) | 1 | 2025-07-29 | 2025-07-29
R7S1ONAR-AP06SF162 | Paint Finishes and Touchups - Final Coat - AP#06 (SF - Garbage Room) | 2 | 2025-08-31 | 2025-09-02
BALCONIES |  | 111 | 2025-05-05 | 2025-09-10
R7S1ONAR-AP06FF237 | Wetarea Waterproofing - AP#06 (SF - Balconies) | 8 | 2025-05-05 | 2025-05-14
R7S1ONAR-AP06FF238 | Flooring - AP#06 (SF - Balconies) | 6 | 2025-05-10 | 2025-05-17
R7S1ONAR-AP06FF239 | Painting - Surface Prep., Primer & 1st Coat - AP#06 (SF - Balconies) | 8 | 2025-05-12 | 2025-05-21
R7S1ONAR-AP06FF241 | Fixing Handrail - AP#06 (SF - Balconies) | 6 | 2025-08-26 | 2025-09-01
R7S1ONAR-AP06FF242 | Paint for Handrail - AP#06 (SF - Balconies) | 4 | 2025-09-02 | 2025-09-06
R7S1ONAR-AP06FF240 | Painting - 2nd Coat - AP#06 (SF - Balconies) | 4 | 2025-09-07 | 2025-09-10
MEP WORKS |  | 94 | 2025-05-17 | 2025-09-03
MECHANICAL |  | 94 | 2025-05-17 | 2025-08-31
CHILLED WATER |  | 52 | 2025-05-17 | 2025-06-29
R7S1ONME-AP06SF221 | Installation of Chilled water hanger and supports - AP#06 (SF Corridor) | 4 | 2025-05-17 | 2025-05-21
R7S1ONME-AP06SF271 | Installation of CHWP connection for FCU with Valve package in Corridor, Electrical Room & ICT Room | 4 | 2025-05-17 | 2025-05-21
R7S1ONME-AP06SF223 | Installation of BTU Meter with valves - AP#06 (SF Corridor) | 2 | 2025-05-22 | 2025-05-25
R7S1ONME-AP06SF222 | Installation of CHWP piping (connection between modular cages & modular to apartment) - AP#06 (SF Corridor) | 4 | 2025-05-21 | 2025-05-26
R7S1ONME-AP06SF224 | CHWP piping risers connections - AP#06 (SF Corridor) | 3 | 2025-05-25 | 2025-05-28
R7S1ONME-AP06SF225 | Pressure Testing of CHWP piping - AP#06 (SF Corridor) | 1 | 2025-05-28 | 2025-05-29
R7S1ONME-AP06SF260 | CHWP Insulation - AP#06 (SF Corridor) | 4 | 2025-05-29 | 2025-06-03
R7S1ONME-AP06SF596 | CHWP Installation/Connections and Insulation (In Front of Lift Shaft) - AP#06 | 4 | 2025-06-25 | 2025-06-29
HVAC DUCTING |  | 75 | 2025-05-17 | 2025-08-30
R7S1ONME-AP06SF226 | Duct Riser Continuation - AP#06 (SF Corridor) | 4 | 2025-05-17 | 2025-05-21
R7S1ONME-AP06SF272 | Installation of FCU's & Duct Connection in Corridor, Electrical Room & ICT Room - AP#06 (SF Corridor) | 4 | 2025-05-17 | 2025-05-21
R7S1ONME-AP06SF227 | A/C drain & Copper pipe connection in ELV room - AP#06 (SF Corridor) | 2 | 2025-05-21 | 2025-05-24
R7S1ONME-AP06SF273 | Installation of Ducting and insulation (connection between modular cages) - AP#06 (SF Corridor) | 3 | 2025-05-21 | 2025-05-25
R7S1ONME-AP06SF261 | Installation of Duct & Grill in Garbage Room - AP#06 (SF Corridor) | 2 | 2025-08-27 | 2025-08-30
R7S1ONME-AP06SF274 | Installation of Grilles in the Corridor - AP#06 (SF Corridor) | 2 | 2025-08-27 | 2025-08-30
FIRE FIGHTING |  | 94 | 2025-05-17 | 2025-08-31
R7S1ONME-AP06SF228 | Riser Continuity Succ - Closing of Gysum Boards on shaft - AP#06 (SF Corridor) | 4 | 2025-05-17 | 2025-05-21
R7S1ONME-AP06SF229 | FF Contiuation on High Level with Valves - AP#06 (SF Corridor) | 4 | 2025-05-17 | 2025-05-21
R7S1ONME-AP06SF230 | Installation of Sprinklers drops - AP#06 (SF Corridor) | 4 | 2025-05-21 | 2025-05-26
R7S1ONME-AP06SF231 | Pressure Test for FF Piping - AP#06 (SF Corridor) | 2 | 2025-05-26 | 2025-05-28
R7S1ONME-AP06SF946 | Installation of F.F Pipes, Testing & Final Fixtures (In Front of Lift Shaft) - AP#06 | 3 | 2025-06-28 | 2025-06-30
R7S1ONME-AP06SF232 | Installation of Sprinklers - AP#06 (SF Corridor) | 1 | 2025-08-27 | 2025-08-28
R7S1ONME-AP06SF233 | Installation of Fire Extinguishers - AP#06 (SF Corridor) | 3 | 2025-08-27 | 2025-08-31
R7S1ONME-AP06SF262 | Installation of Pipe & sprinkler in Garbage Room - AP#06 (SF Corridor) | 3 | 2025-08-27 | 2025-08-31
WATER SUPPLY |  | 24 | 2025-05-17 | 2025-06-18
R7S1ONME-AP06SF263 | Installation of WS Pipe in Garbage Room - AP#06 (SF Corridor) | 2 | 2025-05-17 | 2025-05-19
R7S1ONME-AP06SF264 | Installation of Sanitary Fixtures in Janitor Room - AP#06 (SF Corridor) | 2 | 2025-05-17 | 2025-05-19
R7S1ONME-AP06SF234 | Riser Continuity - AP#06 (SF Corridor) | 4 | 2025-05-17 | 2025-05-21
R7S1ONME-AP06SF235 | WS High Level Pipe continuation & Insulation works - AP#06 (SF Corridor) | 4 | 2025-05-17 | 2025-05-21
R7S1ONME-AP06SF236 | Instalation of Hot water line in corridor - AP#06 (SF Corridor) | 4 | 2025-05-21 | 2025-05-26
R7S1ONME-AP06SF237 | Water Meter Installation - AP#06 (SF Corridor) | 4 | 2025-05-26 | 2025-05-31
R7S1ONME-AP06SF238 | Pressure Test for WS - AP#06 (SF Corridor) | 4 | 2025-06-04 | 2025-06-14
R7S1ONME-AP06FF299 | Insulation for Hot water line & Hot water return in corridor - AP#06 (SF Corridor) | 4 | 2025-06-14 | 2025-06-18
DRAINAGE |  | 16 | 2025-05-17 | 2025-06-04
R7S1ONME-AP06SF239 | Installation of Clean-outs - AP#06 (SF Corridor) | 4 | 2025-05-17 | 2025-05-21
R7S1ONME-AP06SF240 | Rain Water Riser continuation - AP#06 (SF Corridor) | 4 | 2025-05-17 | 2025-05-21
R7S1ONME-AP06SF241 | Drainage Riser continuation - AP#06 (SF Corridor) | 4 | 2025-05-17 | 2025-05-21
R7S1ONME-AP06SF242 | Testing for Rain Water Riser - AP#06 (SF Corridor) | 4 | 2025-05-31 | 2025-06-04
R7S1ONME-AP06SF243 | Testing for Drainage Riser - AP#06 (SF Corridor) | 4 | 2025-05-31 | 2025-06-04
ELECTRICAL |  | 77 | 2025-05-17 | 2025-09-03
POWER & LIGHTING |  | 70 | 2025-05-17 | 2025-09-03
R7S1ONME-AP06SF244 | Contiuation of Cable Trays & apartment branches - AP#06 (SF Corridor) | 4 | 2025-05-17 | 2025-05-21
R7S1ONME-AP06SF245 | Contiuation of Cable Trunking with Flexible conduits for Lights - AP#06 (SF Corridor) | 4 | 2025-05-17 | 2025-05-21
R7S1ONME-AP06SF246 | Installation of EMT pipes - AP#06 (SF Corridor) | 5 | 2025-05-17 | 2025-05-22
R7S1ONME-AP06SF247 | Installation of Busbar, Electrical Meter & Tap-off in Corridor - AP#06 (SF Corridor) | 3 | 2025-06-21 | 2025-06-23
R7S1ONME-AP06SF270 | Termination of Tap-off with Electrical Meter in the apartments - AP#06 (SF Corridor) | 3 | 2025-06-24 | 2025-06-26
R7S1ONME-AP06SF248 | Corridor Wire Pulling - AP#06 (SF Corridor) | 6 | 2025-06-22 | 2025-06-28
R7S1ONME-AP06SF1126 | Continuation of Cable Tray/Trunking with Flexible conduits for Lights (In Front of Lift Shaft) - AP#06 | 4 | 2025-06-26 | 2025-06-30
R7S1ONME-AP06SF249 | Electrical Room - Installation of Cable trays, SMDB & Termination - AP#06 (SF Corridor) | 6 | 2025-07-30 | 2025-08-06
R7S1ONME-AP06SF251 | Installation, Termination of Emergeny & Exit Lights with contiuity - AP#06 (SF Corridor) | 2 | 2025-08-27 | 2025-08-30
R7S1ONME-AP06SF250 | Installation, Termination of Light Fixtures with continuity test - AP#06 (SF - Corridor & Balconies) | 3 | 2025-08-27 | 2025-08-31
R7S1ONME-AP06SF252 | Installation, Termination of PIR sensors with continuity test - AP#06 (SF Corridor) | 2 | 2025-09-01 | 2025-09-03
LOW CURRENT SYSTEM |  | 77 | 2025-05-17 | 2025-09-01
R7S1ONME-AP06SF275 | CBS System cable installation - AP#06 (SF Corridor) | 3 | 2025-05-17 | 2025-05-20
R7S1ONME-AP06SF253 | Installation of Basket trays for BMS, CCTV, Access Control - AP#06 (SF Corridor) | 4 | 2025-05-17 | 2025-05-21
R7S1ONME-AP06SF255 | Fire alarm cable installation - AP#06 (SF Corridor) | 3 | 2025-05-18 | 2025-05-21
R7S1ONME-AP06SF254 | Voice Evacuation cable installation - AP#06 (SF Corridor) | 3 | 2025-05-20 | 2025-05-24
R7S1ONME-AP06SF257 | BMS, CCTV & Access control Cable installation - AP#06 (SF Corridor) | 2 | 2025-07-03 | 2025-07-05
R7S1ONME-AP06SF1306 | Installation of Basket trays for Low Current, Cable Installation (In Front of Lift Shaft) - AP#06 | 4 | 2025-07-03 | 2025-07-07
R7S1ONME-AP06SF258 | Low Current Works including BMS Panel in ICT Room - AP#06 (SF Corridor) | 10 | 2025-07-24 | 2025-08-05
R7S1ONME-AP06SF269 | Fluke test for CCTV & Fibre Optic Cable - AP#06 (SF Corridor) | 2 | 2025-08-03 | 2025-08-05
R7S1ONME-AP06SF256 | Fibre optic Cable pulling & Termination with OTO (in corridors to ONU) - AP#06 (SF Corridor) | 2 | 2025-08-05 | 2025-08-07
R7S1ONME-AP06SF265 | Installation & Termination of CCTV Cameras - AP#06 (SF Corridor) | 2 | 2025-08-27 | 2025-08-30
R7S1ONME-AP06SF266 | Installation & Termination of Access control system for Electrical Room - AP#06 (SF Corridor) | 2 | 2025-08-27 | 2025-08-30
R7S1ONME-AP06SF268 | Installation & Termination of Wireless Gateway & RF Node in corridors - AP#06 (SF Corridor) | 2 | 2025-08-27 | 2025-08-30
R7S1ONME-AP06SF259 | Installation & Termination of Fire alarm devices & Speakers - AP#06 (SF Corridor) | 4 | 2025-08-27 | 2025-09-01
R7S1ONME-AP06SF267 | Installation & Termination of Active Components & UPS installation in ICT Room - AP#06 (SF Corridor) | 2 | 2025-08-30 | 2025-09-01
ROOF WORKS |  | 101 | 2025-05-31 | 2025-09-13
ARCH./ CIVIL WORKS |  | 83 | 2025-05-31 | 2025-09-09
R7S1ONAR-AP06RF35 | Roof Box Stiching (Concrete Works) - AP#06 (Roof) | 6 | 2025-05-31 | 2025-06-11
R7S1ONME-AP06RF251 | Installation of Roof Drains - AP#06 (Roof) | 2 | 2025-06-04 | 2025-06-11
R7S1ONAR-AP06RF36 | Roof Waterproofing Works with testing - AP#06 (Roof) | 20 | 2025-06-29 | 2025-07-22
R7S1ONAR-AP06RF37 | Laying of Gravel - AP#06 (Roof) | 2 | 2025-07-22 | 2025-07-24
R7S1ONAR-AP06RF38 | Surface Preparation & Primer for Parapets - AP#06 (Roof) | 6 | 2025-08-11 | 2025-08-18
R7S1ONAR-AP06RF39 | 1st Coat Paint for Parapets - AP#06 (Roof) | 2 | 2025-08-18 | 2025-08-20
R7S1ONAR-AP06RF40 | 2nd Coat Paint for Parapets - AP#06 (Roof) | 2 | 2025-08-20 | 2025-08-23
R7S1ONAR-AP06RF42 | Fixing Fall Arrest System - AP#06 (Roof) | 2 | 2025-08-23 | 2025-08-25
R7S1ONAR-AP06RF41 | Crossover Bridges Installation & application of Sealant on MEP penetrations - AP#06 (Roof) | 4 | 2025-09-04 | 2025-09-09
MECHANICAL |  | 69 | 2025-07-24 | 2025-08-17
HVAC |  | 27 | 2025-07-24 | 2025-08-10
R7S1ONME-AP06RF215 | Modular Installation - AP#06 (Roof) | 5 | 2025-07-24 | 2025-07-30
R7S1ONME-AP06RF216 | Continuation of Roof duct works/FAHU Connections - AP#06 (Roof) | 5 | 2025-07-27 | 2025-08-02
R7S1ONME-AP06RF218 | Insulations for ducts - AP#06 (Roof) | 5 | 2025-07-28 | 2025-08-03
R7S1ONME-AP06RF220 | Installation of FAHU - AP#06 (Roof) | 2 | 2025-08-02 | 2025-08-04
R7S1ONME-AP06RF225 | Installation of Outdoor VRF/DX Units - AP#06 (Roof) | 2 | 2025-08-03 | 2025-08-05
R7S1ONME-AP06RF226 | Installation & Insulation of the Condensation Drain - AP#06 (Roof) | 1 | 2025-08-04 | 2025-08-05
R7S1ONME-AP06RF228 | Installation of Ventilation Fans - AP#06 (Roof) | 3 | 2025-08-02 | 2025-08-05
R7S1ONME-AP06RF223 | Chilled Water System Continuation and Connections with Valve package of FAHU - AP#06 (Roof) | 4 | 2025-08-02 | 2025-08-06
R7S1ONME-AP06RF230 | Installation of Louvers - AP#06 (Roof) | 2 | 2025-08-05 | 2025-08-07
R7S1ONME-AP06RF233 | Installation & Testing of Copper Pipes - AP#06 (Roof) | 2 | 2025-08-05 | 2025-08-07
R7S1ONME-AP06RF234 | Miscellaneous Works for Mechanical Connections (Fire & Volume Dampers etc.) - AP#06 (Roof) | 2 | 2025-08-07 | 2025-08-10
WATERSUPPLY & DRAINAGE |  | 31 | 2025-07-30 | 2025-08-16
R7S1ONME-AP06RF214 | Testing for the Rain Water Risers - AP#06 (Roof) | 2 | 2025-08-02 | 2025-08-04
R7S1ONME-AP06RF217 | Installation & Continuation of Water supply pipes (connection between modular cages & modular to Shaft Riser) - AP#06 | 4 | 2025-07-30 | 2025-08-04
R7S1ONME-AP06RF221 | Installation of Air Vent & Pressure Guage with Valves at Roof - AP#06 (Roof) | 4 | 2025-08-02 | 2025-08-06
R7S1ONME-AP06RF222 | Vertical Continuation of Vent Pipes To The Roof (Drainage) - AP#06 (Roof) | 4 | 2025-08-03 | 2025-08-07
R7S1ONME-AP06RF224 | Installation of Rain Water outlet - AP#06 (Roof) | 3 | 2025-08-04 | 2025-08-07
R7S1ONME-AP06RF219 | Installation of Air Vent with Valve for Water Supply - AP#06 (Roof) | 4 | 2025-08-04 | 2025-08-09
R7S1ONME-AP06RF227 | Testing of Water Supply Pipes - AP#06 (Roof) | 2 | 2025-08-09 | 2025-08-11
R7S1ONME-AP06RF229 | Insulation of Roof Water Line - AP#06 (Roof) | 2 | 2025-08-10 | 2025-08-12
R7S1ONME-AP06RF231 | Testing for the Drainage Pipes Risers - AP#06 (Roof) | 2 | 2025-08-12 | 2025-08-14
R7S1ONME-AP06RF232 | Installation of Vent Cowl - AP#06 (Roof) | 1 | 2025-08-14 | 2025-08-16
SOLAR HEATER |  | 60 | 2025-08-04 | 2025-08-17
R7S1ONME-AP06RF246 | Installation of Solar water pumps and circulation pumps with valves(For Water Only) - AP#06 (Roof) | 2 | 2025-08-05 | 2025-08-07
R7S1ONME-AP06RF244 | Installation of Structure and Solar Panels (For Water Only) - AP#06 (Roof) | 5 | 2025-08-04 | 2025-08-10
R7S1ONME-AP06RF245 | Installation of Solar Calorifier Tank & Air cooler (For Water Only) - AP#06 (Roof) | 5 | 2025-08-05 | 2025-08-11
R7S1ONME-AP06RF247 | Installation of Solar Pipes Primary Loop - AP#06 (Roof) | 5 | 2025-08-05 | 2025-08-11
R7S1ONME-AP06RF248 | Testing of Solar Pipes Primary Loop - AP#06 (Roof) | 1 | 2025-08-11 | 2025-08-12
R7S1ONME-AP06RF249 | Insulation of Solar Pipes Primary Loop - AP#06 (Roof) | 1 | 2025-08-11 | 2025-08-12
R7S1ONME-AP06RF250 | Aluminum Cladding of Solar Pipes Primary Loop - AP#06 (Roof) | 4 | 2025-08-12 | 2025-08-17
ELECTRICAL |  | 38 | 2025-07-30 | 2025-09-13
POWER & LOW CURRENT |  | 38 | 2025-07-30 | 2025-09-13
R7S1ONME-AP06RF235 | Installation of Cables for Fire Alarm system - AP#06 (Roof) | 3 | 2025-07-30 | 2025-08-03
R7S1ONME-AP06RF236 | Installation of Cables for BMS - AP#06 (Roof) | 3 | 2025-07-30 | 2025-08-03
R7S1ONME-AP06RF237 | Installation of Fire Alarm Devices - AP#06 (Roof) | 3 | 2025-07-30 | 2025-08-03
R7S1ONME-AP06RF239 | Installation of Roof Light Fixtures - AP#06 (Roof) | 3 | 2025-07-30 | 2025-08-03
R7S1ONME-AP06RF238 | Installation of BMS Devices - AP#06 (Roof) | 4 | 2025-07-31 | 2025-08-05
R7S1ONME-AP06RF211 | Installation of Electrical Containments for BMS - AP#06 (Roof) | 7 | 2025-07-30 | 2025-08-07
R7S1ONME-AP06RF241 | Termination for BMS System - AP#06 (Roof) | 1 | 2025-08-07 | 2025-08-09
R7S1ONME-AP06RF253 | Termination of Primary & Secondary pump for Solar system - AP#06 (Roof) | 1 | 2025-08-07 | 2025-08-09
R7S1ONME-AP06RF252 | Installation & Termination of Solar System Panel - AP#06 (Roof) | 3 | 2025-08-17 | 2025-08-20
R7S1ONME-AP06RF210 | Installation of Isolators and Machine Connections - AP#06 (Roof) | 4 | 2025-08-25 | 2025-08-30
R7S1ONME-AP06RF209 | Lightening Protection & Earthing System - AP#06 (Roof) | 7 | 2025-08-23 | 2025-08-31
R7S1ONME-AP06RF212 | Installation of Fire Alarm Containment for FAHU, Fans - AP#06 (Roof) | 4 | 2025-08-31 | 2025-09-04
R7S1ONME-AP06RF242 | Termination for Fire Alarm Device - AP#06 (Roof) | 1 | 2025-09-04 | 2025-09-06
R7S1ONME-AP06RF213 | Installation of LV Power Cables for Roof Equipment - AP#06 (Roof) | 5 | 2025-09-04 | 2025-09-10
R7S1ONME-AP06RF240 | Termination for LV Cables - AP#06 (Roof) | 1 | 2025-09-10 | 2025-09-11
R7S1ONME-AP06RF243 | Megger Test for the Power Cables - AP#06 (Roof) | 1 | 2025-09-11 | 2025-09-13
STAIR CASE |  | 113 | 2025-06-11 | 2025-08-02
CIVIL WORKS |  | 113 | 2025-06-11 | 2025-07-28
STAIR CASE (MAIN WITH LIFT) |  | 106 | 2025-06-11 | 2025-07-09
R7S1ONST-AP06RG365 | Stair Flooring (Roof to GF) - AP#06 (Main Stair) | 7 | 2025-06-11 | 2025-06-19
R7S1ONST-AP06RG366 | Stair Hand Rails (Roof to GF) - AP#06 (Main Stair) | 6 | 2025-06-19 | 2025-06-26
R7S1ONST-AP06RG367 | Stair Paint - Primer & 1st Coat (Roof to GF)- AP#06 (Main Stair) | 7 | 2025-06-26 | 2025-07-05
R7S1ONST-AP06RG368 | Stair Paint - Final Coat (Roof to GF)- AP#06 (Main Stair) | 4 | 2025-07-05 | 2025-07-09
STAIR CASE (LEFT SIDE) |  | 92 | 2025-06-19 | 2025-07-15
R7S1ONST-AP06RG375 | Stair Flooring (Roof to GF) - AP#06 Left Side Stair | 7 | 2025-06-19 | 2025-06-28
R7S1ONST-AP06RG376 | Stair Hand Rails (Roof to GF) - AP#06 Left Side Stair | 6 | 2025-06-28 | 2025-07-05
R7S1ONST-AP06RG377 | Stair Paint - Primer & 1st Coat (Roof to GF) - AP#06 Left Side Stair | 6 | 2025-07-05 | 2025-07-12
R7S1ONST-AP06RG378 | Stair Paint - Final Coat (Roof to GF) - AP#06 Left Side Stair | 3 | 2025-07-12 | 2025-07-15
STAIR CASE (RIGHT SIDE) |  | 84 | 2025-06-28 | 2025-07-28
R7S1ONST-AP06RG379 | Stair Flooring (Roof to GF) - AP#06 Right Side Stair | 8 | 2025-06-28 | 2025-07-07
R7S1ONST-AP06RG380 | Stair Hand Rails (Roof to GF) - AP#06 Right Side Stair | 7 | 2025-07-07 | 2025-07-15
R7S1ONST-AP06RG381 | Stair Paint - Primer & 1st Coat (Roof to GF) - AP#06 Right Side Stair | 7 | 2025-07-15 | 2025-07-23
R7S1ONST-AP06RG382 | Stair Paint - Final Coat (Roof to GF) - AP#06 Right Side Stair | 4 | 2025-07-23 | 2025-07-28
MEP WORKS |  | 48 | 2025-06-18 | 2025-08-02
STAIR CASE (MAIN WITH LIFT) |  | 38 | 2025-06-18 | 2025-07-14
R7S1ONST-AP06RG364 | Main Staircase Wire Pulling - AP#06 (Main Stair) | 3 | 2025-06-18 | 2025-06-21
R7S1ONST-AP06RG383 | Final fix - Main Staircase Lights Fixtures & Motion Sensor - AP#06 (Main Stair) | 2 | 2025-07-09 | 2025-07-12
R7S1ONST-AP06RG384 | Final fix - Main Staircase Emergency Lights Fixtures - AP#06 (Main Stair) | 2 | 2025-07-12 | 2025-07-14
STAIR CASE (LEFT SIDE) |  | 39 | 2025-06-22 | 2025-07-20
R7S1ONST-AP06RG369 | Left Staircase Wire Pulling - AP#06 (Main Stair) | 3 | 2025-06-22 | 2025-06-24
R7S1ONST-AP06RG371 | Final fix - Left Staircase Lights Fixtures & Motion Sensor - AP#06 (Main Stair) | 2 | 2025-07-15 | 2025-07-17
R7S1ONST-AP06RG373 | Final fix - Left Staircase Emergency Lights Fixtures - AP#06 (Main Stair) | 2 | 2025-07-17 | 2025-07-20
STAIR CASE (RIGHT SIDE) |  | 42 | 2025-06-25 | 2025-08-02
R7S1ONST-AP06RG370 | Right Staircase Wire Pulling - AP#06 (Main Stair) | 3 | 2025-06-25 | 2025-06-28
R7S1ONST-AP06RG372 | Final fix - Right Staircase Lights Fixtures & Motion Sensor - AP#06 (Main Stair) | 2 | 2025-07-28 | 2025-07-30
R7S1ONST-AP06RG374 | Final fix - Right Staircase Emergency Lights Fixtures - AP#06 (Main Stair) | 2 | 2025-07-30 | 2025-08-02
ELEVATOR WORKS |  | 33 | 2025-08-09 | 2025-09-02
R7S1ONEL-AP06GR619 | Installation of Rails - AP#06 (Elevator Works) | 6 | 2025-08-09 | 2025-08-14
R7S1ONEL-AP06GR620 | Assembly of Cabin - AP#06 (Elevator Works) | 4 | 2025-08-16 | 2025-08-19
R7S1ONEL-AP06GR621 | Installation of Motor - AP#06 (Elevator Works) | 4 | 2025-08-20 | 2025-08-24
R7S1ONEL-AP06GR622 | Installation of Main Cables - AP#06 (Elevator Works) | 4 | 2025-08-25 | 2025-08-28
R7S1ONEL-AP06GR623 | Installation of Doors, Indicator, Push Button - AP#06 (Elevator Works) | 2 | 2025-08-30 | 2025-08-31
R7S1ONEL-AP06GR624 | Interior Finishes - AP#06 (Elevator Works) | 2 | 2025-09-01 | 2025-09-02
EXTERNAL ELEVATIONS |  | 58 | 2025-07-24 | 2025-09-13
ARCH./ CIVIL WORKS |  | 58 | 2025-07-24 | 2025-09-13
R7S1ONEE-AP06GR513 | External Selant Works - For Boxes - AP#06 (External Elevations) | 15 | 2025-07-24 | 2025-08-11
R7S1ONEE-AP06GR514 | Final Finishes & Touchups - AP#06 (External Elevations) | 20 | 2025-08-11 | 2025-09-03
R7S1ONME-AP06GF523 | Installation of rain water outlet - External façade - AP#06 (External Elevations) | 2 | 2025-09-03 | 2025-09-06
R7S1ONEE-AP06GR516 | Installation of External Signages - AP#06 (External Elevations) | 4 | 2025-09-06 | 2025-09-10
R7S1ONEE-AP06GR515 | Fixing Cage Ladder - AP#06 (External Elevations) | 2 | 2025-09-10 | 2025-09-13
EXTERNAL - CIVIL WORKS |  | 35 | 2025-07-10 | 2025-08-07
DRAINAGE |  | 12 | 2025-07-10 | 2025-07-23
R7S1ONECW-AP06-325 | Excavation Works & Sand Bedding - AP#06 (External Drainage) | 3 | 2025-07-10 | 2025-07-13
R7S1ONECW-AP06-326 | Drainage Manholes - AP#06 | 6 | 2025-07-10 | 2025-07-16
R7S1ONECW-AP06-327 | Drainage Backfilling - AP#06 | 2 | 2025-07-22 | 2025-07-23
WATERSUPPLY |  | 16 | 2025-07-14 | 2025-08-07
R7S1ONECW-AP06-328 | Excavation Works & Sand Bedding - Watersupply - AP#06 (External Watersupply Civil) | 3 | 2025-07-14 | 2025-07-16
R7S1ONECW-AP06-329 | Watersupply Manholes - AP#06 | 6 | 2025-07-17 | 2025-07-23
R7S1ONECW-AP06-330 | Watersupply Backfilling - AP#06 | 2 | 2025-08-06 | 2025-08-07
CHILLED WATER |  | 9 | 2025-07-17 | 2025-07-29
R7S1ONECW-AP06-334 | Excavation Works & Sand Bedding - AP#06 (External Chilled Water Civil) | 3 | 2025-07-17 | 2025-07-20
R7S1ONECW-AP06-335 | Chilled Water Manholes - AP#06 | 6 | 2025-07-21 | 2025-07-27
R7S1ONECW-AP06-336 | Chilled Water Backfilling - AP#06 | 2 | 2025-07-28 | 2025-07-29
FIRE FIGHTING |  | 11 | 2025-07-21 | 2025-08-07
R7S1ONECW-AP06-331 | Excavation Works & Sand Bedding - AP#06 (External Chilled Water Civil) | 3 | 2025-07-21 | 2025-07-23
R7S1ONECW-AP06-332 | Fire Fighting Manholes - AP#06 | 6 | 2025-07-24 | 2025-07-30
R7S1ONECW-AP06-333 | Fire Fighting Backfilling - AP#06 | 2 | 2025-08-06 | 2025-08-07
POWER |  | 22 | 2025-07-24 | 2025-08-02
R7S1ONECW-AP06-337 | Excavation Works & Sand Bedding - AP#06 (External Power Civil) | 3 | 2025-07-24 | 2025-07-27
R7S1ONECW-AP06-338 | Power Manholes - AP#06 | 3 | 2025-07-28 | 2025-07-30
R7S1ONECW-AP06-339 | Power Backfilling - AP#06 | 2 | 2025-07-31 | 2025-08-02
LOW CURRENT |  | 8 | 2025-07-28 | 2025-08-05
R7S1ONECW-AP06-340 | Excavation Works & Sand Bedding - AP#06 (External Low Current Civil) | 3 | 2025-07-28 | 2025-07-30
R7S1ONECW-AP06-341 | Low Current Manholes - AP#06 | 3 | 2025-07-31 | 2025-08-03
R7S1ONECW-AP06-342 | Low Current Backfilling - AP#06 | 2 | 2025-08-04 | 2025-08-05
EXTERNAL - MEP SERVICES |  | 31 | 2025-07-17 | 2025-08-07
DRAINAGE |  | 4 | 2025-07-17 | 2025-07-21
R7S1ONEME-AP06-221 | External Drainage Network - AP#06 (External Drainage MEP) | 4 | 2025-07-17 | 2025-07-21
WATERSUPPLY |  | 8 | 2025-07-24 | 2025-08-07
R7S1ONEME-AP06-222 | PRV statiuon assembly including meters- AP#06 (External WS MEP) | 4 | 2025-07-24 | 2025-07-28
R7S1ONEME-AP06-224 | Installation of valve station incl. BTU meter- AP#06 (External WS MEP) | 3 | 2025-08-05 | 2025-08-07
CHILLED WATER |  | 7 | 2025-07-29 | 2025-08-05
R7S1ONEME-AP06-223 | Installation of Chilled water line- AP#06 (External CWP MEP) | 6 | 2025-07-29 | 2025-08-04
R7S1ONEME-AP06-225 | Pressure Test for chilled water line- AP#06 (External CWP MEP) | 1 | 2025-08-05 | 2025-08-05
FIRE FIGHTING |  | 14 | 2025-07-24 | 2025-08-05
R7S1ONEME-AP06-226 | Installation of External FF network - AP#06 (External FF MEP) | 6 | 2025-07-24 | 2025-07-30
R7S1ONEME-AP06-227 | Installation of Alarm check valves- AP#06 (External FF MEP) | 3 | 2025-07-31 | 2025-08-03
R7S1ONEME-AP06-228 | Testing of External FF - AP#06 (External FF MEP) | 2 | 2025-08-04 | 2025-08-05
POWER |  | 1 | 2025-07-28 | 2025-07-28
R7S1ONEME-AP06-229 | Cable pulling from Manhole to the building MDB - AP#06 (External Power MEP) | 1 | 2025-07-28 | 2025-07-28
LOW CURRENT |  | 3 | 2025-07-31 | 2025-08-03
R7S1ONEME-AP06-230 | Low Current Cable pulling- AP#06 (External FF MEP) | 3 | 2025-07-31 | 2025-08-03
BUILDING # AP07 (MGT BLDG) |  | 280 | 2024-11-21 | 2025-09-18
SUB-STRUCTURE |  | 49 | 2024-11-21 | 2025-01-16
R7S1-ONSB-AP07-248 | Site Setting Out Works - AP#07 | 1 | 2024-11-21 | 2024-11-21
R7S1-ONSB-AP07-245 | Site levelling & earthworks - AP#07 | 2 | 2024-11-28 | 2024-11-30
R7S1-ONSB-AP07-249 | Anti-termite & Polythene Sheet Works - AP#07 | 1 | 2024-12-28 | 2024-12-28
R7S1-ONSB-AP07-246 | Blinding PCC - AP#07 | 3 | 2024-12-29 | 2024-12-31
R7S1-ONSB-AP07-247 | Waterproofing for Blinding PCC (Bitumen Paint) - AP#07 | 2 | 2025-01-01 | 2025-01-02
R7S1-ONSB-AP07-254 | Installation of MEP U/G services below Boxes - AP#07 | 2 | 2025-01-06 | 2025-01-07
R7S1-ONSB-AP07-250 | Foundations/Upstands - Rebar - AP#07 | 2 | 2025-01-12 | 2025-01-13
R7S1-ONSB-AP07-251 | Foundations/Upstands - Shuttering (Including dowel Works) - AP#07 | 11 | 2025-01-02 | 2025-01-14
R7S1-ONSB-AP07-252 | Foundations/Upstands - Casting - AP#07 | 1 | 2025-01-14 | 2025-01-14
R7S1-ONSB-AP07-253 | Waterproofing For Foundations/Upstands - AP#07 | 1 | 2025-01-15 | 2025-01-15
R7S1-ONSB-AP07-255 | Backfilling & Compaction - AP#07 | 1 | 2025-01-16 | 2025-01-16
SLAB-ON-GRADE & UG MEP WORKS (in Corridor) |  | 43 | 2025-03-01 | 2025-04-24
LEFT SIDE |  | 43 | 2025-03-01 | 2025-04-24
R7S1-ONSG-AP07-301 | Block Work below Corridor area - AP#07 | 8 | 2025-03-01 | 2025-03-10
R7S1-ONSG-AP07-307 | Backfilling upto Pipe Level - AP#07 | 8 | 2025-03-02 | 2025-03-11
R7S1-ONSG-AP07-302 | UG MEP Works (Laying of Pipes) - AP#07 | 8 | 2025-03-03 | 2025-03-12
R7S1-ONSG-AP07-303 | Backfilling Works after Pipe Laying - AP#07 | 6 | 2025-03-06 | 2025-03-13
R7S1-ONSG-AP07-315 | Plaster Work for Blockwork - AP#07 | 8 | 2025-03-04 | 2025-03-13
R7S1-ONSG-AP07-304 | Antitermite Works - AP#07 | 5 | 2025-03-08 | 2025-03-13
R7S1-ONSG-AP07-305 | Polythene & Rebar Mesh Works - AP#07 | 5 | 2025-03-09 | 2025-03-15
R7S1-ONSG-AP07-306 | Pouring SOG Concrete - AP#07 | 5 | 2025-03-10 | 2025-03-16
R7S1-ONSG-AP07-330 | Backfilling & SOG (In Front of Lift Shaft) - AP#07 | 4 | 2025-04-21 | 2025-04-24
RIGHT SIDE |  | 13 | 2025-03-03 | 2025-03-18
R7S1-ONSG-AP07-308 | Block Work below Corridor area - AP#07 | 7 | 2025-03-03 | 2025-03-11
R7S1-ONSG-AP07-314 | Backfilling upto Pipe Level - AP#07 | 7 | 2025-03-04 | 2025-03-12
R7S1-ONSG-AP07-309 | UG MEP Works (Laying of Pipes) - AP#07 | 7 | 2025-03-05 | 2025-03-13
R7S1-ONSG-AP07-310 | Backfilling Works after Pipe Laying - AP#07 | 5 | 2025-03-09 | 2025-03-15
R7S1-ONSG-AP07-311 | Antitermite Works - AP#07 | 5 | 2025-03-10 | 2025-03-16
R7S1-ONSG-AP07-312 | Polythene & Rebar Mesh Works - AP#07 | 5 | 2025-03-11 | 2025-03-17
R7S1-ONSG-AP07-313 | Pouring SOG Concrete - AP#07 | 5 | 2025-03-12 | 2025-03-18
ERECTION WORKS |  | 80 | 2025-02-25 | 2025-06-04
GROUND FLOOR |  | 76 | 2025-02-25 | 2025-05-08
R7S1ONER-AP07GF175 | Erection of GF Boxes (Left Side) including Lift Box & Staircase - AP#07 | 9 | 2025-02-25 | 2025-03-08
R7S1ONER-AP07GF176 | Erection of GF Boxes (Right Side) - AP#07 | 10 | 2025-02-27 | 2025-03-11
R7S1ONER-AP07GF177 | Erection of GF MEP Modular Cages (Left Side) - AP#07 | 6 | 2025-03-11 | 2025-03-18
R7S1ONER-AP07GF178 | Erection of GF Corridor Slabs (Left Side) - AP#07 | 6 | 2025-03-13 | 2025-03-20
R7S1ONER-AP07GF179 | Erection of GF MEP Modular Cages (Right Side) - AP#07 | 6 | 2025-03-13 | 2025-03-20
R7S1ONER-AP07GF180 | Erection of GF Corridor Slabs Right Side) - AP#07 | 6 | 2025-03-16 | 2025-03-23
R7S1ONER-AP07GF322 | Erection of Columns/Beams Frame & Slab/Loose Elements (In Front of Lift Shaft) - AP#07 | 2 | 2025-05-07 | 2025-05-08
FIRST FLOOR |  | 48 | 2025-04-07 | 2025-05-11
R7S1ONER-AP07FF175 | Erection of FF Boxes (Left Side) - AP#07 | 4 | 2025-04-07 | 2025-04-10
R7S1ONER-AP07FF176 | Erection of FF Boxes (Right Side) - AP#07 | 3 | 2025-04-13 | 2025-04-15
R7S1ONER-AP07FF177 | Erection of FF MEP Modular Cages (Left Side) - AP#07 | 4 | 2025-04-16 | 2025-04-20
R7S1ONER-AP07FF179 | Erection of FF MEP Modular Cages (Right Side) - AP#07 | 2 | 2025-04-19 | 2025-04-20
R7S1ONER-AP07FF178 | Erection of FF Corridor Slabs (Left Side) - AP#07 | 4 | 2025-04-19 | 2025-04-22
R7S1ONER-AP07FF180 | Erection of FF Corridor Slabs Right Side) - AP#07 | 2 | 2025-04-21 | 2025-04-22
R7S1ONER-AP07FF332 | Erection of Columns/Beams Frame & Slab/Loose Elements (In Front of Lift Shaft) - AP#07 | 2 | 2025-05-10 | 2025-05-11
SECOND FLOOR |  | 22 | 2025-05-10 | 2025-05-21
R7S1ONER-AP07SF175 | Erection of SF Boxes (Left Side) - AP#07 | 2 | 2025-05-10 | 2025-05-12
R7S1ONER-AP07SF342 | Erection of Columns/Beams Frame & Slab/Loose Elements (In Front of Lift Shaft) - AP#07 | 2 | 2025-05-12 | 2025-05-13
R7S1ONER-AP07SF176 | Erection of SF Boxes (Right Side) - AP#07 | 2 | 2025-05-12 | 2025-05-14
R7S1ONER-AP07SF177 | Erection of SF MEP Modular Cages (Left Side) - AP#07 | 3 | 2025-05-12 | 2025-05-15
R7S1ONER-AP07SF178 | Erection of SF Corridor Slabs (Left Side) - AP#07 | 2 | 2025-05-15 | 2025-05-18
R7S1ONER-AP07SF179 | Erection of SF MEP Modular Cages (Right Side) - AP#07 | 2 | 2025-05-17 | 2025-05-19
R7S1ONER-AP07SF180 | Erection of SF Corridor Slabs Right Side) - AP#07 | 2 | 2025-05-19 | 2025-05-21
ROOF |  | 12 | 2025-05-21 | 2025-06-04
R7S1ONER-AP07RF105 | Erection of Loose Roof Parapets, Shaft Covers, MEP Foundation etc. - AP#07 Roof | 12 | 2025-05-21 | 2025-06-04
MEP WORKS & FINISHES |  | 171 | 2025-03-18 | 2025-09-17
GROUND FLOOR |  | 169 | 2025-03-18 | 2025-09-11
ARCH./ CIVIL WORKS |  | 159 | 2025-04-05 | 2025-09-11
CORRIDOR AREA |  | 132 | 2025-04-10 | 2025-09-11
R7S1ONAR-AP07GF167 | Flooring in Corridor - AP#07 (GF Corridor) | 83 | 2025-04-10 | 2025-07-21
R7S1ONAR-AP07GF168 | Corridor Skirting - AP#07 (GF Corridor) | 2 | 2025-07-20 | 2025-07-22
R7S1ONAR-AP07GF165 | False Ceiling - 1st Fix - AP#07 (GF - Corridor) | 4 | 2025-07-22 | 2025-07-27
R7S1ONAR-AP07GF166 | Gypsum Wall Cladding - 1st Fix (Shafts) - AP#07 (GF Corridor) | 100 | 2025-04-12 | 2025-08-11
R7S1ONAR-AP07GF169 | Gypsum Wall Cladding (Shafts) -2nd Fix - AP#07 (GF Corridor) | 4 | 2025-08-11 | 2025-08-16
R7S1ONAR-AP07GF173 | Fixing Architrave - AP#07 (GF Corridor) | 2 | 2025-08-16 | 2025-08-18
R7S1ONAR-AP07GF174 | Fixing Aluminium Doors - AP#07 (GF Corridor) | 2 | 2025-08-18 | 2025-08-20
R7S1ONAR-AP07GF170 | False Ceiling - 2nd Fix (Closing the Ceiling) - AP#07 (GF Corridor) | 3 | 2025-08-20 | 2025-08-24
R7S1ONAR-AP07GF171 | Painting - Surface Prep., Primer & 1st Coat - AP#07 (GF Corridor) | 8 | 2025-08-16 | 2025-08-25
R7S1ONAR-AP07GF195 | Painting - Surface Prep., Primer & 1st Coat for Ceiling - AP#07 (GF Corridor) | 4 | 2025-08-24 | 2025-08-28
R7S1ONAR-AP07GF172 | Painting - Final Coat (Ceiling + Walls) - AP#07 (GF Corridor) | 3 | 2025-09-09 | 2025-09-11
INSIDE BOXES |  | 88 | 2025-04-05 | 2025-07-30
R7S1ONAR-AP07GF175 | Fixing Thresholds (Joining the Room) - AP#07 (GF - inside Boxes) | 88 | 2025-04-05 | 2025-07-21
R7S1ONAR-AP07GF176 | Fixing Wooden Doors - AP#07 (GF - inside Boxes) | 4 | 2025-07-21 | 2025-07-26
R7S1ONAR-AP07GF177 | Fixing Aluminium Doors - AP#07 (GF - inside Boxes) | 4 | 2025-07-26 | 2025-07-30
IN FRONT OF LIFT SHAFT |  | 91 | 2025-04-26 | 2025-09-08
R7S1ONAR-AP07GF179 | Flooring - AP#07 (GF - Front of Lift Shaft) | 2 | 2025-04-26 | 2025-04-27
R7S1ONAR-AP07GF180 | Skirting & Thresholds - AP#07 (GF - Front of Lift Shaft) | 1 | 2025-04-27 | 2025-04-27
R7S1ONAR-AP07GF181 | Painting - Surface Prep., Primer & 1st Coat - AP#07 (GF - Front of Lift Shaft) | 2 | 2025-04-28 | 2025-04-29
R7S1ONAR-AP07GF178 | False Ceiling - 1st Fix - AP#07 (GF - Front of Lift Shaft) | 2 | 2025-04-30 | 2025-05-01
R7S1ONAR-AP07GF182 | False Ceiling - Final Fix - AP#07 (GF - Front of Lift Shaft) | 1 | 2025-05-03 | 2025-05-03
R7S1ONAR-AP07GF184 | Fixing Handrail - AP#07 (GF - Front of Lift Shaft) | 3 | 2025-08-30 | 2025-09-01
R7S1ONAR-AP07GF185 | Paint for Handrail - AP#07 (GF - Front of Lift Shaft) | 1 | 2025-09-02 | 2025-09-02
R7S1ONAR-AP07GF183 | Painting - Final Coat - AP#07 (GF - Front of Lift Shaft) | 1 | 2025-09-03 | 2025-09-03
R7S1ONAR-AP07GF187 | Fixing Wall Guard - AP#07 (GF - Front of Lift Shaft) | 2 | 2025-09-04 | 2025-09-06
R7S1ONAR-AP07GF186 | Fixing Floor Mat - AP#07 (GF - Front of Lift Shaft) | 2 | 2025-09-07 | 2025-09-08
GARBAGE ROOM |  | 2 | 2025-08-10 | 2025-08-11
R7S1ONAR-AP07GF188 | Paint Finishes and Touchups - Final Coat - AP#07 (GF - Garbage Room) | 2 | 2025-08-10 | 2025-08-11
BALCONIES |  | 152 | 2025-04-10 | 2025-09-06
R7S1ONAR-AP07GF189 | Wetarea Waterproofing - AP#07 (GF - Balconies) | 83 | 2025-04-10 | 2025-07-21
R7S1ONAR-AP07GF190 | Flooring - AP#07 (GF - Front of Lift Shaft) | 6 | 2025-07-17 | 2025-07-24
R7S1ONAR-AP07GF191 | Painting - Surface Prep., Primer & 1st Coat - AP#07 (GF - Front of Lift Shaft) | 6 | 2025-07-21 | 2025-07-28
R7S1ONAR-AP07GF193 | Fixing Handrail - AP#07 (GF - Front of Lift Shaft) | 6 | 2025-08-26 | 2025-09-01
R7S1ONAR-AP07GF194 | Paint for Handrail - AP#07 (GF - Front of Lift Shaft) | 2 | 2025-09-02 | 2025-09-03
R7S1ONAR-AP07GF192 | Painting - Final Coat - AP#07 (GF - Front of Lift Shaft) | 2 | 2025-09-04 | 2025-09-06
MEP WORKS |  | 129 | 2025-03-18 | 2025-08-30
MECHANICAL |  | 129 | 2025-03-18 | 2025-08-27
CHILLED WATER |  | 98 | 2025-03-18 | 2025-06-29
R7S1ONME-AP07GF565 | Installation of BTU Meter with valves - AP#07 (GF - Corridor) | 2 | 2025-03-24 | 2025-03-25
R7S1ONME-AP07GF564 | Installation of CHWP piping (connection between modular cages & modular to apartment) - AP#07 (GF - Corridor) | 13 | 2025-03-23 | 2025-04-12
R7S1ONME-AP07GF563 | Installation of Chilled water hanger and supports - AP#07 (GF - Corridor) | 19 | 2025-03-18 | 2025-04-14
R7S1ONME-AP07GF566 | CHWP piping risers connections - AP#07 (GF - Corridor) | 6 | 2025-04-13 | 2025-04-19
R7S1ONME-AP07GF615 | Installation of CHWP connection for FCU with Valve package in Corridor, Electrical Room & ICT Room - AP#07 (GF) | 22 | 2025-04-05 | 2025-04-29
R7S1ONME-AP07GF567 | Pressure Testing of CHWP piping - AP#07 (GF - Corridor) | 1 | 2025-04-29 | 2025-04-30
R7S1ONME-AP07GF603 | CHWP Insulation - AP#07 (GF - Corridor) | 4 | 2025-04-30 | 2025-05-05
R7S1ONME-AP07GF906 | CHWP Installation/Connections and Insulation (In Front of Lift Shaft) - AP#07 | 4 | 2025-06-25 | 2025-06-29
HVAC DUCTING |  | 110 | 2025-03-23 | 2025-08-26
R7S1ONME-AP07GF568 | Duct Riser Continuation - AP#07 (GF - Corridor) | 9 | 2025-04-17 | 2025-04-27
R7S1ONME-AP07GF569 | A/C drain & Copper pipe connection in ELV room - AP#07 (GF) | 8 | 2025-04-19 | 2025-04-27
R7S1ONME-AP07GF604 | Installation of Duct & Grill in Garbage Room - AP#07 (GF - Garbage Room) | 10 | 2025-04-16 | 2025-04-27
R7S1ONME-AP07GF614 | Installation of FCU's & Duct Connection in Corridor, Electrical Room & ICT Room - AP#07 (GF) | 22 | 2025-04-05 | 2025-04-29
R7S1ONME-AP07GF616 | Installation of Ducting and insulation (connection between modular cages) - AP#07 (GF - Corridor) | 28 | 2025-03-23 | 2025-04-29
R7S1ONME-AP07GF617 | Installation of Grilles in the Corridor - AP#07 (GF - Corridor) | 2 | 2025-08-24 | 2025-08-26
FIRE FIGHTING |  | 117 | 2025-04-07 | 2025-08-27
R7S1ONME-AP07GF570 | Riser Continuity in corridor - AP#07 (GF - Corridor) | 2 | 2025-04-16 | 2025-04-17
R7S1ONME-AP07GF571 | Continuitu of FF pipes & ZC Valves (connection between modular cages & modular to apartment) - AP#07 (GF - Corridor) | 16 | 2025-04-07 | 2025-04-24
R7S1ONME-AP07GF956 | Installation of F.F Pipes, Testing & Final Fixtures (In Front of Lift Shaft) - AP#07 | 3 | 2025-06-30 | 2025-07-02
R7S1ONME-AP07GF605 | Installation of Pipe & sprinkler in Garbage Room - AP#07 (GF - Garbage Room) | 90 | 2025-04-12 | 2025-07-30
R7S1ONME-AP07GF572 | Installation of Sprinklers drops in corridor - AP#07 (GF - Corridor) | 4 | 2025-07-27 | 2025-07-31
R7S1ONME-AP07GF573 | Pressure Test for FF Piping in corridor - AP#07 (GF - Corridor) | 2 | 2025-07-31 | 2025-08-03
R7S1ONME-AP07GF618 | FF Flushing network - AP#07 (GF - Corridor) | 1 | 2025-08-03 | 2025-08-04
R7S1ONME-AP07GF575 | Installation of Alarm check valve, Fire Extinguishers & Blanket - AP#07 (GF - Corridor) | 2 | 2025-08-24 | 2025-08-26
R7S1ONME-AP07GF574 | Installation of Sprinklers in corridor - AP#07 (GF - Corridor) | 3 | 2025-08-24 | 2025-08-27
WATER SUPPLY |  | 70 | 2025-03-18 | 2025-06-14
R7S1ONME-AP07GF606 | Installation of WS Pipe in Garbage Room - AP#07 (GF - Garbage Room) | 6 | 2025-03-18 | 2025-03-25
R7S1ONME-AP07GF607 | Installation of Sanitary Fixtures in Janitor Room - AP#07 (GF - Janitor Room) | 11 | 2025-03-18 | 2025-04-05
R7S1ONME-AP07GF576 | Riser Continuity in Shafts - AP#07 (GF - Corridor) | 4 | 2025-04-17 | 2025-04-21
R7S1ONME-AP07GF577 | WS High Level Pipe continuation & Insulation works - AP#07 (GF - Corridor) | 19 | 2025-04-07 | 2025-04-29
R7S1ONME-AP07GF578 | Installation of Cold, Hot water line & Hot water return - AP#07 (GF - Corridor) | 28 | 2025-03-23 | 2025-04-29
R7S1ONME-AP07GF579 | Water Meter Installation - AP#07 (GF - Corridor) | 4 | 2025-04-29 | 2025-05-04
R7S1ONME-AP07GF580 | Pressure Test for WS - AP#07 (GF - Corridor) | 4 | 2025-06-04 | 2025-06-14
R7S1ONME-AP07GF619 | Insulation for Hot water line & Hot water return - AP#07 (GF - Corridor) | 50 | 2025-04-12 | 2025-06-14
DRAINAGE |  | 65 | 2025-03-18 | 2025-06-14
R7S1ONME-AP07GF582 | Installation of Clean-outs, Floor drain in balcony - AP#07 (GF - Corridor) | 24 | 2025-03-18 | 2025-04-20
R7S1ONME-AP07GF584 | Drainage Riser continuation in Shafts - AP#07 (GF - Corridor) | 2 | 2025-04-19 | 2025-04-20
R7S1ONME-AP07GF583 | Rain Water Riser continuation in Shafts - AP#07 (GF - Corridor) | 4 | 2025-04-26 | 2025-04-29
R7S1ONME-AP07GF585 | Testing for Rain Water Riser - AP#07 (GF - Corridor) | 4 | 2025-06-04 | 2025-06-14
R7S1ONME-AP07GF586 | Testing for Drainage Riser1 - AP#07 (GF - Corridor) | 4 | 2025-06-04 | 2025-06-14
ELECTRICAL |  | 122 | 2025-03-18 | 2025-08-30
POWER & LIGHTING |  | 117 | 2025-03-18 | 2025-08-30
R7S1ONME-AP07GF587 | Contiuation of Cable Trays & apartment branches - AP#07 (GF - Corridor) | 8 | 2025-03-18 | 2025-03-27
R7S1ONME-AP07GF588 | Contiuation of Cable Trunking with Flexible conduits for Lights - AP#07 (GF - Corridor) | 8 | 2025-03-18 | 2025-03-27
R7S1ONME-AP07GF589 | Installation of EMT pipes - AP#07 (GF - Corridor) | 5 | 2025-03-24 | 2025-03-29
R7S1ONME-AP07GF590 | Installation of Busbar, Electrical Meter & Tap-off - AP#07 (GF - Corridor) | 3 | 2025-06-24 | 2025-06-26
R7S1ONME-AP07GF591 | Corridor Wire Pulling - AP#07 (GF - Corridor) | 70 | 2025-03-30 | 2025-06-28
R7S1ONME-AP07GF592 | Electrical Room - Installation of Cable trays, SMDB & Termination - AP#07 (GF - Corridor) | 62 | 2025-04-13 | 2025-06-28
R7S1ONME-AP07GF613 | Termination of Tap-off with Electrical Meter in the apartments - AP#07 (GF - Corridor) | 3 | 2025-06-28 | 2025-06-30
R7S1ONME-AP07GF1136 | Continuation of Cable Tray/Trunking with Flexible conduits for Lights (In Front of Lift Shaft) - AP#07 | 4 | 2025-06-30 | 2025-07-03
R7S1ONME-AP07GF594 | Installation, Termination of Emergeny & Exit Lights with contiuity - AP#07 (GF - Corridor) | 2 | 2025-08-24 | 2025-08-26
R7S1ONME-AP07GF593 | Installation, Termination of Light Fixtures with continuity test - AP#07 (GF - Corridor & Balconies) | 3 | 2025-08-24 | 2025-08-27
R7S1ONME-AP07GF595 | Installation, Termination of PIR sensors with continuity test - AP#07 (GF - Corridor) | 2 | 2025-08-27 | 2025-08-30
LOW CURRENT SYSTEM |  | 122 | 2025-03-18 | 2025-08-28
R7S1ONME-AP07GF596 | Installation of Basket trays for BMS, CCTV, Access Control - AP#07 (GF - Corridor) | 8 | 2025-03-18 | 2025-03-27
R7S1ONME-AP07GF597 | Voice Evacuation cable installation - AP#07 (GF - Corridor) | 5 | 2025-03-22 | 2025-03-27
R7S1ONME-AP07GF620 | CBS System cable installation - AP#07 (GF - Corridor) | 8 | 2025-03-18 | 2025-03-27
R7S1ONME-AP07GF598 | Fire alarm cable installation - AP#07 (GF - Corridor) | 10 | 2025-03-19 | 2025-04-05
R7S1ONME-AP07GF600 | BMS, CCTV & Access control Cable installation - AP#07 (GF - Corridor) | 2 | 2025-07-08 | 2025-07-09
R7S1ONME-AP07GF1316 | Installation of Basket trays for Low Current, Cable Installation (In Front of Lift Shaft) - AP#07 | 4 | 2025-07-08 | 2025-07-12
R7S1ONME-AP07GF601 | Low Current Works including BMS Panel in ICT Room - AP#07 (GF - Corridor) | 10 | 2025-07-03 | 2025-07-14
R7S1ONME-AP07GF609 | Installation & Termination of Access control system for Electrical Room - AP#07 (GF) | 2 | 2025-07-14 | 2025-07-15
R7S1ONME-AP07GF599 | Fibre optic Cable pulling & Termination with OTO (in corridors to ONU) - AP#07 (GF - Corridor) | 2 | 2025-07-15 | 2025-07-16
R7S1ONME-AP07GF612 | Fluke test for CCTV & Fibre Optic Cable - AP#07 (GF - Corridor) (Ceiling 1st Fix) | 2 | 2025-07-17 | 2025-07-19
R7S1ONME-AP07GF608 | Installation & Termination of CCTV Cameras - AP#07 (GF - Corridor) | 2 | 2025-08-24 | 2025-08-26
R7S1ONME-AP07GF611 | Installation & Termination of Wireless Gateway & RF Node in corridors - AP#07 (GF - Corridor) | 2 | 2025-08-24 | 2025-08-26
R7S1ONME-AP07GF602 | Installation & Termination of Fire alarm devices & Speakers - AP#07 (GF - Corridor) | 4 | 2025-08-24 | 2025-08-28
R7S1ONME-AP07GF610 | Installation & Termination of Active Components & UPS installation in ICT Room - AP#07 (GF - Corridor) | 2 | 2025-08-26 | 2025-08-28
FIRST FLOOR |  | 149 | 2025-04-19 | 2025-09-15
ARCH./ CIVIL WORKS |  | 131 | 2025-04-26 | 2025-09-15
CORRIDOR AREA |  | 110 | 2025-05-10 | 2025-09-15
R7S1ONAR-AP07FF246 | Flooring in Corridor - AP#07 (FF - Corridor) | 6 | 2025-05-10 | 2025-05-15
R7S1ONAR-AP07FF247 | Corridor Skirting - AP#07 (FF - Corridor) | 2 | 2025-05-15 | 2025-05-17
R7S1ONAR-AP07FF244 | False Ceiling - 1st Fix - AP#07 (FF - Corridor) | 4 | 2025-05-18 | 2025-05-21
R7S1ONAR-AP07FF245 | Gypsum Wall Cladding (Shafts) - AP#07 (FF - Corridor) | 6 | 2025-07-30 | 2025-08-06
R7S1ONAR-AP07FF248 | Gypsum Wall Cladding (Shafts) -2nd Fix - AP#07 (FF Corridor) | 4 | 2025-08-06 | 2025-08-11
R7S1ONAR-AP07FF252 | Fixing Architrave - AP#07 (FF Corridor) | 2 | 2025-08-11 | 2025-08-13
R7S1ONAR-AP07FF253 | Fixing Aluminium Doors - AP#07 (FF Corridor) | 2 | 2025-08-13 | 2025-08-16
R7S1ONAR-AP07FF249 | False Ceiling - 2nd Fix (Closing the Ceiling) - AP#07 (FF Corridor) | 3 | 2025-08-16 | 2025-08-19
R7S1ONAR-AP07FF250 | Painting - Surface Prep., Primer & 1st Coat for Walls - AP#07 (FF Corridor) | 8 | 2025-08-11 | 2025-08-20
R7S1ONAR-AP07FF285 | Painting - Surface Prep., Primer & 1st Coat for Ceiling - AP#07 (FF Corridor) | 4 | 2025-08-19 | 2025-08-24
R7S1ONAR-AP07FF251 | Painting - Final Coat (Ceiling + Walls) - AP#07 (FF Corridor) | 3 | 2025-09-13 | 2025-09-15
INSIDE BOXES |  | 44 | 2025-05-21 | 2025-06-04
R7S1ONAR-AP07FF254 | Fixing Thresholds (Joining the Room) - AP#07 (FF - inside Boxes) | 4 | 2025-05-21 | 2025-05-26
R7S1ONAR-AP07FF255 | Fixing Wooden Doors - AP#07 (FF - inside Boxes) | 4 | 2025-05-26 | 2025-05-31
R7S1ONAR-AP07FF256 | Fixing Aluminium Doors (Next Floor) - AP#07 (FF - inside Boxes) | 4 | 2025-05-31 | 2025-06-04
IN FRONT OF LIFT SHAFT |  | 93 | 2025-04-26 | 2025-09-10
R7S1ONAR-AP07FF258 | Flooring - AP#07 (FF - Front of Lift Shaft) | 4 | 2025-04-26 | 2025-04-29
R7S1ONAR-AP07FF259 | Skirting & Thresholds - AP#07 (FF - Front of Lift Shaft) | 1 | 2025-04-29 | 2025-04-29
R7S1ONAR-AP07FF260 | Painting - Surface Prep., Primer & 1st Coat - AP#07 (FF - Front of Lift Shaft) | 2 | 2025-04-30 | 2025-05-01
R7S1ONAR-AP07FF257 | False Ceiling - 1st Fix - AP#07 (FF - Front of Lift Shaft) | 2 | 2025-05-03 | 2025-05-04
R7S1ONAR-AP07FF261 | False Ceiling - Final Fix - AP#07 (FF - Front of Lift Shaft) | 1 | 2025-05-29 | 2025-05-29
R7S1ONAR-AP07FF263 | Fixing Handrail - AP#07 (FF - Front of Lift Shaft) | 3 | 2025-09-02 | 2025-09-04
R7S1ONAR-AP07FF264 | Paint for Handrail - AP#07 (FF - Front of Lift Shaft) | 1 | 2025-09-06 | 2025-09-06
R7S1ONAR-AP07FF262 | Painting - 2nd Coat - AP#07 (FF - Front of Lift Shaft) | 1 | 2025-09-07 | 2025-09-07
R7S1ONAR-AP07FF266 | Fixing Wall Guard - AP#07 (FF - Front of Lift Shaft) | 2 | 2025-09-08 | 2025-09-09
R7S1ONAR-AP07FF265 | Fixing Floor Mat - AP#07 (FF - Front of Lift Shaft) | 2 | 2025-09-09 | 2025-09-10
GARBAGE ROOM |  | 19 | 2025-08-02 | 2025-08-09
R7S1ONAR-AP07FF267 | Installation of Dry Walls - First Fix - AP#07 (FF - Garbage Room) | 1 | 2025-08-02 | 2025-08-02
R7S1ONAR-AP07FF268 | Installation of Dry Walls - Final Fix - AP#07 (FF - Garbage Room) | 1 | 2025-08-03 | 2025-08-03
R7S1ONAR-AP07FF269 | Garbage Rooms - Wall Tile Finishes (One Side) - AP#07 (FF - Garbage Room) | 1 | 2025-08-04 | 2025-08-04
R7S1ONAR-AP07FF270 | Paint Works of Dry Walls - First Coat - AP#07 (FF - Garbage Room) | 1 | 2025-08-05 | 2025-08-05
R7S1ONAR-AP07FF271 | Installation of the Garbage Chute Door - AP#07 (FF - Garbage Room) | 1 | 2025-08-06 | 2025-08-06
R7S1ONAR-AP07FF272 | Paint Finishes and Touchups - Final Coat - AP#07 (FF - Garbage Room) | 2 | 2025-08-07 | 2025-08-09
BALCONIES |  | 120 | 2025-05-18 | 2025-09-10
R7S1ONAR-AP07FF273 | Wetarea Waterproofing - AP#07 (FF - Balconies) | 8 | 2025-05-18 | 2025-05-26
R7S1ONAR-AP07FF274 | Flooring - AP#07 (FF - Balconies) | 6 | 2025-05-22 | 2025-05-28
R7S1ONAR-AP07FF275 | Painting - Surface Prep., Primer & 1st Coat - AP#07 (FF - Balconies) | 8 | 2025-05-25 | 2025-06-02
R7S1ONAR-AP07FF277 | Fixing Handrail - AP#07 (FF - Balconies) | 6 | 2025-08-26 | 2025-09-01
R7S1ONAR-AP07FF278 | Paint for Handrail - AP#07 (FF - Balconies) | 4 | 2025-09-02 | 2025-09-06
R7S1ONAR-AP07FF276 | Painting - 2nd Coat - AP#07 (FF - Balconies) | 4 | 2025-09-07 | 2025-09-10
MEP WORKS |  | 112 | 2025-04-19 | 2025-09-01
MECHANICAL |  | 112 | 2025-04-19 | 2025-08-28
CHILLED WATER |  | 70 | 2025-04-26 | 2025-06-29
R7S1ONME-AP07FF300 | Installation of Chilled water hanger and supports - AP#07 (FF Corridor) | 4 | 2025-04-26 | 2025-04-29
R7S1ONME-AP07FF350 | Installation of CHWP connection for FCU with Valve package in Corridor, Electrical Room & ICT Room | 4 | 2025-04-26 | 2025-04-29
R7S1ONME-AP07FF301 | Installation of CHWP piping (connection between modular cages & modular to apartment) - AP#07 -(FF Corridor) | 4 | 2025-04-30 | 2025-05-04
R7S1ONME-AP07FF302 | Installation of BTU Meter with valves - AP#07 (FF Corridor) | 4 | 2025-05-01 | 2025-05-05
R7S1ONME-AP07FF303 | CHWP piping risers connections - AP#07 (FF Corridor) | 3 | 2025-05-12 | 2025-05-15
R7S1ONME-AP07FF304 | Pressure Testing of CHWP piping - AP#07 (FF Corridor) | 1 | 2025-05-15 | 2025-05-17
R7S1ONME-AP07FF339 | CHWP Insulation - AP#07 (FF Corridor) | 4 | 2025-05-17 | 2025-05-21
R7S1ONME-AP07FF616 | CHWP Installation/Connections and Insulation (In Front of Lift Shaft) - AP#07 | 4 | 2025-06-25 | 2025-06-29
HVAC DUCTING |  | 86 | 2025-04-26 | 2025-08-21
R7S1ONME-AP07FF351 | Installation of FCU's & Duct Connection in Corridor, Electrical Room & ICT Room - AP#07 (FF Corridor) | 4 | 2025-04-26 | 2025-04-29
R7S1ONME-AP07FF305 | Duct Riser Continuation - AP#07 (FF Corridor) | 4 | 2025-05-12 | 2025-05-17
R7S1ONME-AP07FF306 | A/C drain & Copper pipe connection in ELV room - AP#07 (FF Corridor) | 2 | 2025-05-17 | 2025-05-19
R7S1ONME-AP07FF352 | Installation of Ducting and insulation (connection between modular cages) - AP#07 (FF Corridor) | 3 | 2025-05-17 | 2025-05-20
R7S1ONME-AP07FF340 | Installation of Duct & Grill in Garbage Room - AP#07 (FF Corridor) | 2 | 2025-05-19 | 2025-05-21
R7S1ONME-AP07FF353 | Installation of Grilles in the Corridor - AP#07 (FF Corridor) | 2 | 2025-08-19 | 2025-08-21
FIRE FIGHTING |  | 112 | 2025-04-19 | 2025-08-28
R7S1ONME-AP07FF307 | Riser Continuity in corridor - AP#07 (FF Corridor) | 4 | 2025-05-12 | 2025-05-17
R7S1ONME-AP07FF308 | Continuation of FF pipes & ZC Valves (connection between modular cages & modular to apartment) - AP#07 (FF Corridor) | 4 | 2025-05-12 | 2025-05-17
R7S1ONME-AP07FF309 | Installation of Sprinklers drops in corridor - AP#07 (FF Corridor) | 4 | 2025-05-22 | 2025-05-26
R7S1ONME-AP07FF310 | Pressure Test for FF Piping in corridor - AP#07 (FF Corridor) | 2 | 2025-05-27 | 2025-05-28
R7S1ONME-AP07FF354 | FF Flushing network - AP#07 (FF Corridor) | 1 | 2025-06-02 | 2025-06-03
R7S1ONME-AP07FF966 | Installation of F.F Pipes, Testing & Final Fixtures (In Front of Lift Shaft) - AP#07 | 3 | 2025-06-30 | 2025-07-02
R7S1ONME-AP07FF341 | Installation of Pipe & sprinkler in Garbage Room - AP#07 (FF Corridor) | 84 | 2025-04-19 | 2025-07-30
R7S1ONME-AP07FF311 | Installation of Sprinklers in corridor - AP#07 (FF Corridor) | 3 | 2025-08-19 | 2025-08-23
R7S1ONME-AP07FF312 | Installation of Alarm check valve, Fire Extinguishers & Blanket (Last Stage of the Building) - AP#07 (FF Corridor) | 2 | 2025-08-26 | 2025-08-28
WATER SUPPLY |  | 42 | 2025-04-26 | 2025-06-18
R7S1ONME-AP07FF342 | Installation of WS Pipe in Garbage Room - AP#07 (FF Corridor) | 2 | 2025-04-26 | 2025-04-27
R7S1ONME-AP07FF343 | Installation of Sanitary Fixtures in Janitor Room - AP#07 (FF Corridor) | 2 | 2025-04-26 | 2025-04-27
R7S1ONME-AP07FF314 | WS High Level Pipe continuation & Insulation works in Corridor - AP#07 (FF Corridor) | 4 | 2025-04-26 | 2025-04-29
R7S1ONME-AP07FF315 | Installation of Cold, Hot water line & Hot water return in corridor - AP#07 (FF Corridor) | 4 | 2025-04-30 | 2025-05-04
R7S1ONME-AP07FF316 | Water Meter Installation in Corridor - AP#07 (FF Corridor) | 4 | 2025-05-05 | 2025-05-08
R7S1ONME-AP07FF313 | Riser Continuity in Shafts - AP#07 (FF Corridor) | 4 | 2025-05-12 | 2025-05-17
R7S1ONME-AP07FF317 | Pressure Test for WS - AP#07 (FF Corridor) | 4 | 2025-06-04 | 2025-06-14
R7S1ONME-AP07FF355 | Insulation for Hot water line & Hot water return in corridor - AP#07 (FF Corridor) | 4 | 2025-06-14 | 2025-06-18
DRAINAGE |  | 37 | 2025-04-26 | 2025-06-14
R7S1ONME-AP07FF318 | Installation of Clean-outs, Floor drain in balcony - AP#07 (FF Corridor) | 4 | 2025-04-26 | 2025-04-29
R7S1ONME-AP07FF319 | Rain Water Riser continuation in Shafts - AP#07 (FF Corridor) | 4 | 2025-05-12 | 2025-05-17
R7S1ONME-AP07FF320 | Drainage Riser continuation in Shafts - AP#07 (FF Corridor) | 4 | 2025-05-12 | 2025-05-17
R7S1ONME-AP07FF321 | Testing for Rain Water Riser - AP#07 (FF Corridor) | 4 | 2025-06-04 | 2025-06-14
R7S1ONME-AP07FF322 | Testing for Drainage Riser - AP#07 (FF Corridor) | 4 | 2025-06-04 | 2025-06-14
ELECTRICAL |  | 101 | 2025-04-26 | 2025-09-01
POWER & LIGHTING |  | 91 | 2025-04-26 | 2025-09-01
R7S1ONME-AP07FF323 | Contiuation of Cable Trays & apartment branches - AP#07 (FF Corridor) | 4 | 2025-04-26 | 2025-04-29
R7S1ONME-AP07FF324 | Contiuation of Cable Trunking with Flexible conduits for Lights - AP#07 (FF Corridor) | 4 | 2025-04-26 | 2025-04-29
R7S1ONME-AP07FF325 | Installation of EMT pipes - AP#07 (FF Corridor) | 5 | 2025-04-26 | 2025-04-30
R7S1ONME-AP07FF326 | Installation of Busbar, Electrical Meter & Tap-off - AP#07 (FF Corridor) | 3 | 2025-06-28 | 2025-06-30
R7S1ONME-AP07FF349 | Termination of Tap-off with Electrical Meter in the apartments - AP#07 (FF Corridor) | 3 | 2025-07-01 | 2025-07-03
R7S1ONME-AP07FF1146 | Continuation of Cable Tray/Trunking with Flexible conduits for Lights (In Front of Lift Shaft) - AP#07 | 4 | 2025-06-30 | 2025-07-03
R7S1ONME-AP07FF327 | Corridor Wire Pulling - AP#07 (FF Corridor) | 6 | 2025-06-29 | 2025-07-05
R7S1ONME-AP07FF328 | Electrical Room - Installation of Cable trays, SMDB & Termination - AP#07 (FF Corridor) | 6 | 2025-07-06 | 2025-07-12
R7S1ONME-AP07FF330 | Installation, Termination of Emergeny & Exit Lights with contiuity - AP#07 (FF Corridor) | 2 | 2025-08-19 | 2025-08-21
R7S1ONME-AP07FF329 | Installation, Termination of Light Fixtures with continuity test - AP#07 (FF - Corridor & Balconies) | 3 | 2025-08-19 | 2025-08-23
R7S1ONME-AP07FF331 | Installation, Termination of PIR sensors with continuity test - AP#07 (FF Corridor) | 2 | 2025-08-30 | 2025-09-01
LOW CURRENT SYSTEM |  | 101 | 2025-04-26 | 2025-08-24
R7S1ONME-AP07FF356 | CBS System cable installation - AP#07 (FF Corridor) | 3 | 2025-04-26 | 2025-04-28
R7S1ONME-AP07FF332 | Installation of Basket trays for BMS, CCTV, Access Control - AP#07 (FF Corridor) | 4 | 2025-04-26 | 2025-04-29
R7S1ONME-AP07FF334 | Fire alarm cable installation - AP#07 (FF Corridor) | 3 | 2025-04-27 | 2025-04-29
R7S1ONME-AP07FF333 | Voice Evacuation cable installation - AP#07 (FF Corridor) | 3 | 2025-04-29 | 2025-05-01
R7S1ONME-AP07FF336 | BMS, CCTV & Access control Cable installation - AP#07 (FF Corridor) | 2 | 2025-07-13 | 2025-07-14
R7S1ONME-AP07FF1326 | Installation of Basket trays for Low Current, Cable Installation (In Front of Lift Shaft) - AP#07 | 4 | 2025-07-13 | 2025-07-16
R7S1ONME-AP07FF337 | Low Current Works including BMS Panel in ICT Room - AP#07 (FF Corridor) | 10 | 2025-07-08 | 2025-07-19
R7S1ONME-AP07FF335 | Fibre optic Cable pulling & Termination with OTO (in corridors to ONU) - AP#07 (FF Corridor) | 2 | 2025-07-20 | 2025-07-21
R7S1ONME-AP07FF348 | Fluke test for CCTV & Fibre Optic Cable - AP#07 (FF Corridor) | 2 | 2025-07-20 | 2025-07-21
R7S1ONME-AP07FF344 | Installation & Termination of CCTV Cameras - AP#07 (FF Corridor) | 2 | 2025-08-19 | 2025-08-21
R7S1ONME-AP07FF345 | Installation & Termination of Access control system for Electrical Room - AP#07 (FF Corridor) | 2 | 2025-08-19 | 2025-08-21
R7S1ONME-AP07FF347 | Installation & Termination of Wireless Gateway & RF Node - AP#07 (FF Corridor) | 2 | 2025-08-19 | 2025-08-21
R7S1ONME-AP07FF338 | Installation & Termination of Fire alarm devices & Speakers - AP#07 (FF Corridor) | 4 | 2025-08-19 | 2025-08-24
R7S1ONME-AP07FF346 | Installation & Termination of Active Components & UPS installation in ICT Room | 2 | 2025-08-21 | 2025-08-24
SECOND FLOOR |  | 124 | 2025-05-05 | 2025-09-17
ARCH./ CIVIL WORKS |  | 121 | 2025-05-05 | 2025-09-17
CORRIDOR AREA |  | 99 | 2025-05-05 | 2025-09-17
R7S1ONAR-AP07SF167 | Flooring in Corridor - AP#07 (SF Corridor) | 6 | 2025-05-05 | 2025-05-12
R7S1ONAR-AP07SF168 | Corridor Skirting - AP#07 (SF Corridor) | 2 | 2025-05-11 | 2025-05-13
R7S1ONAR-AP07SF165 | False Ceiling - 1st Fix - AP#07 (SF Corridor) | 4 | 2025-05-13 | 2025-05-18
R7S1ONAR-AP07SF166 | Gypsum Wall Cladding (Shafts) - AP#07 (SF Corridor) | 6 | 2025-08-14 | 2025-08-21
R7S1ONAR-AP07SF169 | Gypsum Wall Cladding (Shafts) -2nd Fix - AP#07 (SF Corridor) | 4 | 2025-08-21 | 2025-08-26
R7S1ONAR-AP07SF173 | Fixing Architrave - AP#07 (SF Corridor) | 2 | 2025-08-26 | 2025-08-28
R7S1ONAR-AP07SF174 | Fixing Aluminium Doors - AP#07 (SF Corridor) | 2 | 2025-08-28 | 2025-08-31
R7S1ONAR-AP07SF170 | False Ceiling - 2nd Fix (Closing the Ceiling) - AP#07 (SF Corridor) | 3 | 2025-08-31 | 2025-09-03
R7S1ONAR-AP07SF171 | Painting - Surface Prep., Primer & 1st Coat - AP#07 (SF Corridor) | 8 | 2025-08-26 | 2025-09-04
R7S1ONAR-AP07SF195 | Painting - Surface Prep., Primer & 1st Coat - AP#07 (SF Corridor) | 4 | 2025-09-03 | 2025-09-08
R7S1ONAR-AP07SF172 | Painting - Final Coat (Ceiling + Walls) - AP#07 (SF Corridor) | 3 | 2025-09-15 | 2025-09-17
INSIDE BOXES |  | 36 | 2025-05-21 | 2025-06-04
R7S1ONAR-AP07SF175 | Fixing Thresholds (Joining the Room) - AP#07 (SF - inside Boxes) | 4 | 2025-05-21 | 2025-05-26
R7S1ONAR-AP07SF176 | Fixing Wooden Doors - AP#07 (SF - inside Boxes) | 4 | 2025-05-26 | 2025-05-31
R7S1ONAR-AP07SF177 | Fixing Aluminium Doors (Next Floor) - AP#07 (SF - inside Boxes) | 4 | 2025-05-31 | 2025-06-04
IN FRONT OF LIFT SHAFT |  | 121 | 2025-05-21 | 2025-09-13
R7S1ONAR-AP07SF178 | False Ceiling - 1st Fix - AP#07 (SF - Front of Lift Shaft) | 3 | 2025-05-21 | 2025-05-25
R7S1ONAR-AP07SF179 | Flooring - AP#07 (SF - Front of Lift Shaft) | 4 | 2025-05-25 | 2025-05-29
R7S1ONAR-AP07SF180 | Skirting & Thresholds - AP#07 (SF - Front of Lift Shaft) | 2 | 2025-05-29 | 2025-06-01
R7S1ONAR-AP07SF181 | Painting - Surface Prep., Primer & 1st Coat - AP#07 (SF - Front of Lift Shaft) | 2 | 2025-06-01 | 2025-06-03
R7S1ONAR-AP07SF182 | False Ceiling - Final Fix - AP#07 (SF - Front of Lift Shaft) | 1 | 2025-06-03 | 2025-06-04
R7S1ONAR-AP07SF184 | Fixing Handrail - AP#07 (SF - Front of Lift Shaft) | 3 | 2025-09-06 | 2025-09-08
R7S1ONAR-AP07SF185 | Paint for Handrail - AP#07 (SF - Front of Lift Shaft) | 1 | 2025-09-09 | 2025-09-09
R7S1ONAR-AP07SF183 | Painting - 2nd Coat - AP#07 (SF - Front of Lift Shaft) | 1 | 2025-09-10 | 2025-09-10
R7S1ONAR-AP07SF186 | Fixing Floor Mat - AP#07 (SF - Front of Lift Shaft) | 2 | 2025-09-11 | 2025-09-13
R7S1ONAR-AP07SF187 | Fixing Wall Guard - AP#07 (SF - Front of Lift Shaft) | 2 | 2025-09-11 | 2025-09-13
GARBAGE ROOM |  | 32 | 2025-07-19 | 2025-09-08
R7S1ONAR-AP07SF194 | Installation of Garbage Chute Full System from GF to 2nd Floor - AP#07 (SF - Garbage Room) | 10 | 2025-07-19 | 2025-07-29
R7S1ONAR-AP07SF188 | Installation of Dry Walls - First Fix - AP#07 (SF - Garbage Room) | 1 | 2025-07-30 | 2025-07-30
R7S1ONAR-AP07SF189 | Installation of Dry Walls - Final Fix - AP#07 (SF - Garbage Room) | 1 | 2025-07-31 | 2025-07-31
R7S1ONAR-AP07SF190 | Garbage Rooms - Wall Tile Finishes (One Side) - AP#07 (SF - Garbage Room) | 1 | 2025-08-02 | 2025-08-02
R7S1ONAR-AP07SF191 | Paint Works of Dry Walls - First Coat - AP#07 (SF - Garbage Room) | 1 | 2025-08-03 | 2025-08-03
R7S1ONAR-AP07SF192 | Installation of the Garbage Chute Door - AP#07 (SF - Garbage Room) | 1 | 2025-08-04 | 2025-08-04
R7S1ONAR-AP07SF193 | Paint Finishes and Touchups - Final Coat - AP#07 (SF - Garbage Room) | 2 | 2025-09-06 | 2025-09-08
BALCONIES |  | 109 | 2025-05-12 | 2025-09-14
R7S1ONAR-AP07FF279 | Wetarea Waterproofing - AP#07 (SF - Balconies) | 8 | 2025-05-12 | 2025-05-21
R7S1ONAR-AP07FF280 | Flooring - AP#07 (SF - Balconies) | 6 | 2025-05-17 | 2025-05-24
R7S1ONAR-AP07FF281 | Painting - Surface Prep., Primer & 1st Coat - AP#07 (SF - Balconies) | 8 | 2025-05-19 | 2025-05-28
R7S1ONAR-AP07FF283 | Fixing Handrail - AP#07 (SF - Balconies) | 6 | 2025-08-30 | 2025-09-04
R7S1ONAR-AP07FF284 | Paint for Handrail - AP#07 (SF - Balconies) | 4 | 2025-09-06 | 2025-09-09
R7S1ONAR-AP07FF282 | Painting - 2nd Coat - AP#07 (SF - Balconies) | 4 | 2025-09-10 | 2025-09-14
MEP WORKS |  | 99 | 2025-05-21 | 2025-09-09
MECHANICAL |  | 99 | 2025-05-21 | 2025-09-07
CHILLED WATER |  | 23 | 2025-05-21 | 2025-07-03
R7S1ONME-AP07SF276 | Installation of Chilled water hanger and supports - AP#07 (SF Corridor) | 4 | 2025-05-21 | 2025-05-26
R7S1ONME-AP07SF326 | Installation of CHWP connection for FCU with Valve package in Corridor, Electrical Room & ICT Room | 4 | 2025-05-21 | 2025-05-26
R7S1ONME-AP07SF277 | Installation of CHWP piping (connection between modular cages & modular to apartment) - AP#07 (SF Corridor) | 4 | 2025-05-26 | 2025-05-31
R7S1ONME-AP07SF278 | Installation of BTU Meter with valves - AP#07 (SF Corridor) | 4 | 2025-05-27 | 2025-06-01
R7S1ONME-AP07SF279 | CHWP piping risers connections - AP#07 (SF Corridor) | 3 | 2025-06-01 | 2025-06-04
R7S1ONME-AP07SF280 | Pressure Testing of CHWP piping - AP#07 (SF Corridor) | 1 | 2025-06-04 | 2025-06-10
R7S1ONME-AP07SF315 | CHWP Insulation - AP#07 (SF Corridor) | 4 | 2025-06-10 | 2025-06-15
R7S1ONME-AP07SF916 | CHWP Installation/Connections and Insulation (In Front of Lift Shaft) - AP#07 | 4 | 2025-06-30 | 2025-07-03
HVAC DUCTING |  | 82 | 2025-05-21 | 2025-09-06
R7S1ONME-AP07SF281 | Duct Riser Continuation - AP#07 (SF Corridor) | 4 | 2025-05-21 | 2025-05-26
R7S1ONME-AP07SF327 | Installation of FCU's & Duct Connection in Corridor, Electrical Room & ICT Room - AP#07 (SF Corridor) | 4 | 2025-05-21 | 2025-05-26
R7S1ONME-AP07SF282 | A/C drain & Copper pipe connection in ELV room - AP#07 (SF Corridor) | 2 | 2025-05-26 | 2025-05-28
R7S1ONME-AP07SF328 | Installation of Ducting and insulation (connection between modular cages) - AP#07 (SF Corridor) | 3 | 2025-05-26 | 2025-05-29
R7S1ONME-AP07SF316 | Installation of Duct & Grill in Garbage Room - AP#07 (SF Corridor) | 2 | 2025-09-03 | 2025-09-06
R7S1ONME-AP07SF329 | Installation of Grilles in the Corridor - AP#07 (SF Corridor) | 2 | 2025-09-03 | 2025-09-06
FIRE FIGHTING |  | 99 | 2025-05-21 | 2025-09-07
R7S1ONME-AP07SF283 | Riser Continuity Succ - Closing of Gysum Boards on shaft - AP#07 (SF Corridor) | 4 | 2025-05-21 | 2025-05-26
R7S1ONME-AP07SF284 | FF Contiuation on High Level with Valves - AP#07 (SF Corridor) | 4 | 2025-05-21 | 2025-05-26
R7S1ONME-AP07SF285 | Installation of Sprinklers drops - AP#07 (SF Corridor) | 4 | 2025-05-26 | 2025-05-31
R7S1ONME-AP07SF286 | Pressure Test for FF Piping - AP#07 (SF Corridor) | 2 | 2025-05-31 | 2025-06-02
R7S1ONME-AP07SF976 | Installation of F.F Pipes, Testing & Final Fixtures (In Front of Lift Shaft) - AP#07 | 3 | 2025-07-05 | 2025-07-07
R7S1ONME-AP07SF317 | Installation of Pipe & sprinkler in Garbage Room - AP#07 (SF Corridor) | 2 | 2025-09-03 | 2025-09-06
R7S1ONME-AP07SF287 | Installation of Sprinklers - AP#07 (SF Corridor) | 3 | 2025-09-03 | 2025-09-07
R7S1ONME-AP07SF288 | Installation of Fire Extinguishers - AP#07 (SF Corridor) | 3 | 2025-09-03 | 2025-09-07
WATER SUPPLY |  | 35 | 2025-05-21 | 2025-06-23
R7S1ONME-AP07SF318 | Installation of WS Pipe in Garbage Room - AP#07 (SF Corridor) | 2 | 2025-05-21 | 2025-05-24
R7S1ONME-AP07SF319 | Installation of Sanitary Fixtures in Janitor Room - AP#07 (SF Corridor) | 2 | 2025-05-21 | 2025-05-24
R7S1ONME-AP07SF289 | Riser Continuity - AP#07 (SF Corridor) | 4 | 2025-05-21 | 2025-05-26
R7S1ONME-AP07SF290 | WS High Level Pipe continuation & Insulation works - AP#07 (SF Corridor) | 4 | 2025-05-21 | 2025-05-26
R7S1ONME-AP07SF291 | Instalation of Hot water line in corridor - AP#07 (SF Corridor) | 4 | 2025-05-26 | 2025-05-31
R7S1ONME-AP07SF292 | Water Meter Installation - AP#07 (SF Corridor) | 4 | 2025-05-31 | 2025-06-04
R7S1ONME-AP07SF293 | Pressure Test for WS - AP#07 (SF Corridor) | 4 | 2025-06-14 | 2025-06-18
R7S1ONME-AP07FF357 | Insulation for Hot water line & Hot water return in corridor - AP#07 (SF Corridor) | 4 | 2025-06-18 | 2025-06-23
DRAINAGE |  | 20 | 2025-05-21 | 2025-06-14
R7S1ONME-AP07SF294 | Installation of Clean-outs - AP#07 (SF Corridor) | 4 | 2025-05-21 | 2025-05-26
R7S1ONME-AP07SF295 | Rain Water Riser continuation - AP#07 (SF Corridor) | 4 | 2025-05-21 | 2025-05-26
R7S1ONME-AP07SF296 | Drainage Riser continuation - AP#07 (SF Corridor) | 4 | 2025-05-21 | 2025-05-26
R7S1ONME-AP07SF297 | Testing for Rain Water Riser - AP#07 (SF Corridor) | 4 | 2025-06-04 | 2025-06-14
R7S1ONME-AP07SF298 | Testing for Drainage Riser - AP#07 (SF Corridor) | 4 | 2025-06-04 | 2025-06-14
ELECTRICAL |  | 98 | 2025-05-21 | 2025-09-09
POWER & LIGHTING |  | 98 | 2025-05-21 | 2025-09-09
R7S1ONME-AP07SF299 | Contiuation of Cable Trays & apartment branches - AP#07 (SF Corridor) | 4 | 2025-05-21 | 2025-05-26
R7S1ONME-AP07SF300 | Contiuation of Cable Trunking with Flexible conduits for Lights - AP#07 (SF Corridor) | 4 | 2025-05-21 | 2025-05-26
R7S1ONME-AP07SF301 | Installation of EMT pipes - AP#07 (SF Corridor) | 5 | 2025-05-21 | 2025-05-27
R7S1ONME-AP07SF302 | Installation of Busbar, Electrical Meter & Tap-off in Corridor - AP#07 (SF Corridor) | 3 | 2025-07-01 | 2025-07-03
R7S1ONME-AP07SF325 | Termination of Tap-off with Electrical Meter in the apartments - AP#07 (SF Corridor) | 3 | 2025-07-05 | 2025-07-07
R7S1ONME-AP07SF303 | Corridor Wire Pulling - AP#07 (SF Corridor) | 6 | 2025-07-02 | 2025-07-08
R7S1ONME-AP07SF1156 | Continuation of Cable Tray/Trunking with Flexible conduits for Lights (In Front of Lift Shaft) - AP#07 | 4 | 2025-07-05 | 2025-07-08
R7S1ONME-AP07SF304 | Electrical Room - Installation of Cable trays, SMDB & Termination - AP#07 (SF Corridor) | 6 | 2025-08-06 | 2025-08-13
R7S1ONME-AP07SF306 | Installation, Termination of Emergeny & Exit Lights with contiuity - AP#07 (SF Corridor) | 2 | 2025-09-03 | 2025-09-06
R7S1ONME-AP07SF305 | Installation, Termination of Light Fixtures with continuity test - AP#07 (SF - Corridor & Balconies) | 3 | 2025-09-03 | 2025-09-07
R7S1ONME-AP07SF307 | Installation, Termination of PIR sensors with continuity test - AP#07 (SF Corridor) | 2 | 2025-09-07 | 2025-09-09
LOW CURRENT SYSTEM |  | 95 | 2025-05-21 | 2025-09-08
R7S1ONME-AP07SF330 | CBS System cable installation - AP#07 (SF Corridor) | 3 | 2025-05-21 | 2025-05-25
R7S1ONME-AP07SF308 | Installation of Basket trays for BMS, CCTV, Access Control - AP#07 (SF Corridor) | 4 | 2025-05-21 | 2025-05-26
R7S1ONME-AP07SF310 | Fire alarm cable installation - AP#07 (SF Corridor) | 3 | 2025-05-22 | 2025-05-26
R7S1ONME-AP07SF309 | Voice Evacuation cable installation - AP#07 (SF Corridor) | 3 | 2025-05-25 | 2025-05-28
R7S1ONME-AP07SF312 | BMS, CCTV & Access control Cable installation - AP#07 (SF Corridor) | 2 | 2025-07-17 | 2025-07-19
R7S1ONME-AP07SF1336 | Installation of Basket trays for Low Current, Cable Installation (In Front of Lift Shaft) - AP#07 | 4 | 2025-07-17 | 2025-07-21
R7S1ONME-AP07SF313 | Low Current Works including BMS Panel in ICT Room - AP#07 (SF Corridor) | 10 | 2025-07-31 | 2025-08-12
R7S1ONME-AP07SF324 | Fluke test for CCTV & Fibre Optic Cable - AP#07 (SF Corridor) | 2 | 2025-08-10 | 2025-08-12
R7S1ONME-AP07SF311 | Fibre optic Cable pulling & Termination with OTO (in corridors to ONU) - AP#07 (SF Corridor) | 2 | 2025-08-12 | 2025-08-14
R7S1ONME-AP07SF320 | Installation & Termination of CCTV Cameras - AP#07 (SF Corridor) | 2 | 2025-09-03 | 2025-09-06
R7S1ONME-AP07SF321 | Installation & Termination of Access control system for Electrical Room - AP#07 (SF Corridor) | 2 | 2025-09-03 | 2025-09-06
R7S1ONME-AP07SF323 | Installation & Termination of Wireless Gateway & RF Node in corridors - AP#07 (SF Corridor) | 2 | 2025-09-03 | 2025-09-06
R7S1ONME-AP07SF314 | Installation & Termination of Fire alarm devices & Speakers - AP#07 (SF Corridor) | 4 | 2025-09-03 | 2025-09-08
R7S1ONME-AP07SF322 | Installation & Termination of Active Components & UPS installation in ICT Room - AP#07 (SF Corridor) | 2 | 2025-09-06 | 2025-09-08
ROOF WORKS |  | 110 | 2025-06-04 | 2025-09-16
ARCH./ CIVIL WORKS |  | 93 | 2025-06-04 | 2025-09-16
R7S1ONAR-AP07RF43 | Roof Box Stiching (Concrete Works) - AP#07 (Roof) | 6 | 2025-06-04 | 2025-06-16
R7S1ONME-AP07RF296 | Installation of Roof Drains - AP#07 (Roof) | 2 | 2025-06-14 | 2025-06-16
R7S1ONAR-AP07RF44 | Roof Waterproofing Works with testing - AP#07 (Roof) | 20 | 2025-07-05 | 2025-07-28
R7S1ONAR-AP07RF45 | Laying of Gravel - AP#07 (Roof) | 2 | 2025-07-28 | 2025-07-30
R7S1ONAR-AP07RF46 | Surface Preparation & Primer for Parapets - AP#07 (Roof) | 6 | 2025-08-17 | 2025-08-24
R7S1ONAR-AP07RF47 | 1st Coat Paint for Parapets - AP#07 (Roof) | 2 | 2025-08-24 | 2025-08-26
R7S1ONAR-AP07RF48 | 2nd Coat Paint for Parapets - AP#07 (Roof) | 2 | 2025-08-26 | 2025-08-28
R7S1ONAR-AP07RF50 | Fixing Fall Arrest System - AP#07 (Roof) | 2 | 2025-08-26 | 2025-08-28
R7S1ONAR-AP07RF49 | Crossover Bridges Installation & application of Sealant on MEP penetrations - AP#07 (Roof) | 12 | 2025-09-02 | 2025-09-16
MECHANICAL |  | 73 | 2025-07-30 | 2025-08-24
HVAC |  | 41 | 2025-07-30 | 2025-08-17
R7S1ONME-AP07RF260 | Modular Installation - AP#07 (Roof) | 6 | 2025-07-30 | 2025-08-06
R7S1ONME-AP07RF261 | Continuation of Roof duct works/FAHU Connections - AP#07 (Roof) | 5 | 2025-08-03 | 2025-08-09
R7S1ONME-AP07RF263 | Insulations for ducts - AP#07 (Roof) | 5 | 2025-08-04 | 2025-08-10
R7S1ONME-AP07RF265 | Installation of FAHU - AP#07 (Roof) | 2 | 2025-08-09 | 2025-08-11
R7S1ONME-AP07RF270 | Installation of Outdoor VRF/DX Units - AP#07 (Roof) | 2 | 2025-08-10 | 2025-08-12
R7S1ONME-AP07RF271 | Installation & Insulation of the Condensation Drain - AP#07 (Roof) | 1 | 2025-08-11 | 2025-08-12
R7S1ONME-AP07RF273 | Installation of Ventilation Fans - AP#07 (Roof) | 3 | 2025-08-09 | 2025-08-12
R7S1ONME-AP07RF268 | Chilled Water System Continuation and Connections with Valve package of FAHU - AP#07 (Roof) | 4 | 2025-08-09 | 2025-08-13
R7S1ONME-AP07RF275 | Installation of Louvers - AP#07 (Roof) | 2 | 2025-08-12 | 2025-08-14
R7S1ONME-AP07RF278 | Installation & Testing of Copper Pipes - AP#07 (Roof) | 2 | 2025-08-12 | 2025-08-14
R7S1ONME-AP07RF279 | Miscellaneous Works for Mechanical Connections (Fire & Volume Dampers etc.) - AP#07 (Roof) | 2 | 2025-08-14 | 2025-08-17
WATERSUPPLY & DRAINAGE |  | 34 | 2025-08-06 | 2025-08-23
R7S1ONME-AP07RF259 | Testing for the Rain Water Risers - AP#07 (Roof) | 2 | 2025-08-09 | 2025-08-11
R7S1ONME-AP07RF262 | Installation & Continuation of Water supply pipes (connection between modular cages & modular to Shaft Riser) - AP#07 | 4 | 2025-08-06 | 2025-08-11
R7S1ONME-AP07RF266 | Installation of Air Vent & Pressure Guage with Valves at Roof - AP#07 (Roof) | 4 | 2025-08-09 | 2025-08-13
R7S1ONME-AP07RF267 | Vertical Continuation of Vent Pipes To The Roof (Drainage) - AP#07 (Roof) | 4 | 2025-08-10 | 2025-08-14
R7S1ONME-AP07RF269 | Installation of Rain Water outlet - AP#07 (Roof) | 3 | 2025-08-11 | 2025-08-14
R7S1ONME-AP07RF264 | Installation of Air Vent with Valve for Water Supply - AP#07 (Roof) | 4 | 2025-08-11 | 2025-08-16
R7S1ONME-AP07RF272 | Testing of Water Supply Pipes - AP#07 (Roof) | 2 | 2025-08-16 | 2025-08-18
R7S1ONME-AP07RF274 | Insulation of Roof Water Line - AP#07 (Roof) | 2 | 2025-08-17 | 2025-08-19
R7S1ONME-AP07RF276 | Testing for the Drainage Pipes Risers - AP#07 (Roof) | 2 | 2025-08-19 | 2025-08-21
R7S1ONME-AP07RF277 | Installation of Vent Cowl - AP#07 (Roof) | 1 | 2025-08-21 | 2025-08-23
SOLAR HEATER |  | 59 | 2025-08-11 | 2025-08-24
R7S1ONME-AP07RF291 | Installation of Solar water pumps and circulation pumps with valves(For Water Only) - AP#07 (Roof) | 2 | 2025-08-12 | 2025-08-14
R7S1ONME-AP07RF289 | Installation of Structure and Solar Panels (For Water Only) - AP#07 (Roof) | 5 | 2025-08-11 | 2025-08-17
R7S1ONME-AP07RF290 | Installation of Solar Calorifier Tank & Air cooler (For Water Only) - AP#07 (Roof) | 5 | 2025-08-12 | 2025-08-18
R7S1ONME-AP07RF292 | Installation of Solar Pipes Primary Loop - AP#07 (Roof) | 5 | 2025-08-12 | 2025-08-18
R7S1ONME-AP07RF293 | Testing of Solar Pipes Primary Loop - AP#07 (Roof) | 1 | 2025-08-18 | 2025-08-19
R7S1ONME-AP07RF294 | Insulation of Solar Pipes Primary Loop - AP#07 (Roof) | 1 | 2025-08-18 | 2025-08-19
R7S1ONME-AP07RF295 | Aluminum Cladding of Solar Pipes Primary Loop - AP#07 (Roof) | 4 | 2025-08-19 | 2025-08-24
ELECTRICAL |  | 66 | 2025-08-06 | 2025-09-10
POWER & LOW CURRENT |  | 66 | 2025-08-06 | 2025-09-10
R7S1ONME-AP07RF280 | Installation of Cables for Fire Alarm system - AP#07 (Roof) | 3 | 2025-08-06 | 2025-08-10
R7S1ONME-AP07RF281 | Installation of Cables for BMS - AP#07 (Roof) | 3 | 2025-08-06 | 2025-08-10
R7S1ONME-AP07RF282 | Installation of Fire Alarm Devices - AP#07 (Roof) | 3 | 2025-08-06 | 2025-08-10
R7S1ONME-AP07RF284 | Installation of Roof Light Fixtures - AP#07 (Roof) | 3 | 2025-08-06 | 2025-08-10
R7S1ONME-AP07RF283 | Installation of BMS Devices - AP#07 (Roof) | 4 | 2025-08-07 | 2025-08-12
R7S1ONME-AP07RF256 | Installation of Electrical Containments for BMS - AP#07 (Roof) | 7 | 2025-08-06 | 2025-08-14
R7S1ONME-AP07RF286 | Termination for BMS System - AP#07 (Roof) | 1 | 2025-08-14 | 2025-08-16
R7S1ONME-AP07RF298 | Termination of Primary & Secondary pump for Solar system - AP#07 (Roof) | 1 | 2025-08-14 | 2025-08-16
R7S1ONME-AP07RF297 | Installation & Termination of Solar System Panel - AP#07 (Roof) | 3 | 2025-08-24 | 2025-08-27
R7S1ONME-AP07RF254 | Lightening Protection & Earthing System - AP#07 (Roof) | 7 | 2025-08-20 | 2025-08-28
R7S1ONME-AP07RF255 | Installation of Isolators and Machine Connections - AP#07 (Roof) | 4 | 2025-08-28 | 2025-09-02
R7S1ONME-AP07RF257 | Installation of Fire Alarm Containment for FAHU, Fans - AP#07 (Roof) | 4 | 2025-08-28 | 2025-09-02
R7S1ONME-AP07RF287 | Termination for Fire Alarm Device - AP#07 (Roof) | 1 | 2025-09-02 | 2025-09-03
R7S1ONME-AP07RF258 | Installation of LV Power Cables for Roof Equipment - AP#07 (Roof) | 5 | 2025-09-02 | 2025-09-08
R7S1ONME-AP07RF285 | Termination for LV Cables - AP#07 (Roof) | 1 | 2025-09-08 | 2025-09-09
R7S1ONME-AP07RF288 | Megger Test for the Power Cables - AP#07 (Roof) | 1 | 2025-09-09 | 2025-09-10
STAIR CASE |  | 102 | 2025-06-16 | 2025-08-06
CIVIL WORKS |  | 102 | 2025-06-16 | 2025-08-02
STAIR CASE (MAIN WITH LIFT) |  | 101 | 2025-06-16 | 2025-07-14
R7S1ONST-AP07RG386 | Stair Flooring (Roof to GF) - AP#07 (Main Stair) | 7 | 2025-06-16 | 2025-06-24
R7S1ONST-AP07RG387 | Stair Hand Rails (Roof to GF) - AP#07 (Main Stair) | 6 | 2025-06-24 | 2025-07-01
R7S1ONST-AP07RG388 | Stair Paint - Primer & 1st Coat (Roof to GF)- AP#07 (Main Stair) | 7 | 2025-07-01 | 2025-07-09
R7S1ONST-AP07RG389 | Stair Paint - Final Coat (Roof to GF)- AP#07 (Main Stair) | 4 | 2025-07-09 | 2025-07-14
STAIR CASE (LEFT SIDE) |  | 89 | 2025-06-24 | 2025-07-20
R7S1ONST-AP07RG396 | Stair Flooring (Roof to GF) - AP#07 Left Side Stair | 7 | 2025-06-24 | 2025-07-02
R7S1ONST-AP07RG397 | Stair Hand Rails (Roof to GF) - AP#07 Left Side Stair | 6 | 2025-07-02 | 2025-07-09
R7S1ONST-AP07RG398 | Stair Paint - Primer & 1st Coat (Roof to GF) - AP#07 Left Side Stair | 6 | 2025-07-09 | 2025-07-16
R7S1ONST-AP07RG399 | Stair Paint - Final Coat (Roof to GF) - AP#07 Left Side Stair | 3 | 2025-07-16 | 2025-07-20
STAIR CASE (RIGHT SIDE) |  | 83 | 2025-07-02 | 2025-08-02
R7S1ONST-AP07RG400 | Stair Flooring (Roof to GF) - AP#07 Right Side Stair | 8 | 2025-07-02 | 2025-07-12
R7S1ONST-AP07RG401 | Stair Hand Rails (Roof to GF) - AP#07 Right Side Stair | 7 | 2025-07-12 | 2025-07-20
R7S1ONST-AP07RG402 | Stair Paint - Primer & 1st Coat (Roof to GF) - AP#07 Right Side Stair | 7 | 2025-07-20 | 2025-07-28
R7S1ONST-AP07RG403 | Stair Paint - Final Coat (Roof to GF) - AP#07 Right Side Stair | 4 | 2025-07-28 | 2025-08-02
MEP WORKS |  | 79 | 2025-06-29 | 2025-08-06
STAIR CASE (MAIN WITH LIFT) |  | 66 | 2025-06-29 | 2025-07-19
R7S1ONST-AP07RG385 | Main Staircase Wire Pulling - AP#07 (Main Stair) | 3 | 2025-06-29 | 2025-07-01
R7S1ONST-AP07RG404 | Final fix - Main Staircase Lights Fixtures & Motion Sensor - AP#07 (Main Stair) | 2 | 2025-07-14 | 2025-07-16
R7S1ONST-AP07RG405 | Final fix - Main Staircase Emergency Lights Fixtures - AP#07 (Main Stair) | 2 | 2025-07-16 | 2025-07-19
STAIR CASE (LEFT SIDE) |  | 70 | 2025-07-02 | 2025-07-24
R7S1ONST-AP07RG390 | Left Staircase Wire Pulling - AP#07 (Main Stair) | 3 | 2025-07-02 | 2025-07-05
R7S1ONST-AP07RG392 | Final fix - Left Staircase Lights Fixtures & Motion Sensor - AP#07 (Main Stair) | 2 | 2025-07-20 | 2025-07-22
R7S1ONST-AP07RG394 | Final fix - Left Staircase Emergency Lights Fixtures - AP#07 (Main Stair) | 2 | 2025-07-22 | 2025-07-24
STAIR CASE (RIGHT SIDE) |  | 73 | 2025-07-06 | 2025-08-06
R7S1ONST-AP07RG391 | Right Staircase Wire Pulling - AP#07 (Main Stair) | 3 | 2025-07-06 | 2025-07-08
R7S1ONST-AP07RG393 | Final fix - Right Staircase Lights Fixtures & Motion Sensor - AP#07 (Main Stair) | 2 | 2025-08-02 | 2025-08-04
R7S1ONST-AP07RG395 | Final fix - Right Staircase Emergency Lights Fixtures - AP#07 (Main Stair) | 2 | 2025-08-04 | 2025-08-06
ELEVATOR WORKS |  | 45 | 2025-08-16 | 2025-09-09
R7S1ONEL-AP07GR625 | Installation of Rails - AP#07 (Elevator Works) | 6 | 2025-08-16 | 2025-08-21
R7S1ONEL-AP07GR626 | Assembly of Cabin - AP#07 (Elevator Works) | 4 | 2025-08-23 | 2025-08-26
R7S1ONEL-AP07GR627 | Installation of Motor - AP#07 (Elevator Works) | 4 | 2025-08-27 | 2025-08-31
R7S1ONEL-AP07GR628 | Installation of Main Cables - AP#07 (Elevator Works) | 4 | 2025-09-01 | 2025-09-04
R7S1ONEL-AP07GR629 | Installation of Doors, Indicator, Push Button - AP#07 (Elevator Works) | 2 | 2025-09-06 | 2025-09-07
R7S1ONEL-AP07GR630 | Interior Finishes - AP#07 (Elevator Works) | 2 | 2025-09-08 | 2025-09-09
EXTERNAL ELEVATIONS |  | 64 | 2025-07-30 | 2025-09-18
ARCH./ CIVIL WORKS |  | 64 | 2025-07-30 | 2025-09-18
R7S1ONEE-AP07GR517 | External Selant Works - For Boxes - AP#07 (External Elevations) | 15 | 2025-07-30 | 2025-08-17
R7S1ONEE-AP07GR518 | Final Finishes & Touchups - AP#07 (External Elevations) | 20 | 2025-08-17 | 2025-09-09
R7S1ONME-AP07GF581 | Installation of rain water outlet - External façade - AP#07 (External Elevations) | 2 | 2025-09-09 | 2025-09-11
R7S1ONEE-AP07GR520 | Installation of External Signages - AP#07 (External Elevations) | 4 | 2025-09-11 | 2025-09-16
R7S1ONEE-AP07GR519 | Fixing Cage Ladder - AP#07 (External Elevations) | 2 | 2025-09-16 | 2025-09-18
EXTERNAL - CIVIL WORKS |  | 33 | 2025-07-22 | 2025-08-19
DRAINAGE |  | 13 | 2025-07-22 | 2025-07-31
R7S1ONECW-AP07-343 | Excavation Works & Sand Bedding - AP#07 (External Drainage) | 3 | 2025-07-22 | 2025-07-24
R7S1ONECW-AP07-344 | Drainage Manholes - AP#07 | 6 | 2025-07-22 | 2025-07-28
R7S1ONECW-AP07-345 | Drainage Backfilling - AP#07 | 2 | 2025-07-30 | 2025-07-31
WATERSUPPLY |  | 11 | 2025-07-26 | 2025-08-19
R7S1ONECW-AP07-346 | Excavation Works & Sand Bedding - Watersupply - AP#07 (External Watersupply Civil) | 3 | 2025-07-26 | 2025-07-28
R7S1ONECW-AP07-347 | Watersupply Manholes - AP#07 | 6 | 2025-07-29 | 2025-08-04
R7S1ONECW-AP07-348 | Watersupply Backfilling - AP#07 | 2 | 2025-08-18 | 2025-08-19
CHILLED WATER |  | 8 | 2025-07-29 | 2025-08-10
R7S1ONECW-AP07-352 | Excavation Works & Sand Bedding - AP#07 (External Chilled Water Civil) | 3 | 2025-07-29 | 2025-07-31
R7S1ONECW-AP07-353 | Chilled Water Manholes - AP#07 | 6 | 2025-08-02 | 2025-08-07
R7S1ONECW-AP07-354 | Chilled Water Backfilling - AP#07 | 2 | 2025-08-09 | 2025-08-10
FIRE FIGHTING |  | 16 | 2025-08-02 | 2025-08-19
R7S1ONECW-AP07-349 | Excavation Works & Sand Bedding - AP#07 (External Chilled Water Civil) | 3 | 2025-08-02 | 2025-08-04
R7S1ONECW-AP07-350 | Fire Fighting Manholes - AP#07 | 6 | 2025-08-05 | 2025-08-11
R7S1ONECW-AP07-351 | Fire Fighting Backfilling - AP#07 | 2 | 2025-08-18 | 2025-08-19
POWER |  | 23 | 2025-08-05 | 2025-08-13
R7S1ONECW-AP07-355 | Excavation Works & Sand Bedding - AP#07 (External Power Civil) | 3 | 2025-08-05 | 2025-08-07
R7S1ONECW-AP07-356 | Power Manholes - AP#07 | 3 | 2025-08-09 | 2025-08-11
R7S1ONECW-AP07-357 | Power Backfilling - AP#07 | 2 | 2025-08-12 | 2025-08-13
LOW CURRENT |  | 8 | 2025-08-09 | 2025-08-17
R7S1ONECW-AP07-358 | Excavation Works & Sand Bedding - AP#07 (External Low Current Civil) | 3 | 2025-08-09 | 2025-08-11
R7S1ONECW-AP07-359 | Low Current Manholes - AP#07 | 3 | 2025-08-12 | 2025-08-14
R7S1ONECW-AP07-360 | Low Current Backfilling - AP#07 | 2 | 2025-08-16 | 2025-08-17
EXTERNAL - MEP SERVICES |  | 29 | 2025-07-26 | 2025-08-19
DRAINAGE |  | 4 | 2025-07-26 | 2025-07-29
R7S1ONEME-AP07-231 | External Drainage Network - AP#07 (External Drainage MEP) | 4 | 2025-07-26 | 2025-07-29
WATERSUPPLY |  | 7 | 2025-08-05 | 2025-08-19
R7S1ONEME-AP07-232 | PRV statiuon assembly including meters- AP#07 (External WS MEP) | 4 | 2025-08-05 | 2025-08-09
R7S1ONEME-AP07-234 | Installation of valve station incl. BTU meter- AP#07 (External WS MEP) | 3 | 2025-08-17 | 2025-08-19
CHILLED WATER |  | 7 | 2025-08-10 | 2025-08-17
R7S1ONEME-AP07-233 | Installation of Chilled water line- AP#07 (External CWP MEP) | 6 | 2025-08-10 | 2025-08-16
R7S1ONEME-AP07-235 | Pressure Test for chilled water line- AP#07 (External CWP MEP) | 1 | 2025-08-17 | 2025-08-17
FIRE FIGHTING |  | 19 | 2025-08-05 | 2025-08-17
R7S1ONEME-AP07-236 | Installation of External FF network - AP#07 (External FF MEP) | 6 | 2025-08-05 | 2025-08-11
R7S1ONEME-AP07-237 | Installation of Alarm check valves- AP#07 (External FF MEP) | 3 | 2025-08-12 | 2025-08-14
R7S1ONEME-AP07-238 | Testing of External FF - AP#07 (External FF MEP) | 2 | 2025-08-16 | 2025-08-17
POWER |  | 1 | 2025-08-09 | 2025-08-09
R7S1ONEME-AP07-239 | Cable pulling from Manhole to the building MDB - AP#07 (External Power MEP) | 1 | 2025-08-09 | 2025-08-09
LOW CURRENT |  | 3 | 2025-08-12 | 2025-08-14
R7S1ONEME-AP07-240 | Low Current Cable pulling- AP#07 (External FF MEP) | 3 | 2025-08-12 | 2025-08-14
INFRA WORKS INCLUDE HUBS |  | 281 | 2025-02-13 | 2025-09-24
EV - 18 HUB (SECONDARY) |  | 233 | 2025-04-16 | 2025-09-24
SUB-STRUCTURE |  | 36 | 2025-04-16 | 2025-05-18
R7S1-ONSB-EV18-10 | Site Setting Out Works - EV18 | 1 | 2025-04-16 | 2025-04-16
R7S1-ONSB-EV18-20 | Site levelling & earthworks - EV18 | 6 | 2025-04-17 | 2025-04-23
R7S1-ONSB-EV18-30 | Anti-termite & Polythene Sheet Works - EV18 | 2 | 2025-04-26 | 2025-04-27
R7S1-ONSB-EV18-40 | Blinding PCC - EV18 | 3 | 2025-04-27 | 2025-04-29
R7S1-ONSB-EV18-50 | Waterproofing for Blinding PCC (Bitumen Paint) - EV18 | 2 | 2025-04-29 | 2025-04-30
R7S1-ONSB-EV18-60 | Foundations/Trenches - Rebar - EV18 | 6 | 2025-04-30 | 2025-05-06
R7S1-ONSB-EV18-70 | Foundations/Trenches - Shuttering (Including dowel Works) - EV18 | 6 | 2025-05-04 | 2025-05-10
R7S1-ONSB-EV18-80 | Installation of MEP U/G services below Boxes - EV18 | 4 | 2025-05-08 | 2025-05-12
R7S1-ONSB-EV18-90 | Foundations/Upstands - Casting - EV18 | 1 | 2025-05-13 | 2025-05-13
R7S1-ONSB-EV18-100 | Waterproofing For Foundations/Upstands - EV18 | 1 | 2025-05-14 | 2025-05-14
R7S1-ONSB-EV18-110 | Backfilling/Subbase & Compaction - EV18 | 3 | 2025-05-15 | 2025-05-18
TRENCH WORKS OUTSIDE THE HUB |  | 16 | 2025-07-15 | 2025-08-02
R7S1-ONSB-EV18-120 | Earthworks for Trenches - EV18 | 2 | 2025-07-15 | 2025-07-16
R7S1-ONSB-EV18-140 | Blinding PCC for Trenches - EV18 | 3 | 2025-07-15 | 2025-07-17
R7S1-ONSB-EV18-150 | Foundations/Trenches - Rebar - EV18 | 6 | 2025-07-15 | 2025-07-21
R7S1-ONSB-EV18-160 | MEP UG Services - EV18 | 6 | 2025-07-15 | 2025-07-21
R7S1-ONSB-EV18-170 | Trenches - Shuttering - EV18 | 6 | 2025-07-15 | 2025-07-21
R7S1-ONSB-EV18-180 | Trenches - Concrete - EV18 | 1 | 2025-07-22 | 2025-07-22
R7S1-ONSB-EV18-190 | Waterproofing For Trenches - EV18 | 2 | 2025-07-23 | 2025-07-24
R7S1-ONSB-EV18-200 | Backfilling - EV18 | 4 | 2025-07-22 | 2025-07-26
R7S1-ONSB-EV18-210 | Slab on Grade works - EV18 | 6 | 2025-07-27 | 2025-08-02
ERECTION WORKS |  | 12 | 2025-07-09 | 2025-07-21
R7S1-ONER-EV18-100 | Erection of Boxes - EV18 | 5 | 2025-07-09 | 2025-07-14
R7S1-ONER-EV18-110 | Erection of Loose Loose Elements - EV18 | 6 | 2025-07-15 | 2025-07-21
INSIDE HUBS (MEP & CIVIL FINISHES) |  | 147 | 2025-07-19 | 2025-08-17
CIVIL WORKS / FINISHES INSIDE THE HUB & ROOF |  | 133 | 2025-07-19 | 2025-08-14
R7S1-ONFIN-EV18-150 | Roof Stiching Works - EV18 | 7 | 2025-07-19 | 2025-07-26
R7S1-ONFIN-EV18-190 | Installation of Roof Drain Works - EV18 | 3 | 2025-07-24 | 2025-07-27
R7S1-ONFIN-EV18-140 | Roof Waterproofing works & Test - EV18 | 12 | 2025-07-28 | 2025-08-10
R7S1-ONFIN-EV18-130 | MEP Equipment Foundation Works - EV18 | 8 | 2025-08-06 | 2025-08-14
R7S1-ONFIN-EV18-160 | Internal final paint - EV18 | 10 | 2025-08-04 | 2025-08-14
R7S1-ONFIN-EV18-170 | External final paint (including parapets) - EV18 | 10 | 2025-08-04 | 2025-08-14
R7S1-ONFIN-EV18-180 | Installation of Cage Ladder - EV18 | 2 | 2025-08-13 | 2025-08-14
R7S1-ONFIN-EV18-200 | Installation of Roof Water pipes - EV18 | 2 | 2025-08-13 | 2025-08-14
MEP WORKS |  | 137 | 2025-07-19 | 2025-08-17
MECHANICAL |  | 47 | 2025-07-21 | 2025-08-14
CHILLED WATER |  | 32 | 2025-07-21 | 2025-08-14
R7S1-MECH-EV18-120 | Chilled water pump connection Works - EV18 | 5 | 2025-07-22 | 2025-07-27
R7S1-MECH-EV18-130 | Chemical Dosing unit connection Works - EV18 | 5 | 2025-07-22 | 2025-07-27
R7S1-MECH-EV18-140 | Pressurization unit -connection Works - EV18 | 5 | 2025-07-22 | 2025-07-27
R7S1-MECH-EV18-564 | Installation of Expansion Tank - EV18 | 6 | 2025-07-21 | 2025-07-27
R7S1-MECH-EV18-566 | Installation of Air Separator - EV18 | 2 | 2025-07-28 | 2025-07-29
R7S1-MECH-EV18-560 | Installation of External Out door unit for DX Split A/C - EV18 | 6 | 2025-07-28 | 2025-08-03
R7S1-MECH-EV18-562 | Installation of EX-Fan - EV18 | 2 | 2025-08-02 | 2025-08-03
R7S1-MECH-EV18-150 | Installation of CHW Pipes/Valves/Fittings - EV18 | 14 | 2025-07-30 | 2025-08-14
WATER SUPPLY |  | 28 | 2025-07-27 | 2025-08-14
R7S1-MECH-EV18-160 | Installation of GRP Tank - EV18 | 10 | 2025-07-27 | 2025-08-06
R7S1-MECH-EV18-190 | Booster Pumps connection Works - EV18 | 4 | 2025-08-07 | 2025-08-11
R7S1-MECH-EV18-200 | Ionization Filter connection Works - EV18 | 4 | 2025-08-07 | 2025-08-11
R7S1-MECH-EV18-210 | Connection of WS Pipes/Valves/Fittings - EV18 | 10 | 2025-08-04 | 2025-08-14
DRAINAGE |  | 33 | 2025-07-31 | 2025-08-14
R7S1-MECH-EV18-510 | Installation of PVC pipes for A/C drain with insulation - EV18 | 6 | 2025-07-31 | 2025-08-06
R7S1-MECH-EV18-580 | Installation of Trench drain - EV18 | 4 | 2025-08-03 | 2025-08-06
R7S1-MECH-EV18-590 | Installation of External Manhole & UPVC pipes - EV18 | 4 | 2025-08-03 | 2025-08-06
R7S1-MECH-EV18-570 | Installation of UPVC pipes for GRP tank overflow drain with valves - EV18 | 4 | 2025-08-11 | 2025-08-14
FIRE FIGHTING |  | 23 | 2025-07-27 | 2025-08-13
R7S1-MECH-EV18-220 | Fire Fighting Piping installation - EV18 | 8 | 2025-07-27 | 2025-08-04
R7S1-MECH-EV18-340 | NOVEC system installation - EV18 | 6 | 2025-08-03 | 2025-08-09
R7S1-MECH-EV18-280 | Sprinkler installation - EV18 | 2 | 2025-08-10 | 2025-08-11
R7S1-MECH-EV18-290 | FHRC / FE's Installation - EV18 | 2 | 2025-08-12 | 2025-08-13
ELECTRICAL |  | 135 | 2025-07-19 | 2025-08-17
POWER & LIGHTING |  | 132 | 2025-07-22 | 2025-08-17
R7S1-ELEC-EV18-100 | Cable Tray / Trunking continuation (for power & Low current) - EV18 | 6 | 2025-07-22 | 2025-07-28
R7S1-ELEC-EV18-110 | Pulling of wires - EV18 | 6 | 2025-07-24 | 2025-07-30
R7S1-ELEC-EV18-140 | Wiring Accessories installation - EV18 | 6 | 2025-07-27 | 2025-08-02
R7S1-ELEC-EV18-150 | Installation of Harmonic Filters - EV18 | 4 | 2025-07-31 | 2025-08-04
R7S1-ELEC-EV18-160 | Installation of Capacitor Banks - EV18 | 4 | 2025-07-31 | 2025-08-04
R7S1-ELEC-EV18-200 | Installation of DBs/MDBs/SMDBs (Electrical Power) - EV18 | 6 | 2025-08-06 | 2025-08-13
R7S1-ELEC-EV18-270 | Electrical Cables Installation for SMDBS- EV18 | 6 | 2025-08-06 | 2025-08-13
R7S1-ELEC-EV18-230 | Installation of DBs/MDBs/SMDBs for Chilled Water Pumps - EV18 | 6 | 2025-08-06 | 2025-08-13
R7S1-ELEC-EV18-250 | Installation of DBs/MDBs/SMDBs for Booster Pumps - EV18 | 6 | 2025-08-06 | 2025-08-13
R7S1-ELEC-EV18-310 | Electrical Cable Termination from trasforme to LV Panel - EV18 | 3 | 2025-08-12 | 2025-08-16
R7S1-ELEC-EV18-370 | Installation of Light Fittings - EV18 | 2 | 2025-08-13 | 2025-08-16
R7S1-ELEC-EV18-320 | Termination of Harmonic Filters - EV18 | 3 | 2025-08-13 | 2025-08-17
R7S1-ELEC-EV18-330 | Termination of Capacitor Banks - EV18 | 3 | 2025-08-13 | 2025-08-17
R7S1-ELEC-EV18-380 | Installation of Louvers - EV18 | 6 | 2025-08-10 | 2025-08-17
EARTHING |  | 11 | 2025-08-09 | 2025-08-16
R7S1-ELEC-EV18-290 | Installation of Copper Tape at Roof - EV18 | 6 | 2025-08-09 | 2025-08-14
R7S1-ELEC-EV18-350 | Installation of Earth Pit with SS rod - EV18 | 6 | 2025-08-10 | 2025-08-16
R7S1-ELEC-EV18-360 | Installation of Grounding Conductor with Equipment termination - EV18 | 6 | 2025-08-10 | 2025-08-16
LOW CURRENT SYSTEM |  | 39 | 2025-07-19 | 2025-08-16
R7S1-ELEC-EV18-130 | Installation of Firalarm Conduits - EV18 | 12 | 2025-07-19 | 2025-07-31
R7S1-ELEC-EV18-120 | Installation of ICT Pipes & ICT Cables - EV18 | 12 | 2025-07-21 | 2025-08-03
R7S1-ELEC-EV18-190 | Installation of Firalarm Devices with Termination - EV18 | 12 | 2025-07-22 | 2025-08-04
R7S1-ELEC-EV18-170 | Installation of Security System Pipes & ICT Cables - EV18 | 12 | 2025-07-23 | 2025-08-05
R7S1-ELEC-EV18-210 | ICT Equipment with Racks installation - EV18 | 12 | 2025-07-24 | 2025-08-06
R7S1-ELEC-EV18-260 | Installation of Monitor Module/Control Module with Termination - EV18 | 6 | 2025-08-02 | 2025-08-07
R7S1-ELEC-EV18-180 | Installation of BMS Pipes & Cables - EV18 | 12 | 2025-07-27 | 2025-08-09
R7S1-ELEC-EV18-240 | Security System installation & Termination - EV18 | 12 | 2025-07-29 | 2025-08-11
R7S1-ELEC-EV18-220 | Installation of BMS DDC Panel with Termination - EV18 | 12 | 2025-07-30 | 2025-08-12
R7S1-ELEC-EV18-280 | Access control installation - EV18 | 12 | 2025-08-02 | 2025-08-14
R7S1-ELEC-EV18-300 | Termination of BMS Cables with Field Device - EV18 | 12 | 2025-08-03 | 2025-08-16
EXTERNAL CIVIL & MEP WORKS |  | 15 | 2025-07-28 | 2025-08-13
R7S1-MECH-EV18-600 | External MEP & Civil Works - EV18 | 15 | 2025-07-28 | 2025-08-13
TESTING & COMMISSIONING |  | 38 | 2025-08-13 | 2025-09-06
ELECTRICAL |  | 28 | 2025-08-13 | 2025-08-25
POWER/SMDBs |  | 5 | 2025-08-13 | 2025-08-20
R7S1ONTCE-EV18-120 | T&C - LV Panel/SMDB & Energizing Panel (Power-On) - EV18 | 4 | 2025-08-13 | 2025-08-18
R7S1ONTCE-EV18-100 | T&C - Earthing & Lightening System - EV18 | 4 | 2025-08-17 | 2025-08-20
FIRE ALARM SYSTEM |  | 6 | 2025-08-18 | 2025-08-25
R7S1ONTCE-EV18-160 | T&C - Fire Alarm System - EV18 | 6 | 2025-08-18 | 2025-08-25
ICT SYSTEM |  | 6 | 2025-08-18 | 2025-08-25
R7S1ONTCE-EV18-250 | T&C - ICT System - EV18 | 6 | 2025-08-18 | 2025-08-25
SECURITY SYSTEM |  | 24 | 2025-08-18 | 2025-08-25
R7S1ONTCE-EV18-190 | T&C - Security System - EV18 | 6 | 2025-08-18 | 2025-08-25
R7S1ONTCE-EV18-200 | T&C - Access Control System - EV18 | 6 | 2025-08-18 | 2025-08-25
R7S1ONTCE-EV18-210 | T&C - BMS System - EV18 | 6 | 2025-08-18 | 2025-08-25
MECHANICAL |  | 30 | 2025-08-16 | 2025-09-06
CHILLED WATER |  | 13 | 2025-08-18 | 2025-09-06
R7S1ONTCM-EV18-130 | T&C - Chilled Water Pump - EV18 | 4 | 2025-08-18 | 2025-08-23
R7S1ONTCM-EV18-170 | T&C - CHW Flushing - EV18 | 12 | 2025-08-18 | 2025-09-01
R7S1ONTCM-EV18-260 | T&C - CHW Final Chemical - EV18 | 3 | 2025-08-31 | 2025-09-03
R7S1ONTCM-EV18-270 | T&C - CHW - Water Balancing - EV18 | 6 | 2025-08-30 | 2025-09-06
WATER SUPPLY |  | 26 | 2025-08-18 | 2025-09-04
R7S1ONTCM-EV18-140 | T&C - WS Pump - EV18 | 6 | 2025-08-18 | 2025-08-25
R7S1ONTCM-EV18-180 | T&C - WS Flushing - EV18 | 4 | 2025-08-25 | 2025-08-30
R7S1ONTCM-EV18-230 | T&C - WS Disinfection - EV18 | 6 | 2025-08-25 | 2025-09-01
R7S1ONTCM-EV18-240 | T&C - WS - Water Balancing (Mustadam) - EV18 | 8 | 2025-08-26 | 2025-09-04
DRAINAGE |  | 4 | 2025-08-16 | 2025-08-19
R7S1ONTCM-EV18-110 | T&C - Drainage System - EV18 | 4 | 2025-08-16 | 2025-08-19
FIRE FIGHTING |  | 11 | 2025-08-18 | 2025-08-31
R7S1ONTCM-EV18-150 | T&C - NOVEC (3 systems) - EV18 | 8 | 2025-08-18 | 2025-08-27
R7S1ONTCM-EV18-220 | T&C - Fire Fighting System - EV18 | 8 | 2025-08-21 | 2025-08-31
SNAGGING / DESNAGGING |  | 36 | 2025-09-06 | 2025-09-24
R7S1ONSNG-EV18-100 | Receipt of Preliminary Snag List From Employer - EV18 | 2 | 2025-09-06 | 2025-09-08
R7S1ONSNG-EV18-110 | De-Snagging of Preliminary Snags For Civil/MEP Activities - EV18 | 5 | 2025-09-08 | 2025-09-14
R7S1ONSNG-EV18-120 | O & M / Training - EV18 | 5 | 2025-09-11 | 2025-09-17
R7S1ONSNG-EV18-130 | Asbuilt - EV18 | 5 | 2025-09-14 | 2025-09-20
R7S1ONSNG-EV18-140 | Warranties / Guarantees / Spare Parts - EV18 | 5 | 2025-09-16 | 2025-09-22
R7S1ONSNG-EV18-150 | Acknowledgement of Final Snags Closure - EV18 | 4 | 2025-09-18 | 2025-09-24
INFRA WORKS (SECONDARY NETWORK) |  | 182 | 2025-02-13 | 2025-09-13
SECTION - 01 (AROUND AP-01,02 & 03) |  | 178 | 2025-02-13 | 2025-09-10
DRAINAGE WORKS |  | 156 | 2025-02-13 | 2025-08-25
R7S1-INF-SC1-DR-100 | Manhole Excavation (Section - 01 around AP-01,02 & 03) | 6 | 2025-05-12 | 2025-05-18
R7S1-INF-SC1-DR-110 | Maholes Construction (Section - 01 around AP-01,02 & 03) | 12 | 2025-07-08 | 2025-07-21
R7S1-INF-SC1-DR-120 | Excavation for Drainage line (Section - 01 around AP-01,02 & 03) | 129 | 2025-02-13 | 2025-07-24
R7S1-INF-SC1-DR-130 | Laying of Drainage Pipes & Connection (Section - 01 around AP-01,02 & 03) | 130 | 2025-02-15 | 2025-07-27
R7S1-INF-SC1-DR-140 | Testing (Section - 01 around AP-01,02 & 03) | 108 | 2025-03-16 | 2025-07-29
R7S1-INF-SC1-DR-150 | Backfilling+Warning Tape (Section - 01 around AP-01,02 & 03) | 131 | 2025-03-16 | 2025-08-25
CHILLED WATER WORKS |  | 102 | 2025-05-19 | 2025-09-01
R7S1-INF-SC1-CW-100 | Manhole Excavation (Section - 01 around AP-01,02 & 03) | 12 | 2025-05-19 | 2025-06-01
R7S1-INF-SC1-CW-110 | Maholes Construction (Section - 01 around AP-01,02 & 03) | 12 | 2025-05-22 | 2025-06-04
R7S1-INF-SC1-CW-120 | Excavation for CHWP line (Section - 01 around AP-01,02 & 03) | 12 | 2025-05-26 | 2025-06-12
R7S1-INF-SC1-CW-130 | Laying of CH Pipes & VALVES (Section - 01 around AP-01,02 & 03) | 12 | 2025-05-29 | 2025-06-16
R7S1-INF-SC1-CW-140 | Pressure Testing (Section - 01 around AP-01,02 & 03) | 6 | 2025-06-12 | 2025-06-18
R7S1-INF-SC1-CW-150 | Backfilling+Warning Tape (Section - 01 around AP-01,02 & 03) | 9 | 2025-06-14 | 2025-06-23
R7S1-INF-SC1-CW-220 | Chilled Water Pipes Flushing (Section - 01 around AP-01,02 & 03) | 18 | 2025-08-11 | 2025-09-01
WATER SUPPLY WORKS |  | 70 | 2025-06-02 | 2025-09-09
R7S1-INF-SC1-WS-100 | Manhole Excavation (Section - 01 around AP-01,02 & 03) | 12 | 2025-06-02 | 2025-06-19
R7S1-INF-SC1-WS-110 | Maholes Construction (Section - 01 around AP-01,02 & 03) | 12 | 2025-06-21 | 2025-07-03
R7S1-INF-SC1-WS-120 | Excavation for WS line (Section - 01 around AP-01,02 & 03) | 12 | 2025-06-24 | 2025-07-07
R7S1-INF-SC1-WS-130 | Laying of WS Pipes & VALVES (Section - 01 around AP-01,02 & 03) | 12 | 2025-06-28 | 2025-07-10
R7S1-INF-SC1-WS-140 | Pressure Testing (Section - 01 around AP-01,02 & 03) | 6 | 2025-07-07 | 2025-07-13
R7S1-INF-SC1-WS-150 | Backfilling+Warning Tape (Section - 01 around AP-01,02 & 03) | 9 | 2025-08-30 | 2025-09-09
FIRE PROTECTION WORKS |  | 67 | 2025-06-21 | 2025-09-10
R7S1-INF-SC1-FP-100 | Manhole Excavation (Section - 01 around AP-01,02 & 03) | 12 | 2025-06-21 | 2025-07-03
R7S1-INF-SC1-FP-110 | Maholes Construction (Section - 01 around AP-01,02 & 03) | 12 | 2025-06-24 | 2025-07-07
R7S1-INF-SC1-FP-120 | Excavation for FP line (Section - 01 around AP-01,02 & 03) | 12 | 2025-06-28 | 2025-07-10
R7S1-INF-SC1-FP-130 | Laying of FF Pipes & VALVES (Section - 01 around AP-01,02 & 03) | 12 | 2025-07-01 | 2025-07-14
R7S1-INF-SC1-FP-140 | Pressure Testing (Section - 01 around AP-01,02 & 03) | 6 | 2025-07-10 | 2025-07-16
R7S1-INF-SC1-FP-150 | Backfilling+Warning Tape (Section - 01 around AP-01,02 & 03) | 9 | 2025-08-31 | 2025-09-10
POWER - ELECTRICAL |  | 39 | 2025-06-18 | 2025-07-20
R7S1-INF-SC1-PO-100 | Manhole Excavation (Section - 01 around AP-01,02 & 03) | 12 | 2025-06-18 | 2025-07-01
R7S1-INF-SC1-PO-110 | Maholes Construction (Section - 01 around AP-01,02 & 03) | 12 | 2025-06-28 | 2025-07-10
R7S1-INF-SC1-PO-120 | Excavation for LV Cable (Section - 01 around AP-01,02 & 03) | 12 | 2025-07-01 | 2025-07-14
R7S1-INF-SC1-PO-130 | Laying of LV Cable (Section - 01 around AP-01,02 & 03) | 12 | 2025-07-05 | 2025-07-17
R7S1-INF-SC1-PO-140 | Backfilling+Warning Tape (Section - 01 around AP-01,02 & 03) | 9 | 2025-07-10 | 2025-07-20
SECURITY SYSTEM (CCTV & ACCESS CONTROL) - ELECTRICAL |  | 21 | 2025-07-05 | 2025-07-28
R7S1-INF-SC1-ELV-100 | Manhole Excavation (Section - 01 around AP-01,02 & 03) | 6 | 2025-07-05 | 2025-07-10
R7S1-INF-SC1-ELV-110 | Maholes Construction (Section - 01 around AP-01,02 & 03) | 12 | 2025-07-08 | 2025-07-21
R7S1-INF-SC1-ELV-120 | Excavation for ELV Cable (Section - 01 around AP-01,02 & 03) | 12 | 2025-07-10 | 2025-07-23
R7S1-INF-SC1-ELV-130 | Laying of ELV Cable (Section - 01 around AP-01,02 & 03) | 12 | 2025-07-13 | 2025-07-26
R7S1-INF-SC1-ELV-140 | Backfilling+Warning Tape (Section - 01 around AP-01,02 & 03) | 9 | 2025-07-19 | 2025-07-28
ICT - ELECTRICAL |  | 28 | 2025-07-12 | 2025-09-09
R7S1-INF-SC1-ICT-100 | Manhole Excavation (Section - 01 around AP-01,02 & 03) | 6 | 2025-07-12 | 2025-07-17
R7S1-INF-SC1-ICT-110 | Maholes Construction (Section - 01 around AP-01,02 & 03) | 12 | 2025-07-15 | 2025-07-28
R7S1-INF-SC1-ICT-120 | Excavation for ICT Ducts/Cable (Section - 01 around AP-01,02 & 03) | 12 | 2025-07-17 | 2025-07-30
R7S1-INF-SC1-ICT-130 | Laying of Ducts, Road Crossings, ICT Cable Pulling (Section - 01 around AP-01,02 & 03) | 12 | 2025-07-20 | 2025-08-02
R7S1-INF-SC1-ICT-140 | Backfilling+Warning Tape (Section - 01 around AP-01,02 & 03) | 9 | 2025-08-30 | 2025-09-09
SECTION - 02 (AROUND AP-04,06, 07 & 16) |  | 90 | 2025-05-28 | 2025-09-13
DRAINAGE WORKS |  | 90 | 2025-05-28 | 2025-09-13
R7S1-INF-SC2-DR-160 | Manhole Excavation (Section - 02 around AP-04,05,06 & 07) | 6 | 2025-05-28 | 2025-06-04
R7S1-INF-SC2-DR-170 | Maholes Construction (Section - 02 around AP-04,05,06 & 07) | 12 | 2025-06-01 | 2025-06-19
R7S1-INF-SC2-DR-180 | Excavation for Drainage line (Section - 02 around AP-04,05,06 & 07) | 12 | 2025-06-03 | 2025-06-22
R7S1-INF-SC2-DR-190 | Laying of Drainage Pipes (Section - 02 around AP-04,05,06 & 07) | 12 | 2025-06-10 | 2025-06-24
R7S1-INF-SC2-DR-200 | Testing (Section - 02 around AP-04,05,06 & 07) | 6 | 2025-06-19 | 2025-06-26
R7S1-INF-SC2-DR-210 | Backfilling+Warning Tape (Section - 02 around AP-04,05,06 & 07) | 9 | 2025-09-03 | 2025-09-13
CHILLED WATER WORKS |  | 62 | 2025-06-04 | 2025-09-01
R7S1-INF-SC2-CW-160 | Manhole Excavation (Section - 02 around AP-04,05,06 & 07) | 12 | 2025-06-04 | 2025-06-23
R7S1-INF-SC2-CW-170 | Maholes Construction (Section - 02 around AP-04,05,06 & 07) | 12 | 2025-06-12 | 2025-06-26
R7S1-INF-SC2-CW-180 | Excavation for CHWP line (Section - 02 around AP-04,05,06 & 07) | 12 | 2025-06-16 | 2025-06-30
R7S1-INF-SC2-CW-190 | Laying of CH Pipes & VALVES (Section - 02 around AP-04,05,06 & 07) | 12 | 2025-06-19 | 2025-07-03
R7S1-INF-SC2-CW-200 | Pressure Testing (Section - 02 around AP-04,05,06 & 07) | 6 | 2025-06-29 | 2025-07-06
R7S1-INF-SC2-CW-210 | Backfilling+Warning Tape (Section - 02 around AP-04,05,06 & 07) | 9 | 2025-06-30 | 2025-07-10
R7S1-INF-SC2-CW-230 | Chilled Water Pipes Flushing (Section - 02 around AP-04,05,06 & 07) | 18 | 2025-08-11 | 2025-09-01
WATER SUPPLY WORKS |  | 67 | 2025-06-12 | 2025-09-09
R7S1-INF-SC2-WS-160 | Manhole Excavation (Section - 02 around AP-04,05,06 & 07) | 12 | 2025-06-12 | 2025-06-26
R7S1-INF-SC2-WS-170 | Maholes Construction (Section - 02 around AP-04,05,06 & 07) | 12 | 2025-06-16 | 2025-06-30
R7S1-INF-SC2-WS-180 | Excavation for WS line (Section - 02 around AP-04,05,06 & 07) | 12 | 2025-06-19 | 2025-07-03
R7S1-INF-SC2-WS-190 | Laying of WS Pipes & VALVES (Section - 02 around AP-04,05,06 & 07) | 12 | 2025-06-23 | 2025-07-07
R7S1-INF-SC2-WS-200 | Pressure Testing (Section - 02 around AP-04,05,06 & 07) | 6 | 2025-07-02 | 2025-07-09
R7S1-INF-SC2-WS-210 | Backfilling+Warning Tape (Section - 02 around AP-04,05,06 & 07) | 9 | 2025-08-30 | 2025-09-09
FIRE PROTECTION WORKS |  | 63 | 2025-06-16 | 2025-09-10
R7S1-INF-SC2-FP-160 | Manhole Excavation (Section - 02 around AP-04,05,06 & 07) | 12 | 2025-06-16 | 2025-06-30
R7S1-INF-SC2-FP-170 | Maholes Construction (Section - 02 around AP-04,05,06 & 07) | 12 | 2025-06-19 | 2025-07-03
R7S1-INF-SC2-FP-180 | Excavation for FP line (Section - 02 around AP-04,05,06 & 07) | 12 | 2025-06-23 | 2025-07-07
R7S1-INF-SC2-FP-190 | Laying of FF Pipes & VALVES (Section - 02 around AP-04,05,06 & 07) | 12 | 2025-06-26 | 2025-07-10
R7S1-INF-SC2-FP-200 | Pressure Testing (Section - 02 around AP-04,05,06 & 07) | 6 | 2025-07-08 | 2025-07-15
R7S1-INF-SC2-FP-210 | Backfilling+Warning Tape (Section - 02 around AP-04,05,06 & 07) | 9 | 2025-08-31 | 2025-09-10
POWER - ELECTRICAL |  | 51 | 2025-06-19 | 2025-07-16
R7S1-INF-SC2-PO-150 | Manhole Excavation (Section - 02 around AP-04,05,06 & 07) | 12 | 2025-06-19 | 2025-07-03
R7S1-INF-SC2-PO-160 | Maholes Construction (Section - 02 around AP-04,05,06 & 07) | 12 | 2025-06-23 | 2025-07-07
R7S1-INF-SC2-PO-170 | Excavation for LV Cable (Section - 02 around AP-04,05,06 & 07) | 12 | 2025-06-26 | 2025-07-10
R7S1-INF-SC2-PO-180 | Laying of LV Cable (Section - 02 around AP-04,05,06 & 07) | 12 | 2025-06-30 | 2025-07-14
R7S1-INF-SC2-PO-190 | Backfilling+Warning Tape (Section - 02 around AP-04,05,06 & 07) | 9 | 2025-07-06 | 2025-07-16
SECURITY SYSTEM (CCTV & ACCESS CONTROL) - ELECTRICAL |  | 20 | 2025-06-19 | 2025-07-13
R7S1-INF-SC2-ELV-150 | Manhole Excavation (Section - 02 around AP-04,05,06 & 07) | 6 | 2025-06-19 | 2025-06-26
R7S1-INF-SC2-ELV-160 | Maholes Construction (Section - 02 around AP-04,05,06 & 07) | 12 | 2025-06-22 | 2025-07-06
R7S1-INF-SC2-ELV-170 | Excavation for ELV Cable (Section - 02 around AP-04,05,06 & 07) | 12 | 2025-06-23 | 2025-07-07
R7S1-INF-SC2-ELV-180 | Laying of ELV Cable (Section - 02 around AP-04,05,06 & 07) | 12 | 2025-06-26 | 2025-07-10
R7S1-INF-SC2-ELV-190 | Backfilling+Warning Tape (Section - 02 around AP-04,05,06 & 07) | 9 | 2025-07-02 | 2025-07-13
ICT - ELECTRICAL |  | 21 | 2025-06-26 | 2025-07-21
R7S1-INF-SC2-ICT-150 | Manhole Excavation (Section - 02 around AP-04,05,06 & 07) | 6 | 2025-06-26 | 2025-07-03
R7S1-INF-SC2-ICT-160 | Maholes Construction (Section - 02 around AP-04,05,06 & 07) | 12 | 2025-06-30 | 2025-07-14
R7S1-INF-SC2-ICT-170 | Excavation for LV Cable (Section - 02 around AP-04,05,06 & 07) | 12 | 2025-07-02 | 2025-07-16
R7S1-INF-SC2-ICT-180 | Laying of Ducts, Road Crossings, ICT Cable Pulling (Section - 02 around AP-04,05,06 & 07) | 12 | 2025-07-05 | 2025-07-19
R7S1-INF-SC2-ICT-190 | Backfilling+Warning Tape (Section - 02 around AP-04,05,06 & 07) | 9 | 2025-07-10 | 2025-07-21
TIE-IN CONNECTION (SECTION - 01 & 02) |  | 69 | 2025-07-29 | 2025-09-13
DRAINAGE |  | 56 | 2025-07-29 | 2025-08-31
R7S1-INF-TIE-DR-120 | Drainage Tie-in Connection Works - AP03 (MH--L4-8-3) | 4 | 2025-07-29 | 2025-08-03
R7S1-INF-TIE-DR-110 | Drainage Tie-in Connection Works - AP02 (ZUT--SR02-MH-1) | 4 | 2025-07-31 | 2025-08-05
R7S1-INF-TIE-DR-100 | Drainage Tie-in Connection Works - AP01 (MH-L4-11) | 4 | 2025-08-20 | 2025-08-24
R7S1-INF-TIE-DR-130 | Drainage Tie-in Connection Works - AP04 (IC--L8-4-1) | 4 | 2025-08-23 | 2025-08-26
R7S1-INF-TIE-DR-140 | Drainage Tie-in Connection Works - AP06 (ZUT--SR02-MH-IC) | 4 | 2025-08-25 | 2025-08-28
R7S1-INF-TIE-DR-150 | Drainage Tie-in Connection Works - AP07 (IC--L4-12-1) | 4 | 2025-08-27 | 2025-08-31
CHILLED WATER |  | 23 | 2025-08-16 | 2025-09-06
R7S1-INF-TIE-CHW-170 | Connect Pipe from the Heat Exchanger to the Existing Valve Chamber near EV-18 | 2 | 2025-08-16 | 2025-08-17
R7S1-INF-TIE-CHW-180 | Connect Pipe from the Heat Exchanger to Chilled Waterpump | 2 | 2025-08-18 | 2025-08-19
R7S1-INF-TIE-CHW-190 | Open Valve to Flow to the Network (after Flushing) | 1 | 2025-09-04 | 2025-09-06
WATER SUPPLY |  | 4 | 2025-08-16 | 2025-08-19
R7S1-INF-TIE-WS-170 | Watersupply Pipe Laying & Connecting to the Existing Tank Primary Tank to Secondary GRP tank | 4 | 2025-08-16 | 2025-08-19
FIRE PROTECTION |  | 4 | 2025-09-08 | 2025-09-13
R7S1-INF-TIE-FF-160 | Fire Protection Tie-in Connection Works - AP01,02,03,04,05, 06,07 (ZUT--FP2-GV6) | 4 | 2025-09-08 | 2025-09-13
PRIORITY - 2 |  | 346 | 2024-12-11 | 2025-12-22
STUDIO BUILDINGS |  | 339 | 2024-12-11 | 2025-12-02
BUILDING # AP16 (LARGE STUDIO) |  | 334 | 2024-12-14 | 2025-11-12
SUB-STRUCTURE |  | 107 | 2024-12-14 | 2025-04-22
R7S1-ONSB-AP16-325 | Site Setting Out Works - AP#16 | 2 | 2024-12-14 | 2024-12-15
R7S1-ONSB-AP16-322 | Site levelling & earthworks - AP#16 | 5 | 2024-12-15 | 2024-12-19
R7S1-ONSB-AP16-326 | Anti-termite & Polythene Sheet Works - AP#16 | 7 | 2025-01-26 | 2025-02-02
R7S1-ONSB-AP16-323 | Blinding PCC - AP#16 | 9 | 2025-01-27 | 2025-02-05
R7S1-ONSB-AP16-324 | Waterproofing for Blinding PCC (Bitumen Paint) - AP#16 | 7 | 2025-01-30 | 2025-02-06
R7S1-ONSB-AP16-327 | Foundations/Upstands - Rebar - AP#16 | 24 | 2025-02-01 | 2025-03-02
R7S1-ONSB-AP16-328 | Foundations/Upstands - Shuttering (Including dowel Works) - AP#16 | 24 | 2025-02-02 | 2025-03-03
R7S1-ONSB-AP16-331 | Installation of MEP U/G services below Boxes - AP#16 | 18 | 2025-02-09 | 2025-03-03
R7S1-ONSB-AP16-329 | Foundations/Upstands - Casting - AP#16 | 16 | 2025-02-12 | 2025-03-04
R7S1-ONSB-AP16-330 | Waterproofing For Foundations/Upstands - AP#16 | 20 | 2025-02-13 | 2025-03-09
R7S1-ONSB-AP16-332 | Backfilling & Compaction - AP#16 | 53 | 2025-02-15 | 2025-04-22
SLAB-ON-GRADE & UG MEP WORKS (in Corridor) |  | 13 | 2025-05-17 | 2025-05-29
LEFT SIDE |  | 13 | 2025-05-17 | 2025-05-26
R7S1-ONSG-AP16-406 | Block Work below Corridor area - AP#16 | 1 | 2025-05-19 | 2025-05-19
R7S1-ONSG-AP16-340 | Backfilling & SOG (In Front of Lift Shaft) - AP#16 | 3 | 2025-05-17 | 2025-05-19
R7S1-ONSG-AP16-412 | Backfilling upto Pipe Level - AP#16 | 1 | 2025-05-20 | 2025-05-20
R7S1-ONSG-AP16-420 | Plaster Work for Blockwork - AP#16 | 1 | 2025-05-20 | 2025-05-20
R7S1-ONSG-AP16-407 | UG MEP Works (Laying of Pipes) - AP#16 | 2 | 2025-05-20 | 2025-05-21
R7S1-ONSG-AP16-408 | Backfilling Works after Pipe Laying - AP#16 | 1 | 2025-05-22 | 2025-05-22
R7S1-ONSG-AP16-409 | Antitermite Works - AP#16 | 1 | 2025-05-22 | 2025-05-22
R7S1-ONSG-AP16-410 | Polythene & Rebar Mesh Works - AP#16 | 2 | 2025-05-24 | 2025-05-25
R7S1-ONSG-AP16-411 | Pouring SOG Concrete - AP#16 | 1 | 2025-05-26 | 2025-05-26
RIGHT SIDE |  | 9 | 2025-05-22 | 2025-05-29
R7S1-ONSG-AP16-413 | Block Work below Corridor area - AP#16 | 1 | 2025-05-22 | 2025-05-24
R7S1-ONSG-AP16-419 | Backfilling upto Pipe Level - AP#16 | 1 | 2025-05-24 | 2025-05-25
R7S1-ONSG-AP16-414 | UG MEP Works (Laying of Pipes) - AP#16 | 1 | 2025-05-25 | 2025-05-26
R7S1-ONSG-AP16-415 | Backfilling Works after Pipe Laying - AP#16 | 1 | 2025-05-26 | 2025-05-27
R7S1-ONSG-AP16-416 | Antitermite Works - AP#16 | 1 | 2025-05-26 | 2025-05-27
R7S1-ONSG-AP16-417 | Polythene & Rebar Mesh Works - AP#16 | 1 | 2025-05-27 | 2025-05-28
R7S1-ONSG-AP16-418 | Pouring SOG Concrete - AP#16 | 1 | 2025-05-28 | 2025-05-29
ERECTION WORKS |  | 92 | 2025-05-14 | 2025-08-28
GROUND FLOOR |  | 24 | 2025-05-14 | 2025-06-02
R7S1ONER-AP16GF352 | Erection of Columns/Beams Frame & Slab/Loose Elements (In Front of Lift Shaft) - AP#16 | 2 | 2025-05-14 | 2025-05-15
R7S1ONER-AP16GF217 | Erection of GF Boxes (Left Side) including Lift Box & Staircase - AP#16 - Large Studio | 4 | 2025-05-14 | 2025-05-18
R7S1ONER-AP16GF218 | Erection of GF Boxes (Right Side) - AP#16 - Large Studio | 4 | 2025-05-18 | 2025-05-22
R7S1ONER-AP16GF219 | Erection of GF MEP Modular Cages (Left Side) - AP#16 | 2 | 2025-05-27 | 2025-05-28
R7S1ONER-AP16GF220 | Erection of GF Corridor Slabs (Left Side) - AP#16 | 2 | 2025-05-28 | 2025-05-29
R7S1ONER-AP16GF221 | Erection of GF MEP Modular Cages (Right Side) - AP#16 | 2 | 2025-05-29 | 2025-06-01
R7S1ONER-AP16GF222 | Erection of GF Corridor Slabs Right Side) - AP#16 | 2 | 2025-05-31 | 2025-06-02
FIRST FLOOR |  | 18 | 2025-05-17 | 2025-08-09
R7S1ONER-AP16FF362 | Erection of Columns/Beams Frame & Slab/Loose Elements (In Front of Lift Shaft) - AP#16 | 2 | 2025-05-17 | 2025-05-18
R7S1ONER-AP16FF217 | Erection of FF Boxes (Left Side) - AP#16 - Large Studio | 2 | 2025-08-03 | 2025-08-04
R7S1ONER-AP16FF218 | Erection of FF Boxes (Right Side) - AP#16 - Large Studio | 2 | 2025-08-05 | 2025-08-06
R7S1ONER-AP16FF219 | Erection of FF MEP Modular Cages (Left Side) - AP#16 | 2 | 2025-08-05 | 2025-08-06
R7S1ONER-AP16FF220 | Erection of FF Corridor Slabs (Left Side) - AP#16 | 2 | 2025-08-05 | 2025-08-06
R7S1ONER-AP16FF221 | Erection of FF MEP Modular Cages (Right Side) - AP#16 | 2 | 2025-08-06 | 2025-08-09
R7S1ONER-AP16FF222 | Erection of FF Corridor Slabs Right Side) - AP#16 | 2 | 2025-08-06 | 2025-08-09
SECOND FLOOR |  | 26 | 2025-05-19 | 2025-08-17
R7S1ONER-AP16SF372 | Erection of Columns/Beams Frame & Slab/Loose Elements (In Front of Lift Shaft) - AP#16 | 2 | 2025-05-19 | 2025-05-20
R7S1ONER-AP16SF217 | Erection of SF Boxes (Left Side) - AP#16 - Large Studio | 2 | 2025-08-06 | 2025-08-07
R7S1ONER-AP16SF218 | Erection of SF Boxes (Right Side) - AP#16 - Large Studio | 1 | 2025-08-09 | 2025-08-10
R7S1ONER-AP16SF219 | Erection of SF MEP Modular Cages (Left Side) - AP#16 | 3 | 2025-08-09 | 2025-08-11
R7S1ONER-AP16SF220 | Erection of SF Corridor Slabs (Left Side) - AP#16 | 2 | 2025-08-12 | 2025-08-13
R7S1ONER-AP16SF221 | Erection of SF MEP Modular Cages (Right Side) - AP#16 | 2 | 2025-08-13 | 2025-08-14
R7S1ONER-AP16SF222 | Erection of SF Corridor Slabs Right Side) - AP#16 | 2 | 2025-08-16 | 2025-08-17
ROOF |  | 10 | 2025-08-18 | 2025-08-28
R7S1ONER-AP16RF112 | Erection of Loose Roof Parapets, Shaft Covers, MEP Foundation etc. - AP#16 Roof | 10 | 2025-08-18 | 2025-08-28
MEP WORKS & FINISHES |  | 175 | 2025-05-20 | 2025-11-09
GROUND FLOOR |  | 168 | 2025-05-20 | 2025-10-07
ARCH./ CIVIL WORKS |  | 134 | 2025-05-20 | 2025-10-07
CORRIDOR AREA |  | 82 | 2025-07-14 | 2025-10-07
R7S1ONAR-AP16GF354 | Flooring in Corridor - AP#16 (GF Corridor) | 6 | 2025-07-14 | 2025-07-21
R7S1ONAR-AP16GF355 | Corridor Skirting - AP#16 (GF Corridor) | 2 | 2025-07-20 | 2025-07-22
R7S1ONAR-AP16GF352 | False Ceiling - 1st Fix - AP#16 (GF - Corridor) | 4 | 2025-07-22 | 2025-07-27
R7S1ONAR-AP16GF353 | Gypsum Wall Cladding - 1st Fix (Shafts) - AP#16 (GF Corridor) | 6 | 2025-09-08 | 2025-09-14
R7S1ONAR-AP16GF356 | Gypsum Wall Cladding (Shafts) -2nd Fix - AP#16 (GF Corridor) | 4 | 2025-09-15 | 2025-09-18
R7S1ONAR-AP16GF360 | Fixing Architrave - AP#16 (GF Corridor) | 2 | 2025-09-20 | 2025-09-21
R7S1ONAR-AP16GF361 | Fixing Aluminium Doors - AP#16 (GF Corridor) | 2 | 2025-09-22 | 2025-09-24
R7S1ONAR-AP16GF357 | False Ceiling - 2nd Fix (Closing the Ceiling) - AP#16 (GF Corridor) | 3 | 2025-09-25 | 2025-09-28
R7S1ONAR-AP16GF358 | Painting - Surface Prep., Primer & 1st Coat - AP#16 (GF Corridor) | 8 | 2025-09-20 | 2025-09-29
R7S1ONAR-AP16GF376 | Painting - Surface Prep., Primer & 1st Coat for Ceiling - AP#16 (GF Corridor) | 4 | 2025-09-29 | 2025-10-02
R7S1ONAR-AP16GF359 | Painting - Final Coat (Ceiling + Walls) - AP#16 (GF Corridor) | 3 | 2025-10-05 | 2025-10-07
INSIDE BOXES |  | 12 | 2025-08-05 | 2025-08-18
R7S1ONAR-AP16GF362 | Fixing Thresholds (Joining the Room) - AP#16 (GF - inside Boxes) | 4 | 2025-08-05 | 2025-08-09
R7S1ONAR-AP16GF363 | Fixing Wooden Doors - AP#16 (GF - inside Boxes) | 4 | 2025-08-10 | 2025-08-13
R7S1ONAR-AP16GF364 | Fixing Aluminium Doors - AP#16 (GF - inside Boxes) | 4 | 2025-08-14 | 2025-08-18
IN FRONT OF LIFT SHAFT |  | 90 | 2025-05-20 | 2025-09-21
R7S1ONAR-AP16GF366 | Flooring - AP#16 (GF - Front of Lift Shaft) | 4 | 2025-05-20 | 2025-05-24
R7S1ONAR-AP16GF367 | Skirting & Thresholds - AP#16 (GF - Front of Lift Shaft) | 2 | 2025-05-22 | 2025-05-24
R7S1ONAR-AP16GF368 | Painting - Surface Prep., Primer & 1st Coat - AP#16 (GF - Front of Lift Shaft) | 4 | 2025-05-25 | 2025-05-28
R7S1ONAR-AP16GF365 | False Ceiling - 1st Fix - AP#16 (GF - Front of Lift Shaft) | 4 | 2025-05-29 | 2025-06-02
R7S1ONAR-AP16GF369 | False Ceiling - Final Fix - AP#16 (GF - Front of Lift Shaft) | 3 | 2025-06-03 | 2025-06-10
R7S1ONAR-AP16GF371 | Fixing Handrail - AP#16 (GF - Front of Lift Shaft) | 3 | 2025-09-09 | 2025-09-11
R7S1ONAR-AP16GF372 | Paint for Handrail - AP#16 (GF - Front of Lift Shaft) | 2 | 2025-09-13 | 2025-09-14
R7S1ONAR-AP16GF370 | Painting - Final Coat - AP#16 (GF - Front of Lift Shaft) | 2 | 2025-09-15 | 2025-09-16
R7S1ONAR-AP16GF374 | Fixing Wall Guard - AP#16 (GF - Front of Lift Shaft) | 2 | 2025-09-17 | 2025-09-18
R7S1ONAR-AP16GF373 | Fixing Floor Mat - AP#16 (GF - Front of Lift Shaft) | 2 | 2025-09-20 | 2025-09-21
GARBAGE ROOM |  | 2 | 2025-09-03 | 2025-09-04
R7S1ONAR-AP16GF375 | Paint Finishes and Touchups - Final Coat - AP#16 (GF - Garbage Room) | 2 | 2025-09-03 | 2025-09-04
MEP WORKS |  | 97 | 2025-06-02 | 2025-10-04
MECHANICAL |  | 96 | 2025-06-02 | 2025-10-02
CHILLED WATER |  | 65 | 2025-06-02 | 2025-08-13
R7S1ONME-AP16GF969 | Installation of Chilled water hanger and supports - AP#16 (GF - Corridor) | 4 | 2025-06-02 | 2025-06-11
R7S1ONME-AP16GF1021 | Installation of CHWP connection for FCU with Valve package in Corridor, Electrical Room & ICT Room - AP#16 (GF) | 4 | 2025-06-02 | 2025-06-11
R7S1ONME-AP16GF971 | Installation of BTU Meter with valves - AP#16 (GF - Corridor) | 2 | 2025-06-12 | 2025-06-15
R7S1ONME-AP16GF970 | Installation of CHWP piping (connection between modular cages & modular to apartment) - AP#16 (GF - Corridor) | 4 | 2025-06-11 | 2025-06-16
R7S1ONME-AP16GF1346 | CHWP Installation/Connections and Insulation (In Front of Lift Shaft) - AP#16 | 4 | 2025-06-30 | 2025-07-03
R7S1ONME-AP16GF972 | CHWP piping risers connections - AP#16 (GF - Corridor) | 3 | 2025-08-05 | 2025-08-07
R7S1ONME-AP16GF973 | Pressure Testing of CHWP piping - AP#16 (GF - Corridor) | 1 | 2025-08-09 | 2025-08-09
R7S1ONME-AP16GF1009 | CHWP Insulation - AP#16 (GF - Corridor) | 4 | 2025-08-10 | 2025-08-13
HVAC DUCTING |  | 92 | 2025-06-02 | 2025-09-30
R7S1ONME-AP16GF1020 | Installation of FCU's & Duct Connection in Corridor, Electrical Room & ICT Room - AP#16 (GF) | 4 | 2025-06-02 | 2025-06-11
R7S1ONME-AP16GF1022 | Installation of Ducting and insulation (connection between modular cages) - AP#16 (GF - Corridor) | 3 | 2025-06-11 | 2025-06-15
R7S1ONME-AP16GF974 | Duct Riser Continuation - AP#16 (GF - Corridor) | 4 | 2025-08-05 | 2025-08-09
R7S1ONME-AP16GF975 | A/C drain & Copper pipe connection in ELV room - AP#16 (GF) | 2 | 2025-08-10 | 2025-08-11
R7S1ONME-AP16GF1010 | Installation of Duct & Grill in Garbage Room - AP#16 (GF - Garbage Room) | 2 | 2025-08-12 | 2025-08-13
R7S1ONME-AP16GF1023 | Installation of Grilles in the Corridor - AP#16 (GF - Corridor) | 2 | 2025-09-29 | 2025-09-30
FIRE FIGHTING |  | 88 | 2025-07-05 | 2025-10-02
R7S1ONME-AP16GF1556 | Installation of F.F Pipes, Testing & Final Fixtures (In Front of Lift Shaft) - AP16 | 3 | 2025-07-05 | 2025-07-07
R7S1ONME-AP16GF1011 | Installation of Pipe & sprinkler in Garbage Room - AP#16 (GF - Garbage Room) | 1 | 2025-08-06 | 2025-08-07
R7S1ONME-AP16GF976 | Riser Continuity in corridor - AP#16 (GF - Corridor) | 4 | 2025-08-05 | 2025-08-09
R7S1ONME-AP16GF977 | Continuitu of FF pipes & ZC Valves (connection between modular cages & modular to apartment) - AP#16 (GF - Corridor) | 4 | 2025-08-05 | 2025-08-09
R7S1ONME-AP16GF978 | Installation of Sprinklers drops in corridor - AP#16 (GF - Corridor) | 4 | 2025-08-10 | 2025-08-13
R7S1ONME-AP16GF979 | Pressure Test for FF Piping in corridor - AP#16 (GF - Corridor) | 4 | 2025-08-14 | 2025-08-18
R7S1ONME-AP16GF1024 | FF Flushing network - AP#16 (GF - Corridor) | 1 | 2025-08-30 | 2025-08-30
R7S1ONME-AP16GF981 | Installation of Alarm check valve, Fire Extinguishers & Blanket - AP#16 (GF - Corridor) | 2 | 2025-09-29 | 2025-09-30
R7S1ONME-AP16GF980 | Installation of Sprinklers in corridor - AP#16 (GF - Corridor) | 4 | 2025-09-29 | 2025-10-02
WATER SUPPLY |  | 79 | 2025-06-02 | 2025-09-07
R7S1ONME-AP16GF1012 | Installation of WS Pipe in Garbage Room - AP#16 (GF - Garbage Room) | 2 | 2025-06-02 | 2025-06-04
R7S1ONME-AP16GF1013 | Installation of Sanitary Fixtures in Janitor Room - AP#16 (GF - Janitor Room) | 2 | 2025-06-02 | 2025-06-04
R7S1ONME-AP16GF983 | WS High Level Pipe continuation & Insulation works - AP#16 (GF - Corridor) | 4 | 2025-06-02 | 2025-06-11
R7S1ONME-AP16GF984 | Installation of Cold, Hot water line & Hot water return - AP#16 (GF - Corridor) | 4 | 2025-06-11 | 2025-06-16
R7S1ONME-AP16GF985 | Water Meter Installation - AP#16 (GF - Corridor) | 4 | 2025-06-16 | 2025-06-21
R7S1ONME-AP16GF982 | Riser Continuity in Shafts - AP#16 (GF - Corridor) | 4 | 2025-08-05 | 2025-08-09
R7S1ONME-AP16GF986 | Pressure Test for WS - AP#16 (GF - Corridor) | 4 | 2025-08-30 | 2025-09-02
R7S1ONME-AP16GF1025 | Insulation for Hot water line & Hot water return - AP#16 (GF - Corridor) | 4 | 2025-09-03 | 2025-09-07
DRAINAGE |  | 68 | 2025-06-02 | 2025-09-02
R7S1ONME-AP16GF988 | Installation of Clean-outs, Floor drain in balcony - AP#16 (GF - Corridor) | 4 | 2025-06-02 | 2025-06-11
R7S1ONME-AP16GF989 | Rain Water Riser continuation in Shafts - AP#16 (GF - Corridor) | 4 | 2025-08-05 | 2025-08-09
R7S1ONME-AP16GF990 | Drainage Riser continuation in Shafts - AP#16 (GF - Corridor) | 4 | 2025-08-05 | 2025-08-09
R7S1ONME-AP16GF991 | Testing for Rain Water Riser - AP#16 (GF - Corridor) | 4 | 2025-08-30 | 2025-09-02
R7S1ONME-AP16GF992 | Testing for Drainage Riser1 - AP#16 (GF - Corridor) | 4 | 2025-08-30 | 2025-09-02
ELECTRICAL |  | 97 | 2025-06-02 | 2025-10-04
POWER & LIGHTING |  | 97 | 2025-06-02 | 2025-10-04
R7S1ONME-AP16GF993 | Contiuation of Cable Trays & apartment branches - AP#16 (GF - Corridor) | 4 | 2025-06-02 | 2025-06-11
R7S1ONME-AP16GF994 | Contiuation of Cable Trunking with Flexible conduits for Lights - AP#16 (GF - Corridor) | 4 | 2025-06-02 | 2025-06-11
R7S1ONME-AP16GF995 | Installation of EMT pipes - AP#16 (GF - Corridor) | 5 | 2025-06-02 | 2025-06-12
R7S1ONME-AP16GF996 | Installation of Busbar, Electrical Meter & Tap-off - AP#16 (GF - Corridor) | 3 | 2025-06-28 | 2025-06-30
R7S1ONME-AP16GF1019 | Termination of Tap-off with Electrical Meter in the apartments - AP#16 (GF - Corridor) | 3 | 2025-07-01 | 2025-07-03
R7S1ONME-AP16GF997 | Corridor Wire Pulling - AP#16 (GF - Corridor) | 6 | 2025-06-29 | 2025-07-05
R7S1ONME-AP16GF1766 | Continuation of Cable Tray/Trunking with Flexible conduits for Lights (In Front of Lift Shaft) - AP#16 | 4 | 2025-07-05 | 2025-07-08
R7S1ONME-AP16GF998 | Electrical Room - Installation of Cable trays, SMDB & Termination - AP#16 (GF - Corridor) | 6 | 2025-08-10 | 2025-08-17
R7S1ONME-AP16GF1000 | Installation, Termination of Emergeny & Exit Lights with contiuity - AP#16 (GF - Corridor) | 2 | 2025-09-29 | 2025-09-30
R7S1ONME-AP16GF999 | Installation, Termination of Light Fixtures with continuity test - AP#16 (GF - Corridor & Balconies) | 3 | 2025-09-29 | 2025-10-01
R7S1ONME-AP16GF1001 | Installation, Termination of PIR sensors with continuity test - AP#16 (GF - Corridor) | 2 | 2025-10-02 | 2025-10-04
LOW CURRENT SYSTEM |  | 96 | 2025-06-02 | 2025-10-02
R7S1ONME-AP16GF1026 | CBS System cable installation - AP#16 (GF - Corridor) | 3 | 2025-06-02 | 2025-06-10
R7S1ONME-AP16GF1002 | Installation of Basket trays for BMS, CCTV, Access Control - AP#16 (GF - Corridor) | 4 | 2025-06-02 | 2025-06-11
R7S1ONME-AP16GF1004 | Fire alarm cable installation - AP#16 (GF - Corridor) | 3 | 2025-06-03 | 2025-06-11
R7S1ONME-AP16GF1003 | Voice Evacuation cable installation - AP#16 (GF - Corridor) | 3 | 2025-06-10 | 2025-06-14
R7S1ONME-AP16GF1005 | Fibre optic Cable pulling & Termination with OTO (in corridors to ONU) - AP#16 (GF - Corridor) | 2 | 2025-07-20 | 2025-07-21
R7S1ONME-AP16GF1006 | BMS, CCTV & Access control Cable installation - AP#16 (GF - Corridor) | 2 | 2025-07-20 | 2025-07-21
R7S1ONME-AP16GF1976 | Installation of Basket trays for Low Current, Cable Installation (In Front of Lift Shaft) - AP#16 | 4 | 2025-07-22 | 2025-07-26
R7S1ONME-AP16GF1007 | Low Current Works including BMS Panel in ICT Room - AP#16 (GF - Corridor) | 10 | 2025-08-09 | 2025-08-19
R7S1ONME-AP16GF1018 | Fluke test for CCTV & Fibre Optic Cable - AP#16 (GF - Corridor) (Ceiling 1st Fix) | 2 | 2025-08-18 | 2025-08-19
R7S1ONME-AP16GF1015 | Installation & Termination of Access control system for Electrical Room - AP#16 (GF) | 2 | 2025-08-19 | 2025-08-20
R7S1ONME-AP16GF1014 | Installation & Termination of CCTV Cameras - AP#16 (GF - Corridor) | 2 | 2025-09-29 | 2025-09-30
R7S1ONME-AP16GF1017 | Installation & Termination of Wireless Gateway & RF Node in corridors - AP#16 (GF - Corridor) | 2 | 2025-09-29 | 2025-09-30
R7S1ONME-AP16GF1008 | Installation & Termination of Fire alarm devices & Speakers - AP#16 (GF - Corridor) | 4 | 2025-09-29 | 2025-10-02
R7S1ONME-AP16GF1016 | Installation & Termination of Active Components & UPS installation in ICT Room - AP#16 (GF - Corridor) | 2 | 2025-10-01 | 2025-10-02
FIRST FLOOR |  | 135 | 2025-06-30 | 2025-10-11
ARCH./ CIVIL WORKS |  | 127 | 2025-07-21 | 2025-10-11
CORRIDOR AREA |  | 71 | 2025-07-21 | 2025-10-11
R7S1ONAR-AP16FF480 | Flooring in Corridor - AP#16 (FF - Corridor) | 6 | 2025-07-21 | 2025-07-28
R7S1ONAR-AP16FF481 | Corridor Skirting - AP#16 (FF - Corridor) | 2 | 2025-07-27 | 2025-07-29
R7S1ONAR-AP16FF478 | False Ceiling - 1st Fix - AP#16 (FF - Corridor) | 4 | 2025-07-29 | 2025-08-03
R7S1ONAR-AP16FF479 | Gypsum Wall Cladding (Shafts) - AP#16 (FF - Corridor) | 6 | 2025-09-13 | 2025-09-18
R7S1ONAR-AP16FF482 | Gypsum Wall Cladding (Shafts) -2nd Fix - AP#16 (FF Corridor) | 4 | 2025-09-20 | 2025-09-24
R7S1ONAR-AP16FF486 | Fixing Architrave - AP#16 (FF Corridor) | 2 | 2025-09-25 | 2025-09-27
R7S1ONAR-AP16FF487 | Fixing Aluminium Doors - AP#16 (FF Corridor) | 2 | 2025-09-28 | 2025-09-29
R7S1ONAR-AP16FF483 | False Ceiling - 2nd Fix (Closing the Ceiling) - AP#16 (FF Corridor) | 3 | 2025-09-30 | 2025-10-02
R7S1ONAR-AP16FF484 | Painting - Surface Prep., Primer & 1st Coat for Walls - AP#16 (FF Corridor) | 8 | 2025-09-25 | 2025-10-04
R7S1ONAR-AP16FF507 | Painting - Surface Prep., Primer & 1st Coat for Ceiling - AP#16 (FF Corridor) | 4 | 2025-10-04 | 2025-10-07
R7S1ONAR-AP16FF485 | Painting - Final Coat (Ceiling + Walls) - AP#16 (FF Corridor) | 3 | 2025-10-08 | 2025-10-11
INSIDE BOXES |  | 12 | 2025-08-18 | 2025-08-31
R7S1ONAR-AP16FF488 | Fixing Thresholds (Joining the Room) - AP#16 (FF - inside Boxes) | 4 | 2025-08-18 | 2025-08-21
R7S1ONAR-AP16FF489 | Fixing Wooden Doors - AP#16 (FF - inside Boxes) | 4 | 2025-08-23 | 2025-08-26
R7S1ONAR-AP16FF490 | Fixing Aluminium Doors (Next Floor) - AP#16 (FF - inside Boxes) | 4 | 2025-08-27 | 2025-08-31
IN FRONT OF LIFT SHAFT |  | 105 | 2025-08-09 | 2025-09-24
R7S1ONAR-AP16FF492 | Flooring - AP#16 (FF - Front of Lift Shaft) | 4 | 2025-08-09 | 2025-08-13
R7S1ONAR-AP16FF493 | Skirting & Thresholds - AP#16 (FF - Front of Lift Shaft) | 1 | 2025-08-12 | 2025-08-13
R7S1ONAR-AP16FF494 | Painting - Surface Prep., Primer & 1st Coat - AP#16 (FF - Front of Lift Shaft) | 4 | 2025-08-13 | 2025-08-18
R7S1ONAR-AP16FF491 | False Ceiling - 1st Fix - AP#16 (FF - Front of Lift Shaft) | 4 | 2025-08-18 | 2025-08-23
R7S1ONAR-AP16FF495 | False Ceiling - Final Fix - AP#16 (FF - Front of Lift Shaft) | 3 | 2025-08-23 | 2025-08-26
R7S1ONAR-AP16FF497 | Fixing Handrail - AP#16 (FF - Front of Lift Shaft) | 3 | 2025-09-09 | 2025-09-11
R7S1ONAR-AP16FF498 | Paint for Handrail - AP#16 (FF - Front of Lift Shaft) | 3 | 2025-09-13 | 2025-09-15
R7S1ONAR-AP16FF496 | Painting - 2nd Coat - AP#16 (FF - Front of Lift Shaft) | 2 | 2025-09-16 | 2025-09-17
R7S1ONAR-AP16FF500 | Fixing Wall Guard - AP#16 (FF - Front of Lift Shaft) | 2 | 2025-09-20 | 2025-09-21
R7S1ONAR-AP16FF499 | Fixing Floor Mat - AP#16 (FF - Front of Lift Shaft) | 2 | 2025-09-22 | 2025-09-24
GARBAGE ROOM |  | 29 | 2025-08-23 | 2025-09-02
R7S1ONAR-AP16FF501 | Installation of Dry Walls - First Fix - AP#16 (FF - Garbage Room) | 2 | 2025-08-23 | 2025-08-24
R7S1ONAR-AP16FF502 | Installation of Dry Walls - Final Fix - AP#16 (FF - Garbage Room) | 2 | 2025-08-24 | 2025-08-25
R7S1ONAR-AP16FF503 | Garbage Rooms - Wall Tile Finishes (One Side) - AP#16 (FF - Garbage Room) | 2 | 2025-08-25 | 2025-08-26
R7S1ONAR-AP16FF504 | Paint Works of Dry Walls - First Coat - AP#16 (FF - Garbage Room) | 2 | 2025-08-27 | 2025-08-28
R7S1ONAR-AP16FF505 | Installation of the Garbage Chute Door - AP#16 (FF - Garbage Room) | 2 | 2025-08-30 | 2025-08-31
R7S1ONAR-AP16FF506 | Paint Finishes and Touchups - Final Coat - AP#16 (FF - Garbage Room) | 2 | 2025-09-01 | 2025-09-02
MEP WORKS |  | 62 | 2025-06-30 | 2025-10-08
MECHANICAL |  | 61 | 2025-06-30 | 2025-10-07
CHILLED WATER |  | 28 | 2025-06-30 | 2025-08-26
R7S1ONME-AP16FF1356 | CHWP Installation/Connections and Insulation (In Front of Lift Shaft) - AP#16 | 4 | 2025-06-30 | 2025-07-03
R7S1ONME-AP16FF706 | Installation of Chilled water hanger and supports - AP#16 (FF Corridor) | 4 | 2025-08-09 | 2025-08-13
R7S1ONME-AP16FF756 | Installation of CHWP connection for FCU with Valve package in Corridor, Electrical Room & ICT Room | 4 | 2025-08-09 | 2025-08-13
R7S1ONME-AP16FF708 | Installation of BTU Meter with valves - AP#16 (FF Corridor) | 2 | 2025-08-14 | 2025-08-17
R7S1ONME-AP16FF707 | Installation of CHWP piping (connection between modular cages & modular to apartment) - AP#16 -(FF Corridor) | 4 | 2025-08-13 | 2025-08-18
R7S1ONME-AP16FF709 | CHWP piping risers connections - AP#16 (FF Corridor) | 3 | 2025-08-17 | 2025-08-20
R7S1ONME-AP16FF710 | Pressure Testing of CHWP piping - AP#16 (FF Corridor) | 1 | 2025-08-20 | 2025-08-21
R7S1ONME-AP16FF745 | CHWP Insulation - AP#16 (FF Corridor) | 4 | 2025-08-21 | 2025-08-26
HVAC DUCTING |  | 52 | 2025-08-09 | 2025-10-05
R7S1ONME-AP16FF711 | Duct Riser Continuation - AP#16 (FF Corridor) | 4 | 2025-08-09 | 2025-08-13
R7S1ONME-AP16FF757 | Installation of FCU's & Duct Connection in Corridor, Electrical Room & ICT Room - AP#16 (FF Corridor) | 4 | 2025-08-09 | 2025-08-13
R7S1ONME-AP16FF712 | A/C drain & Copper pipe connection in ELV room - AP#16 (FF Corridor) | 2 | 2025-08-13 | 2025-08-16
R7S1ONME-AP16FF758 | Installation of Ducting and insulation (connection between modular cages) - AP#16 (FF Corridor) | 3 | 2025-08-13 | 2025-08-17
R7S1ONME-AP16FF746 | Installation of Duct & Grill in Garbage Room - AP#16 (FF Corridor) | 2 | 2025-08-16 | 2025-08-18
R7S1ONME-AP16FF759 | Installation of Grilles in the Corridor - AP#16 (FF Corridor) | 2 | 2025-10-04 | 2025-10-05
FIRE FIGHTING |  | 57 | 2025-07-05 | 2025-10-07
R7S1ONME-AP16FF1566 | Installation of F.F Pipes, Testing & Final Fixtures (In Front of Lift Shaft) - AP16 | 3 | 2025-07-05 | 2025-07-07
R7S1ONME-AP16FF747 | Installation of Pipe & sprinkler in Garbage Room - AP#16 (FF Corridor) | 1 | 2025-08-09 | 2025-08-10
R7S1ONME-AP16FF713 | Riser Continuity in corridor - AP#16 (FF Corridor) | 4 | 2025-08-09 | 2025-08-13
R7S1ONME-AP16FF714 | Continuation of FF pipes & ZC Valves (connection between modular cages & modular to apartment) - AP#16 (FF Corridor) | 4 | 2025-08-09 | 2025-08-13
R7S1ONME-AP16FF715 | Installation of Sprinklers drops in corridor - AP#16 (FF Corridor) | 4 | 2025-08-13 | 2025-08-18
R7S1ONME-AP16FF716 | Pressure Test for FF Piping in corridor - AP#16 (FF Corridor) | 2 | 2025-08-18 | 2025-08-20
R7S1ONME-AP16FF760 | FF Flushing network - AP#16 (FF Corridor) | 4 | 2025-08-30 | 2025-09-02
R7S1ONME-AP16FF718 | Installation of Alarm check valve, Fire Extinguishers & Blanket (Last Stage of the Building) - AP#16 (FF Corridor) | 2 | 2025-10-04 | 2025-10-05
R7S1ONME-AP16FF717 | Installation of Sprinklers in corridor - AP#16 (FF Corridor) | 4 | 2025-10-04 | 2025-10-07
WATER SUPPLY |  | 36 | 2025-08-09 | 2025-09-11
R7S1ONME-AP16FF748 | Installation of WS Pipe in Garbage Room - AP#16 (FF Corridor) | 2 | 2025-08-09 | 2025-08-11
R7S1ONME-AP16FF749 | Installation of Sanitary Fixtures in Janitor Room - AP#16 (FF Corridor) | 2 | 2025-08-09 | 2025-08-11
R7S1ONME-AP16FF719 | Riser Continuity in Shafts - AP#16 (FF Corridor) | 4 | 2025-08-09 | 2025-08-13
R7S1ONME-AP16FF720 | WS High Level Pipe continuation & Insulation works in Corridor - AP#16 (FF Corridor) | 4 | 2025-08-09 | 2025-08-13
R7S1ONME-AP16FF721 | Installation of Cold, Hot water line & Hot water return in corridor - AP#16 (FF Corridor) | 4 | 2025-08-13 | 2025-08-18
R7S1ONME-AP16FF722 | Water Meter Installation in Corridor - AP#16 (FF Corridor) | 4 | 2025-08-18 | 2025-08-23
R7S1ONME-AP16FF723 | Pressure Test for WS - AP#16 (FF Corridor) | 4 | 2025-08-30 | 2025-09-02
R7S1ONME-AP16FF761 | Insulation for Hot water line & Hot water return in corridor - AP#16 (FF Corridor) | 4 | 2025-09-08 | 2025-09-11
DRAINAGE |  | 21 | 2025-08-09 | 2025-09-02
R7S1ONME-AP16FF724 | Installation of Clean-outs, Floor drain in balcony - AP#16 (FF Corridor) | 4 | 2025-08-09 | 2025-08-13
R7S1ONME-AP16FF725 | Rain Water Riser continuation in Shafts - AP#16 (FF Corridor) | 4 | 2025-08-09 | 2025-08-13
R7S1ONME-AP16FF726 | Drainage Riser continuation in Shafts - AP#16 (FF Corridor) | 4 | 2025-08-09 | 2025-08-13
R7S1ONME-AP16FF727 | Testing for Rain Water Riser - AP#16 (FF Corridor) | 4 | 2025-08-30 | 2025-09-02
R7S1ONME-AP16FF728 | Testing for Drainage Riser - AP#16 (FF Corridor) | 4 | 2025-08-30 | 2025-09-02
ELECTRICAL |  | 58 | 2025-07-05 | 2025-10-08
POWER & LIGHTING |  | 58 | 2025-07-05 | 2025-10-08
R7S1ONME-AP16FF1776 | Continuation of Cable Tray/Trunking with Flexible conduits for Lights (In Front of Lift Shaft) - AP#16 | 4 | 2025-07-05 | 2025-07-08
R7S1ONME-AP16FF729 | Contiuation of Cable Trays & apartment branches - AP#16 (FF Corridor) | 4 | 2025-08-09 | 2025-08-13
R7S1ONME-AP16FF730 | Contiuation of Cable Trunking with Flexible conduits for Lights - AP#16 (FF Corridor) | 4 | 2025-08-09 | 2025-08-13
R7S1ONME-AP16FF731 | Installation of EMT pipes - AP#16 (FF Corridor) | 5 | 2025-08-09 | 2025-08-14
R7S1ONME-AP16FF732 | Installation of Busbar, Electrical Meter & Tap-off - AP#16 (FF Corridor) | 3 | 2025-08-13 | 2025-08-17
R7S1ONME-AP16FF755 | Termination of Tap-off with Electrical Meter in the apartments - AP#16 (FF Corridor) | 3 | 2025-08-17 | 2025-08-20
R7S1ONME-AP16FF733 | Corridor Wire Pulling - AP#16 (FF Corridor) | 6 | 2025-08-14 | 2025-08-21
R7S1ONME-AP16FF734 | Electrical Room - Installation of Cable trays, SMDB & Termination - AP#16 (FF Corridor) | 6 | 2025-08-21 | 2025-08-28
R7S1ONME-AP16FF736 | Installation, Termination of Emergeny & Exit Lights with contiuity - AP#16 (FF Corridor) | 2 | 2025-10-04 | 2025-10-05
R7S1ONME-AP16FF735 | Installation, Termination of Light Fixtures with continuity test - AP#16 (FF - Corridor & Balconies) | 3 | 2025-10-04 | 2025-10-06
R7S1ONME-AP16FF737 | Installation, Termination of PIR sensors with continuity test - AP#16 (FF Corridor) | 2 | 2025-10-07 | 2025-10-08
LOW CURRENT SYSTEM |  | 53 | 2025-07-27 | 2025-10-07
R7S1ONME-AP16FF1986 | Installation of Basket trays for Low Current, Cable Installation (In Front of Lift Shaft) - AP#16 | 4 | 2025-07-27 | 2025-07-30
R7S1ONME-AP16FF762 | CBS System cable installation - AP#16 (FF Corridor) | 3 | 2025-08-09 | 2025-08-12
R7S1ONME-AP16FF738 | Installation of Basket trays for BMS, CCTV, Access Control - AP#16 (FF Corridor) | 4 | 2025-08-09 | 2025-08-13
R7S1ONME-AP16FF740 | Fire alarm cable installation - AP#16 (FF Corridor) | 3 | 2025-08-10 | 2025-08-13
R7S1ONME-AP16FF739 | Voice Evacuation cable installation - AP#16 (FF Corridor) | 3 | 2025-08-12 | 2025-08-16
R7S1ONME-AP16FF741 | Fibre optic Cable pulling & Termination with OTO (in corridors to ONU) - AP#16 (FF Corridor) | 2 | 2025-08-14 | 2025-08-17
R7S1ONME-AP16FF742 | BMS, CCTV & Access control Cable installation - AP#16 (FF Corridor) | 2 | 2025-08-14 | 2025-08-17
R7S1ONME-AP16FF743 | Low Current Works including BMS Panel in ICT Room - AP#16 (FF Corridor) | 10 | 2025-08-10 | 2025-08-21
R7S1ONME-AP16FF754 | Fluke test for CCTV & Fibre Optic Cable - AP#16 (FF Corridor) | 2 | 2025-08-19 | 2025-08-21
R7S1ONME-AP16FF750 | Installation & Termination of CCTV Cameras - AP#16 (FF Corridor) | 2 | 2025-10-04 | 2025-10-05
R7S1ONME-AP16FF751 | Installation & Termination of Access control system for Electrical Room - AP#16 (FF Corridor) | 2 | 2025-10-04 | 2025-10-05
R7S1ONME-AP16FF753 | Installation & Termination of Wireless Gateway & RF Node - AP#16 (FF Corridor) | 2 | 2025-10-04 | 2025-10-05
R7S1ONME-AP16FF744 | Installation & Termination of Fire alarm devices & Speakers - AP#16 (FF Corridor) | 4 | 2025-10-04 | 2025-10-07
R7S1ONME-AP16FF752 | Installation & Termination of Active Components & UPS installation in ICT Room | 2 | 2025-10-06 | 2025-10-07
SECOND FLOOR |  | 111 | 2025-07-24 | 2025-11-09
ARCH./ CIVIL WORKS |  | 99 | 2025-07-24 | 2025-11-09
CORRIDOR AREA |  | 52 | 2025-07-28 | 2025-11-09
R7S1ONAR-AP16SF384 | Flooring in Corridor - AP#16 (SF Corridor) | 6 | 2025-07-28 | 2025-08-04
R7S1ONAR-AP16SF385 | Corridor Skirting - AP#16 (SF Corridor) | 2 | 2025-08-03 | 2025-08-05
R7S1ONAR-AP16SF382 | False Ceiling - 1st Fix - AP#16 (SF Corridor) | 4 | 2025-08-05 | 2025-08-10
R7S1ONAR-AP16SF383 | Gypsum Wall Cladding (Shafts) - AP#16 (SF Corridor) | 6 | 2025-10-12 | 2025-10-18
R7S1ONAR-AP16SF386 | Gypsum Wall Cladding (Shafts) -2nd Fix - AP#16 (SF Corridor) | 4 | 2025-10-19 | 2025-10-22
R7S1ONAR-AP16SF390 | Fixing Architrave - AP#16 (SF Corridor) | 2 | 2025-10-23 | 2025-10-25
R7S1ONAR-AP16SF391 | Fixing Aluminium Doors - AP#16 (SF Corridor) | 2 | 2025-10-26 | 2025-10-27
R7S1ONAR-AP16SF387 | False Ceiling - 2nd Fix (Closing the Ceiling) - AP#16 (SF Corridor) | 3 | 2025-10-28 | 2025-10-30
R7S1ONAR-AP16SF388 | Painting - Surface Prep., Primer & 1st Coat - AP#16 (SF Corridor) | 8 | 2025-10-23 | 2025-11-01
R7S1ONAR-AP16SF412 | Painting - Surface Prep., Primer & 1st Coat - AP#16 (SF Corridor) | 4 | 2025-11-01 | 2025-11-04
R7S1ONAR-AP16SF389 | Painting - Final Coat (Ceiling + Walls) - AP#16 (SF Corridor) | 3 | 2025-11-06 | 2025-11-09
INSIDE BOXES |  | 12 | 2025-08-18 | 2025-08-31
R7S1ONAR-AP16SF392 | Fixing Thresholds (Joining the Room) - AP#16 (SF - inside Boxes) | 4 | 2025-08-18 | 2025-08-21
R7S1ONAR-AP16SF393 | Fixing Wooden Doors - AP#16 (SF - inside Boxes) | 4 | 2025-08-23 | 2025-08-26
R7S1ONAR-AP16SF394 | Fixing Aluminium Doors (Next Floor) - AP#16 (SF - inside Boxes) | 4 | 2025-08-27 | 2025-08-31
IN FRONT OF LIFT SHAFT |  | 99 | 2025-08-18 | 2025-10-16
R7S1ONAR-AP16SF396 | Flooring - AP#16 (SF - Front of Lift Shaft) | 4 | 2025-08-18 | 2025-08-21
R7S1ONAR-AP16SF397 | Skirting & Thresholds - AP#16 (SF - Front of Lift Shaft) | 2 | 2025-08-23 | 2025-08-24
R7S1ONAR-AP16SF395 | False Ceiling - 1st Fix - AP#16 (SF - Front of Lift Shaft) | 4 | 2025-08-25 | 2025-08-28
R7S1ONAR-AP16SF398 | Painting - Surface Prep., Primer & 1st Coat - AP#16 (SF - Front of Lift Shaft) | 4 | 2025-08-30 | 2025-09-02
R7S1ONAR-AP16SF399 | False Ceiling - Final Fix - AP#16 (SF - Front of Lift Shaft) | 3 | 2025-09-03 | 2025-09-06
R7S1ONAR-AP16SF401 | Fixing Handrail - AP#16 (SF - Front of Lift Shaft) | 3 | 2025-09-07 | 2025-09-09
R7S1ONAR-AP16SF402 | Paint for Handrail - AP#16 (SF - Front of Lift Shaft) | 3 | 2025-09-10 | 2025-09-13
R7S1ONAR-AP16SF400 | Painting - 2nd Coat - AP#16 (SF - Front of Lift Shaft) | 2 | 2025-10-13 | 2025-10-14
R7S1ONAR-AP16SF403 | Fixing Floor Mat - AP#16 (SF - Front of Lift Shaft) | 2 | 2025-10-15 | 2025-10-16
R7S1ONAR-AP16SF404 | Fixing Wall Guard - AP#16 (SF - Front of Lift Shaft) | 2 | 2025-10-15 | 2025-10-16
GARBAGE ROOM |  | 30 | 2025-07-24 | 2025-11-04
R7S1ONAR-AP16SF411 | Installation of Garbage Chute Full System from GF to 2nd Floor - AP#16 (SF - Garbage Room) | 10 | 2025-07-24 | 2025-08-04
R7S1ONAR-AP16SF405 | Installation of Dry Walls - First Fix - AP#16 (SF - Garbage Room) | 2 | 2025-08-05 | 2025-08-06
R7S1ONAR-AP16SF406 | Installation of Dry Walls - Final Fix - AP#16 (SF - Garbage Room) | 2 | 2025-08-07 | 2025-08-09
R7S1ONAR-AP16SF407 | Garbage Rooms - Wall Tile Finishes (One Side) - AP#16 (SF - Garbage Room) | 2 | 2025-08-09 | 2025-08-10
R7S1ONAR-AP16SF408 | Paint Works of Dry Walls - First Coat - AP#16 (SF - Garbage Room) | 2 | 2025-08-11 | 2025-08-12
R7S1ONAR-AP16SF409 | Installation of the Garbage Chute Door - AP#16 (SF - Garbage Room) | 2 | 2025-08-13 | 2025-08-14
R7S1ONAR-AP16SF410 | Paint Finishes and Touchups - Final Coat - AP#16 (SF - Garbage Room) | 2 | 2025-11-03 | 2025-11-04
MEP WORKS |  | 67 | 2025-07-31 | 2025-11-05
MECHANICAL |  | 67 | 2025-07-31 | 2025-11-04
CHILLED WATER |  | 17 | 2025-07-31 | 2025-09-03
R7S1ONME-AP16SF1366 | CHWP Installation/Connections and Insulation (In Front of Lift Shaft) - AP#16 | 4 | 2025-07-31 | 2025-08-04
R7S1ONME-AP16SF661 | Installation of Chilled water hanger and supports - AP#16 (SF Corridor) | 4 | 2025-08-18 | 2025-08-21
R7S1ONME-AP16SF711 | Installation of CHWP connection for FCU with Valve package in Corridor, Electrical Room & ICT Room | 4 | 2025-08-18 | 2025-08-21
R7S1ONME-AP16SF663 | Installation of BTU Meter with valves - AP#16 (SF Corridor) | 2 | 2025-08-24 | 2025-08-25
R7S1ONME-AP16SF662 | Installation of CHWP piping (connection between modular cages & modular to apartment) - AP#16 (SF Corridor) | 4 | 2025-08-23 | 2025-08-26
R7S1ONME-AP16SF664 | CHWP piping risers connections - AP#16 (SF Corridor) | 3 | 2025-08-26 | 2025-08-28
R7S1ONME-AP16SF665 | Pressure Testing of CHWP piping - AP#16 (SF Corridor) | 1 | 2025-08-30 | 2025-08-30
R7S1ONME-AP16SF700 | CHWP Insulation - AP#16 (SF Corridor) | 4 | 2025-08-31 | 2025-09-03
HVAC DUCTING |  | 67 | 2025-08-18 | 2025-11-02
R7S1ONME-AP16SF666 | Duct Riser Continuation - AP#16 (SF Corridor) | 4 | 2025-08-18 | 2025-08-21
R7S1ONME-AP16SF712 | Installation of FCU's & Duct Connection in Corridor, Electrical Room & ICT Room - AP#16 (SF Corridor) | 4 | 2025-08-18 | 2025-08-21
R7S1ONME-AP16SF667 | A/C drain & Copper pipe connection in ELV room - AP#16 (SF Corridor) | 2 | 2025-08-23 | 2025-08-24
R7S1ONME-AP16SF713 | Installation of Ducting and insulation (connection between modular cages) - AP#16 (SF Corridor) | 3 | 2025-08-23 | 2025-08-25
R7S1ONME-AP16SF701 | Installation of Duct & Grill in Garbage Room - AP#16 (SF Corridor) | 2 | 2025-11-01 | 2025-11-02
R7S1ONME-AP16SF714 | Installation of Grilles in the Corridor - AP#16 (SF Corridor) | 2 | 2025-11-01 | 2025-11-02
FIRE FIGHTING |  | 62 | 2025-08-05 | 2025-11-04
R7S1ONME-AP16SF1576 | Installation of F.F Pipes, Testing & Final Fixtures (In Front of Lift Shaft) - AP16 | 3 | 2025-08-05 | 2025-08-07
R7S1ONME-AP16SF668 | Riser Continuity Succ - Closing of Gysum Boards on shaft - AP#16 (SF Corridor) | 4 | 2025-08-18 | 2025-08-21
R7S1ONME-AP16SF669 | FF Contiuation on High Level with Valves - AP#16 (SF Corridor) | 4 | 2025-08-18 | 2025-08-21
R7S1ONME-AP16SF670 | Installation of Sprinklers drops - AP#16 (SF Corridor) | 4 | 2025-08-23 | 2025-08-26
R7S1ONME-AP16SF671 | Pressure Test for FF Piping - AP#16 (SF Corridor) | 2 | 2025-08-27 | 2025-08-28
R7S1ONME-AP16SF673 | Installation of Fire Extinguishers - AP#16 (SF Corridor) | 2 | 2025-11-01 | 2025-11-02
R7S1ONME-AP16SF702 | Installation of Pipe & sprinkler in Garbage Room - AP#16 (SF Corridor) | 2 | 2025-11-01 | 2025-11-02
R7S1ONME-AP16SF672 | Installation of Sprinklers - AP#16 (SF Corridor) | 4 | 2025-11-01 | 2025-11-04
WATER SUPPLY |  | 29 | 2025-08-18 | 2025-09-16
R7S1ONME-AP16SF703 | Installation of WS Pipe in Garbage Room - AP#16 (SF Corridor) | 2 | 2025-08-18 | 2025-08-19
R7S1ONME-AP16SF704 | Installation of Sanitary Fixtures in Janitor Room - AP#16 (SF Corridor) | 2 | 2025-08-18 | 2025-08-19
R7S1ONME-AP16SF674 | Riser Continuity - AP#16 (SF Corridor) | 4 | 2025-08-18 | 2025-08-21
R7S1ONME-AP16SF675 | WS High Level Pipe continuation & Insulation works - AP#16 (SF Corridor) | 4 | 2025-08-18 | 2025-08-21
R7S1ONME-AP16SF676 | Instalation of Hot water line in corridor - AP#16 (SF Corridor) | 4 | 2025-08-23 | 2025-08-26
R7S1ONME-AP16SF677 | Water Meter Installation - AP#16 (SF Corridor) | 4 | 2025-08-27 | 2025-08-31
R7S1ONME-AP16SF678 | Pressure Test for WS - AP#16 (SF Corridor) | 4 | 2025-09-03 | 2025-09-07
R7S1ONME-AP16FF763 | Insulation for Hot water line & Hot water return in corridor - AP#16 (SF Corridor) | 4 | 2025-09-13 | 2025-09-16
DRAINAGE |  | 10 | 2025-08-18 | 2025-09-02
R7S1ONME-AP16SF679 | Installation of Clean-outs - AP#16 (SF Corridor) | 4 | 2025-08-18 | 2025-08-21
R7S1ONME-AP16SF680 | Rain Water Riser continuation - AP#16 (SF Corridor) | 4 | 2025-08-18 | 2025-08-21
R7S1ONME-AP16SF681 | Drainage Riser continuation - AP#16 (SF Corridor) | 4 | 2025-08-18 | 2025-08-21
R7S1ONME-AP16SF682 | Testing for Rain Water Riser - AP#16 (SF Corridor) | 4 | 2025-08-30 | 2025-09-02
R7S1ONME-AP16SF683 | Testing for Drainage Riser - AP#16 (SF Corridor) | 4 | 2025-08-30 | 2025-09-02
ELECTRICAL |  | 45 | 2025-08-05 | 2025-11-05
POWER & LIGHTING |  | 43 | 2025-08-05 | 2025-11-05
R7S1ONME-AP16SF1786 | Continuation of Cable Tray/Trunking with Flexible conduits for Lights (In Front of Lift Shaft) - AP#16 | 4 | 2025-08-05 | 2025-08-09
R7S1ONME-AP16SF684 | Contiuation of Cable Trays & apartment branches - AP#16 (SF Corridor) | 4 | 2025-08-18 | 2025-08-21
R7S1ONME-AP16SF685 | Contiuation of Cable Trunking with Flexible conduits for Lights - AP#16 (SF Corridor) | 4 | 2025-08-18 | 2025-08-21
R7S1ONME-AP16SF686 | Installation of EMT pipes - AP#16 (SF Corridor) | 5 | 2025-08-18 | 2025-08-23
R7S1ONME-AP16SF687 | Installation of Busbar, Electrical Meter & Tap-off in Corridor - AP#16 (SF Corridor) | 3 | 2025-08-23 | 2025-08-25
R7S1ONME-AP16SF710 | Termination of Tap-off with Electrical Meter in the apartments - AP#16 (SF Corridor) | 3 | 2025-08-26 | 2025-08-28
R7S1ONME-AP16SF688 | Corridor Wire Pulling - AP#16 (SF Corridor) | 6 | 2025-08-24 | 2025-08-30
R7S1ONME-AP16SF689 | Electrical Room - Installation of Cable trays, SMDB & Termination - AP#16 (SF Corridor) | 6 | 2025-10-06 | 2025-10-12
R7S1ONME-AP16SF691 | Installation, Termination of Emergeny & Exit Lights with contiuity - AP#16 (SF Corridor) | 2 | 2025-11-01 | 2025-11-02
R7S1ONME-AP16SF690 | Installation, Termination of Light Fixtures with continuity test - AP#16 (SF - Corridor & Balconies) | 3 | 2025-11-01 | 2025-11-03
R7S1ONME-AP16SF692 | Installation, Termination of PIR sensors with continuity test - AP#16 (SF Corridor) | 2 | 2025-11-04 | 2025-11-05
LOW CURRENT SYSTEM |  | 45 | 2025-08-10 | 2025-11-04
R7S1ONME-AP16SF1996 | Installation of Basket trays for Low Current, Cable Installation (In Front of Lift Shaft) - AP#16 | 4 | 2025-08-10 | 2025-08-13
R7S1ONME-AP16SF715 | CBS System cable installation - AP#16 (SF Corridor) | 3 | 2025-08-18 | 2025-08-20
R7S1ONME-AP16SF693 | Installation of Basket trays for BMS, CCTV, Access Control - AP#16 (SF Corridor) | 4 | 2025-08-18 | 2025-08-21
R7S1ONME-AP16SF695 | Fire alarm cable installation - AP#16 (SF Corridor) | 3 | 2025-08-19 | 2025-08-21
R7S1ONME-AP16SF694 | Voice Evacuation cable installation - AP#16 (SF Corridor) | 3 | 2025-08-21 | 2025-08-24
R7S1ONME-AP16SF696 | Fibre optic Cable pulling & Termination with OTO (in corridors to ONU) - AP#16 (SF Corridor) | 2 | 2025-08-24 | 2025-08-25
R7S1ONME-AP16SF697 | BMS, CCTV & Access control Cable installation - AP#16 (SF Corridor) | 2 | 2025-08-24 | 2025-08-25
R7S1ONME-AP16SF698 | Low Current Works including BMS Panel in ICT Room - AP#16 (SF Corridor) | 10 | 2025-09-30 | 2025-10-11
R7S1ONME-AP16SF709 | Fluke test for CCTV & Fibre Optic Cable - AP#16 (SF Corridor) | 2 | 2025-10-09 | 2025-10-11
R7S1ONME-AP16SF705 | Installation & Termination of CCTV Cameras - AP#16 (SF Corridor) | 2 | 2025-11-01 | 2025-11-02
R7S1ONME-AP16SF706 | Installation & Termination of Access control system for Electrical Room - AP#16 (SF Corridor) | 2 | 2025-11-01 | 2025-11-02
R7S1ONME-AP16SF708 | Installation & Termination of Wireless Gateway & RF Node in corridors - AP#16 (SF Corridor) | 2 | 2025-11-01 | 2025-11-02
R7S1ONME-AP16SF699 | Installation & Termination of Fire alarm devices & Speakers - AP#16 (SF Corridor) | 4 | 2025-11-01 | 2025-11-04
R7S1ONME-AP16SF707 | Installation & Termination of Active Components & UPS installation in ICT Room - AP#16 (SF Corridor) | 2 | 2025-11-03 | 2025-11-04
ROOF WORKS |  | 57 | 2025-08-30 | 2025-10-28
ARCH./ CIVIL WORKS |  | 57 | 2025-08-30 | 2025-10-20
R7S1ONAR-AP16RF99 | Roof Box Stiching (Concrete Works) - AP#16 (Roof) | 5 | 2025-08-30 | 2025-09-03
R7S1ONME-AP16RF611 | Installation of Roof Drains - AP#16 (Roof) | 2 | 2025-09-02 | 2025-09-03
R7S1ONAR-AP16RF100 | Roof Waterproofing Works with testing - AP#16 (Roof) | 20 | 2025-09-04 | 2025-09-28
R7S1ONAR-AP16RF101 | Laying of Gravel - AP#16 (Roof) | 1 | 2025-09-29 | 2025-09-29
R7S1ONAR-AP16RF102 | Surface Preparation & Primer for Parapets - AP#16 (Roof) | 4 | 2025-09-30 | 2025-10-04
R7S1ONAR-AP16RF103 | 1st Coat Paint for Parapets - AP#16 (Roof) | 2 | 2025-10-05 | 2025-10-06
R7S1ONAR-AP16RF104 | 2nd Coat Paint for Parapets - AP#16 (Roof) | 2 | 2025-10-07 | 2025-10-08
R7S1ONAR-AP16RF106 | Fixing Fall Arrest System - AP#16 (Roof) | 2 | 2025-10-14 | 2025-10-15
R7S1ONAR-AP16RF105 | Crossover Bridges Installation & application of Sealant on MEP penetrations - AP#16 (Roof) | 6 | 2025-10-14 | 2025-10-20
MECHANICAL |  | 31 | 2025-09-30 | 2025-10-25
HVAC |  | 23 | 2025-09-30 | 2025-10-15
R7S1ONME-AP16RF575 | Modular Installation - AP#16 (Roof) | 5 | 2025-09-30 | 2025-10-05
R7S1ONME-AP16RF576 | Continuation of Roof duct works/FAHU Connections - AP#16 (Roof) | 5 | 2025-10-02 | 2025-10-07
R7S1ONME-AP16RF578 | Insulations for ducts - AP#16 (Roof) | 5 | 2025-10-04 | 2025-10-08
R7S1ONME-AP16RF580 | Installation of FAHU - AP#16 (Roof) | 2 | 2025-10-08 | 2025-10-09
R7S1ONME-AP16RF585 | Installation of Outdoor VRF/DX Units - AP#16 (Roof) | 2 | 2025-10-09 | 2025-10-11
R7S1ONME-AP16RF586 | Installation & Insulation of the Condensation Drain - AP#16 (Roof) | 1 | 2025-10-11 | 2025-10-11
R7S1ONME-AP16RF588 | Installation of Ventilation Fans - AP#16 (Roof) | 3 | 2025-10-08 | 2025-10-11
R7S1ONME-AP16RF583 | Chilled Water System Continuation and Connections with Valve package of FAHU - AP#16 (Roof) | 4 | 2025-10-08 | 2025-10-12
R7S1ONME-AP16RF590 | Installation of Louvers - AP#16 (Roof) | 2 | 2025-10-12 | 2025-10-13
R7S1ONME-AP16RF593 | Installation & Testing of Copper Pipes - AP#16 (Roof) | 2 | 2025-10-12 | 2025-10-13
R7S1ONME-AP16RF594 | Miscellaneous Works for Mechanical Connections (Fire & Volume Dampers etc.) - AP#16 (Roof) | 2 | 2025-10-14 | 2025-10-15
WATERSUPPLY & DRAINAGE |  | 22 | 2025-10-06 | 2025-10-21
R7S1ONME-AP16RF574 | Testing for the Rain Water Risers - AP#16 (Roof) | 2 | 2025-10-08 | 2025-10-09
R7S1ONME-AP16RF577 | Installation & Continuation of Water supply pipes (connection between modular cages & modular to Shaft Riser) - AP#16 | 4 | 2025-10-06 | 2025-10-09
R7S1ONME-AP16RF581 | Installation of Air Vent & Pressure Guage with Valves at Roof - AP#16 (Roof) | 4 | 2025-10-08 | 2025-10-12
R7S1ONME-AP16RF582 | Vertical Continuation of Vent Pipes To The Roof (Drainage) - AP#16 (Roof) | 4 | 2025-10-09 | 2025-10-13
R7S1ONME-AP16RF584 | Installation of Rain Water outlet - AP#16 (Roof) | 3 | 2025-10-11 | 2025-10-13
R7S1ONME-AP16RF579 | Installation of Air Vent with Valve for Water Supply - AP#16 (Roof) | 4 | 2025-10-11 | 2025-10-14
R7S1ONME-AP16RF587 | Testing of Water Supply Pipes - AP#16 (Roof) | 2 | 2025-10-15 | 2025-10-16
R7S1ONME-AP16RF589 | Insulation of Roof Water Line - AP#16 (Roof) | 2 | 2025-10-16 | 2025-10-18
R7S1ONME-AP16RF591 | Testing for the Drainage Pipes Risers - AP#16 (Roof) | 2 | 2025-10-19 | 2025-10-20
R7S1ONME-AP16RF592 | Installation of Vent Cowl - AP#16 (Roof) | 1 | 2025-10-21 | 2025-10-21
SOLAR HEATER |  | 19 | 2025-10-11 | 2025-10-25
R7S1ONME-AP16RF604 | Installation of Structure and Solar Panels (For Water Only) - AP#16 (Roof) | 5 | 2025-10-11 | 2025-10-15
R7S1ONME-AP16RF606 | Installation of Solar water pumps and circulation pumps with valves(For Water Only) - AP#16 (Roof) | 2 | 2025-10-14 | 2025-10-15
R7S1ONME-AP16RF605 | Installation of Solar Calorifier Tank & Air cooler (For Water Only) - AP#16 (Roof) | 5 | 2025-10-14 | 2025-10-19
R7S1ONME-AP16RF607 | Installation of Solar Pipes Primary Loop - AP#16 (Roof) | 5 | 2025-10-14 | 2025-10-19
R7S1ONME-AP16RF608 | Testing of Solar Pipes Primary Loop - AP#16 (Roof) | 1 | 2025-10-20 | 2025-10-20
R7S1ONME-AP16RF609 | Insulation of Solar Pipes Primary Loop - AP#16 (Roof) | 1 | 2025-10-20 | 2025-10-20
R7S1ONME-AP16RF610 | Aluminum Cladding of Solar Pipes Primary Loop - AP#16 (Roof) | 4 | 2025-10-21 | 2025-10-25
ELECTRICAL |  | 28 | 2025-10-06 | 2025-10-28
POWER & LOW CURRENT |  | 28 | 2025-10-06 | 2025-10-28
R7S1ONME-AP16RF595 | Installation of Cables for Fire Alarm system - AP#16 (Roof) | 3 | 2025-10-06 | 2025-10-08
R7S1ONME-AP16RF596 | Installation of Cables for BMS - AP#16 (Roof) | 3 | 2025-10-06 | 2025-10-08
R7S1ONME-AP16RF597 | Installation of Fire Alarm Devices - AP#16 (Roof) | 3 | 2025-10-06 | 2025-10-08
R7S1ONME-AP16RF599 | Installation of Roof Light Fixtures - AP#16 (Roof) | 3 | 2025-10-06 | 2025-10-08
R7S1ONME-AP16RF569 | Lightening Protection & Earthing System - AP#16 (Roof) | 4 | 2025-10-06 | 2025-10-09
R7S1ONME-AP16RF572 | Installation of Fire Alarm Containment for FAHU, Fans - AP#16 (Roof) | 4 | 2025-10-07 | 2025-10-11
R7S1ONME-AP16RF598 | Installation of BMS Devices - AP#16 (Roof) | 4 | 2025-10-07 | 2025-10-11
R7S1ONME-AP16RF602 | Termination for Fire Alarm Device - AP#16 (Roof) | 1 | 2025-10-12 | 2025-10-12
R7S1ONME-AP16RF571 | Installation of Electrical Containments for BMS - AP#16 (Roof) | 7 | 2025-10-06 | 2025-10-13
R7S1ONME-AP16RF601 | Termination for BMS System - AP#16 (Roof) | 1 | 2025-10-14 | 2025-10-14
R7S1ONME-AP16RF570 | Installation of Isolators and Machine Connections - AP#16 (Roof) | 3 | 2025-10-13 | 2025-10-15
R7S1ONME-AP16RF573 | Installation of LV Power Cables for Roof Equipment - AP#16 (Roof) | 4 | 2025-10-12 | 2025-10-15
R7S1ONME-AP16RF600 | Termination for LV Cables - AP#16 (Roof) | 1 | 2025-10-16 | 2025-10-16
R7S1ONME-AP16RF603 | Megger Test for the Power Cables - AP#16 (Roof) | 1 | 2025-10-16 | 2025-10-16
R7S1ONME-AP16RF613 | Termination of Primary & Secondary pump for Solar system - AP#16 (Roof) | 1 | 2025-10-16 | 2025-10-16
R7S1ONME-AP16RF612 | Installation & Termination of Solar System Panel - AP#16 (Roof) | 3 | 2025-10-26 | 2025-10-28
STAIR CASE |  | 88 | 2025-08-30 | 2025-10-26
CIVIL WORKS |  | 88 | 2025-09-04 | 2025-10-21
STAIR CASE (MAIN WITH LIFT) |  | 83 | 2025-09-04 | 2025-10-02
R7S1ONST-AP16RG533 | Stair Flooring (Roof to GF) - AP#16 (Main Stair) | 7 | 2025-09-04 | 2025-09-11
R7S1ONST-AP16RG534 | Stair Hand Rails (Roof to GF) - AP#16 (Main Stair) | 6 | 2025-09-13 | 2025-09-18
R7S1ONST-AP16RG535 | Stair Paint - Primer & 1st Coat (Roof to GF)- AP#16 (Main Stair) | 7 | 2025-09-20 | 2025-09-28
R7S1ONST-AP16RG536 | Stair Paint - Final Coat (Roof to GF)- AP#16 (Main Stair) | 4 | 2025-09-29 | 2025-10-02
STAIR CASE (LEFT SIDE) |  | 58 | 2025-09-13 | 2025-10-08
R7S1ONST-AP16RG543 | Stair Flooring (Roof to GF) - AP#16 Left Side Stair | 7 | 2025-09-13 | 2025-09-20
R7S1ONST-AP16RG544 | Stair Hand Rails (Roof to GF) - AP#16 Left Side Stair | 6 | 2025-09-21 | 2025-09-28
R7S1ONST-AP16RG545 | Stair Paint - Primer & 1st Coat (Roof to GF) - AP#16 Left Side Stair | 6 | 2025-09-29 | 2025-10-05
R7S1ONST-AP16RG546 | Stair Paint - Final Coat (Roof to GF) - AP#16 Left Side Stair | 3 | 2025-10-06 | 2025-10-08
STAIR CASE (RIGHT SIDE) |  | 52 | 2025-09-21 | 2025-10-21
R7S1ONST-AP16RG547 | Stair Flooring (Roof to GF) - AP#16 Right Side Stair | 8 | 2025-09-21 | 2025-09-30
R7S1ONST-AP16RG548 | Stair Hand Rails (Roof to GF) - AP#16 Right Side Stair | 7 | 2025-10-01 | 2025-10-08
R7S1ONST-AP16RG549 | Stair Paint - Primer & 1st Coat (Roof to GF) - AP#16 Right Side Stair | 7 | 2025-10-09 | 2025-10-16
R7S1ONST-AP16RG550 | Stair Paint - Final Coat (Roof to GF) - AP#16 Right Side Stair | 4 | 2025-10-18 | 2025-10-21
MEP WORKS |  | 42 | 2025-08-30 | 2025-10-26
STAIR CASE (MAIN WITH LIFT) |  | 26 | 2025-08-30 | 2025-10-07
R7S1ONST-AP16RG532 | Main Staircase Wire Pulling - AP#16 (Main Stair) | 3 | 2025-08-30 | 2025-09-01
R7S1ONST-AP16RG551 | Final fix - Main Staircase Lights Fixtures & Motion Sensor - AP#16 (Main Stair) | 2 | 2025-10-04 | 2025-10-05
R7S1ONST-AP16RG552 | Final fix - Main Staircase Emergency Lights Fixtures - AP#16 (Main Stair) | 2 | 2025-10-06 | 2025-10-07
STAIR CASE (LEFT SIDE) |  | 28 | 2025-09-02 | 2025-10-13
R7S1ONST-AP16RG537 | Left Staircase Wire Pulling - AP#16 (Main Stair) | 3 | 2025-09-02 | 2025-09-04
R7S1ONST-AP16RG539 | Final fix - Left Staircase Lights Fixtures & Motion Sensor - AP#16 (Main Stair) | 2 | 2025-10-09 | 2025-10-11
R7S1ONST-AP16RG541 | Final fix - Left Staircase Emergency Lights Fixtures - AP#16 (Main Stair) | 2 | 2025-10-12 | 2025-10-13
STAIR CASE (RIGHT SIDE) |  | 36 | 2025-09-06 | 2025-10-26
R7S1ONST-AP16RG538 | Right Staircase Wire Pulling - AP#16 (Main Stair) | 3 | 2025-09-06 | 2025-09-08
R7S1ONST-AP16RG540 | Final fix - Right Staircase Lights Fixtures & Motion Sensor - AP#16 (Main Stair) | 2 | 2025-10-22 | 2025-10-23
R7S1ONST-AP16RG542 | Final fix - Right Staircase Emergency Lights Fixtures - AP#16 (Main Stair) | 2 | 2025-10-25 | 2025-10-26
ELEVATOR WORKS |  | 24 | 2025-10-07 | 2025-11-01
R7S1ONEL-AP16GR667 | Installation of Rails - AP#16 (Elevator Works) | 6 | 2025-10-07 | 2025-10-13
R7S1ONEL-AP16GR668 | Assembly of Cabin - AP#16 (Elevator Works) | 4 | 2025-10-14 | 2025-10-18
R7S1ONEL-AP16GR669 | Installation of Motor - AP#16 (Elevator Works) | 4 | 2025-10-19 | 2025-10-22
R7S1ONEL-AP16GR670 | Installation of Main Cables - AP#16 (Elevator Works) | 4 | 2025-10-23 | 2025-10-27
R7S1ONEL-AP16GR671 | Installation of Doors, Indicator, Push Button - AP#16 (Elevator Works) | 2 | 2025-10-28 | 2025-10-29
R7S1ONEL-AP16GR672 | Interior Finishes - AP#16 (Elevator Works) | 2 | 2025-10-30 | 2025-11-01
EXTERNAL ELEVATIONS |  | 97 | 2025-09-30 | 2025-11-12
ARCH./ CIVIL WORKS |  | 97 | 2025-09-30 | 2025-11-12
R7S1ONEE-AP16GR545 | External Selant Works - For Boxes - AP#16 (External Elevations) | 15 | 2025-09-30 | 2025-10-16
R7S1ONEE-AP16GR546 | Final Finishes & Touchups - AP#16 (External Elevations) | 15 | 2025-10-18 | 2025-11-03
R7S1ONME-AP16GF987 | Installation of rain water outlet - External façade - AP#16 (External Elevations) | 2 | 2025-11-04 | 2025-11-05
R7S1ONEE-AP16GR548 | Installation of External Signages - AP#16 (External Elevations) | 4 | 2025-11-06 | 2025-11-10
R7S1ONEE-AP16GR547 | Fixing Cage Ladder - AP#16 (External Elevations) | 2 | 2025-11-11 | 2025-11-12
EXTERNAL - CIVIL WORKS |  | 54 | 2025-08-19 | 2025-10-21
DRAINAGE |  | 9 | 2025-08-19 | 2025-09-02
R7S1ONECW-AP16-469 | Excavation Works & Sand Bedding - AP#16 (External Drainage) | 3 | 2025-08-19 | 2025-08-21
R7S1ONECW-AP16-470 | Drainage Manholes - AP#16 | 6 | 2025-08-20 | 2025-08-26
R7S1ONECW-AP16-471 | Drainage Backfilling - AP#16 | 2 | 2025-09-01 | 2025-09-02
WATERSUPPLY |  | 22 | 2025-08-30 | 2025-09-24
R7S1ONECW-AP16-472 | Excavation Works & Sand Bedding - Watersupply - AP#16 (External Watersupply Civil) | 3 | 2025-08-30 | 2025-09-01
R7S1ONECW-AP16-473 | Watersupply Manholes - AP#16 | 6 | 2025-09-02 | 2025-09-08
R7S1ONECW-AP16-474 | Watersupply Backfilling - AP#16 | 2 | 2025-09-22 | 2025-09-24
CHILLED WATER |  | 9 | 2025-09-02 | 2025-09-14
R7S1ONECW-AP16-478 | Excavation Works & Sand Bedding - AP#16 (External Chilled Water Civil) | 3 | 2025-09-02 | 2025-09-04
R7S1ONECW-AP16-479 | Chilled Water Manholes - AP#16 | 6 | 2025-09-06 | 2025-09-11
R7S1ONECW-AP16-480 | Chilled Water Backfilling - AP#16 | 2 | 2025-09-13 | 2025-09-14
FIRE FIGHTING |  | 10 | 2025-09-02 | 2025-09-20
R7S1ONECW-AP16-475 | Excavation Works & Sand Bedding - AP#16 (External Chilled Water Civil) | 3 | 2025-09-02 | 2025-09-04
R7S1ONECW-AP16-476 | Fire Fighting Manholes - AP#16 | 6 | 2025-09-06 | 2025-09-11
R7S1ONECW-AP16-477 | Fire Fighting Backfilling - AP#16 | 2 | 2025-09-18 | 2025-09-20
POWER |  | 39 | 2025-09-06 | 2025-10-21
R7S1ONECW-AP16-481 | Excavation Works & Sand Bedding - AP#16 (External Power Civil) | 3 | 2025-09-06 | 2025-09-08
R7S1ONECW-AP16-482 | Power Manholes - AP#16 | 3 | 2025-09-09 | 2025-09-11
R7S1ONECW-AP16-483 | Power Backfilling - AP#16 | 2 | 2025-10-20 | 2025-10-21
LOW CURRENT |  | 8 | 2025-09-06 | 2025-09-14
R7S1ONECW-AP16-484 | Excavation Works & Sand Bedding - AP#16 (External Low Current Civil) | 3 | 2025-09-06 | 2025-09-08
R7S1ONECW-AP16-485 | Low Current Manholes - AP#16 | 3 | 2025-09-09 | 2025-09-11
R7S1ONECW-AP16-486 | Low Current Backfilling - AP#16 | 2 | 2025-09-13 | 2025-09-14
EXTERNAL - MEP SERVICES |  | 47 | 2025-08-27 | 2025-10-19
DRAINAGE |  | 4 | 2025-08-27 | 2025-08-31
R7S1ONEME-AP16-301 | External Drainage Network - AP#16 (External Drainage MEP) | 4 | 2025-08-27 | 2025-08-31
WATERSUPPLY |  | 7 | 2025-09-09 | 2025-09-24
R7S1ONEME-AP16-302 | PRV statiuon assembly including meters- AP#16 (External WS MEP) | 4 | 2025-09-09 | 2025-09-13
R7S1ONEME-AP16-304 | Installation of valve station incl. BTU meter- AP#16 (External WS MEP) | 3 | 2025-09-21 | 2025-09-24
CHILLED WATER |  | 7 | 2025-09-14 | 2025-09-21
R7S1ONEME-AP16-303 | Installation of Chilled water line- AP#16 (External CWP MEP) | 6 | 2025-09-14 | 2025-09-20
R7S1ONEME-AP16-305 | Pressure Test for chilled water line- AP#16 (External CWP MEP) | 1 | 2025-09-21 | 2025-09-21
FIRE FIGHTING |  | 11 | 2025-09-06 | 2025-09-17
R7S1ONEME-AP16-306 | Installation of External FF network - AP#16 (External FF MEP) | 6 | 2025-09-06 | 2025-09-11
R7S1ONEME-AP16-307 | Installation of Alarm check valves- AP#16 (External FF MEP) | 3 | 2025-09-13 | 2025-09-15
R7S1ONEME-AP16-308 | Testing of External FF - AP#16 (External FF MEP) | 2 | 2025-09-16 | 2025-09-17
POWER |  | 1 | 2025-10-19 | 2025-10-19
R7S1ONEME-AP16-309 | Cable pulling from Manhole to the building MDB - AP#16 (External Power MEP) | 1 | 2025-10-19 | 2025-10-19
LOW CURRENT |  | 3 | 2025-09-09 | 2025-09-11
R7S1ONEME-AP16-310 | Low Current Cable pulling- AP#16 (External FF MEP) | 3 | 2025-09-09 | 2025-09-11
BUILDING # AP17 (LARGE STUDIO) |  | 334 | 2024-12-14 | 2025-11-20
SUB-STRUCTURE |  | 113 | 2024-12-14 | 2025-04-30
R7S1-ONSB-AP17-292 | Site Setting Out Works - AP#17 | 2 | 2024-12-14 | 2024-12-15
R7S1-ONSB-AP17-289 | Site levelling & earthworks - AP#17 | 5 | 2024-12-15 | 2024-12-19
R7S1-ONSB-AP17-293 | Anti-termite & Polythene Sheet Works - AP#17 | 1 | 2025-01-12 | 2025-01-12
R7S1-ONSB-AP17-290 | Blinding PCC - AP#17 | 4 | 2025-01-13 | 2025-01-16
R7S1-ONSB-AP17-291 | Waterproofing for Blinding PCC (Bitumen Paint) - AP#17 | 2 | 2025-01-18 | 2025-01-19
R7S1-ONSB-AP17-294 | Foundations/Upstands - Rebar - AP#17 | 44 | 2025-02-08 | 2025-04-06
R7S1-ONSB-AP17-295 | Foundations/Upstands - Shuttering (Including dowel Works) - AP#17 | 44 | 2025-02-09 | 2025-04-07
R7S1-ONSB-AP17-298 | Installation of MEP U/G services below Boxes - AP#17 | 40 | 2025-02-16 | 2025-04-09
R7S1-ONSB-AP17-296 | Foundations/Upstands - Casting - AP#17 | 42 | 2025-02-19 | 2025-04-15
R7S1-ONSB-AP17-297 | Waterproofing For Foundations/Upstands - AP#17 | 45 | 2025-02-20 | 2025-04-19
R7S1-ONSB-AP17-299 | Backfilling & Compaction - AP#17 | 10 | 2025-04-19 | 2025-04-30
SLAB-ON-GRADE & UG MEP WORKS (in Corridor) |  | 14 | 2025-05-24 | 2025-06-14
LEFT SIDE |  | 14 | 2025-05-24 | 2025-06-04
R7S1-ONSG-AP17-350 | Backfilling & SOG (In Front of Lift Shaft) - AP#17 | 3 | 2025-05-24 | 2025-05-26
R7S1-ONSG-AP17-361 | Block Work below Corridor area - AP#17 | 1 | 2025-05-27 | 2025-05-28
R7S1-ONSG-AP17-367 | Backfilling upto Pipe Level - AP#17 | 1 | 2025-05-28 | 2025-05-29
R7S1-ONSG-AP17-375 | Plaster Work for Blockwork - AP#17 | 1 | 2025-05-28 | 2025-05-29
R7S1-ONSG-AP17-362 | UG MEP Works (Laying of Pipes) - AP#17 | 2 | 2025-05-28 | 2025-05-31
R7S1-ONSG-AP17-363 | Backfilling Works after Pipe Laying - AP#17 | 1 | 2025-05-31 | 2025-06-01
R7S1-ONSG-AP17-364 | Antitermite Works - AP#17 | 1 | 2025-05-31 | 2025-06-01
R7S1-ONSG-AP17-365 | Polythene & Rebar Mesh Works - AP#17 | 2 | 2025-06-01 | 2025-06-03
R7S1-ONSG-AP17-366 | Pouring SOG Concrete - AP#17 | 1 | 2025-06-03 | 2025-06-04
RIGHT SIDE |  | 9 | 2025-06-01 | 2025-06-14
R7S1-ONSG-AP17-368 | Block Work below Corridor area - AP#17 | 2 | 2025-06-01 | 2025-06-03
R7S1-ONSG-AP17-374 | Backfilling upto Pipe Level - AP#17 | 1 | 2025-06-03 | 2025-06-04
R7S1-ONSG-AP17-369 | UG MEP Works (Laying of Pipes) - AP#17 | 1 | 2025-06-04 | 2025-06-10
R7S1-ONSG-AP17-370 | Backfilling Works after Pipe Laying - AP#17 | 1 | 2025-06-10 | 2025-06-11
R7S1-ONSG-AP17-371 | Antitermite Works - AP#17 | 1 | 2025-06-10 | 2025-06-11
R7S1-ONSG-AP17-372 | Polythene & Rebar Mesh Works - AP#17 | 1 | 2025-06-11 | 2025-06-12
R7S1-ONSG-AP17-373 | Pouring SOG Concrete - AP#17 | 1 | 2025-06-12 | 2025-06-14
ERECTION WORKS |  | 88 | 2025-05-21 | 2025-09-03
GROUND FLOOR |  | 45 | 2025-05-21 | 2025-06-17
R7S1ONER-AP17GF382 | Erection of Columns/Beams Frame & Slab/Loose Elements (In Front of Lift Shaft) - AP#17 | 2 | 2025-05-21 | 2025-05-22
R7S1ONER-AP17GF199 | Erection of GF Boxes (Left Side) including Lift Box & Staircase - AP#17 - Large Studio | 4 | 2025-05-22 | 2025-05-27
R7S1ONER-AP17GF200 | Erection of GF Boxes (Right Side) - AP#17 - Large Studio | 4 | 2025-05-27 | 2025-06-01
R7S1ONER-AP17GF201 | Erection of GF MEP Modular Cages (Left Side) - AP#17 | 2 | 2025-06-04 | 2025-06-11
R7S1ONER-AP17GF202 | Erection of GF Corridor Slabs (Left Side) - AP#17 | 2 | 2025-06-10 | 2025-06-12
R7S1ONER-AP17GF203 | Erection of GF MEP Modular Cages (Right Side) - AP#17 | 2 | 2025-06-14 | 2025-06-16
R7S1ONER-AP17GF204 | Erection of GF Corridor Slabs Right Side) - AP#17 | 2 | 2025-06-15 | 2025-06-17
FIRST FLOOR |  | 22 | 2025-05-24 | 2025-07-19
R7S1ONER-AP17FF392 | Erection of Columns/Beams Frame & Slab/Loose Elements (In Front of Lift Shaft) - AP#17 | 2 | 2025-05-24 | 2025-05-25
R7S1ONER-AP17FF199 | Erection of FF Boxes (Left Side) - AP#17 - Large Studio | 2 | 2025-07-09 | 2025-07-12
R7S1ONER-AP17FF200 | Erection of FF Boxes (Right Side) - AP#17 - Large Studio | 2 | 2025-07-12 | 2025-07-14
R7S1ONER-AP17FF201 | Erection of FF MEP Modular Cages (Left Side) - AP#17 | 2 | 2025-07-12 | 2025-07-14
R7S1ONER-AP17FF202 | Erection of FF Corridor Slabs (Left Side) - AP#17 | 2 | 2025-07-14 | 2025-07-16
R7S1ONER-AP17FF203 | Erection of FF MEP Modular Cages (Right Side) - AP#17 | 2 | 2025-07-14 | 2025-07-16
R7S1ONER-AP17FF204 | Erection of FF Corridor Slabs Right Side) - AP#17 | 2 | 2025-07-16 | 2025-07-19
SECOND FLOOR |  | 23 | 2025-05-26 | 2025-08-20
R7S1ONER-AP17SF402 | Erection of Columns/Beams Frame & Slab/Loose Elements (In Front of Lift Shaft) - AP#17 | 2 | 2025-05-26 | 2025-05-27
R7S1ONER-AP17SF199 | Erection of SF Boxes (Left Side) - AP#17 - Large Studio | 2 | 2025-08-10 | 2025-08-11
R7S1ONER-AP17SF200 | Erection of SF Boxes (Right Side) - AP#17 - Large Studio | 2 | 2025-08-12 | 2025-08-13
R7S1ONER-AP17SF201 | Erection of SF MEP Modular Cages (Left Side) - AP#17 | 3 | 2025-08-12 | 2025-08-14
R7S1ONER-AP17SF202 | Erection of SF Corridor Slabs (Left Side) - AP#17 | 2 | 2025-08-16 | 2025-08-17
R7S1ONER-AP17SF203 | Erection of SF MEP Modular Cages (Right Side) - AP#17 | 2 | 2025-08-17 | 2025-08-18
R7S1ONER-AP17SF204 | Erection of SF Corridor Slabs Right Side) - AP#17 | 2 | 2025-08-19 | 2025-08-20
ROOF |  | 12 | 2025-08-21 | 2025-09-03
R7S1ONER-AP17RF109 | Erection of Loose Roof Parapets, Shaft Covers, MEP Foundation etc. - AP#17 Roof | 12 | 2025-08-21 | 2025-09-03
MEP WORKS & FINISHES |  | 176 | 2025-05-27 | 2025-11-16
GROUND FLOOR |  | 172 | 2025-05-27 | 2025-10-14
ARCH./ CIVIL WORKS |  | 137 | 2025-05-27 | 2025-10-14
CORRIDOR AREA |  | 62 | 2025-07-21 | 2025-10-14
R7S1ONAR-AP17GF279 | Flooring in Corridor - AP#17 (GF Corridor) | 6 | 2025-07-21 | 2025-07-28
R7S1ONAR-AP17GF280 | Corridor Skirting - AP#17 (GF Corridor) | 2 | 2025-07-27 | 2025-07-29
R7S1ONAR-AP17GF277 | False Ceiling - 1st Fix - AP#17 (GF - Corridor) | 4 | 2025-07-29 | 2025-08-03
R7S1ONAR-AP17GF278 | Gypsum Wall Cladding - 1st Fix (Shafts) - AP#17 (GF Corridor) | 6 | 2025-09-15 | 2025-09-21
R7S1ONAR-AP17GF281 | Gypsum Wall Cladding (Shafts) -2nd Fix - AP#17 (GF Corridor) | 4 | 2025-09-22 | 2025-09-27
R7S1ONAR-AP17GF285 | Fixing Architrave - AP#17 (GF Corridor) | 2 | 2025-09-28 | 2025-09-29
R7S1ONAR-AP17GF286 | Fixing Aluminium Doors - AP#17 (GF Corridor) | 2 | 2025-09-30 | 2025-10-01
R7S1ONAR-AP17GF282 | False Ceiling - 2nd Fix (Closing the Ceiling) - AP#17 (GF Corridor) | 3 | 2025-10-02 | 2025-10-05
R7S1ONAR-AP17GF283 | Painting - Surface Prep., Primer & 1st Coat - AP#17 (GF Corridor) | 8 | 2025-09-28 | 2025-10-06
R7S1ONAR-AP17GF301 | Painting - Surface Prep., Primer & 1st Coat for Ceiling - AP#17 (GF Corridor) | 4 | 2025-10-06 | 2025-10-09
R7S1ONAR-AP17GF284 | Painting - Final Coat (Ceiling + Walls) - AP#17 (GF Corridor) | 3 | 2025-10-12 | 2025-10-14
INSIDE BOXES |  | 12 | 2025-07-28 | 2025-08-11
R7S1ONAR-AP17GF287 | Fixing Thresholds (Joining the Room) - AP#17 (GF - inside Boxes) | 4 | 2025-07-28 | 2025-08-02
R7S1ONAR-AP17GF288 | Fixing Wooden Doors - AP#17 (GF - inside Boxes) | 4 | 2025-08-02 | 2025-08-06
R7S1ONAR-AP17GF289 | Fixing Aluminium Doors - AP#17 (GF - inside Boxes) | 4 | 2025-08-06 | 2025-08-11
IN FRONT OF LIFT SHAFT |  | 105 | 2025-05-27 | 2025-09-16
R7S1ONAR-AP17GF291 | Flooring - AP#17 (GF - Front of Lift Shaft) | 4 | 2025-05-27 | 2025-05-31
R7S1ONAR-AP17GF292 | Skirting & Thresholds - AP#17 (GF - Front of Lift Shaft) | 1 | 2025-05-31 | 2025-05-31
R7S1ONAR-AP17GF293 | Painting - Surface Prep., Primer & 1st Coat - AP#17 (GF - Front of Lift Shaft) | 4 | 2025-06-01 | 2025-06-04
R7S1ONAR-AP17GF290 | False Ceiling - 1st Fix - AP#17 (GF - Front of Lift Shaft) | 4 | 2025-06-10 | 2025-06-14
R7S1ONAR-AP17GF294 | False Ceiling - Final Fix - AP#17 (GF - Front of Lift Shaft) | 3 | 2025-06-15 | 2025-06-17
R7S1ONAR-AP17GF296 | Fixing Handrail - AP#17 (GF - Front of Lift Shaft) | 3 | 2025-06-18 | 2025-06-21
R7S1ONAR-AP17GF297 | Paint for Handrail - AP#17 (GF - Front of Lift Shaft) | 2 | 2025-06-22 | 2025-06-23
R7S1ONAR-AP17GF295 | Painting - Final Coat - AP#17 (GF - Front of Lift Shaft) | 2 | 2025-09-10 | 2025-09-11
R7S1ONAR-AP17GF299 | Fixing Wall Guard - AP#17 (GF - Front of Lift Shaft) | 2 | 2025-09-13 | 2025-09-14
R7S1ONAR-AP17GF298 | Fixing Floor Mat - AP#17 (GF - Front of Lift Shaft) | 2 | 2025-09-15 | 2025-09-16
GARBAGE ROOM |  | 2 | 2025-09-07 | 2025-09-08
R7S1ONAR-AP17GF300 | Paint Finishes and Touchups - Final Coat - AP#17 (GF - Garbage Room) | 2 | 2025-09-07 | 2025-09-08
MEP WORKS |  | 98 | 2025-06-17 | 2025-10-11
MECHANICAL |  | 98 | 2025-06-17 | 2025-10-09
CHILLED WATER |  | 64 | 2025-06-17 | 2025-08-23
R7S1ONME-AP17GF795 | Installation of Chilled water hanger and supports - AP#17 (GF - Corridor) | 4 | 2025-06-17 | 2025-06-22
R7S1ONME-AP17GF847 | Installation of CHWP connection for FCU with Valve package in Corridor, Electrical Room & ICT Room - AP#17 (GF) | 4 | 2025-06-17 | 2025-06-22
R7S1ONME-AP17GF797 | Installation of BTU Meter with valves - AP#17 (GF - Corridor) | 2 | 2025-06-23 | 2025-06-25
R7S1ONME-AP17GF796 | Installation of CHWP piping (connection between modular cages & modular to apartment) - AP#17 (GF - Corridor) | 4 | 2025-06-22 | 2025-06-26
R7S1ONME-AP17GF798 | CHWP piping risers connections - AP#17 (GF - Corridor) | 3 | 2025-06-25 | 2025-06-29
R7S1ONME-AP17GF799 | Pressure Testing of CHWP piping - AP#17 (GF - Corridor) | 1 | 2025-06-29 | 2025-06-30
R7S1ONME-AP17GF835 | CHWP Insulation - AP#17 (GF - Corridor) | 4 | 2025-06-30 | 2025-07-05
R7S1ONME-AP17GF1376 | CHWP Installation/Connections and Insulation (In Front of Lift Shaft) - AP#17 | 4 | 2025-08-19 | 2025-08-23
HVAC DUCTING |  | 95 | 2025-06-17 | 2025-10-07
R7S1ONME-AP17GF846 | Installation of FCU's & Duct Connection in Corridor, Electrical Room & ICT Room - AP#17 (GF) | 4 | 2025-06-17 | 2025-06-22
R7S1ONME-AP17GF848 | Installation of Ducting and insulation (connection between modular cages) - AP#17 (GF - Corridor) | 3 | 2025-06-22 | 2025-06-25
R7S1ONME-AP17GF800 | Duct Riser Continuation - AP#17 (GF - Corridor) | 4 | 2025-07-12 | 2025-07-16
R7S1ONME-AP17GF801 | A/C drain & Copper pipe connection in ELV room - AP#17 (GF) | 2 | 2025-07-16 | 2025-07-19
R7S1ONME-AP17GF836 | Installation of Duct & Grill in Garbage Room - AP#17 (GF - Garbage Room) | 2 | 2025-07-19 | 2025-07-21
R7S1ONME-AP17GF849 | Installation of Grilles in the Corridor - AP#17 (GF - Corridor) | 2 | 2025-10-06 | 2025-10-07
FIRE FIGHTING |  | 80 | 2025-07-12 | 2025-10-09
R7S1ONME-AP17GF802 | Riser Continuity in corridor - AP#17 (GF - Corridor) | 4 | 2025-07-12 | 2025-07-16
R7S1ONME-AP17GF803 | Continuitu of FF pipes & ZC Valves (connection between modular cages & modular to apartment) - AP#17 (GF - Corridor) | 4 | 2025-07-12 | 2025-07-16
R7S1ONME-AP17GF804 | Installation of Sprinklers drops in corridor - AP#17 (GF - Corridor) | 4 | 2025-08-03 | 2025-08-07
R7S1ONME-AP17GF805 | Pressure Test for FF Piping in corridor - AP#17 (GF - Corridor) | 2 | 2025-08-07 | 2025-08-10
R7S1ONME-AP17GF837 | Installation of Pipe & sprinkler in Garbage Room - AP#17 (GF - Garbage Room) | 1 | 2025-08-10 | 2025-08-10
R7S1ONME-AP17GF1586 | Installation of F.F Pipes, Testing & Final Fixtures (In Front of Lift Shaft) - AP17 | 3 | 2025-08-24 | 2025-08-26
R7S1ONME-AP17GF850 | FF Flushing network - AP#17 (GF - Corridor) | 1 | 2025-09-02 | 2025-09-02
R7S1ONME-AP17GF807 | Installation of Alarm check valve, Fire Extinguishers & Blanket - AP#17 (GF - Corridor) | 2 | 2025-10-06 | 2025-10-07
R7S1ONME-AP17GF806 | Installation of Sprinklers in corridor - AP#17 (GF - Corridor) | 4 | 2025-10-06 | 2025-10-09
WATER SUPPLY |  | 67 | 2025-06-17 | 2025-09-13
R7S1ONME-AP17GF838 | Installation of WS Pipe in Garbage Room - AP#17 (GF - Garbage Room) | 2 | 2025-06-17 | 2025-06-19
R7S1ONME-AP17GF839 | Installation of Sanitary Fixtures in Janitor Room - AP#17 (GF - Janitor Room) | 2 | 2025-06-17 | 2025-06-19
R7S1ONME-AP17GF809 | WS High Level Pipe continuation & Insulation works - AP#17 (GF - Corridor) | 4 | 2025-06-17 | 2025-06-22
R7S1ONME-AP17GF810 | Installation of Cold, Hot water line & Hot water return - AP#17 (GF - Corridor) | 4 | 2025-06-22 | 2025-06-26
R7S1ONME-AP17GF811 | Water Meter Installation - AP#17 (GF - Corridor) | 4 | 2025-06-26 | 2025-07-01
R7S1ONME-AP17GF808 | Riser Continuity in Shafts - AP#17 (GF - Corridor) | 4 | 2025-07-12 | 2025-07-16
R7S1ONME-AP17GF812 | Pressure Test for WS - AP#17 (GF - Corridor) | 4 | 2025-09-04 | 2025-09-08
R7S1ONME-AP17GF851 | Insulation for Hot water line & Hot water return - AP#17 (GF - Corridor) | 4 | 2025-09-09 | 2025-09-13
DRAINAGE |  | 64 | 2025-06-17 | 2025-09-08
R7S1ONME-AP17GF814 | Installation of Clean-outs, Floor drain in balcony - AP#17 (GF - Corridor) | 4 | 2025-06-17 | 2025-06-22
R7S1ONME-AP17GF815 | Rain Water Riser continuation in Shafts - AP#17 (GF - Corridor) | 4 | 2025-07-12 | 2025-07-16
R7S1ONME-AP17GF816 | Drainage Riser continuation in Shafts - AP#17 (GF - Corridor) | 4 | 2025-07-12 | 2025-07-16
R7S1ONME-AP17GF817 | Testing for Rain Water Riser - AP#17 (GF - Corridor) | 4 | 2025-09-04 | 2025-09-08
R7S1ONME-AP17GF818 | Testing for Drainage Riser1 - AP#17 (GF - Corridor) | 4 | 2025-09-04 | 2025-09-08
ELECTRICAL |  | 93 | 2025-06-17 | 2025-10-11
POWER & LIGHTING |  | 91 | 2025-06-17 | 2025-10-11
R7S1ONME-AP17GF819 | Contiuation of Cable Trays & apartment branches - AP#17 (GF - Corridor) | 4 | 2025-06-17 | 2025-06-22
R7S1ONME-AP17GF820 | Contiuation of Cable Trunking with Flexible conduits for Lights - AP#17 (GF - Corridor) | 4 | 2025-06-17 | 2025-06-22
R7S1ONME-AP17GF821 | Installation of EMT pipes - AP#17 (GF - Corridor) | 5 | 2025-06-17 | 2025-06-23
R7S1ONME-AP17GF1796 | Continuation of Cable Tray/Trunking with Flexible conduits for Lights (In Front of Lift Shaft) - AP#17 | 4 | 2025-08-10 | 2025-08-13
R7S1ONME-AP17GF822 | Installation of Busbar, Electrical Meter & Tap-off - AP#17 (GF - Corridor) | 3 | 2025-08-26 | 2025-08-28
R7S1ONME-AP17GF845 | Termination of Tap-off with Electrical Meter in the apartments - AP#17 (GF - Corridor) | 3 | 2025-08-30 | 2025-09-01
R7S1ONME-AP17GF823 | Corridor Wire Pulling - AP#17 (GF - Corridor) | 6 | 2025-08-27 | 2025-09-02
R7S1ONME-AP17GF824 | Electrical Room - Installation of Cable trays, SMDB & Termination - AP#17 (GF - Corridor) | 6 | 2025-09-03 | 2025-09-09
R7S1ONME-AP17GF826 | Installation, Termination of Emergeny & Exit Lights with contiuity - AP#17 (GF - Corridor) | 2 | 2025-10-06 | 2025-10-07
R7S1ONME-AP17GF825 | Installation, Termination of Light Fixtures with continuity test - AP#17 (GF - Corridor & Balconies) | 3 | 2025-10-06 | 2025-10-08
R7S1ONME-AP17GF827 | Installation, Termination of PIR sensors with continuity test - AP#17 (GF - Corridor) | 2 | 2025-10-09 | 2025-10-11
LOW CURRENT SYSTEM |  | 93 | 2025-06-17 | 2025-10-09
R7S1ONME-AP17GF852 | CBS System cable installation - AP#17 (GF - Corridor) | 3 | 2025-06-17 | 2025-06-21
R7S1ONME-AP17GF828 | Installation of Basket trays for BMS, CCTV, Access Control - AP#17 (GF - Corridor) | 4 | 2025-06-17 | 2025-06-22
R7S1ONME-AP17GF830 | Fire alarm cable installation - AP#17 (GF - Corridor) | 3 | 2025-06-18 | 2025-06-22
R7S1ONME-AP17GF829 | Voice Evacuation cable installation - AP#17 (GF - Corridor) | 3 | 2025-06-21 | 2025-06-24
R7S1ONME-AP17GF2006 | Installation of Basket trays for Low Current, Cable Installation (In Front of Lift Shaft) - AP#17 | 4 | 2025-08-14 | 2025-08-18
R7S1ONME-AP17GF831 | Fibre optic Cable pulling & Termination with OTO (in corridors to ONU) - AP#17 (GF - Corridor) | 2 | 2025-08-26 | 2025-08-27
R7S1ONME-AP17GF832 | BMS, CCTV & Access control Cable installation - AP#17 (GF - Corridor) | 2 | 2025-08-26 | 2025-08-27
R7S1ONME-AP17GF833 | Low Current Works including BMS Panel in ICT Room - AP#17 (GF - Corridor) | 10 | 2025-08-21 | 2025-09-01
R7S1ONME-AP17GF844 | Fluke test for CCTV & Fibre Optic Cable - AP#17 (GF - Corridor) (Ceiling 1st Fix) | 2 | 2025-08-31 | 2025-09-01
R7S1ONME-AP17GF841 | Installation & Termination of Access control system for Electrical Room - AP#17 (GF) | 2 | 2025-09-01 | 2025-09-02
R7S1ONME-AP17GF840 | Installation & Termination of CCTV Cameras - AP#17 (GF - Corridor) | 2 | 2025-10-06 | 2025-10-07
R7S1ONME-AP17GF843 | Installation & Termination of Wireless Gateway & RF Node in corridors - AP#17 (GF - Corridor) | 2 | 2025-10-06 | 2025-10-07
R7S1ONME-AP17GF834 | Installation & Termination of Fire alarm devices & Speakers - AP#17 (GF - Corridor) | 4 | 2025-10-06 | 2025-10-09
R7S1ONME-AP17GF842 | Installation & Termination of Active Components & UPS installation in ICT Room - AP#17 (GF - Corridor) | 2 | 2025-10-08 | 2025-10-09
FIRST FLOOR |  | 147 | 2025-07-05 | 2025-10-18
ARCH./ CIVIL WORKS |  | 133 | 2025-07-19 | 2025-10-18
CORRIDOR AREA |  | 61 | 2025-07-28 | 2025-10-18
R7S1ONAR-AP17FF390 | Flooring in Corridor - AP#17 (FF - Corridor) | 6 | 2025-07-28 | 2025-08-04
R7S1ONAR-AP17FF391 | Corridor Skirting - AP#17 (FF - Corridor) | 2 | 2025-08-03 | 2025-08-05
R7S1ONAR-AP17FF388 | False Ceiling - 1st Fix - AP#17 (FF - Corridor) | 4 | 2025-08-05 | 2025-08-10
R7S1ONAR-AP17FF389 | Gypsum Wall Cladding (Shafts) - AP#17 (FF - Corridor) | 6 | 2025-09-18 | 2025-09-25
R7S1ONAR-AP17FF392 | Gypsum Wall Cladding (Shafts) -2nd Fix - AP#17 (FF Corridor) | 4 | 2025-09-27 | 2025-09-30
R7S1ONAR-AP17FF396 | Fixing Architrave - AP#17 (FF Corridor) | 2 | 2025-10-01 | 2025-10-02
R7S1ONAR-AP17FF397 | Fixing Aluminium Doors - AP#17 (FF Corridor) | 2 | 2025-10-04 | 2025-10-05
R7S1ONAR-AP17FF393 | False Ceiling - 2nd Fix (Closing the Ceiling) - AP#17 (FF Corridor) | 3 | 2025-10-06 | 2025-10-08
R7S1ONAR-AP17FF394 | Painting - Surface Prep., Primer & 1st Coat for Walls - AP#17 (FF Corridor) | 8 | 2025-10-01 | 2025-10-09
R7S1ONAR-AP17FF417 | Painting - Surface Prep., Primer & 1st Coat for Ceiling - AP#17 (FF Corridor) | 4 | 2025-10-09 | 2025-10-13
R7S1ONAR-AP17FF395 | Painting - Final Coat (Ceiling + Walls) - AP#17 (FF Corridor) | 3 | 2025-10-15 | 2025-10-18
INSIDE BOXES |  | 12 | 2025-08-21 | 2025-09-03
R7S1ONAR-AP17FF398 | Fixing Thresholds (Joining the Room) - AP#17 (FF - inside Boxes) | 4 | 2025-08-21 | 2025-08-25
R7S1ONAR-AP17FF399 | Fixing Wooden Doors - AP#17 (FF - inside Boxes) | 4 | 2025-08-26 | 2025-08-30
R7S1ONAR-AP17FF400 | Fixing Aluminium Doors (Next Floor) - AP#17 (FF - inside Boxes) | 4 | 2025-08-31 | 2025-09-03
IN FRONT OF LIFT SHAFT |  | 111 | 2025-07-19 | 2025-09-18
R7S1ONAR-AP17FF402 | Flooring - AP#17 (FF - Front of Lift Shaft) | 4 | 2025-07-19 | 2025-07-23
R7S1ONAR-AP17FF403 | Skirting & Thresholds - AP#17 (FF - Front of Lift Shaft) | 1 | 2025-07-22 | 2025-07-23
R7S1ONAR-AP17FF404 | Painting - Surface Prep., Primer & 1st Coat - AP#17 (FF - Front of Lift Shaft) | 4 | 2025-07-23 | 2025-07-28
R7S1ONAR-AP17FF401 | False Ceiling - 1st Fix - AP#17 (FF - Front of Lift Shaft) | 4 | 2025-07-28 | 2025-08-02
R7S1ONAR-AP17FF405 | False Ceiling - Final Fix - AP#17 (FF - Front of Lift Shaft) | 3 | 2025-08-24 | 2025-08-26
R7S1ONAR-AP17FF407 | Fixing Handrail - AP#17 (FF - Front of Lift Shaft) | 3 | 2025-08-27 | 2025-08-30
R7S1ONAR-AP17FF408 | Paint for Handrail - AP#17 (FF - Front of Lift Shaft) | 3 | 2025-08-31 | 2025-09-02
R7S1ONAR-AP17FF406 | Painting - 2nd Coat - AP#17 (FF - Front of Lift Shaft) | 3 | 2025-09-14 | 2025-09-16
R7S1ONAR-AP17FF409 | Fixing Floor Mat - AP#17 (FF - Front of Lift Shaft) | 2 | 2025-09-17 | 2025-09-18
R7S1ONAR-AP17FF410 | Fixing Wall Guard - AP#17 (FF - Front of Lift Shaft) | 2 | 2025-09-17 | 2025-09-18
GARBAGE ROOM |  | 24 | 2025-08-26 | 2025-09-06
R7S1ONAR-AP17FF411 | Installation of Dry Walls - First Fix - AP#17 (FF - Garbage Room) | 2 | 2025-08-26 | 2025-08-27
R7S1ONAR-AP17FF412 | Installation of Dry Walls - Final Fix - AP#17 (FF - Garbage Room) | 2 | 2025-08-27 | 2025-08-28
R7S1ONAR-AP17FF413 | Garbage Rooms - Wall Tile Finishes (One Side) - AP#17 (FF - Garbage Room) | 2 | 2025-08-28 | 2025-08-30
R7S1ONAR-AP17FF414 | Paint Works of Dry Walls - First Coat - AP#17 (FF - Garbage Room) | 2 | 2025-08-31 | 2025-09-01
R7S1ONAR-AP17FF415 | Installation of the Garbage Chute Door - AP#17 (FF - Garbage Room) | 2 | 2025-09-02 | 2025-09-03
R7S1ONAR-AP17FF416 | Paint Finishes and Touchups - Final Coat - AP#17 (FF - Garbage Room) | 2 | 2025-09-04 | 2025-09-06
MEP WORKS |  | 73 | 2025-07-05 | 2025-10-14
MECHANICAL |  | 73 | 2025-07-05 | 2025-10-13
CHILLED WATER |  | 39 | 2025-07-05 | 2025-08-20
R7S1ONME-AP17FF1386 | CHWP Installation/Connections and Insulation (In Front of Lift Shaft) - AP#17 | 4 | 2025-07-05 | 2025-07-08
R7S1ONME-AP17FF532 | Installation of Chilled water hanger and supports - AP#17 (FF Corridor) | 4 | 2025-07-19 | 2025-07-23
R7S1ONME-AP17FF582 | Installation of CHWP connection for FCU with Valve package in Corridor, Electrical Room & ICT Room | 4 | 2025-07-19 | 2025-07-23
R7S1ONME-AP17FF534 | Installation of BTU Meter with valves - AP#17 (FF Corridor) | 2 | 2025-07-24 | 2025-07-27
R7S1ONME-AP17FF533 | Installation of CHWP piping (connection between modular cages & modular to apartment) - AP#17 -(FF Corridor) | 4 | 2025-07-23 | 2025-07-28
R7S1ONME-AP17FF535 | CHWP piping risers connections - AP#17 (FF Corridor) | 3 | 2025-08-12 | 2025-08-14
R7S1ONME-AP17FF536 | Pressure Testing of CHWP piping - AP#17 (FF Corridor) | 1 | 2025-08-16 | 2025-08-16
R7S1ONME-AP17FF571 | CHWP Insulation - AP#17 (FF Corridor) | 4 | 2025-08-17 | 2025-08-20
HVAC DUCTING |  | 71 | 2025-07-19 | 2025-10-11
R7S1ONME-AP17FF583 | Installation of FCU's & Duct Connection in Corridor, Electrical Room & ICT Room - AP#17 (FF Corridor) | 4 | 2025-07-19 | 2025-07-23
R7S1ONME-AP17FF537 | Duct Riser Continuation - AP#17 (FF Corridor) | 4 | 2025-08-12 | 2025-08-16
R7S1ONME-AP17FF538 | A/C drain & Copper pipe connection in ELV room - AP#17 (FF Corridor) | 2 | 2025-08-17 | 2025-08-18
R7S1ONME-AP17FF584 | Installation of Ducting and insulation (connection between modular cages) - AP#17 (FF Corridor) | 3 | 2025-08-17 | 2025-08-19
R7S1ONME-AP17FF572 | Installation of Duct & Grill in Garbage Room - AP#17 (FF Corridor) | 2 | 2025-08-19 | 2025-08-20
R7S1ONME-AP17FF585 | Installation of Grilles in the Corridor - AP#17 (FF Corridor) | 2 | 2025-10-09 | 2025-10-11
FIRE FIGHTING |  | 59 | 2025-07-09 | 2025-10-13
R7S1ONME-AP17FF1596 | Installation of F.F Pipes, Testing & Final Fixtures (In Front of Lift Shaft) - AP17 | 3 | 2025-07-09 | 2025-07-12
R7S1ONME-AP17FF573 | Installation of Pipe & sprinkler in Garbage Room - AP#17 (FF Corridor) | 1 | 2025-08-10 | 2025-08-10
R7S1ONME-AP17FF539 | Riser Continuity in corridor - AP#17 (FF Corridor) | 4 | 2025-08-12 | 2025-08-16
R7S1ONME-AP17FF540 | Continuation of FF pipes & ZC Valves (connection between modular cages & modular to apartment) - AP#17 (FF Corridor) | 4 | 2025-08-12 | 2025-08-16
R7S1ONME-AP17FF541 | Installation of Sprinklers drops in corridor - AP#17 (FF Corridor) | 4 | 2025-08-17 | 2025-08-20
R7S1ONME-AP17FF542 | Pressure Test for FF Piping in corridor - AP#17 (FF Corridor) | 2 | 2025-08-21 | 2025-08-23
R7S1ONME-AP17FF586 | FF Flushing network - AP#17 (FF Corridor) | 4 | 2025-09-02 | 2025-09-06
R7S1ONME-AP17FF544 | Installation of Alarm check valve, Fire Extinguishers & Blanket (Last Stage of the Building) - AP#17 (FF Corridor) | 2 | 2025-10-09 | 2025-10-11
R7S1ONME-AP17FF543 | Installation of Sprinklers in corridor - AP#17 (FF Corridor) | 4 | 2025-10-09 | 2025-10-13
WATER SUPPLY |  | 43 | 2025-07-19 | 2025-09-17
R7S1ONME-AP17FF574 | Installation of WS Pipe in Garbage Room - AP#17 (FF Corridor) | 2 | 2025-07-19 | 2025-07-21
R7S1ONME-AP17FF575 | Installation of Sanitary Fixtures in Janitor Room - AP#17 (FF Corridor) | 2 | 2025-07-19 | 2025-07-21
R7S1ONME-AP17FF546 | WS High Level Pipe continuation & Insulation works in Corridor - AP#17 (FF Corridor) | 4 | 2025-07-19 | 2025-07-23
R7S1ONME-AP17FF547 | Installation of Cold, Hot water line & Hot water return in corridor - AP#17 (FF Corridor) | 4 | 2025-07-23 | 2025-07-28
R7S1ONME-AP17FF548 | Water Meter Installation in Corridor - AP#17 (FF Corridor) | 4 | 2025-07-28 | 2025-08-02
R7S1ONME-AP17FF545 | Riser Continuity in Shafts - AP#17 (FF Corridor) | 4 | 2025-08-12 | 2025-08-16
R7S1ONME-AP17FF549 | Pressure Test for WS - AP#17 (FF Corridor) | 4 | 2025-09-04 | 2025-09-08
R7S1ONME-AP17FF587 | Insulation for Hot water line & Hot water return in corridor - AP#17 (FF Corridor) | 4 | 2025-09-14 | 2025-09-17
DRAINAGE |  | 8 | 2025-07-19 | 2025-09-08
R7S1ONME-AP17FF550 | Installation of Clean-outs, Floor drain in balcony - AP#17 (FF Corridor) | 4 | 2025-07-19 | 2025-07-23
R7S1ONME-AP17FF551 | Rain Water Riser continuation in Shafts - AP#17 (FF Corridor) | 4 | 2025-08-12 | 2025-08-16
R7S1ONME-AP17FF552 | Drainage Riser continuation in Shafts - AP#17 (FF Corridor) | 4 | 2025-08-12 | 2025-08-16
R7S1ONME-AP17FF553 | Testing for Rain Water Riser - AP#17 (FF Corridor) | 4 | 2025-09-04 | 2025-09-08
R7S1ONME-AP17FF554 | Testing for Drainage Riser - AP#17 (FF Corridor) | 4 | 2025-09-04 | 2025-09-08
ELECTRICAL |  | 67 | 2025-07-13 | 2025-10-14
POWER & LIGHTING |  | 67 | 2025-07-13 | 2025-10-14
R7S1ONME-AP17FF1806 | Continuation of Cable Tray/Trunking with Flexible conduits for Lights (In Front of Lift Shaft) - AP#17 | 4 | 2025-07-13 | 2025-07-16
R7S1ONME-AP17FF555 | Contiuation of Cable Trays & apartment branches - AP#17 (FF Corridor) | 4 | 2025-07-19 | 2025-07-23
R7S1ONME-AP17FF556 | Contiuation of Cable Trunking with Flexible conduits for Lights - AP#17 (FF Corridor) | 4 | 2025-07-19 | 2025-07-23
R7S1ONME-AP17FF557 | Installation of EMT pipes - AP#17 (FF Corridor) | 5 | 2025-07-19 | 2025-07-24
R7S1ONME-AP17FF558 | Installation of Busbar, Electrical Meter & Tap-off - AP#17 (FF Corridor) | 3 | 2025-08-30 | 2025-09-01
R7S1ONME-AP17FF581 | Termination of Tap-off with Electrical Meter in the apartments - AP#17 (FF Corridor) | 3 | 2025-09-02 | 2025-09-04
R7S1ONME-AP17FF559 | Corridor Wire Pulling - AP#17 (FF Corridor) | 6 | 2025-08-31 | 2025-09-06
R7S1ONME-AP17FF560 | Electrical Room - Installation of Cable trays, SMDB & Termination - AP#17 (FF Corridor) | 6 | 2025-09-07 | 2025-09-13
R7S1ONME-AP17FF562 | Installation, Termination of Emergeny & Exit Lights with contiuity - AP#17 (FF Corridor) | 2 | 2025-10-09 | 2025-10-11
R7S1ONME-AP17FF561 | Installation, Termination of Light Fixtures with continuity test - AP#17 (FF - Corridor & Balconies) | 3 | 2025-10-09 | 2025-10-12
R7S1ONME-AP17FF563 | Installation, Termination of PIR sensors with continuity test - AP#17 (FF Corridor) | 2 | 2025-10-13 | 2025-10-14
LOW CURRENT SYSTEM |  | 66 | 2025-07-17 | 2025-10-13
R7S1ONME-AP17FF2016 | Installation of Basket trays for Low Current, Cable Installation (In Front of Lift Shaft) - AP#17 | 4 | 2025-07-17 | 2025-07-21
R7S1ONME-AP17FF588 | CBS System cable installation - AP#17 (FF Corridor) | 3 | 2025-07-19 | 2025-07-22
R7S1ONME-AP17FF564 | Installation of Basket trays for BMS, CCTV, Access Control - AP#17 (FF Corridor) | 4 | 2025-07-19 | 2025-07-23
R7S1ONME-AP17FF566 | Fire alarm cable installation - AP#17 (FF Corridor) | 3 | 2025-07-20 | 2025-07-23
R7S1ONME-AP17FF565 | Voice Evacuation cable installation - AP#17 (FF Corridor) | 3 | 2025-07-22 | 2025-07-26
R7S1ONME-AP17FF567 | Fibre optic Cable pulling & Termination with OTO (in corridors to ONU) - AP#17 (FF Corridor) | 2 | 2025-08-28 | 2025-08-30
R7S1ONME-AP17FF568 | BMS, CCTV & Access control Cable installation - AP#17 (FF Corridor) | 2 | 2025-08-28 | 2025-08-30
R7S1ONME-AP17FF569 | Low Current Works including BMS Panel in ICT Room - AP#17 (FF Corridor) | 10 | 2025-08-24 | 2025-09-03
R7S1ONME-AP17FF580 | Fluke test for CCTV & Fibre Optic Cable - AP#17 (FF Corridor) | 2 | 2025-09-02 | 2025-09-03
R7S1ONME-AP17FF576 | Installation & Termination of CCTV Cameras - AP#17 (FF Corridor) | 2 | 2025-10-09 | 2025-10-11
R7S1ONME-AP17FF577 | Installation & Termination of Access control system for Electrical Room - AP#17 (FF Corridor) | 2 | 2025-10-09 | 2025-10-11
R7S1ONME-AP17FF579 | Installation & Termination of Wireless Gateway & RF Node - AP#17 (FF Corridor) | 2 | 2025-10-09 | 2025-10-11
R7S1ONME-AP17FF570 | Installation & Termination of Fire alarm devices & Speakers - AP#17 (FF Corridor) | 4 | 2025-10-09 | 2025-10-13
R7S1ONME-AP17FF578 | Installation & Termination of Active Components & UPS installation in ICT Room | 2 | 2025-10-12 | 2025-10-13
SECOND FLOOR |  | 121 | 2025-07-09 | 2025-11-16
ARCH./ CIVIL WORKS |  | 111 | 2025-07-30 | 2025-11-16
CORRIDOR AREA |  | 46 | 2025-08-04 | 2025-11-16
R7S1ONAR-AP17SF291 | Flooring in Corridor - AP#17 (SF Corridor) | 6 | 2025-08-04 | 2025-08-11
R7S1ONAR-AP17SF292 | Corridor Skirting - AP#17 (SF Corridor) | 2 | 2025-08-10 | 2025-08-12
R7S1ONAR-AP17SF289 | False Ceiling - 1st Fix - AP#17 (SF Corridor) | 4 | 2025-08-12 | 2025-08-17
R7S1ONAR-AP17SF290 | Gypsum Wall Cladding (Shafts) - AP#17 (SF Corridor) | 6 | 2025-10-20 | 2025-10-26
R7S1ONAR-AP17SF293 | Gypsum Wall Cladding (Shafts) -2nd Fix - AP#17 (SF Corridor) | 4 | 2025-10-27 | 2025-10-30
R7S1ONAR-AP17SF297 | Fixing Architrave - AP#17 (SF Corridor) | 2 | 2025-11-01 | 2025-11-02
R7S1ONAR-AP17SF298 | Fixing Aluminium Doors - AP#17 (SF Corridor) | 2 | 2025-11-03 | 2025-11-04
R7S1ONAR-AP17SF294 | False Ceiling - 2nd Fix (Closing the Ceiling) - AP#17 (SF Corridor) | 2 | 2025-11-05 | 2025-11-06
R7S1ONAR-AP17SF295 | Painting - Surface Prep., Primer & 1st Coat - AP#17 (SF Corridor) | 8 | 2025-11-01 | 2025-11-09
R7S1ONAR-AP17SF319 | Painting - Surface Prep., Primer & 1st Coat - AP#17 (SF Corridor) | 4 | 2025-11-08 | 2025-11-11
R7S1ONAR-AP17SF296 | Painting - Final Coat (Ceiling + Walls) - AP#17 (SF Corridor) | 3 | 2025-11-13 | 2025-11-16
INSIDE BOXES |  | 8 | 2025-08-21 | 2025-08-30
R7S1ONAR-AP17SF299 | Fixing Thresholds (Joining the Room) - AP#17 (SF - inside Boxes) | 4 | 2025-08-21 | 2025-08-25
R7S1ONAR-AP17SF300 | Fixing Wooden Doors - AP#17 (SF - inside Boxes) | 2 | 2025-08-26 | 2025-08-27
R7S1ONAR-AP17SF301 | Fixing Aluminium Doors (Next Floor) - AP#17 (SF - inside Boxes) | 2 | 2025-08-28 | 2025-08-30
IN FRONT OF LIFT SHAFT |  | 111 | 2025-08-21 | 2025-10-25
R7S1ONAR-AP17SF303 | Flooring - AP#17 (SF - Front of Lift Shaft) | 6 | 2025-08-21 | 2025-08-27
R7S1ONAR-AP17SF304 | Skirting & Thresholds - AP#17 (SF - Front of Lift Shaft) | 2 | 2025-08-28 | 2025-08-30
R7S1ONAR-AP17SF305 | Painting - Surface Prep., Primer & 1st Coat - AP#17 (SF - Front of Lift Shaft) | 3 | 2025-08-31 | 2025-09-02
R7S1ONAR-AP17SF302 | False Ceiling - 1st Fix - AP#17 (SF - Front of Lift Shaft) | 3 | 2025-09-03 | 2025-09-06
R7S1ONAR-AP17SF306 | False Ceiling - Final Fix - AP#17 (SF - Front of Lift Shaft) | 3 | 2025-09-07 | 2025-09-09
R7S1ONAR-AP17SF308 | Fixing Handrail - AP#17 (SF - Front of Lift Shaft) | 3 | 2025-09-10 | 2025-09-13
R7S1ONAR-AP17SF309 | Paint for Handrail - AP#17 (SF - Front of Lift Shaft) | 2 | 2025-09-14 | 2025-09-15
R7S1ONAR-AP17SF307 | Painting - 2nd Coat - AP#17 (SF - Front of Lift Shaft) | 2 | 2025-10-21 | 2025-10-22
R7S1ONAR-AP17SF310 | Fixing Floor Mat - AP#17 (SF - Front of Lift Shaft) | 2 | 2025-10-23 | 2025-10-25
R7S1ONAR-AP17SF311 | Fixing Wall Guard - AP#17 (SF - Front of Lift Shaft) | 2 | 2025-10-23 | 2025-10-25
GARBAGE ROOM |  | 27 | 2025-07-30 | 2025-11-11
R7S1ONAR-AP17SF318 | Installation of Garbage Chute Full System from GF to 2nd Floor - AP#17 (SF - Garbage Room) | 10 | 2025-07-30 | 2025-08-10
R7S1ONAR-AP17SF312 | Installation of Dry Walls - First Fix - AP#17 (SF - Garbage Room) | 2 | 2025-08-11 | 2025-08-12
R7S1ONAR-AP17SF313 | Installation of Dry Walls - Final Fix - AP#17 (SF - Garbage Room) | 2 | 2025-08-13 | 2025-08-14
R7S1ONAR-AP17SF314 | Garbage Rooms - Wall Tile Finishes (One Side) - AP#17 (SF - Garbage Room) | 2 | 2025-08-14 | 2025-08-16
R7S1ONAR-AP17SF315 | Paint Works of Dry Walls - First Coat - AP#17 (SF - Garbage Room) | 2 | 2025-08-17 | 2025-08-18
R7S1ONAR-AP17SF316 | Installation of the Garbage Chute Door - AP#17 (SF - Garbage Room) | 2 | 2025-08-19 | 2025-08-20
R7S1ONAR-AP17SF317 | Paint Finishes and Touchups - Final Coat - AP#17 (SF - Garbage Room) | 2 | 2025-11-10 | 2025-11-11
MEP WORKS |  | 68 | 2025-07-09 | 2025-11-12
MECHANICAL |  | 68 | 2025-07-09 | 2025-11-11
CHILLED WATER |  | 15 | 2025-07-09 | 2025-09-07
R7S1ONME-AP17SF1396 | CHWP Installation/Connections and Insulation (In Front of Lift Shaft) - AP#17 | 4 | 2025-07-09 | 2025-07-13
R7S1ONME-AP17SF496 | Installation of Chilled water hanger and supports - AP#17 (SF Corridor) | 4 | 2025-08-21 | 2025-08-25
R7S1ONME-AP17SF546 | Installation of CHWP connection for FCU with Valve package in Corridor, Electrical Room & ICT Room | 4 | 2025-08-21 | 2025-08-25
R7S1ONME-AP17SF498 | Installation of BTU Meter with valves - AP#17 (SF Corridor) | 2 | 2025-08-27 | 2025-08-28
R7S1ONME-AP17SF497 | Installation of CHWP piping (connection between modular cages & modular to apartment) - AP#17 (SF Corridor) | 4 | 2025-08-26 | 2025-08-30
R7S1ONME-AP17SF499 | CHWP piping risers connections - AP#17 (SF Corridor) | 3 | 2025-08-30 | 2025-09-01
R7S1ONME-AP17SF500 | Pressure Testing of CHWP piping - AP#17 (SF Corridor) | 1 | 2025-09-02 | 2025-09-02
R7S1ONME-AP17SF535 | CHWP Insulation - AP#17 (SF Corridor) | 4 | 2025-09-03 | 2025-09-07
HVAC DUCTING |  | 64 | 2025-08-21 | 2025-11-09
R7S1ONME-AP17SF501 | Duct Riser Continuation - AP#17 (SF Corridor) | 4 | 2025-08-21 | 2025-08-25
R7S1ONME-AP17SF547 | Installation of FCU's & Duct Connection in Corridor, Electrical Room & ICT Room - AP#17 (SF Corridor) | 4 | 2025-08-21 | 2025-08-25
R7S1ONME-AP17SF502 | A/C drain & Copper pipe connection in ELV room - AP#17 (SF Corridor) | 2 | 2025-08-26 | 2025-08-27
R7S1ONME-AP17SF548 | Installation of Ducting and insulation (connection between modular cages) - AP#17 (SF Corridor) | 3 | 2025-08-26 | 2025-08-28
R7S1ONME-AP17SF536 | Installation of Duct & Grill in Garbage Room - AP#17 (SF Corridor) | 2 | 2025-11-08 | 2025-11-09
R7S1ONME-AP17SF549 | Installation of Grilles in the Corridor - AP#17 (SF Corridor) | 2 | 2025-11-08 | 2025-11-09
FIRE FIGHTING |  | 48 | 2025-07-14 | 2025-11-11
R7S1ONME-AP17SF1606 | Installation of F.F Pipes, Testing & Final Fixtures (In Front of Lift Shaft) - AP17 | 3 | 2025-07-14 | 2025-07-16
R7S1ONME-AP17SF503 | Riser Continuity Succ - Closing of Gysum Boards on shaft - AP#17 (SF Corridor) | 4 | 2025-08-21 | 2025-08-25
R7S1ONME-AP17SF504 | FF Contiuation on High Level with Valves - AP#17 (SF Corridor) | 4 | 2025-08-21 | 2025-08-25
R7S1ONME-AP17SF505 | Installation of Sprinklers drops - AP#17 (SF Corridor) | 4 | 2025-08-26 | 2025-08-30
R7S1ONME-AP17SF506 | Pressure Test for FF Piping - AP#17 (SF Corridor) | 2 | 2025-08-31 | 2025-09-01
R7S1ONME-AP17SF508 | Installation of Fire Extinguishers - AP#17 (SF Corridor) | 2 | 2025-11-08 | 2025-11-09
R7S1ONME-AP17SF537 | Installation of Pipe & sprinkler in Garbage Room - AP#17 (SF Corridor) | 2 | 2025-11-08 | 2025-11-09
R7S1ONME-AP17SF507 | Installation of Sprinklers - AP#17 (SF Corridor) | 4 | 2025-11-08 | 2025-11-11
WATER SUPPLY |  | 25 | 2025-08-21 | 2025-09-22
R7S1ONME-AP17SF538 | Installation of WS Pipe in Garbage Room - AP#17 (SF Corridor) | 2 | 2025-08-21 | 2025-08-23
R7S1ONME-AP17SF539 | Installation of Sanitary Fixtures in Janitor Room - AP#17 (SF Corridor) | 2 | 2025-08-21 | 2025-08-23
R7S1ONME-AP17SF509 | Riser Continuity - AP#17 (SF Corridor) | 4 | 2025-08-21 | 2025-08-25
R7S1ONME-AP17SF510 | WS High Level Pipe continuation & Insulation works - AP#17 (SF Corridor) | 4 | 2025-08-21 | 2025-08-25
R7S1ONME-AP17SF511 | Instalation of Hot water line in corridor - AP#17 (SF Corridor) | 4 | 2025-08-26 | 2025-08-30
R7S1ONME-AP17SF512 | Water Meter Installation - AP#17 (SF Corridor) | 4 | 2025-08-31 | 2025-09-03
R7S1ONME-AP17SF513 | Pressure Test for WS - AP#17 (SF Corridor) | 4 | 2025-09-09 | 2025-09-13
R7S1ONME-AP17FF589 | Insulation for Hot water line & Hot water return in corridor - AP#17 (SF Corridor) | 4 | 2025-09-18 | 2025-09-22
DRAINAGE |  | 9 | 2025-08-21 | 2025-09-08
R7S1ONME-AP17SF514 | Installation of Clean-outs - AP#17 (SF Corridor) | 4 | 2025-08-21 | 2025-08-25
R7S1ONME-AP17SF515 | Rain Water Riser continuation - AP#17 (SF Corridor) | 4 | 2025-08-21 | 2025-08-25
R7S1ONME-AP17SF516 | Drainage Riser continuation - AP#17 (SF Corridor) | 4 | 2025-08-21 | 2025-08-25
R7S1ONME-AP17SF517 | Testing for Rain Water Riser - AP#17 (SF Corridor) | 4 | 2025-09-04 | 2025-09-08
R7S1ONME-AP17SF518 | Testing for Drainage Riser - AP#17 (SF Corridor) | 4 | 2025-09-04 | 2025-09-08
ELECTRICAL |  | 51 | 2025-07-17 | 2025-11-12
POWER & LIGHTING |  | 51 | 2025-07-17 | 2025-11-12
R7S1ONME-AP17SF1816 | Continuation of Cable Tray/Trunking with Flexible conduits for Lights (In Front of Lift Shaft) - AP#17 | 4 | 2025-07-17 | 2025-07-21
R7S1ONME-AP17SF519 | Contiuation of Cable Trays & apartment branches - AP#17 (SF Corridor) | 4 | 2025-08-21 | 2025-08-25
R7S1ONME-AP17SF520 | Contiuation of Cable Trunking with Flexible conduits for Lights - AP#17 (SF Corridor) | 4 | 2025-08-21 | 2025-08-25
R7S1ONME-AP17SF521 | Installation of EMT pipes - AP#17 (SF Corridor) | 5 | 2025-08-21 | 2025-08-26
R7S1ONME-AP17SF522 | Installation of Busbar, Electrical Meter & Tap-off in Corridor - AP#17 (SF Corridor) | 3 | 2025-09-02 | 2025-09-04
R7S1ONME-AP17SF545 | Termination of Tap-off with Electrical Meter in the apartments - AP#17 (SF Corridor) | 3 | 2025-09-06 | 2025-09-08
R7S1ONME-AP17SF523 | Corridor Wire Pulling - AP#17 (SF Corridor) | 6 | 2025-09-03 | 2025-09-09
R7S1ONME-AP17SF524 | Electrical Room - Installation of Cable trays, SMDB & Termination - AP#17 (SF Corridor) | 6 | 2025-10-14 | 2025-10-20
R7S1ONME-AP17SF526 | Installation, Termination of Emergeny & Exit Lights with contiuity - AP#17 (SF Corridor) | 2 | 2025-11-08 | 2025-11-09
R7S1ONME-AP17SF525 | Installation, Termination of Light Fixtures with continuity test - AP#17 (SF - Corridor & Balconies) | 3 | 2025-11-08 | 2025-11-10
R7S1ONME-AP17SF527 | Installation, Termination of PIR sensors with continuity test - AP#17 (SF Corridor) | 2 | 2025-11-11 | 2025-11-12
LOW CURRENT SYSTEM |  | 49 | 2025-07-22 | 2025-11-11
R7S1ONME-AP17SF2026 | Installation of Basket trays for Low Current, Cable Installation (In Front of Lift Shaft) - AP#17 | 4 | 2025-07-22 | 2025-07-26
R7S1ONME-AP17SF550 | CBS System cable installation - AP#17 (SF Corridor) | 3 | 2025-08-21 | 2025-08-24
R7S1ONME-AP17SF528 | Installation of Basket trays for BMS, CCTV, Access Control - AP#17 (SF Corridor) | 4 | 2025-08-21 | 2025-08-25
R7S1ONME-AP17SF530 | Fire alarm cable installation - AP#17 (SF Corridor) | 3 | 2025-08-23 | 2025-08-25
R7S1ONME-AP17SF529 | Voice Evacuation cable installation - AP#17 (SF Corridor) | 3 | 2025-08-25 | 2025-08-27
R7S1ONME-AP17SF531 | Fibre optic Cable pulling & Termination with OTO (in corridors to ONU) - AP#17 (SF Corridor) | 2 | 2025-08-31 | 2025-09-01
R7S1ONME-AP17SF532 | BMS, CCTV & Access control Cable installation - AP#17 (SF Corridor) | 2 | 2025-08-31 | 2025-09-01
R7S1ONME-AP17SF533 | Low Current Works including BMS Panel in ICT Room - AP#17 (SF Corridor) | 10 | 2025-10-08 | 2025-10-19
R7S1ONME-AP17SF544 | Fluke test for CCTV & Fibre Optic Cable - AP#17 (SF Corridor) | 2 | 2025-10-18 | 2025-10-19
R7S1ONME-AP17SF540 | Installation & Termination of CCTV Cameras - AP#17 (SF Corridor) | 2 | 2025-11-08 | 2025-11-09
R7S1ONME-AP17SF541 | Installation & Termination of Access control system for Electrical Room - AP#17 (SF Corridor) | 2 | 2025-11-08 | 2025-11-09
R7S1ONME-AP17SF543 | Installation & Termination of Wireless Gateway & RF Node in corridors - AP#17 (SF Corridor) | 2 | 2025-11-08 | 2025-11-09
R7S1ONME-AP17SF534 | Installation & Termination of Fire alarm devices & Speakers - AP#17 (SF Corridor) | 4 | 2025-11-08 | 2025-11-11
R7S1ONME-AP17SF542 | Installation & Termination of Active Components & UPS installation in ICT Room - AP#17 (SF Corridor) | 2 | 2025-11-10 | 2025-11-11
ROOF WORKS |  | 65 | 2025-09-04 | 2025-11-12
ARCH./ CIVIL WORKS |  | 65 | 2025-09-04 | 2025-11-10
R7S1ONAR-AP17RF75 | Roof Box Stiching (Concrete Works) - AP#17 (Roof) | 6 | 2025-09-04 | 2025-09-10
R7S1ONME-AP17RF476 | Installation of Roof Drains - AP#17 (Roof) | 2 | 2025-09-09 | 2025-09-10
R7S1ONAR-AP17RF76 | Roof Waterproofing Works with testing - AP#17 (Roof) | 20 | 2025-09-11 | 2025-10-05
R7S1ONAR-AP17RF77 | Laying of Gravel - AP#17 (Roof) | 2 | 2025-10-06 | 2025-10-07
R7S1ONAR-AP17RF78 | Surface Preparation & Primer for Parapets - AP#17 (Roof) | 4 | 2025-10-21 | 2025-10-25
R7S1ONAR-AP17RF79 | 1st Coat Paint for Parapets - AP#17 (Roof) | 2 | 2025-10-26 | 2025-10-27
R7S1ONAR-AP17RF80 | 2nd Coat Paint for Parapets - AP#17 (Roof) | 3 | 2025-10-28 | 2025-10-30
R7S1ONAR-AP17RF82 | Fixing Fall Arrest System - AP#17 (Roof) | 2 | 2025-11-01 | 2025-11-02
R7S1ONAR-AP17RF81 | Crossover Bridges Installation & application of Sealant on MEP penetrations - AP#17 (Roof) | 9 | 2025-11-01 | 2025-11-10
MECHANICAL |  | 37 | 2025-10-08 | 2025-10-30
HVAC |  | 25 | 2025-10-08 | 2025-10-23
R7S1ONME-AP17RF440 | Modular Installation - AP#17 (Roof) | 5 | 2025-10-08 | 2025-10-13
R7S1ONME-AP17RF441 | Continuation of Roof duct works/FAHU Connections - AP#17 (Roof) | 5 | 2025-10-11 | 2025-10-15
R7S1ONME-AP17RF443 | Insulations for ducts - AP#17 (Roof) | 5 | 2025-10-12 | 2025-10-16
R7S1ONME-AP17RF445 | Installation of FAHU - AP#17 (Roof) | 2 | 2025-10-16 | 2025-10-18
R7S1ONME-AP17RF450 | Installation of Outdoor VRF/DX Units - AP#17 (Roof) | 2 | 2025-10-18 | 2025-10-19
R7S1ONME-AP17RF451 | Installation & Insulation of the Condensation Drain - AP#17 (Roof) | 1 | 2025-10-19 | 2025-10-19
R7S1ONME-AP17RF453 | Installation of Ventilation Fans - AP#17 (Roof) | 3 | 2025-10-16 | 2025-10-19
R7S1ONME-AP17RF448 | Chilled Water System Continuation and Connections with Valve package of FAHU - AP#17 (Roof) | 4 | 2025-10-16 | 2025-10-20
R7S1ONME-AP17RF455 | Installation of Louvers - AP#17 (Roof) | 2 | 2025-10-20 | 2025-10-21
R7S1ONME-AP17RF458 | Installation & Testing of Copper Pipes - AP#17 (Roof) | 2 | 2025-10-20 | 2025-10-21
R7S1ONME-AP17RF459 | Miscellaneous Works for Mechanical Connections (Fire & Volume Dampers etc.) - AP#17 (Roof) | 2 | 2025-10-22 | 2025-10-23
WATERSUPPLY & DRAINAGE |  | 33 | 2025-10-14 | 2025-10-29
R7S1ONME-AP17RF439 | Testing for the Rain Water Risers - AP#17 (Roof) | 2 | 2025-10-16 | 2025-10-18
R7S1ONME-AP17RF442 | Installation & Continuation of Water supply pipes (connection between modular cages & modular to Shaft Riser) - AP#17 | 4 | 2025-10-14 | 2025-10-18
R7S1ONME-AP17RF446 | Installation of Air Vent & Pressure Guage with Valves at Roof - AP#17 (Roof) | 4 | 2025-10-16 | 2025-10-20
R7S1ONME-AP17RF447 | Vertical Continuation of Vent Pipes To The Roof (Drainage) - AP#17 (Roof) | 4 | 2025-10-18 | 2025-10-21
R7S1ONME-AP17RF449 | Installation of Rain Water outlet - AP#17 (Roof) | 3 | 2025-10-19 | 2025-10-21
R7S1ONME-AP17RF444 | Installation of Air Vent with Valve for Water Supply - AP#17 (Roof) | 4 | 2025-10-19 | 2025-10-22
R7S1ONME-AP17RF452 | Testing of Water Supply Pipes - AP#17 (Roof) | 2 | 2025-10-23 | 2025-10-25
R7S1ONME-AP17RF454 | Insulation of Roof Water Line - AP#17 (Roof) | 2 | 2025-10-25 | 2025-10-26
R7S1ONME-AP17RF456 | Testing for the Drainage Pipes Risers - AP#17 (Roof) | 2 | 2025-10-27 | 2025-10-28
R7S1ONME-AP17RF457 | Installation of Vent Cowl - AP#17 (Roof) | 1 | 2025-10-29 | 2025-10-29
SOLAR HEATER |  | 27 | 2025-10-19 | 2025-10-30
R7S1ONME-AP17RF471 | Installation of Solar water pumps and circulation pumps with valves(For Water Only) - AP#17 (Roof) | 2 | 2025-10-20 | 2025-10-21
R7S1ONME-AP17RF469 | Installation of Structure and Solar Panels (For Water Only) - AP#17 (Roof) | 5 | 2025-10-19 | 2025-10-23
R7S1ONME-AP17RF470 | Installation of Solar Calorifier Tank & Air cooler (For Water Only) - AP#17 (Roof) | 5 | 2025-10-20 | 2025-10-25
R7S1ONME-AP17RF472 | Installation of Solar Pipes Primary Loop - AP#17 (Roof) | 5 | 2025-10-20 | 2025-10-25
R7S1ONME-AP17RF473 | Testing of Solar Pipes Primary Loop - AP#17 (Roof) | 1 | 2025-10-26 | 2025-10-26
R7S1ONME-AP17RF474 | Insulation of Solar Pipes Primary Loop - AP#17 (Roof) | 1 | 2025-10-26 | 2025-10-26
R7S1ONME-AP17RF475 | Aluminum Cladding of Solar Pipes Primary Loop - AP#17 (Roof) | 4 | 2025-10-27 | 2025-10-30
ELECTRICAL |  | 36 | 2025-10-14 | 2025-11-12
POWER & LOW CURRENT |  | 36 | 2025-10-14 | 2025-11-12
R7S1ONME-AP17RF460 | Installation of Cables for Fire Alarm system - AP#17 (Roof) | 3 | 2025-10-14 | 2025-10-16
R7S1ONME-AP17RF461 | Installation of Cables for BMS - AP#17 (Roof) | 3 | 2025-10-14 | 2025-10-16
R7S1ONME-AP17RF462 | Installation of Fire Alarm Devices - AP#17 (Roof) | 3 | 2025-10-14 | 2025-10-16
R7S1ONME-AP17RF464 | Installation of Roof Light Fixtures - AP#17 (Roof) | 3 | 2025-10-14 | 2025-10-16
R7S1ONME-AP17RF435 | Installation of Isolators and Machine Connections - AP#17 (Roof) | 5 | 2025-10-14 | 2025-10-19
R7S1ONME-AP17RF463 | Installation of BMS Devices - AP#17 (Roof) | 4 | 2025-10-15 | 2025-10-19
R7S1ONME-AP17RF436 | Installation of Electrical Containments for BMS - AP#17 (Roof) | 7 | 2025-10-14 | 2025-10-21
R7S1ONME-AP17RF466 | Termination for BMS System - AP#17 (Roof) | 1 | 2025-10-22 | 2025-10-22
R7S1ONME-AP17RF478 | Termination of Primary & Secondary pump for Solar system - AP#17 (Roof) | 1 | 2025-10-22 | 2025-10-22
R7S1ONME-AP17RF434 | Lightening Protection & Earthing System - AP#17 (Roof) | 7 | 2025-10-23 | 2025-10-30
R7S1ONME-AP17RF477 | Installation & Termination of Solar System Panel - AP#17 (Roof) | 3 | 2025-11-01 | 2025-11-03
R7S1ONME-AP17RF437 | Installation of Fire Alarm Containment for FAHU, Fans - AP#17 (Roof) | 4 | 2025-11-01 | 2025-11-04
R7S1ONME-AP17RF467 | Termination for Fire Alarm Device - AP#17 (Roof) | 1 | 2025-11-05 | 2025-11-05
R7S1ONME-AP17RF438 | Installation of LV Power Cables for Roof Equipment - AP#17 (Roof) | 5 | 2025-11-05 | 2025-11-10
R7S1ONME-AP17RF465 | Termination for LV Cables - AP#17 (Roof) | 1 | 2025-11-11 | 2025-11-11
R7S1ONME-AP17RF468 | Megger Test for the Power Cables - AP#17 (Roof) | 1 | 2025-11-12 | 2025-11-12
STAIR CASE |  | 101 | 2025-09-04 | 2025-11-02
CIVIL WORKS |  | 101 | 2025-09-11 | 2025-10-28
STAIR CASE (MAIN WITH LIFT) |  | 101 | 2025-09-11 | 2025-10-09
R7S1ONST-AP17RG470 | Stair Flooring (Roof to GF) - AP#17 (Main Stair) | 7 | 2025-09-11 | 2025-09-18
R7S1ONST-AP17RG471 | Stair Hand Rails (Roof to GF) - AP#17 (Main Stair) | 6 | 2025-09-20 | 2025-09-27
R7S1ONST-AP17RG472 | Stair Paint - Primer & 1st Coat (Roof to GF)- AP#17 (Main Stair) | 7 | 2025-09-28 | 2025-10-05
R7S1ONST-AP17RG473 | Stair Paint - Final Coat (Roof to GF)- AP#17 (Main Stair) | 4 | 2025-10-06 | 2025-10-09
STAIR CASE (LEFT SIDE) |  | 66 | 2025-09-20 | 2025-10-15
R7S1ONST-AP17RG480 | Stair Flooring (Roof to GF) - AP#17 Left Side Stair | 7 | 2025-09-20 | 2025-09-28
R7S1ONST-AP17RG481 | Stair Hand Rails (Roof to GF) - AP#17 Left Side Stair | 6 | 2025-09-29 | 2025-10-05
R7S1ONST-AP17RG482 | Stair Paint - Primer & 1st Coat (Roof to GF) - AP#17 Left Side Stair | 6 | 2025-10-06 | 2025-10-12
R7S1ONST-AP17RG483 | Stair Paint - Final Coat (Roof to GF) - AP#17 Left Side Stair | 3 | 2025-10-13 | 2025-10-15
STAIR CASE (RIGHT SIDE) |  | 60 | 2025-09-29 | 2025-10-28
R7S1ONST-AP17RG484 | Stair Flooring (Roof to GF) - AP#17 Right Side Stair | 8 | 2025-09-29 | 2025-10-07
R7S1ONST-AP17RG485 | Stair Hand Rails (Roof to GF) - AP#17 Right Side Stair | 7 | 2025-10-08 | 2025-10-15
R7S1ONST-AP17RG486 | Stair Paint - Primer & 1st Coat (Roof to GF) - AP#17 Right Side Stair | 7 | 2025-10-16 | 2025-10-23
R7S1ONST-AP17RG487 | Stair Paint - Final Coat (Roof to GF) - AP#17 Right Side Stair | 4 | 2025-10-25 | 2025-10-28
MEP WORKS |  | 53 | 2025-09-04 | 2025-11-02
STAIR CASE (MAIN WITH LIFT) |  | 37 | 2025-09-04 | 2025-10-14
R7S1ONST-AP17RG469 | Main Staircase Wire Pulling - AP#17 (Main Stair) | 3 | 2025-09-04 | 2025-09-07
R7S1ONST-AP17RG488 | Final fix - Main Staircase Lights Fixtures & Motion Sensor - AP#17 (Main Stair) | 2 | 2025-10-11 | 2025-10-12
R7S1ONST-AP17RG489 | Final fix - Main Staircase Emergency Lights Fixtures - AP#17 (Main Stair) | 2 | 2025-10-13 | 2025-10-14
STAIR CASE (LEFT SIDE) |  | 39 | 2025-09-08 | 2025-10-20
R7S1ONST-AP17RG474 | Left Staircase Wire Pulling - AP#17 (Main Stair) | 3 | 2025-09-08 | 2025-09-10
R7S1ONST-AP17RG476 | Final fix - Left Staircase Lights Fixtures & Motion Sensor - AP#17 (Main Stair) | 2 | 2025-10-16 | 2025-10-18
R7S1ONST-AP17RG478 | Final fix - Left Staircase Emergency Lights Fixtures - AP#17 (Main Stair) | 2 | 2025-10-19 | 2025-10-20
STAIR CASE (RIGHT SIDE) |  | 42 | 2025-09-11 | 2025-11-02
R7S1ONST-AP17RG475 | Right Staircase Wire Pulling - AP#17 (Main Stair) | 3 | 2025-09-11 | 2025-09-14
R7S1ONST-AP17RG477 | Final fix - Right Staircase Lights Fixtures & Motion Sensor - AP#17 (Main Stair) | 2 | 2025-10-29 | 2025-10-30
R7S1ONST-AP17RG479 | Final fix - Right Staircase Emergency Lights Fixtures - AP#17 (Main Stair) | 2 | 2025-11-01 | 2025-11-02
ELEVATOR WORKS |  | 14 | 2025-10-05 | 2025-10-29
R7S1ONEL-AP17GR649 | Installation of Rails - AP#17 (Elevator Works) | 6 | 2025-10-05 | 2025-10-11
R7S1ONEL-AP17GR650 | Assembly of Cabin - AP#17 (Elevator Works) | 4 | 2025-10-12 | 2025-10-15
R7S1ONEL-AP17GR651 | Installation of Motor - AP#17 (Elevator Works) | 4 | 2025-10-16 | 2025-10-20
R7S1ONEL-AP17GR652 | Installation of Main Cables - AP#17 (Elevator Works) | 4 | 2025-10-21 | 2025-10-25
R7S1ONEL-AP17GR653 | Installation of Doors, Indicator, Push Button - AP#17 (Elevator Works) | 2 | 2025-10-26 | 2025-10-27
R7S1ONEL-AP17GR654 | Interior Finishes - AP#17 (Elevator Works) | 2 | 2025-10-28 | 2025-10-29
EXTERNAL ELEVATIONS |  | 103 | 2025-10-08 | 2025-11-20
ARCH./ CIVIL WORKS |  | 103 | 2025-10-08 | 2025-11-20
R7S1ONEE-AP17GR533 | External Selant Works - For Boxes - AP#17 (External Elevations) | 15 | 2025-10-08 | 2025-10-25
R7S1ONEE-AP17GR534 | Final Finishes & Touchups - AP#17 (External Elevations) | 15 | 2025-10-26 | 2025-11-11
R7S1ONME-AP17GF813 | Installation of rain water outlet - External façade - AP#17 (External Elevations) | 2 | 2025-11-12 | 2025-11-13
R7S1ONEE-AP17GR536 | Installation of External Signages - AP#17 (External Elevations) | 4 | 2025-11-15 | 2025-11-18
R7S1ONEE-AP17GR535 | Fixing Cage Ladder - AP#17 (External Elevations) | 2 | 2025-11-19 | 2025-11-20
EXTERNAL - CIVIL WORKS |  | 199 | 2025-02-23 | 2025-10-22
DRAINAGE |  | 10 | 2025-09-04 | 2025-09-17
R7S1ONECW-AP17-415 | Excavation Works & Sand Bedding - AP#17 (External Drainage) | 3 | 2025-09-04 | 2025-09-07
R7S1ONECW-AP17-416 | Drainage Manholes - AP#17 | 6 | 2025-09-04 | 2025-09-10
R7S1ONECW-AP17-417 | Drainage Backfilling - AP#17 | 2 | 2025-09-16 | 2025-09-17
WATERSUPPLY |  | 179 | 2025-02-23 | 2025-10-01
R7S1ONECW-AP17-418 | Excavation Works & Sand Bedding - Watersupply - AP#17 (External Watersupply Civil) | 161 | 2025-02-23 | 2025-09-08
R7S1ONECW-AP17-419 | Watersupply Manholes - AP#17 | 6 | 2025-09-08 | 2025-09-15
R7S1ONECW-AP17-420 | Watersupply Backfilling - AP#17 | 2 | 2025-09-29 | 2025-10-01
CHILLED WATER |  | 9 | 2025-09-08 | 2025-09-21
R7S1ONECW-AP17-424 | Excavation Works & Sand Bedding - AP#17 (External Chilled Water Civil) | 3 | 2025-09-08 | 2025-09-11
R7S1ONECW-AP17-425 | Chilled Water Manholes - AP#17 | 6 | 2025-09-11 | 2025-09-18
R7S1ONECW-AP17-426 | Chilled Water Backfilling - AP#17 | 2 | 2025-09-18 | 2025-09-21
FIRE FIGHTING |  | 171 | 2025-02-23 | 2025-09-21
R7S1ONECW-AP17-421 | Excavation Works & Sand Bedding - AP#17 (External Chilled Water Civil) | 164 | 2025-02-23 | 2025-09-11
R7S1ONECW-AP17-422 | Fire Fighting Manholes - AP#17 | 6 | 2025-09-11 | 2025-09-18
R7S1ONECW-AP17-423 | Fire Fighting Backfilling - AP#17 | 2 | 2025-09-18 | 2025-09-21
POWER |  | 34 | 2025-09-11 | 2025-10-22
R7S1ONECW-AP17-427 | Excavation Works & Sand Bedding - AP#17 (External Power Civil) | 3 | 2025-09-11 | 2025-09-15
R7S1ONECW-AP17-428 | Power Manholes - AP#17 | 3 | 2025-09-15 | 2025-09-18
R7S1ONECW-AP17-429 | Power Backfilling - AP#17 | 2 | 2025-10-21 | 2025-10-22
LOW CURRENT |  | 16 | 2025-09-11 | 2025-09-21
R7S1ONECW-AP17-430 | Excavation Works & Sand Bedding - AP#17 (External Low Current Civil) | 3 | 2025-09-11 | 2025-09-15
R7S1ONECW-AP17-431 | Low Current Manholes - AP#17 | 3 | 2025-09-15 | 2025-09-18
R7S1ONECW-AP17-432 | Low Current Backfilling - AP#17 | 2 | 2025-09-18 | 2025-09-21
EXTERNAL - MEP SERVICES |  | 196 | 2025-02-24 | 2025-10-20
DRAINAGE |  | 4 | 2025-09-11 | 2025-09-15
R7S1ONEME-AP17-271 | External Drainage Network - AP#17 (External Drainage MEP) | 4 | 2025-09-11 | 2025-09-15
WATERSUPPLY |  | 10 | 2025-09-15 | 2025-10-01
R7S1ONEME-AP17-272 | PRV statiuon assembly including meters- AP#17 (External WS MEP) | 4 | 2025-09-15 | 2025-09-20
R7S1ONEME-AP17-274 | Installation of valve station incl. BTU meter- AP#17 (External WS MEP) | 3 | 2025-09-28 | 2025-10-01
CHILLED WATER |  | 7 | 2025-09-20 | 2025-09-29
R7S1ONEME-AP17-273 | Installation of Chilled water line- AP#17 (External CWP MEP) | 6 | 2025-09-20 | 2025-09-28
R7S1ONEME-AP17-275 | Pressure Test for chilled water line- AP#17 (External CWP MEP) | 1 | 2025-09-28 | 2025-09-29
FIRE FIGHTING |  | 163 | 2025-02-24 | 2025-09-17
R7S1ONEME-AP17-276 | Installation of External FF network - AP#17 (External FF MEP) | 163 | 2025-02-24 | 2025-09-11
R7S1ONEME-AP17-277 | Installation of Alarm check valves- AP#17 (External FF MEP) | 3 | 2025-09-11 | 2025-09-15
R7S1ONEME-AP17-278 | Testing of External FF - AP#17 (External FF MEP) | 2 | 2025-09-15 | 2025-09-17
POWER |  | 1 | 2025-10-20 | 2025-10-20
R7S1ONEME-AP17-279 | Cable pulling from Manhole to the building MDB - AP#17 (External Power MEP) | 1 | 2025-10-20 | 2025-10-20
LOW CURRENT |  | 3 | 2025-09-15 | 2025-09-18
R7S1ONEME-AP17-280 | Low Current Cable pulling- AP#17 (External FF MEP) | 3 | 2025-09-15 | 2025-09-18
BUILDING # AP18 (LARGE STUDIO) |  | 336 | 2024-12-11 | 2025-11-20
SUB-STRUCTURE |  | 118 | 2024-12-11 | 2025-05-04
R7S1-ONSB-AP18-281 | Site Setting Out Works - AP#18 | 2 | 2024-12-11 | 2024-12-12
R7S1-ONSB-AP18-278 | Site levelling & earthworks - AP#18 | 5 | 2024-12-14 | 2024-12-18
R7S1-ONSB-AP18-282 | Anti-termite & Polythene Sheet Works - AP#18 | 8 | 2025-01-23 | 2025-02-01
R7S1-ONSB-AP18-279 | Blinding PCC - AP#18 | 4 | 2025-02-01 | 2025-02-04
R7S1-ONSB-AP18-280 | Waterproofing for Blinding PCC (Bitumen Paint) - AP#18 | 2 | 2025-02-04 | 2025-02-05
R7S1-ONSB-AP18-283 | Foundations/Upstands - Rebar - AP#18 | 12 | 2025-02-23 | 2025-03-09
R7S1-ONSB-AP18-284 | Foundations/Upstands - Shuttering (Including dowel Works) - AP#18 | 13 | 2025-02-23 | 2025-03-10
R7S1-ONSB-AP18-287 | Installation of MEP U/G services below Boxes - AP#18 | 15 | 2025-02-23 | 2025-03-12
R7S1-ONSB-AP18-285 | Foundations/Upstands - Casting - AP#18 | 12 | 2025-02-27 | 2025-03-13
R7S1-ONSB-AP18-286 | Waterproofing For Foundations/Upstands - AP#18 | 40 | 2025-03-01 | 2025-04-20
R7S1-ONSB-AP18-288 | Backfilling & Compaction - AP#18 | 12 | 2025-04-20 | 2025-05-04
SLAB-ON-GRADE & UG MEP WORKS (in Corridor) |  | 8 | 2025-05-31 | 2025-06-22
LEFT SIDE |  | 6 | 2025-05-31 | 2025-06-17
R7S1-ONSG-AP18-860 | Backfilling & SOG (In Front of Lift Shaft) - AP#18 | 3 | 2025-05-31 | 2025-06-02
R7S1-ONSG-AP18-346 | Block Work below Corridor area - AP#18 | 1 | 2025-06-04 | 2025-06-10
R7S1-ONSG-AP18-352 | Backfilling upto Pipe Level - AP#18 | 1 | 2025-06-10 | 2025-06-11
R7S1-ONSG-AP18-360 | Plaster Work for Blockwork - AP#18 | 1 | 2025-06-10 | 2025-06-11
R7S1-ONSG-AP18-347 | UG MEP Works (Laying of Pipes) - AP#18 | 2 | 2025-06-10 | 2025-06-12
R7S1-ONSG-AP18-348 | Backfilling Works after Pipe Laying - AP#18 | 1 | 2025-06-12 | 2025-06-14
R7S1-ONSG-AP18-349 | Antitermite Works - AP#18 | 1 | 2025-06-12 | 2025-06-14
R7S1-ONSG-AP18-350 | Polythene & Rebar Mesh Works - AP#18 | 2 | 2025-06-14 | 2025-06-16
R7S1-ONSG-AP18-351 | Pouring SOG Concrete - AP#18 | 1 | 2025-06-16 | 2025-06-17
RIGHT SIDE |  | 5 | 2025-06-14 | 2025-06-22
R7S1-ONSG-AP18-353 | Block Work below Corridor area - AP#18 | 2 | 2025-06-14 | 2025-06-16
R7S1-ONSG-AP18-359 | Backfilling upto Pipe Level - AP#18 | 1 | 2025-06-16 | 2025-06-17
R7S1-ONSG-AP18-354 | UG MEP Works (Laying of Pipes) - AP#18 | 1 | 2025-06-17 | 2025-06-18
R7S1-ONSG-AP18-355 | Backfilling Works after Pipe Laying - AP#18 | 1 | 2025-06-18 | 2025-06-19
R7S1-ONSG-AP18-356 | Antitermite Works - AP#18 | 1 | 2025-06-18 | 2025-06-19
R7S1-ONSG-AP18-357 | Polythene & Rebar Mesh Works - AP#18 | 1 | 2025-06-19 | 2025-06-21
R7S1-ONSG-AP18-358 | Pouring SOG Concrete - AP#18 | 1 | 2025-06-21 | 2025-06-22
ERECTION WORKS |  | 87 | 2025-05-28 | 2025-09-07
GROUND FLOOR |  | 20 | 2025-05-28 | 2025-06-25
R7S1ONER-AP18GF412 | Erection of Columns/Beams Frame & Slab/Loose Elements (In Front of Lift Shaft) - AP#18 | 2 | 2025-05-28 | 2025-05-29
R7S1ONER-AP18GF193 | Erection of GF Boxes (Left Side) including Lift Box & Staircase - AP#18 - Large Studio | 4 | 2025-06-01 | 2025-06-04
R7S1ONER-AP18GF194 | Erection of GF Boxes (Right Side) - AP#18 - Large Studio | 4 | 2025-06-04 | 2025-06-14
R7S1ONER-AP18GF195 | Erection of GF MEP Modular Cages (Left Side) - AP#18 | 2 | 2025-06-17 | 2025-06-19
R7S1ONER-AP18GF196 | Erection of GF Corridor Slabs (Left Side) - AP#18 | 2 | 2025-06-18 | 2025-06-21
R7S1ONER-AP18GF197 | Erection of GF MEP Modular Cages (Right Side) - AP#18 | 2 | 2025-06-22 | 2025-06-24
R7S1ONER-AP18GF198 | Erection of GF Corridor Slabs Right Side) - AP#18 | 2 | 2025-06-23 | 2025-06-25
FIRST FLOOR |  | 18 | 2025-05-31 | 2025-07-23
R7S1ONER-AP18FF422 | Erection of Columns/Beams Frame & Slab/Loose Elements (In Front of Lift Shaft) - AP#18 | 2 | 2025-05-31 | 2025-06-01
R7S1ONER-AP18FF193 | Erection of FF Boxes (Left Side) - AP#18 - Large Studio | 2 | 2025-07-14 | 2025-07-15
R7S1ONER-AP18FF195 | Erection of FF MEP Modular Cages (Left Side) - AP#18 | 2 | 2025-07-15 | 2025-07-17
R7S1ONER-AP18FF194 | Erection of FF Boxes (Right Side) - AP#18 - Large Studio | 2 | 2025-07-16 | 2025-07-19
R7S1ONER-AP18FF196 | Erection of FF Corridor Slabs (Left Side) - AP#18 | 2 | 2025-07-17 | 2025-07-20
R7S1ONER-AP18FF197 | Erection of FF MEP Modular Cages (Right Side) - AP#18 | 2 | 2025-07-20 | 2025-07-21
R7S1ONER-AP18FF198 | Erection of FF Corridor Slabs Right Side) - AP#18 | 2 | 2025-07-22 | 2025-07-23
SECOND FLOOR |  | 21 | 2025-06-02 | 2025-08-24
R7S1ONER-AP18SF432 | Erection of Columns/Beams Frame & Slab/Loose Elements (In Front of Lift Shaft) - AP#18 | 2 | 2025-06-02 | 2025-06-03
R7S1ONER-AP18SF193 | Erection of SF Boxes (Left Side) - AP#18 - Large Studio | 2 | 2025-08-13 | 2025-08-14
R7S1ONER-AP18SF194 | Erection of SF Boxes (Right Side) - AP#18 - Large Studio | 2 | 2025-08-16 | 2025-08-17
R7S1ONER-AP18SF195 | Erection of SF MEP Modular Cages (Left Side) - AP#18 | 3 | 2025-08-16 | 2025-08-18
R7S1ONER-AP18SF196 | Erection of SF Corridor Slabs (Left Side) - AP#18 | 2 | 2025-08-19 | 2025-08-20
R7S1ONER-AP18SF197 | Erection of SF MEP Modular Cages (Right Side) - AP#18 | 2 | 2025-08-20 | 2025-08-21
R7S1ONER-AP18SF198 | Erection of SF Corridor Slabs Right Side) - AP#18 | 2 | 2025-08-23 | 2025-08-24
ROOF |  | 12 | 2025-08-25 | 2025-09-07
R7S1ONER-AP18RF108 | Erection of Loose Roof Parapets, Shaft Covers, MEP Foundation etc. - AP#18 Roof | 12 | 2025-08-25 | 2025-09-07
MEP WORKS & FINISHES |  | 172 | 2025-06-03 | 2025-11-20
GROUND FLOOR |  | 170 | 2025-06-03 | 2025-10-12
ARCH./ CIVIL WORKS |  | 141 | 2025-06-03 | 2025-10-12
CORRIDOR AREA |  | 73 | 2025-07-21 | 2025-10-12
R7S1ONAR-AP18GF254 | Flooring in Corridor - AP#18 (GF Corridor) | 6 | 2025-07-21 | 2025-07-28
R7S1ONAR-AP18GF255 | Corridor Skirting - AP#18 (GF Corridor) | 2 | 2025-07-27 | 2025-07-29
R7S1ONAR-AP18GF252 | False Ceiling - 1st Fix - AP#18 (GF - Corridor) | 4 | 2025-07-29 | 2025-08-03
R7S1ONAR-AP18GF253 | Gypsum Wall Cladding - 1st Fix (Shafts) - AP#18 (GF Corridor) | 6 | 2025-09-17 | 2025-09-24
R7S1ONAR-AP18GF256 | Gypsum Wall Cladding (Shafts) -2nd Fix - AP#18 (GF Corridor) | 4 | 2025-09-20 | 2025-09-24
R7S1ONAR-AP18GF260 | Fixing Architrave - AP#18 (GF Corridor) | 2 | 2025-09-25 | 2025-09-27
R7S1ONAR-AP18GF261 | Fixing Aluminium Doors - AP#18 (GF Corridor) | 2 | 2025-09-28 | 2025-09-29
R7S1ONAR-AP18GF257 | False Ceiling - 2nd Fix (Closing the Ceiling) - AP#18 (GF Corridor) | 3 | 2025-09-30 | 2025-10-02
R7S1ONAR-AP18GF258 | Painting - Surface Prep., Primer & 1st Coat - AP#18 (GF Corridor) | 8 | 2025-09-25 | 2025-10-04
R7S1ONAR-AP18GF276 | Painting - Surface Prep., Primer & 1st Coat for Ceiling - AP#18 (GF Corridor) | 4 | 2025-10-04 | 2025-10-07
R7S1ONAR-AP18GF259 | Painting - Final Coat (Ceiling + Walls) - AP#18 (GF Corridor) | 3 | 2025-10-09 | 2025-10-12
INSIDE BOXES |  | 12 | 2025-07-28 | 2025-08-11
R7S1ONAR-AP18GF262 | Fixing Thresholds (Joining the Room) - AP#18 (GF - inside Boxes) | 4 | 2025-07-28 | 2025-08-02
R7S1ONAR-AP18GF263 | Fixing Wooden Doors - AP#18 (GF - inside Boxes) | 4 | 2025-08-02 | 2025-08-06
R7S1ONAR-AP18GF264 | Fixing Aluminium Doors - AP#18 (GF - inside Boxes) | 4 | 2025-08-06 | 2025-08-11
IN FRONT OF LIFT SHAFT |  | 91 | 2025-06-03 | 2025-09-29
R7S1ONAR-AP18GF266 | Flooring - AP#18 (GF - Front of Lift Shaft) | 4 | 2025-06-03 | 2025-06-11
R7S1ONAR-AP18GF267 | Skirting & Thresholds - AP#18 (GF - Front of Lift Shaft) | 1 | 2025-06-11 | 2025-06-11
R7S1ONAR-AP18GF268 | Painting - Surface Prep., Primer & 1st Coat - AP#18 (GF - Front of Lift Shaft) | 4 | 2025-06-12 | 2025-06-16
R7S1ONAR-AP18GF265 | False Ceiling - 1st Fix - AP#18 (GF - Front of Lift Shaft) | 4 | 2025-06-17 | 2025-06-21
R7S1ONAR-AP18GF269 | False Ceiling - Final Fix - AP#18 (GF - Front of Lift Shaft) | 3 | 2025-06-22 | 2025-06-24
R7S1ONAR-AP18GF271 | Fixing Handrail - AP#18 (GF - Front of Lift Shaft) | 3 | 2025-06-25 | 2025-06-28
R7S1ONAR-AP18GF272 | Paint for Handrail - AP#18 (GF - Front of Lift Shaft) | 3 | 2025-06-29 | 2025-07-01
R7S1ONAR-AP18GF270 | Painting - Final Coat - AP#18 (GF - Front of Lift Shaft) | 3 | 2025-09-21 | 2025-09-24
R7S1ONAR-AP18GF274 | Fixing Wall Guard - AP#18 (GF - Front of Lift Shaft) | 2 | 2025-09-25 | 2025-09-27
R7S1ONAR-AP18GF273 | Fixing Floor Mat - AP#18 (GF - Front of Lift Shaft) | 2 | 2025-09-28 | 2025-09-29
GARBAGE ROOM |  | 2 | 2025-09-10 | 2025-09-11
R7S1ONAR-AP18GF275 | Paint Finishes and Touchups - Final Coat - AP#18 (GF - Garbage Room) | 2 | 2025-09-10 | 2025-09-11
MEP WORKS |  | 91 | 2025-06-25 | 2025-10-08
MECHANICAL |  | 91 | 2025-06-25 | 2025-10-07
CHILLED WATER |  | 63 | 2025-06-25 | 2025-07-24
R7S1ONME-AP18GF737 | Installation of Chilled water hanger and supports - AP#18 (GF - Corridor) | 4 | 2025-06-25 | 2025-06-30
R7S1ONME-AP18GF789 | Installation of CHWP connection for FCU with Valve package in Corridor, Electrical Room & ICT Room - AP#18 (GF) | 4 | 2025-06-25 | 2025-06-30
R7S1ONME-AP18GF739 | Installation of BTU Meter with valves - AP#18 (GF - Corridor) | 2 | 2025-07-01 | 2025-07-03
R7S1ONME-AP18GF738 | Installation of CHWP piping (connection between modular cages & modular to apartment) - AP#18 (GF - Corridor) | 4 | 2025-06-30 | 2025-07-05
R7S1ONME-AP18GF1406 | CHWP Installation/Connections and Insulation (In Front of Lift Shaft) - AP#18 | 4 | 2025-07-14 | 2025-07-17
R7S1ONME-AP18GF740 | CHWP piping risers connections - AP#18 (GF - Corridor) | 3 | 2025-07-15 | 2025-07-19
R7S1ONME-AP18GF741 | Pressure Testing of CHWP piping - AP#18 (GF - Corridor) | 1 | 2025-07-19 | 2025-07-20
R7S1ONME-AP18GF777 | CHWP Insulation - AP#18 (GF - Corridor) | 4 | 2025-07-20 | 2025-07-24
HVAC DUCTING |  | 86 | 2025-06-25 | 2025-10-05
R7S1ONME-AP18GF788 | Installation of FCU's & Duct Connection in Corridor, Electrical Room & ICT Room - AP#18 (GF) | 4 | 2025-06-25 | 2025-06-30
R7S1ONME-AP18GF790 | Installation of Ducting and insulation (connection between modular cages) - AP#18 (GF - Corridor) | 3 | 2025-06-30 | 2025-07-03
R7S1ONME-AP18GF742 | Duct Riser Continuation - AP#18 (GF - Corridor) | 4 | 2025-07-15 | 2025-07-20
R7S1ONME-AP18GF743 | A/C drain & Copper pipe connection in ELV room - AP#18 (GF) | 2 | 2025-07-20 | 2025-07-22
R7S1ONME-AP18GF778 | Installation of Duct & Grill in Garbage Room - AP#18 (GF - Garbage Room) | 3 | 2025-07-22 | 2025-07-26
R7S1ONME-AP18GF791 | Installation of Grilles in the Corridor - AP#18 (GF - Corridor) | 2 | 2025-10-04 | 2025-10-05
FIRE FIGHTING |  | 76 | 2025-07-15 | 2025-10-07
R7S1ONME-AP18GF744 | Riser Continuity in corridor - AP#18 (GF - Corridor) | 4 | 2025-07-15 | 2025-07-20
R7S1ONME-AP18GF745 | Continuitu of FF pipes & ZC Valves (connection between modular cages & modular to apartment) - AP#18 (GF - Corridor) | 4 | 2025-07-15 | 2025-07-20
R7S1ONME-AP18GF746 | Installation of Sprinklers drops in corridor - AP#18 (GF - Corridor) | 4 | 2025-08-03 | 2025-08-07
R7S1ONME-AP18GF747 | Pressure Test for FF Piping in corridor - AP#18 (GF - Corridor) | 4 | 2025-08-07 | 2025-08-12
R7S1ONME-AP18GF779 | Installation of Pipe & sprinkler in Garbage Room - AP#18 (GF - Garbage Room) | 2 | 2025-08-14 | 2025-08-16
R7S1ONME-AP18GF1616 | Installation of F.F Pipes, Testing & Final Fixtures (In Front of Lift Shaft) - AP18 | 3 | 2025-08-27 | 2025-08-30
R7S1ONME-AP18GF792 | FF Flushing network - AP#18 (GF - Corridor) | 1 | 2025-09-06 | 2025-09-06
R7S1ONME-AP18GF749 | Installation of Alarm check valve, Fire Extinguishers & Blanket - AP#18 (GF - Corridor) | 2 | 2025-10-04 | 2025-10-05
R7S1ONME-AP18GF748 | Installation of Sprinklers in corridor - AP#18 (GF - Corridor) | 4 | 2025-10-04 | 2025-10-07
WATER SUPPLY |  | 75 | 2025-06-25 | 2025-09-16
R7S1ONME-AP18GF780 | Installation of WS Pipe in Garbage Room - AP#18 (GF - Garbage Room) | 2 | 2025-06-25 | 2025-06-28
R7S1ONME-AP18GF781 | Installation of Sanitary Fixtures in Janitor Room - AP#18 (GF - Janitor Room) | 2 | 2025-06-25 | 2025-06-28
R7S1ONME-AP18GF751 | WS High Level Pipe continuation & Insulation works - AP#18 (GF - Corridor) | 4 | 2025-06-25 | 2025-06-30
R7S1ONME-AP18GF752 | Installation of Cold, Hot water line & Hot water return - AP#18 (GF - Corridor) | 4 | 2025-06-30 | 2025-07-05
R7S1ONME-AP18GF753 | Water Meter Installation - AP#18 (GF - Corridor) | 4 | 2025-07-05 | 2025-07-09
R7S1ONME-AP18GF750 | Riser Continuity in Shafts - AP#18 (GF - Corridor) | 4 | 2025-07-15 | 2025-07-20
R7S1ONME-AP18GF754 | Pressure Test for WS - AP#18 (GF - Corridor) | 4 | 2025-09-08 | 2025-09-11
R7S1ONME-AP18GF793 | Insulation for Hot water line & Hot water return - AP#18 (GF - Corridor) | 4 | 2025-09-13 | 2025-09-16
DRAINAGE |  | 61 | 2025-06-25 | 2025-09-11
R7S1ONME-AP18GF756 | Installation of Clean-outs, Floor drain in balcony - AP#18 (GF - Corridor) | 4 | 2025-06-25 | 2025-06-30
R7S1ONME-AP18GF757 | Rain Water Riser continuation in Shafts - AP#18 (GF - Corridor) | 4 | 2025-07-15 | 2025-07-20
R7S1ONME-AP18GF758 | Drainage Riser continuation in Shafts - AP#18 (GF - Corridor) | 4 | 2025-07-15 | 2025-07-20
R7S1ONME-AP18GF759 | Testing for Rain Water Riser - AP#18 (GF - Corridor) | 4 | 2025-09-08 | 2025-09-11
R7S1ONME-AP18GF760 | Testing for Drainage Riser1 - AP#18 (GF - Corridor) | 4 | 2025-09-08 | 2025-09-11
ELECTRICAL |  | 89 | 2025-06-25 | 2025-10-08
POWER & LIGHTING |  | 89 | 2025-06-25 | 2025-10-08
R7S1ONME-AP18GF761 | Contiuation of Cable Trays & apartment branches - AP#18 (GF - Corridor) | 4 | 2025-06-25 | 2025-06-30
R7S1ONME-AP18GF762 | Contiuation of Cable Trunking with Flexible conduits for Lights - AP#18 (GF - Corridor) | 4 | 2025-06-25 | 2025-06-30
R7S1ONME-AP18GF763 | Installation of EMT pipes - AP#18 (GF - Corridor) | 5 | 2025-06-25 | 2025-07-01
R7S1ONME-AP18GF1826 | Continuation of Cable Tray/Trunking with Flexible conduits for Lights (In Front of Lift Shaft) - AP#18 | 4 | 2025-08-31 | 2025-09-03
R7S1ONME-AP18GF764 | Installation of Busbar, Electrical Meter & Tap-off - AP#18 (GF - Corridor) | 3 | 2025-09-06 | 2025-09-08
R7S1ONME-AP18GF787 | Termination of Tap-off with Electrical Meter in the apartments - AP#18 (GF - Corridor) | 3 | 2025-09-09 | 2025-09-11
R7S1ONME-AP18GF765 | Corridor Wire Pulling - AP#18 (GF - Corridor) | 6 | 2025-09-07 | 2025-09-13
R7S1ONME-AP18GF766 | Electrical Room - Installation of Cable trays, SMDB & Termination - AP#18 (GF - Corridor) | 6 | 2025-09-14 | 2025-09-20
R7S1ONME-AP18GF768 | Installation, Termination of Emergeny & Exit Lights with contiuity - AP#18 (GF - Corridor) | 2 | 2025-10-04 | 2025-10-05
R7S1ONME-AP18GF767 | Installation, Termination of Light Fixtures with continuity test - AP#18 (GF - Corridor & Balconies) | 3 | 2025-10-04 | 2025-10-06
R7S1ONME-AP18GF769 | Installation, Termination of PIR sensors with continuity test - AP#18 (GF - Corridor) | 2 | 2025-10-07 | 2025-10-08
LOW CURRENT SYSTEM |  | 88 | 2025-06-25 | 2025-10-07
R7S1ONME-AP18GF794 | CBS System cable installation - AP#18 (GF - Corridor) | 3 | 2025-06-25 | 2025-06-29
R7S1ONME-AP18GF770 | Installation of Basket trays for BMS, CCTV, Access Control - AP#18 (GF - Corridor) | 4 | 2025-06-25 | 2025-06-30
R7S1ONME-AP18GF772 | Fire alarm cable installation - AP#18 (GF - Corridor) | 3 | 2025-06-26 | 2025-06-30
R7S1ONME-AP18GF771 | Voice Evacuation cable installation - AP#18 (GF - Corridor) | 3 | 2025-06-29 | 2025-07-02
R7S1ONME-AP18GF773 | Fibre optic Cable pulling & Termination with OTO (in corridors to ONU) - AP#18 (GF - Corridor) | 2 | 2025-09-04 | 2025-09-06
R7S1ONME-AP18GF774 | BMS, CCTV & Access control Cable installation - AP#18 (GF - Corridor) | 2 | 2025-09-04 | 2025-09-06
R7S1ONME-AP18GF2036 | Installation of Basket trays for Low Current, Cable Installation (In Front of Lift Shaft) - AP#18 | 4 | 2025-09-04 | 2025-09-08
R7S1ONME-AP18GF775 | Low Current Works including BMS Panel in ICT Room - AP#18 (GF - Corridor) | 10 | 2025-08-31 | 2025-09-10
R7S1ONME-AP18GF786 | Fluke test for CCTV & Fibre Optic Cable - AP#18 (GF - Corridor) (Ceiling 1st Fix) | 2 | 2025-09-09 | 2025-09-10
R7S1ONME-AP18GF783 | Installation & Termination of Access control system for Electrical Room - AP#18 (GF) | 2 | 2025-09-10 | 2025-09-11
R7S1ONME-AP18GF782 | Installation & Termination of CCTV Cameras - AP#18 (GF - Corridor) | 2 | 2025-10-04 | 2025-10-05
R7S1ONME-AP18GF785 | Installation & Termination of Wireless Gateway & RF Node in corridors - AP#18 (GF - Corridor) | 2 | 2025-10-04 | 2025-10-05
R7S1ONME-AP18GF776 | Installation & Termination of Fire alarm devices & Speakers - AP#18 (GF - Corridor) | 4 | 2025-10-04 | 2025-10-07
R7S1ONME-AP18GF784 | Installation & Termination of Active Components & UPS installation in ICT Room - AP#18 (GF - Corridor) | 2 | 2025-10-06 | 2025-10-07
FIRST FLOOR |  | 151 | 2025-07-19 | 2025-10-20
ARCH./ CIVIL WORKS |  | 135 | 2025-07-24 | 2025-10-20
CORRIDOR AREA |  | 68 | 2025-07-28 | 2025-10-20
R7S1ONAR-AP18FF360 | Flooring in Corridor - AP#18 (FF - Corridor) | 6 | 2025-07-28 | 2025-08-04
R7S1ONAR-AP18FF361 | Corridor Skirting - AP#18 (FF - Corridor) | 2 | 2025-08-03 | 2025-08-05
R7S1ONAR-AP18FF358 | False Ceiling - 1st Fix - AP#18 (FF - Corridor) | 4 | 2025-08-05 | 2025-08-10
R7S1ONAR-AP18FF359 | Gypsum Wall Cladding (Shafts) - AP#18 (FF - Corridor) | 6 | 2025-09-22 | 2025-09-29
R7S1ONAR-AP18FF362 | Gypsum Wall Cladding (Shafts) -2nd Fix - AP#18 (FF Corridor) | 4 | 2025-09-30 | 2025-10-04
R7S1ONAR-AP18FF366 | Fixing Architrave - AP#18 (FF Corridor) | 2 | 2025-10-05 | 2025-10-06
R7S1ONAR-AP18FF367 | Fixing Aluminium Doors - AP#18 (FF Corridor) | 2 | 2025-10-07 | 2025-10-08
R7S1ONAR-AP18FF363 | False Ceiling - 2nd Fix (Closing the Ceiling) - AP#18 (FF Corridor) | 3 | 2025-10-09 | 2025-10-12
R7S1ONAR-AP18FF364 | Painting - Surface Prep., Primer & 1st Coat for Walls - AP#18 (FF Corridor) | 8 | 2025-10-05 | 2025-10-13
R7S1ONAR-AP18FF387 | Painting - Surface Prep., Primer & 1st Coat for Ceiling - AP#18 (FF Corridor) | 4 | 2025-10-13 | 2025-10-16
R7S1ONAR-AP18FF365 | Painting - Final Coat (Ceiling + Walls) - AP#18 (FF Corridor) | 3 | 2025-10-18 | 2025-10-20
INSIDE BOXES |  | 12 | 2025-08-25 | 2025-09-07
R7S1ONAR-AP18FF368 | Fixing Thresholds (Joining the Room) - AP#18 (FF - inside Boxes) | 4 | 2025-08-25 | 2025-08-28
R7S1ONAR-AP18FF369 | Fixing Wooden Doors - AP#18 (FF - inside Boxes) | 4 | 2025-08-30 | 2025-09-02
R7S1ONAR-AP18FF370 | Fixing Aluminium Doors (Next Floor) - AP#18 (FF - inside Boxes) | 4 | 2025-09-03 | 2025-09-07
IN FRONT OF LIFT SHAFT |  | 113 | 2025-07-24 | 2025-10-01
R7S1ONAR-AP18FF372 | Flooring - AP#18 (FF - Front of Lift Shaft) | 4 | 2025-07-24 | 2025-07-28
R7S1ONAR-AP18FF373 | Skirting & Thresholds - AP#18 (FF - Front of Lift Shaft) | 1 | 2025-07-28 | 2025-07-28
R7S1ONAR-AP18FF374 | Painting - Surface Prep., Primer & 1st Coat - AP#18 (FF - Front of Lift Shaft) | 4 | 2025-07-29 | 2025-08-02
R7S1ONAR-AP18FF371 | False Ceiling - 1st Fix - AP#18 (FF - Front of Lift Shaft) | 4 | 2025-08-03 | 2025-08-06
R7S1ONAR-AP18FF375 | False Ceiling - Final Fix - AP#18 (FF - Front of Lift Shaft) | 3 | 2025-08-27 | 2025-08-30
R7S1ONAR-AP18FF377 | Fixing Handrail - AP#18 (FF - Front of Lift Shaft) | 3 | 2025-08-31 | 2025-09-02
R7S1ONAR-AP18FF378 | Paint for Handrail - AP#18 (FF - Front of Lift Shaft) | 3 | 2025-09-03 | 2025-09-06
R7S1ONAR-AP18FF376 | Painting - 2nd Coat - AP#18 (FF - Front of Lift Shaft) | 3 | 2025-09-07 | 2025-09-09
R7S1ONAR-AP18FF380 | Fixing Wall Guard - AP#18 (FF - Front of Lift Shaft) | 2 | 2025-09-28 | 2025-09-29
R7S1ONAR-AP18FF379 | Fixing Floor Mat - AP#18 (FF - Front of Lift Shaft) | 2 | 2025-09-30 | 2025-10-01
GARBAGE ROOM |  | 14 | 2025-08-30 | 2025-09-09
R7S1ONAR-AP18FF381 | Installation of Dry Walls - First Fix - AP#18 (FF - Garbage Room) | 2 | 2025-08-30 | 2025-08-31
R7S1ONAR-AP18FF382 | Installation of Dry Walls - Final Fix - AP#18 (FF - Garbage Room) | 2 | 2025-08-31 | 2025-09-01
R7S1ONAR-AP18FF383 | Garbage Rooms - Wall Tile Finishes (One Side) - AP#18 (FF - Garbage Room) | 2 | 2025-09-01 | 2025-09-02
R7S1ONAR-AP18FF384 | Paint Works of Dry Walls - First Coat - AP#18 (FF - Garbage Room) | 2 | 2025-09-03 | 2025-09-04
R7S1ONAR-AP18FF385 | Installation of the Garbage Chute Door - AP#18 (FF - Garbage Room) | 2 | 2025-09-06 | 2025-09-07
R7S1ONAR-AP18FF386 | Paint Finishes and Touchups - Final Coat - AP#18 (FF - Garbage Room) | 2 | 2025-09-08 | 2025-09-09
MEP WORKS |  | 71 | 2025-07-19 | 2025-10-18
MECHANICAL |  | 71 | 2025-07-19 | 2025-10-15
CHILLED WATER |  | 56 | 2025-07-19 | 2025-08-24
R7S1ONME-AP18FF1416 | CHWP Installation/Connections and Insulation (In Front of Lift Shaft) - AP#18 | 4 | 2025-07-19 | 2025-07-22
R7S1ONME-AP18FF474 | Installation of Chilled water hanger and supports - AP#18 (FF Corridor) | 4 | 2025-07-24 | 2025-07-28
R7S1ONME-AP18FF524 | Installation of CHWP connection for FCU with Valve package in Corridor, Electrical Room & ICT Room | 4 | 2025-07-24 | 2025-07-28
R7S1ONME-AP18FF476 | Installation of BTU Meter with valves - AP#18 (FF Corridor) | 2 | 2025-07-30 | 2025-07-31
R7S1ONME-AP18FF475 | Installation of CHWP piping (connection between modular cages & modular to apartment) - AP#18 -(FF Corridor) | 4 | 2025-07-29 | 2025-08-02
R7S1ONME-AP18FF477 | CHWP piping risers connections - AP#18 (FF Corridor) | 3 | 2025-08-16 | 2025-08-18
R7S1ONME-AP18FF478 | Pressure Testing of CHWP piping - AP#18 (FF Corridor) | 1 | 2025-08-19 | 2025-08-19
R7S1ONME-AP18FF513 | CHWP Insulation - AP#18 (FF Corridor) | 4 | 2025-08-20 | 2025-08-24
HVAC DUCTING |  | 63 | 2025-07-24 | 2025-10-14
R7S1ONME-AP18FF525 | Installation of FCU's & Duct Connection in Corridor, Electrical Room & ICT Room - AP#18 (FF Corridor) | 4 | 2025-07-24 | 2025-07-28
R7S1ONME-AP18FF479 | Duct Riser Continuation - AP#18 (FF Corridor) | 4 | 2025-08-16 | 2025-08-19
R7S1ONME-AP18FF480 | A/C drain & Copper pipe connection in ELV room - AP#18 (FF Corridor) | 2 | 2025-08-20 | 2025-08-21
R7S1ONME-AP18FF526 | Installation of Ducting and insulation (connection between modular cages) - AP#18 (FF Corridor) | 3 | 2025-08-20 | 2025-08-23
R7S1ONME-AP18FF514 | Installation of Duct & Grill in Garbage Room - AP#18 (FF Corridor) | 2 | 2025-08-23 | 2025-08-24
R7S1ONME-AP18FF527 | Installation of Grilles in the Corridor - AP#18 (FF Corridor) | 2 | 2025-10-13 | 2025-10-14
FIRE FIGHTING |  | 45 | 2025-07-23 | 2025-10-15
R7S1ONME-AP18FF1626 | Installation of F.F Pipes, Testing & Final Fixtures (In Front of Lift Shaft) - AP18 | 3 | 2025-07-23 | 2025-07-26
R7S1ONME-AP18FF515 | Installation of Pipe & sprinkler in Garbage Room - AP#18 (FF Corridor) | 1 | 2025-08-16 | 2025-08-16
R7S1ONME-AP18FF481 | Riser Continuity in corridor - AP#18 (FF Corridor) | 4 | 2025-08-16 | 2025-08-19
R7S1ONME-AP18FF482 | Continuation of FF pipes & ZC Valves (connection between modular cages & modular to apartment) - AP#18 (FF Corridor) | 4 | 2025-08-16 | 2025-08-19
R7S1ONME-AP18FF483 | Installation of Sprinklers drops in corridor - AP#18 (FF Corridor) | 4 | 2025-08-20 | 2025-08-24
R7S1ONME-AP18FF484 | Pressure Test for FF Piping in corridor - AP#18 (FF Corridor) | 2 | 2025-08-25 | 2025-08-26
R7S1ONME-AP18FF528 | FF Flushing network - AP#18 (FF Corridor) | 2 | 2025-09-06 | 2025-09-07
R7S1ONME-AP18FF486 | Installation of Alarm check valve, Fire Extinguishers & Blanket (Last Stage of the Building) - AP#18 (FF Corridor) | 2 | 2025-10-13 | 2025-10-14
R7S1ONME-AP18FF485 | Installation of Sprinklers in corridor - AP#18 (FF Corridor) | 3 | 2025-10-13 | 2025-10-15
WATER SUPPLY |  | 56 | 2025-07-24 | 2025-09-21
R7S1ONME-AP18FF516 | Installation of WS Pipe in Garbage Room - AP#18 (FF Corridor) | 2 | 2025-07-24 | 2025-07-26
R7S1ONME-AP18FF517 | Installation of Sanitary Fixtures in Janitor Room - AP#18 (FF Corridor) | 2 | 2025-07-24 | 2025-07-26
R7S1ONME-AP18FF488 | WS High Level Pipe continuation & Insulation works in Corridor - AP#18 (FF Corridor) | 4 | 2025-07-24 | 2025-07-28
R7S1ONME-AP18FF489 | Installation of Cold, Hot water line & Hot water return in corridor - AP#18 (FF Corridor) | 4 | 2025-07-29 | 2025-08-02
R7S1ONME-AP18FF490 | Water Meter Installation in Corridor - AP#18 (FF Corridor) | 4 | 2025-08-03 | 2025-08-06
R7S1ONME-AP18FF487 | Riser Continuity in Shafts - AP#18 (FF Corridor) | 4 | 2025-08-16 | 2025-08-19
R7S1ONME-AP18FF491 | Pressure Test for WS - AP#18 (FF Corridor) | 4 | 2025-09-08 | 2025-09-11
R7S1ONME-AP18FF529 | Insulation for Hot water line & Hot water return in corridor - AP#18 (FF Corridor) | 4 | 2025-09-17 | 2025-09-21
DRAINAGE |  | 38 | 2025-07-24 | 2025-09-11
R7S1ONME-AP18FF492 | Installation of Clean-outs, Floor drain in balcony - AP#18 (FF Corridor) | 4 | 2025-07-24 | 2025-07-28
R7S1ONME-AP18FF493 | Rain Water Riser continuation in Shafts - AP#18 (FF Corridor) | 4 | 2025-08-16 | 2025-08-19
R7S1ONME-AP18FF494 | Drainage Riser continuation in Shafts - AP#18 (FF Corridor) | 4 | 2025-08-16 | 2025-08-19
R7S1ONME-AP18FF495 | Testing for Rain Water Riser - AP#18 (FF Corridor) | 4 | 2025-09-08 | 2025-09-11
R7S1ONME-AP18FF496 | Testing for Drainage Riser - AP#18 (FF Corridor) | 4 | 2025-09-08 | 2025-09-11
ELECTRICAL |  | 50 | 2025-07-24 | 2025-10-18
POWER & LIGHTING |  | 44 | 2025-07-24 | 2025-10-18
R7S1ONME-AP18FF497 | Contiuation of Cable Trays & apartment branches - AP#18 (FF Corridor) | 4 | 2025-07-24 | 2025-07-28
R7S1ONME-AP18FF498 | Contiuation of Cable Trunking with Flexible conduits for Lights - AP#18 (FF Corridor) | 4 | 2025-07-24 | 2025-07-28
R7S1ONME-AP18FF499 | Installation of EMT pipes - AP#18 (FF Corridor) | 5 | 2025-07-24 | 2025-07-29
R7S1ONME-AP18FF1836 | Continuation of Cable Tray/Trunking with Flexible conduits for Lights (In Front of Lift Shaft) - AP#18 | 4 | 2025-07-27 | 2025-07-30
R7S1ONME-AP18FF500 | Installation of Busbar, Electrical Meter & Tap-off - AP#18 (FF Corridor) | 3 | 2025-07-29 | 2025-07-31
R7S1ONME-AP18FF523 | Termination of Tap-off with Electrical Meter in the apartments - AP#18 (FF Corridor) | 3 | 2025-08-02 | 2025-08-04
R7S1ONME-AP18FF501 | Corridor Wire Pulling - AP#18 (FF Corridor) | 6 | 2025-07-30 | 2025-08-05
R7S1ONME-AP18FF502 | Electrical Room - Installation of Cable trays, SMDB & Termination - AP#18 (FF Corridor) | 6 | 2025-08-06 | 2025-08-12
R7S1ONME-AP18FF504 | Installation, Termination of Emergeny & Exit Lights with contiuity - AP#18 (FF Corridor) | 2 | 2025-10-13 | 2025-10-14
R7S1ONME-AP18FF503 | Installation, Termination of Light Fixtures with continuity test - AP#18 (FF - Corridor & Balconies) | 3 | 2025-10-13 | 2025-10-15
R7S1ONME-AP18FF505 | Installation, Termination of PIR sensors with continuity test - AP#18 (FF Corridor) | 2 | 2025-10-16 | 2025-10-18
LOW CURRENT SYSTEM |  | 47 | 2025-07-24 | 2025-10-16
R7S1ONME-AP18FF530 | CBS System cable installation - AP#18 (FF Corridor) | 3 | 2025-07-24 | 2025-07-27
R7S1ONME-AP18FF506 | Installation of Basket trays for BMS, CCTV, Access Control - AP#18 (FF Corridor) | 4 | 2025-07-24 | 2025-07-28
R7S1ONME-AP18FF508 | Fire alarm cable installation - AP#18 (FF Corridor) | 3 | 2025-07-26 | 2025-07-28
R7S1ONME-AP18FF507 | Voice Evacuation cable installation - AP#18 (FF Corridor) | 3 | 2025-07-28 | 2025-07-30
R7S1ONME-AP18FF509 | Fibre optic Cable pulling & Termination with OTO (in corridors to ONU) - AP#18 (FF Corridor) | 2 | 2025-09-07 | 2025-09-08
R7S1ONME-AP18FF510 | BMS, CCTV & Access control Cable installation - AP#18 (FF Corridor) | 2 | 2025-09-07 | 2025-09-08
R7S1ONME-AP18FF511 | Low Current Works including BMS Panel in ICT Room - AP#18 (FF Corridor) | 10 | 2025-09-02 | 2025-09-13
R7S1ONME-AP18FF522 | Fluke test for CCTV & Fibre Optic Cable - AP#18 (FF Corridor) | 2 | 2025-09-11 | 2025-09-13
R7S1ONME-AP18FF2046 | Installation of Basket trays for Low Current, Cable Installation (In Front of Lift Shaft) - AP#18 | 4 | 2025-09-09 | 2025-09-13
R7S1ONME-AP18FF518 | Installation & Termination of CCTV Cameras - AP#18 (FF Corridor) | 2 | 2025-10-13 | 2025-10-14
R7S1ONME-AP18FF519 | Installation & Termination of Access control system for Electrical Room - AP#18 (FF Corridor) | 2 | 2025-10-13 | 2025-10-14
R7S1ONME-AP18FF521 | Installation & Termination of Wireless Gateway & RF Node - AP#18 (FF Corridor) | 2 | 2025-10-13 | 2025-10-14
R7S1ONME-AP18FF512 | Installation & Termination of Fire alarm devices & Speakers - AP#18 (FF Corridor) | 4 | 2025-10-13 | 2025-10-16
R7S1ONME-AP18FF520 | Installation & Termination of Active Components & UPS installation in ICT Room | 2 | 2025-10-15 | 2025-10-16
SECOND FLOOR |  | 117 | 2025-07-23 | 2025-11-20
ARCH./ CIVIL WORKS |  | 111 | 2025-08-04 | 2025-11-20
CORRIDOR AREA |  | 50 | 2025-08-04 | 2025-11-20
R7S1ONAR-AP18SF260 | Flooring in Corridor - AP#18 (SF Corridor) | 6 | 2025-08-04 | 2025-08-11
R7S1ONAR-AP18SF261 | Corridor Skirting - AP#18 (SF Corridor) | 2 | 2025-08-10 | 2025-08-12
R7S1ONAR-AP18SF258 | False Ceiling - 1st Fix - AP#18 (SF Corridor) | 4 | 2025-08-12 | 2025-08-17
R7S1ONAR-AP18SF259 | Gypsum Wall Cladding (Shafts) - AP#18 (SF Corridor) | 6 | 2025-10-23 | 2025-10-29
R7S1ONAR-AP18SF262 | Gypsum Wall Cladding (Shafts) -2nd Fix - AP#18 (SF Corridor) | 4 | 2025-10-30 | 2025-11-03
R7S1ONAR-AP18SF266 | Fixing Architrave - AP#18 (SF Corridor) | 2 | 2025-11-04 | 2025-11-05
R7S1ONAR-AP18SF267 | Fixing Aluminium Doors - AP#18 (SF Corridor) | 2 | 2025-11-06 | 2025-11-08
R7S1ONAR-AP18SF263 | False Ceiling - 2nd Fix (Closing the Ceiling) - AP#18 (SF Corridor) | 3 | 2025-11-09 | 2025-11-11
R7S1ONAR-AP18SF264 | Painting - Surface Prep., Primer & 1st Coat - AP#18 (SF Corridor) | 8 | 2025-11-04 | 2025-11-12
R7S1ONAR-AP18SF288 | Painting - Surface Prep., Primer & 1st Coat - AP#18 (SF Corridor) | 4 | 2025-11-12 | 2025-11-16
R7S1ONAR-AP18SF265 | Painting - Final Coat (Ceiling + Walls) - AP#18 (SF Corridor) | 3 | 2025-11-18 | 2025-11-20
INSIDE BOXES |  | 12 | 2025-08-25 | 2025-09-07
R7S1ONAR-AP18SF268 | Fixing Thresholds (Joining the Room) - AP#18 (SF - inside Boxes) | 4 | 2025-08-25 | 2025-08-28
R7S1ONAR-AP18SF269 | Fixing Wooden Doors - AP#18 (SF - inside Boxes) | 4 | 2025-08-30 | 2025-09-02
R7S1ONAR-AP18SF270 | Fixing Aluminium Doors (Next Floor) - AP#18 (SF - inside Boxes) | 4 | 2025-09-03 | 2025-09-07
IN FRONT OF LIFT SHAFT |  | 111 | 2025-08-25 | 2025-10-29
R7S1ONAR-AP18SF272 | Flooring - AP#18 (SF - Front of Lift Shaft) | 4 | 2025-08-25 | 2025-08-28
R7S1ONAR-AP18SF273 | Skirting & Thresholds - AP#18 (SF - Front of Lift Shaft) | 2 | 2025-08-30 | 2025-08-31
R7S1ONAR-AP18SF274 | Painting - Surface Prep., Primer & 1st Coat - AP#18 (SF - Front of Lift Shaft) | 4 | 2025-09-01 | 2025-09-04
R7S1ONAR-AP18SF271 | False Ceiling - 1st Fix - AP#18 (SF - Front of Lift Shaft) | 3 | 2025-09-06 | 2025-09-08
R7S1ONAR-AP18SF275 | False Ceiling - Final Fix - AP#18 (SF - Front of Lift Shaft) | 3 | 2025-09-09 | 2025-09-11
R7S1ONAR-AP18SF277 | Fixing Handrail - AP#18 (SF - Front of Lift Shaft) | 3 | 2025-09-13 | 2025-09-15
R7S1ONAR-AP18SF278 | Paint for Handrail - AP#18 (SF - Front of Lift Shaft) | 3 | 2025-09-16 | 2025-09-18
R7S1ONAR-AP18SF276 | Painting - 2nd Coat - AP#18 (SF - Front of Lift Shaft) | 3 | 2025-10-25 | 2025-10-27
R7S1ONAR-AP18SF279 | Fixing Floor Mat - AP#18 (SF - Front of Lift Shaft) | 2 | 2025-10-28 | 2025-10-29
R7S1ONAR-AP18SF280 | Fixing Wall Guard - AP#18 (SF - Front of Lift Shaft) | 2 | 2025-10-28 | 2025-10-29
GARBAGE ROOM |  | 26 | 2025-08-05 | 2025-11-16
R7S1ONAR-AP18SF287 | Installation of Garbage Chute Full System from GF to 2nd Floor - AP#18 (SF - Garbage Room) | 10 | 2025-08-05 | 2025-08-16
R7S1ONAR-AP18SF281 | Installation of Dry Walls - First Fix - AP#18 (SF - Garbage Room) | 2 | 2025-08-17 | 2025-08-18
R7S1ONAR-AP18SF282 | Installation of Dry Walls - Final Fix - AP#18 (SF - Garbage Room) | 2 | 2025-08-19 | 2025-08-20
R7S1ONAR-AP18SF283 | Garbage Rooms - Wall Tile Finishes (One Side) - AP#18 (SF - Garbage Room) | 2 | 2025-08-20 | 2025-08-21
R7S1ONAR-AP18SF284 | Paint Works of Dry Walls - First Coat - AP#18 (SF - Garbage Room) | 2 | 2025-08-23 | 2025-08-24
R7S1ONAR-AP18SF285 | Installation of the Garbage Chute Door - AP#18 (SF - Garbage Room) | 2 | 2025-08-25 | 2025-08-26
R7S1ONAR-AP18SF286 | Paint Finishes and Touchups - Final Coat - AP#18 (SF - Garbage Room) | 2 | 2025-11-15 | 2025-11-16
MEP WORKS |  | 61 | 2025-07-23 | 2025-11-17
MECHANICAL |  | 61 | 2025-07-23 | 2025-11-16
CHILLED WATER |  | 22 | 2025-07-23 | 2025-09-10
R7S1ONME-AP18SF1426 | CHWP Installation/Connections and Insulation (In Front of Lift Shaft) - AP#18 | 4 | 2025-07-23 | 2025-07-27
R7S1ONME-AP18SF441 | Installation of Chilled water hanger and supports - AP#18 (SF Corridor) | 4 | 2025-08-25 | 2025-08-28
R7S1ONME-AP18SF491 | Installation of CHWP connection for FCU with Valve package in Corridor, Electrical Room & ICT Room | 4 | 2025-08-25 | 2025-08-28
R7S1ONME-AP18SF443 | Installation of BTU Meter with valves - AP#18 (SF Corridor) | 2 | 2025-08-31 | 2025-09-01
R7S1ONME-AP18SF442 | Installation of CHWP piping (connection between modular cages & modular to apartment) - AP#18 (SF Corridor) | 4 | 2025-08-30 | 2025-09-02
R7S1ONME-AP18SF444 | CHWP piping risers connections - AP#18 (SF Corridor) | 3 | 2025-09-02 | 2025-09-04
R7S1ONME-AP18SF445 | Pressure Testing of CHWP piping - AP#18 (SF Corridor) | 1 | 2025-09-06 | 2025-09-06
R7S1ONME-AP18SF480 | CHWP Insulation - AP#18 (SF Corridor) | 4 | 2025-09-07 | 2025-09-10
HVAC DUCTING |  | 61 | 2025-08-25 | 2025-11-13
R7S1ONME-AP18SF446 | Duct Riser Continuation - AP#18 (SF Corridor) | 4 | 2025-08-25 | 2025-08-28
R7S1ONME-AP18SF492 | Installation of FCU's & Duct Connection in Corridor, Electrical Room & ICT Room - AP#18 (SF Corridor) | 4 | 2025-08-25 | 2025-08-28
R7S1ONME-AP18SF447 | A/C drain & Copper pipe connection in ELV room - AP#18 (SF Corridor) | 2 | 2025-08-30 | 2025-08-31
R7S1ONME-AP18SF493 | Installation of Ducting and insulation (connection between modular cages) - AP#18 (SF Corridor) | 3 | 2025-08-30 | 2025-09-01
R7S1ONME-AP18SF481 | Installation of Duct & Grill in Garbage Room - AP#18 (SF Corridor) | 2 | 2025-11-12 | 2025-11-13
R7S1ONME-AP18SF494 | Installation of Grilles in the Corridor - AP#18 (SF Corridor) | 2 | 2025-11-12 | 2025-11-13
FIRE FIGHTING |  | 57 | 2025-07-28 | 2025-11-16
R7S1ONME-AP18SF1636 | Installation of F.F Pipes, Testing & Final Fixtures (In Front of Lift Shaft) - AP18 | 3 | 2025-07-28 | 2025-07-30
R7S1ONME-AP18SF448 | Riser Continuity Succ - Closing of Gysum Boards on shaft - AP#18 (SF Corridor) | 4 | 2025-08-25 | 2025-08-28
R7S1ONME-AP18SF449 | FF Contiuation on High Level with Valves - AP#18 (SF Corridor) | 4 | 2025-08-25 | 2025-08-28
R7S1ONME-AP18SF450 | Installation of Sprinklers drops - AP#18 (SF Corridor) | 4 | 2025-08-30 | 2025-09-02
R7S1ONME-AP18SF451 | Pressure Test for FF Piping - AP#18 (SF Corridor) | 2 | 2025-09-03 | 2025-09-04
R7S1ONME-AP18SF453 | Installation of Fire Extinguishers - AP#18 (SF Corridor) | 2 | 2025-11-12 | 2025-11-13
R7S1ONME-AP18SF482 | Installation of Pipe & sprinkler in Garbage Room - AP#18 (SF Corridor) | 2 | 2025-11-12 | 2025-11-13
R7S1ONME-AP18SF452 | Installation of Sprinklers - AP#18 (SF Corridor) | 4 | 2025-11-12 | 2025-11-16
WATER SUPPLY |  | 30 | 2025-08-25 | 2025-09-27
R7S1ONME-AP18SF483 | Installation of WS Pipe in Garbage Room - AP#18 (SF Corridor) | 2 | 2025-08-25 | 2025-08-26
R7S1ONME-AP18SF484 | Installation of Sanitary Fixtures in Janitor Room - AP#18 (SF Corridor) | 2 | 2025-08-25 | 2025-08-26
R7S1ONME-AP18SF454 | Riser Continuity - AP#18 (SF Corridor) | 4 | 2025-08-25 | 2025-08-28
R7S1ONME-AP18SF455 | WS High Level Pipe continuation & Insulation works - AP#18 (SF Corridor) | 4 | 2025-08-25 | 2025-08-28
R7S1ONME-AP18SF456 | Instalation of Hot water line in corridor - AP#18 (SF Corridor) | 4 | 2025-08-30 | 2025-09-02
R7S1ONME-AP18SF457 | Water Meter Installation - AP#18 (SF Corridor) | 4 | 2025-09-03 | 2025-09-07
R7S1ONME-AP18SF458 | Pressure Test for WS - AP#18 (SF Corridor) | 4 | 2025-09-13 | 2025-09-16
R7S1ONME-AP18FF531 | Insulation for Hot water line & Hot water return in corridor - AP#18 (SF Corridor) | 4 | 2025-09-22 | 2025-09-27
DRAINAGE |  | 8 | 2025-08-25 | 2025-09-11
R7S1ONME-AP18SF459 | Installation of Clean-outs - AP#18 (SF Corridor) | 4 | 2025-08-25 | 2025-08-28
R7S1ONME-AP18SF460 | Rain Water Riser continuation - AP#18 (SF Corridor) | 4 | 2025-08-25 | 2025-08-28
R7S1ONME-AP18SF461 | Drainage Riser continuation - AP#18 (SF Corridor) | 4 | 2025-08-25 | 2025-08-28
R7S1ONME-AP18SF462 | Testing for Rain Water Riser - AP#18 (SF Corridor) | 4 | 2025-09-08 | 2025-09-11
R7S1ONME-AP18SF463 | Testing for Drainage Riser - AP#18 (SF Corridor) | 4 | 2025-09-08 | 2025-09-11
ELECTRICAL |  | 43 | 2025-07-31 | 2025-11-17
POWER & LIGHTING |  | 43 | 2025-07-31 | 2025-11-17
R7S1ONME-AP18SF1846 | Continuation of Cable Tray/Trunking with Flexible conduits for Lights (In Front of Lift Shaft) - AP#18 | 4 | 2025-07-31 | 2025-08-04
R7S1ONME-AP18SF464 | Contiuation of Cable Trays & apartment branches - AP#18 (SF Corridor) | 4 | 2025-08-25 | 2025-08-28
R7S1ONME-AP18SF465 | Contiuation of Cable Trunking with Flexible conduits for Lights - AP#18 (SF Corridor) | 4 | 2025-08-25 | 2025-08-28
R7S1ONME-AP18SF466 | Installation of EMT pipes - AP#18 (SF Corridor) | 5 | 2025-08-25 | 2025-08-30
R7S1ONME-AP18SF467 | Installation of Busbar, Electrical Meter & Tap-off in Corridor - AP#18 (SF Corridor) | 3 | 2025-08-30 | 2025-09-01
R7S1ONME-AP18SF490 | Termination of Tap-off with Electrical Meter in the apartments - AP#18 (SF Corridor) | 3 | 2025-09-02 | 2025-09-04
R7S1ONME-AP18SF468 | Corridor Wire Pulling - AP#18 (SF Corridor) | 6 | 2025-08-31 | 2025-09-06
R7S1ONME-AP18SF469 | Electrical Room - Installation of Cable trays, SMDB & Termination - AP#18 (SF Corridor) | 6 | 2025-10-18 | 2025-10-23
R7S1ONME-AP18SF471 | Installation, Termination of Emergeny & Exit Lights with contiuity - AP#18 (SF Corridor) | 2 | 2025-11-12 | 2025-11-13
R7S1ONME-AP18SF470 | Installation, Termination of Light Fixtures with continuity test - AP#18 (SF - Corridor & Balconies) | 3 | 2025-11-12 | 2025-11-15
R7S1ONME-AP18SF472 | Installation, Termination of PIR sensors with continuity test - AP#18 (SF Corridor) | 2 | 2025-11-16 | 2025-11-17
LOW CURRENT SYSTEM |  | 42 | 2025-08-25 | 2025-11-16
R7S1ONME-AP18SF495 | CBS System cable installation - AP#18 (SF Corridor) | 3 | 2025-08-25 | 2025-08-27
R7S1ONME-AP18SF473 | Installation of Basket trays for BMS, CCTV, Access Control - AP#18 (SF Corridor) | 4 | 2025-08-25 | 2025-08-28
R7S1ONME-AP18SF475 | Fire alarm cable installation - AP#18 (SF Corridor) | 3 | 2025-08-26 | 2025-08-28
R7S1ONME-AP18SF474 | Voice Evacuation cable installation - AP#18 (SF Corridor) | 3 | 2025-08-28 | 2025-08-31
R7S1ONME-AP18SF476 | Fibre optic Cable pulling & Termination with OTO (in corridors to ONU) - AP#18 (SF Corridor) | 2 | 2025-09-09 | 2025-09-10
R7S1ONME-AP18SF477 | BMS, CCTV & Access control Cable installation - AP#18 (SF Corridor) | 2 | 2025-09-09 | 2025-09-10
R7S1ONME-AP18SF2056 | Installation of Basket trays for Low Current, Cable Installation (In Front of Lift Shaft) - AP#18 | 4 | 2025-09-09 | 2025-09-13
R7S1ONME-AP18SF478 | Low Current Works including BMS Panel in ICT Room - AP#18 (SF Corridor) | 10 | 2025-10-12 | 2025-10-22
R7S1ONME-AP18SF489 | Fluke test for CCTV & Fibre Optic Cable - AP#18 (SF Corridor) | 2 | 2025-10-21 | 2025-10-22
R7S1ONME-AP18SF485 | Installation & Termination of CCTV Cameras - AP#18 (SF Corridor) | 2 | 2025-11-12 | 2025-11-13
R7S1ONME-AP18SF486 | Installation & Termination of Access control system for Electrical Room - AP#18 (SF Corridor) | 2 | 2025-11-12 | 2025-11-13
R7S1ONME-AP18SF488 | Installation & Termination of Wireless Gateway & RF Node in corridors - AP#18 (SF Corridor) | 2 | 2025-11-12 | 2025-11-13
R7S1ONME-AP18SF479 | Installation & Termination of Fire alarm devices & Speakers - AP#18 (SF Corridor) | 4 | 2025-11-12 | 2025-11-16
R7S1ONME-AP18SF487 | Installation & Termination of Active Components & UPS installation in ICT Room - AP#18 (SF Corridor) | 2 | 2025-11-15 | 2025-11-16
ROOF WORKS |  | 73 | 2025-09-08 | 2025-11-12
ARCH./ CIVIL WORKS |  | 73 | 2025-09-08 | 2025-11-12
R7S1ONAR-AP18RF67 | Roof Box Stiching (Concrete Works) - AP#18 (Roof) | 6 | 2025-09-08 | 2025-09-14
R7S1ONME-AP18RF431 | Installation of Roof Drains - AP#18 (Roof) | 2 | 2025-09-13 | 2025-09-14
R7S1ONAR-AP18RF68 | Roof Waterproofing Works with testing - AP#18 (Roof) | 20 | 2025-09-15 | 2025-10-08
R7S1ONAR-AP18RF69 | Laying of Gravel - AP#18 (Roof) | 2 | 2025-10-09 | 2025-10-11
R7S1ONAR-AP18RF70 | Surface Preparation & Primer for Parapets - AP#18 (Roof) | 4 | 2025-10-12 | 2025-10-15
R7S1ONAR-AP18RF71 | 1st Coat Paint for Parapets - AP#18 (Roof) | 2 | 2025-10-16 | 2025-10-18
R7S1ONAR-AP18RF72 | 2nd Coat Paint for Parapets - AP#18 (Roof) | 2 | 2025-10-19 | 2025-10-20
R7S1ONAR-AP18RF74 | Fixing Fall Arrest System - AP#18 (Roof) | 2 | 2025-10-26 | 2025-10-27
R7S1ONAR-AP18RF73 | Crossover Bridges Installation & application of Sealant on MEP penetrations - AP#18 (Roof) | 12 | 2025-10-30 | 2025-11-12
MECHANICAL |  | 31 | 2025-10-12 | 2025-11-03
HVAC |  | 26 | 2025-10-12 | 2025-10-27
R7S1ONME-AP18RF395 | Modular Installation - AP#18 (Roof) | 5 | 2025-10-12 | 2025-10-16
R7S1ONME-AP18RF396 | Continuation of Roof duct works/FAHU Connections - AP#18 (Roof) | 5 | 2025-10-14 | 2025-10-19
R7S1ONME-AP18RF398 | Insulations for ducts - AP#18 (Roof) | 5 | 2025-10-15 | 2025-10-20
R7S1ONME-AP18RF400 | Installation of FAHU - AP#18 (Roof) | 2 | 2025-10-20 | 2025-10-21
R7S1ONME-AP18RF405 | Installation of Outdoor VRF/DX Units - AP#18 (Roof) | 2 | 2025-10-21 | 2025-10-22
R7S1ONME-AP18RF406 | Installation & Insulation of the Condensation Drain - AP#18 (Roof) | 1 | 2025-10-22 | 2025-10-22
R7S1ONME-AP18RF408 | Installation of Ventilation Fans - AP#18 (Roof) | 3 | 2025-10-20 | 2025-10-22
R7S1ONME-AP18RF403 | Chilled Water System Continuation and Connections with Valve package of FAHU - AP#18 (Roof) | 4 | 2025-10-20 | 2025-10-23
R7S1ONME-AP18RF410 | Installation of Louvers - AP#18 (Roof) | 2 | 2025-10-23 | 2025-10-25
R7S1ONME-AP18RF413 | Installation & Testing of Copper Pipes - AP#18 (Roof) | 2 | 2025-10-23 | 2025-10-25
R7S1ONME-AP18RF414 | Miscellaneous Works for Mechanical Connections (Fire & Volume Dampers etc.) - AP#18 (Roof) | 2 | 2025-10-26 | 2025-10-27
WATERSUPPLY & DRAINAGE |  | 25 | 2025-10-18 | 2025-11-02
R7S1ONME-AP18RF394 | Testing for the Rain Water Risers - AP#18 (Roof) | 2 | 2025-10-20 | 2025-10-21
R7S1ONME-AP18RF397 | Installation & Continuation of Water supply pipes (connection between modular cages & modular to Shaft Riser) - AP#18 | 4 | 2025-10-18 | 2025-10-21
R7S1ONME-AP18RF401 | Installation of Air Vent & Pressure Guage with Valves at Roof - AP#18 (Roof) | 4 | 2025-10-20 | 2025-10-23
R7S1ONME-AP18RF402 | Vertical Continuation of Vent Pipes To The Roof (Drainage) - AP#18 (Roof) | 4 | 2025-10-21 | 2025-10-25
R7S1ONME-AP18RF404 | Installation of Rain Water outlet - AP#18 (Roof) | 3 | 2025-10-22 | 2025-10-25
R7S1ONME-AP18RF399 | Installation of Air Vent with Valve for Water Supply - AP#18 (Roof) | 4 | 2025-10-22 | 2025-10-26
R7S1ONME-AP18RF407 | Testing of Water Supply Pipes - AP#18 (Roof) | 2 | 2025-10-27 | 2025-10-28
R7S1ONME-AP18RF409 | Insulation of Roof Water Line - AP#18 (Roof) | 2 | 2025-10-28 | 2025-10-29
R7S1ONME-AP18RF411 | Testing for the Drainage Pipes Risers - AP#18 (Roof) | 2 | 2025-10-30 | 2025-11-01
R7S1ONME-AP18RF412 | Installation of Vent Cowl - AP#18 (Roof) | 1 | 2025-11-02 | 2025-11-02
SOLAR HEATER |  | 27 | 2025-10-22 | 2025-11-03
R7S1ONME-AP18RF426 | Installation of Solar water pumps and circulation pumps with valves(For Water Only) - AP#18 (Roof) | 2 | 2025-10-23 | 2025-10-25
R7S1ONME-AP18RF424 | Installation of Structure and Solar Panels (For Water Only) - AP#18 (Roof) | 5 | 2025-10-22 | 2025-10-27
R7S1ONME-AP18RF425 | Installation of Solar Calorifier Tank & Air cooler (For Water Only) - AP#18 (Roof) | 5 | 2025-10-23 | 2025-10-28
R7S1ONME-AP18RF427 | Installation of Solar Pipes Primary Loop - AP#18 (Roof) | 5 | 2025-10-23 | 2025-10-28
R7S1ONME-AP18RF428 | Testing of Solar Pipes Primary Loop - AP#18 (Roof) | 1 | 2025-10-29 | 2025-10-29
R7S1ONME-AP18RF429 | Insulation of Solar Pipes Primary Loop - AP#18 (Roof) | 1 | 2025-10-29 | 2025-10-29
R7S1ONME-AP18RF430 | Aluminum Cladding of Solar Pipes Primary Loop - AP#18 (Roof) | 4 | 2025-10-30 | 2025-11-03
ELECTRICAL |  | 31 | 2025-10-18 | 2025-11-06
POWER & LOW CURRENT |  | 31 | 2025-10-18 | 2025-11-06
R7S1ONME-AP18RF415 | Installation of Cables for Fire Alarm system - AP#18 (Roof) | 3 | 2025-10-18 | 2025-10-20
R7S1ONME-AP18RF416 | Installation of Cables for BMS - AP#18 (Roof) | 3 | 2025-10-18 | 2025-10-20
R7S1ONME-AP18RF417 | Installation of Fire Alarm Devices - AP#18 (Roof) | 3 | 2025-10-18 | 2025-10-20
R7S1ONME-AP18RF419 | Installation of Roof Light Fixtures - AP#18 (Roof) | 3 | 2025-10-18 | 2025-10-20
R7S1ONME-AP18RF390 | Installation of Isolators and Machine Connections - AP#18 (Roof) | 4 | 2025-10-18 | 2025-10-21
R7S1ONME-AP18RF418 | Installation of BMS Devices - AP#18 (Roof) | 4 | 2025-10-19 | 2025-10-22
R7S1ONME-AP18RF389 | Lightening Protection & Earthing System - AP#18 (Roof) | 7 | 2025-10-18 | 2025-10-25
R7S1ONME-AP18RF391 | Installation of Electrical Containments for BMS - AP#18 (Roof) | 7 | 2025-10-18 | 2025-10-25
R7S1ONME-AP18RF421 | Termination for BMS System - AP#18 (Roof) | 1 | 2025-10-26 | 2025-10-26
R7S1ONME-AP18RF433 | Termination of Primary & Secondary pump for Solar system - AP#18 (Roof) | 1 | 2025-10-26 | 2025-10-26
R7S1ONME-AP18RF392 | Installation of Fire Alarm Containment for FAHU, Fans - AP#18 (Roof) | 4 | 2025-10-26 | 2025-10-29
R7S1ONME-AP18RF422 | Termination for Fire Alarm Device - AP#18 (Roof) | 1 | 2025-10-30 | 2025-10-30
R7S1ONME-AP18RF393 | Installation of LV Power Cables for Roof Equipment - AP#18 (Roof) | 5 | 2025-10-30 | 2025-11-04
R7S1ONME-AP18RF420 | Termination for LV Cables - AP#18 (Roof) | 1 | 2025-11-05 | 2025-11-05
R7S1ONME-AP18RF423 | Megger Test for the Power Cables - AP#18 (Roof) | 1 | 2025-11-06 | 2025-11-06
R7S1ONME-AP18RF432 | Installation & Termination of Solar System Panel - AP#18 (Roof) | 3 | 2025-11-04 | 2025-11-06
STAIR CASE |  | 103 | 2025-09-14 | 2025-11-05
CIVIL WORKS |  | 101 | 2025-09-15 | 2025-11-01
STAIR CASE (MAIN WITH LIFT) |  | 101 | 2025-09-15 | 2025-10-13
R7S1ONST-AP18RG449 | Stair Flooring (Roof to GF) - AP#18 (Main Stair) | 7 | 2025-09-15 | 2025-09-22
R7S1ONST-AP18RG450 | Stair Hand Rails (Roof to GF) - AP#18 (Main Stair) | 6 | 2025-09-24 | 2025-09-30
R7S1ONST-AP18RG451 | Stair Paint - Primer & 1st Coat (Roof to GF)- AP#18 (Main Stair) | 7 | 2025-10-01 | 2025-10-08
R7S1ONST-AP18RG452 | Stair Paint - Final Coat (Roof to GF)- AP#18 (Main Stair) | 4 | 2025-10-09 | 2025-10-13
STAIR CASE (LEFT SIDE) |  | 42 | 2025-09-24 | 2025-10-19
R7S1ONST-AP18RG459 | Stair Flooring (Roof to GF) - AP#18 Left Side Stair | 7 | 2025-09-24 | 2025-10-01
R7S1ONST-AP18RG460 | Stair Hand Rails (Roof to GF) - AP#18 Left Side Stair | 6 | 2025-10-02 | 2025-10-08
R7S1ONST-AP18RG461 | Stair Paint - Primer & 1st Coat (Roof to GF) - AP#18 Left Side Stair | 6 | 2025-10-09 | 2025-10-15
R7S1ONST-AP18RG462 | Stair Paint - Final Coat (Roof to GF) - AP#18 Left Side Stair | 3 | 2025-10-16 | 2025-10-19
STAIR CASE (RIGHT SIDE) |  | 36 | 2025-10-02 | 2025-11-01
R7S1ONST-AP18RG463 | Stair Flooring (Roof to GF) - AP#18 Right Side Stair | 8 | 2025-10-02 | 2025-10-11
R7S1ONST-AP18RG464 | Stair Hand Rails (Roof to GF) - AP#18 Right Side Stair | 7 | 2025-10-12 | 2025-10-19
R7S1ONST-AP18RG465 | Stair Paint - Primer & 1st Coat (Roof to GF) - AP#18 Right Side Stair | 7 | 2025-10-20 | 2025-10-27
R7S1ONST-AP18RG466 | Stair Paint - Final Coat (Roof to GF) - AP#18 Right Side Stair | 4 | 2025-10-28 | 2025-11-01
MEP WORKS |  | 68 | 2025-09-14 | 2025-11-05
STAIR CASE (MAIN WITH LIFT) |  | 52 | 2025-09-14 | 2025-10-18
R7S1ONST-AP18RG448 | Main Staircase Wire Pulling - AP#18 (Main Stair) | 3 | 2025-09-14 | 2025-09-16
R7S1ONST-AP18RG467 | Final fix - Main Staircase Lights Fixtures & Motion Sensor - AP#18 (Main Stair) | 2 | 2025-10-14 | 2025-10-15
R7S1ONST-AP18RG468 | Final fix - Main Staircase Emergency Lights Fixtures - AP#18 (Main Stair) | 2 | 2025-10-16 | 2025-10-18
STAIR CASE (LEFT SIDE) |  | 55 | 2025-09-17 | 2025-10-23
R7S1ONST-AP18RG453 | Left Staircase Wire Pulling - AP#18 (Main Stair) | 3 | 2025-09-17 | 2025-09-20
R7S1ONST-AP18RG455 | Final fix - Left Staircase Lights Fixtures & Motion Sensor - AP#18 (Main Stair) | 2 | 2025-10-20 | 2025-10-21
R7S1ONST-AP18RG457 | Final fix - Left Staircase Emergency Lights Fixtures - AP#18 (Main Stair) | 2 | 2025-10-22 | 2025-10-23
STAIR CASE (RIGHT SIDE) |  | 63 | 2025-09-21 | 2025-11-05
R7S1ONST-AP18RG454 | Right Staircase Wire Pulling - AP#18 (Main Stair) | 3 | 2025-09-21 | 2025-09-24
R7S1ONST-AP18RG456 | Final fix - Right Staircase Lights Fixtures & Motion Sensor - AP#18 (Main Stair) | 2 | 2025-11-02 | 2025-11-03
R7S1ONST-AP18RG458 | Final fix - Right Staircase Emergency Lights Fixtures - AP#18 (Main Stair) | 2 | 2025-11-04 | 2025-11-05
ELEVATOR WORKS |  | 18 | 2025-09-28 | 2025-10-22
R7S1ONEL-AP18GR643 | Installation of Rails - AP#18 (Elevator Works) | 6 | 2025-09-28 | 2025-10-04
R7S1ONEL-AP18GR644 | Assembly of Cabin - AP#18 (Elevator Works) | 4 | 2025-10-05 | 2025-10-08
R7S1ONEL-AP18GR645 | Installation of Motor - AP#18 (Elevator Works) | 4 | 2025-10-09 | 2025-10-13
R7S1ONEL-AP18GR646 | Installation of Main Cables - AP#18 (Elevator Works) | 4 | 2025-10-14 | 2025-10-18
R7S1ONEL-AP18GR647 | Installation of Doors, Indicator, Push Button - AP#18 (Elevator Works) | 2 | 2025-10-19 | 2025-10-20
R7S1ONEL-AP18GR648 | Interior Finishes - AP#18 (Elevator Works) | 2 | 2025-10-21 | 2025-10-22
EXTERNAL ELEVATIONS |  | 103 | 2025-09-24 | 2025-11-02
ARCH./ CIVIL WORKS |  | 103 | 2025-09-24 | 2025-11-02
R7S1ONEE-AP18GR529 | External Selant Works - For Boxes - AP#18 (External Elevations) | 15 | 2025-09-24 | 2025-10-11
R7S1ONEE-AP18GR530 | Final Finishes & Touchups - AP#18 (External Elevations) | 20 | 2025-10-01 | 2025-10-23
R7S1ONME-AP18GF755 | Installation of rain water outlet - External façade - AP#18 (External Elevations) | 2 | 2025-10-25 | 2025-10-26
R7S1ONEE-AP18GR532 | Installation of External Signages - AP#18 (External Elevations) | 4 | 2025-10-27 | 2025-10-30
R7S1ONEE-AP18GR531 | Fixing Cage Ladder - AP#18 (External Elevations) | 2 | 2025-11-01 | 2025-11-02
EXTERNAL - CIVIL WORKS |  | 48 | 2025-09-18 | 2025-10-23
DRAINAGE |  | 20 | 2025-09-18 | 2025-10-02
R7S1ONECW-AP18-397 | Excavation Works & Sand Bedding - AP#18 (External Drainage) | 3 | 2025-09-18 | 2025-09-21
R7S1ONECW-AP18-398 | Drainage Manholes - AP#18 | 6 | 2025-09-18 | 2025-09-25
R7S1ONECW-AP18-399 | Drainage Backfilling - AP#18 | 2 | 2025-10-01 | 2025-10-02
WATERSUPPLY |  | 28 | 2025-09-18 | 2025-10-14
R7S1ONECW-AP18-400 | Excavation Works & Sand Bedding - Watersupply - AP#18 (External Watersupply Civil) | 3 | 2025-09-18 | 2025-09-21
R7S1ONECW-AP18-401 | Watersupply Manholes - AP#18 | 6 | 2025-09-22 | 2025-09-29
R7S1ONECW-AP18-402 | Watersupply Backfilling - AP#18 | 2 | 2025-10-13 | 2025-10-14
CHILLED WATER |  | 11 | 2025-09-22 | 2025-10-05
R7S1ONECW-AP18-406 | Excavation Works & Sand Bedding - AP#18 (External Chilled Water Civil) | 3 | 2025-09-22 | 2025-09-25
R7S1ONECW-AP18-407 | Chilled Water Manholes - AP#18 | 6 | 2025-09-27 | 2025-10-02
R7S1ONECW-AP18-408 | Chilled Water Backfilling - AP#18 | 2 | 2025-10-04 | 2025-10-05
FIRE FIGHTING |  | 28 | 2025-09-22 | 2025-10-11
R7S1ONECW-AP18-403 | Excavation Works & Sand Bedding - AP#18 (External Chilled Water Civil) | 3 | 2025-09-22 | 2025-09-25
R7S1ONECW-AP18-404 | Fire Fighting Manholes - AP#18 | 6 | 2025-09-27 | 2025-10-02
R7S1ONECW-AP18-405 | Fire Fighting Backfilling - AP#18 | 2 | 2025-10-09 | 2025-10-11
POWER |  | 39 | 2025-09-27 | 2025-10-23
R7S1ONECW-AP18-409 | Excavation Works & Sand Bedding - AP#18 (External Power Civil) | 3 | 2025-09-27 | 2025-09-29
R7S1ONECW-AP18-410 | Power Manholes - AP#18 | 3 | 2025-09-30 | 2025-10-02
R7S1ONECW-AP18-411 | Power Backfilling - AP#18 | 2 | 2025-10-22 | 2025-10-23
LOW CURRENT |  | 22 | 2025-09-27 | 2025-10-05
R7S1ONECW-AP18-412 | Excavation Works & Sand Bedding - AP#18 (External Low Current Civil) | 3 | 2025-09-27 | 2025-09-29
R7S1ONECW-AP18-413 | Low Current Manholes - AP#18 | 3 | 2025-09-30 | 2025-10-02
R7S1ONECW-AP18-414 | Low Current Backfilling - AP#18 | 2 | 2025-10-04 | 2025-10-05
EXTERNAL - MEP SERVICES |  | 36 | 2025-09-27 | 2025-10-21
DRAINAGE |  | 4 | 2025-09-27 | 2025-09-30
R7S1ONEME-AP18-261 | External Drainage Network - AP#18 (External Drainage MEP) | 4 | 2025-09-27 | 2025-09-30
WATERSUPPLY |  | 13 | 2025-09-30 | 2025-10-14
R7S1ONEME-AP18-262 | PRV statiuon assembly including meters- AP#18 (External WS MEP) | 4 | 2025-09-30 | 2025-10-04
R7S1ONEME-AP18-264 | Installation of valve station incl. BTU meter- AP#18 (External WS MEP) | 3 | 2025-10-12 | 2025-10-14
CHILLED WATER |  | 7 | 2025-10-05 | 2025-10-12
R7S1ONEME-AP18-263 | Installation of Chilled water line- AP#18 (External CWP MEP) | 6 | 2025-10-05 | 2025-10-11
R7S1ONEME-AP18-265 | Pressure Test for chilled water line- AP#18 (External CWP MEP) | 1 | 2025-10-12 | 2025-10-12
FIRE FIGHTING |  | 19 | 2025-09-27 | 2025-10-08
R7S1ONEME-AP18-266 | Installation of External FF network - AP#18 (External FF MEP) | 6 | 2025-09-27 | 2025-10-02
R7S1ONEME-AP18-267 | Installation of Alarm check valves- AP#18 (External FF MEP) | 3 | 2025-10-04 | 2025-10-06
R7S1ONEME-AP18-268 | Testing of External FF - AP#18 (External FF MEP) | 2 | 2025-10-07 | 2025-10-08
POWER |  | 1 | 2025-10-21 | 2025-10-21
R7S1ONEME-AP18-269 | Cable pulling from Manhole to the building MDB - AP#18 (External Power MEP) | 1 | 2025-10-21 | 2025-10-21
LOW CURRENT |  | 3 | 2025-09-30 | 2025-10-02
R7S1ONEME-AP18-270 | Low Current Cable pulling- AP#18 (External FF MEP) | 3 | 2025-09-30 | 2025-10-02
BUILDING # AP19 (MEDIUM STUDIO) |  | 334 | 2024-12-14 | 2025-11-25
SUB-STRUCTURE |  | 115 | 2024-12-14 | 2025-05-01
R7S1-ONSB-AP19-270 | Site Setting Out Works - AP#19 | 2 | 2024-12-14 | 2024-12-15
R7S1-ONSB-AP19-267 | Site levelling & earthworks - AP#19 | 5 | 2024-12-15 | 2024-12-19
R7S1-ONSB-AP19-271 | Anti-termite & Polythene Sheet Works - AP#19 | 1 | 2025-01-28 | 2025-01-28
R7S1-ONSB-AP19-268 | Blinding PCC - AP#19 | 2 | 2025-01-29 | 2025-01-30
R7S1-ONSB-AP19-269 | Waterproofing for Blinding PCC (Bitumen Paint) - AP#19 | 2 | 2025-02-01 | 2025-02-02
R7S1-ONSB-AP19-272 | Foundations/Upstands - Rebar - AP#19 | 45 | 2025-02-23 | 2025-04-20
R7S1-ONSB-AP19-273 | Foundations/Upstands - Shuttering (Including dowel Works) - AP#19 | 45 | 2025-02-24 | 2025-04-21
R7S1-ONSB-AP19-276 | Installation of MEP U/G services below Boxes - AP#19 | 41 | 2025-03-03 | 2025-04-23
R7S1-ONSB-AP19-274 | Foundations/Upstands - Casting - AP#19 | 39 | 2025-03-06 | 2025-04-24
R7S1-ONSB-AP19-275 | Waterproofing For Foundations/Upstands - AP#19 | 2 | 2025-04-24 | 2025-04-27
R7S1-ONSB-AP19-277 | Backfilling & Compaction - AP#19 | 5 | 2025-04-26 | 2025-05-01
SLAB-ON-GRADE & UG MEP WORKS (in Corridor) |  | 17 | 2025-06-11 | 2025-07-01
LEFT SIDE |  | 17 | 2025-06-11 | 2025-06-28
R7S1-ONSG-AP19-390 | Backfilling & SOG (In Front of Lift Shaft) - AP#19 | 3 | 2025-06-11 | 2025-06-14
R7S1-ONSG-AP19-331 | Block Work below Corridor area - AP#19 | 2 | 2025-06-18 | 2025-06-21
R7S1-ONSG-AP19-337 | Backfilling upto Pipe Level - AP#19 | 1 | 2025-06-21 | 2025-06-22
R7S1-ONSG-AP19-345 | Plaster Work for Blockwork - AP#19 | 1 | 2025-06-21 | 2025-06-22
R7S1-ONSG-AP19-332 | UG MEP Works (Laying of Pipes) - AP#19 | 2 | 2025-06-21 | 2025-06-23
R7S1-ONSG-AP19-333 | Backfilling Works after Pipe Laying - AP#19 | 1 | 2025-06-23 | 2025-06-24
R7S1-ONSG-AP19-334 | Antitermite Works - AP#19 | 1 | 2025-06-23 | 2025-06-24
R7S1-ONSG-AP19-335 | Polythene & Rebar Mesh Works - AP#19 | 2 | 2025-06-24 | 2025-06-26
R7S1-ONSG-AP19-336 | Pouring SOG Concrete - AP#19 | 1 | 2025-06-26 | 2025-06-28
RIGHT SIDE |  | 4 | 2025-06-23 | 2025-07-01
R7S1-ONSG-AP19-338 | Block Work below Corridor area - AP#19 | 2 | 2025-06-23 | 2025-06-25
R7S1-ONSG-AP19-344 | Backfilling upto Pipe Level - AP#19 | 1 | 2025-06-25 | 2025-06-26
R7S1-ONSG-AP19-339 | UG MEP Works (Laying of Pipes) - AP#19 | 1 | 2025-06-26 | 2025-06-28
R7S1-ONSG-AP19-340 | Backfilling Works after Pipe Laying - AP#19 | 1 | 2025-06-28 | 2025-06-29
R7S1-ONSG-AP19-341 | Antitermite Works - AP#19 | 1 | 2025-06-28 | 2025-06-29
R7S1-ONSG-AP19-342 | Polythene & Rebar Mesh Works - AP#19 | 1 | 2025-06-29 | 2025-06-30
R7S1-ONSG-AP19-343 | Pouring SOG Concrete - AP#19 | 1 | 2025-06-30 | 2025-07-01
ERECTION WORKS |  | 72 | 2025-06-04 | 2025-09-10
GROUND FLOOR |  | 42 | 2025-06-04 | 2025-07-05
R7S1ONER-AP19GF502 | Erection of Columns/Beams Frame & Slab/Loose Elements (In Front of Lift Shaft) - AP#19 | 2 | 2025-06-04 | 2025-06-10
R7S1ONER-AP19GF187 | Erection of GF Boxes (Left Side) including Lift Box & Staircase - AP#19 - Medium Studio | 4 | 2025-06-14 | 2025-06-18
R7S1ONER-AP19GF188 | Erection of GF Boxes (Right Side) - AP#19 - Medium Studio | 4 | 2025-06-18 | 2025-06-23
R7S1ONER-AP19GF189 | Erection of GF MEP Modular Cages (Left Side) - AP#19 | 2 | 2025-06-28 | 2025-06-30
R7S1ONER-AP19GF190 | Erection of GF Corridor Slabs (Left Side) - AP#19 | 2 | 2025-06-29 | 2025-07-01
R7S1ONER-AP19GF191 | Erection of GF MEP Modular Cages (Right Side) - AP#19 | 2 | 2025-07-01 | 2025-07-03
R7S1ONER-AP19GF192 | Erection of GF Corridor Slabs Right Side) - AP#19 | 2 | 2025-07-02 | 2025-07-05
FIRST FLOOR |  | 14 | 2025-06-11 | 2025-07-27
R7S1ONER-AP19FF512 | Erection of Columns/Beams Frame & Slab/Loose Elements (In Front of Lift Shaft) - AP#19 | 2 | 2025-06-11 | 2025-06-12
R7S1ONER-AP19FF187 | Erection of FF Boxes (Left Side) - AP#19 - Medium Studio | 2 | 2025-07-20 | 2025-07-21
R7S1ONER-AP19FF188 | Erection of FF Boxes (Right Side) - AP#19 - Medium Studio | 2 | 2025-07-21 | 2025-07-22
R7S1ONER-AP19FF189 | Erection of FF MEP Modular Cages (Left Side) - AP#19 | 2 | 2025-07-21 | 2025-07-23
R7S1ONER-AP19FF191 | Erection of FF MEP Modular Cages (Right Side) - AP#19 | 2 | 2025-07-23 | 2025-07-24
R7S1ONER-AP19FF190 | Erection of FF Corridor Slabs (Left Side) - AP#19 | 2 | 2025-07-23 | 2025-07-26
R7S1ONER-AP19FF192 | Erection of FF Corridor Slabs Right Side) - AP#19 | 2 | 2025-07-26 | 2025-07-27
SECOND FLOOR |  | 3 | 2025-06-14 | 2025-08-27
R7S1ONER-AP19SF522 | Erection of Columns/Beams Frame & Slab/Loose Elements (In Front of Lift Shaft) - AP#19 | 2 | 2025-06-14 | 2025-06-15
R7S1ONER-AP19SF187 | Erection of SF Boxes (Left Side) - AP#19 - Medium Studio | 2 | 2025-08-17 | 2025-08-18
R7S1ONER-AP19SF188 | Erection of SF Boxes (Right Side) - AP#19 - Medium Studio | 1 | 2025-08-19 | 2025-08-20
R7S1ONER-AP19SF189 | Erection of SF MEP Modular Cages (Left Side) - AP#19 | 3 | 2025-08-19 | 2025-08-21
R7S1ONER-AP19SF190 | Erection of SF Corridor Slabs (Left Side) - AP#19 | 2 | 2025-08-23 | 2025-08-24
R7S1ONER-AP19SF191 | Erection of SF MEP Modular Cages (Right Side) - AP#19 | 2 | 2025-08-24 | 2025-08-25
R7S1ONER-AP19SF192 | Erection of SF Corridor Slabs Right Side) - AP#19 | 2 | 2025-08-26 | 2025-08-27
ROOF |  | 12 | 2025-08-28 | 2025-09-10
R7S1ONER-AP19RF107 | Erection of Loose Roof Parapets, Shaft Covers, MEP Foundation etc. - AP#19 Roof | 12 | 2025-08-28 | 2025-09-10
MEP WORKS & FINISHES |  | 159 | 2025-06-15 | 2025-11-25
GROUND FLOOR |  | 157 | 2025-06-15 | 2025-10-20
ARCH./ CIVIL WORKS |  | 123 | 2025-06-15 | 2025-10-20
CORRIDOR AREA |  | 62 | 2025-07-21 | 2025-10-20
R7S1ONAR-AP19GF229 | Flooring in Corridor - AP#19 (GF Corridor) | 6 | 2025-07-21 | 2025-07-28
R7S1ONAR-AP19GF230 | Corridor Skirting - AP#19 (GF Corridor) | 2 | 2025-07-27 | 2025-07-29
R7S1ONAR-AP19GF227 | False Ceiling - 1st Fix - AP#19 (GF - Corridor) | 4 | 2025-07-29 | 2025-08-03
R7S1ONAR-AP19GF228 | Gypsum Wall Cladding - 1st Fix (Shafts) - AP#19 (GF Corridor) | 6 | 2025-09-21 | 2025-09-28
R7S1ONAR-AP19GF231 | Gypsum Wall Cladding (Shafts) -2nd Fix - AP#19 (GF Corridor) | 4 | 2025-09-29 | 2025-10-02
R7S1ONAR-AP19GF235 | Fixing Architrave - AP#19 (GF Corridor) | 2 | 2025-10-04 | 2025-10-05
R7S1ONAR-AP19GF236 | Fixing Aluminium Doors - AP#19 (GF Corridor) | 2 | 2025-10-06 | 2025-10-07
R7S1ONAR-AP19GF232 | False Ceiling - 2nd Fix (Closing the Ceiling) - AP#19 (GF Corridor) | 3 | 2025-10-08 | 2025-10-11
R7S1ONAR-AP19GF233 | Painting - Surface Prep., Primer & 1st Coat - AP#19 (GF Corridor) | 8 | 2025-10-04 | 2025-10-12
R7S1ONAR-AP19GF251 | Painting - Surface Prep., Primer & 1st Coat for Ceiling - AP#19 (GF Corridor) | 4 | 2025-10-12 | 2025-10-15
R7S1ONAR-AP19GF234 | Painting - Final Coat (Ceiling + Walls) - AP#19 (GF Corridor) | 3 | 2025-10-18 | 2025-10-20
INSIDE BOXES |  | 12 | 2025-07-28 | 2025-08-11
R7S1ONAR-AP19GF237 | Fixing Thresholds (Joining the Room) - AP#19 (GF - inside Boxes) | 4 | 2025-07-28 | 2025-08-02
R7S1ONAR-AP19GF238 | Fixing Wooden Doors - AP#19 (GF - inside Boxes) | 4 | 2025-08-02 | 2025-08-06
R7S1ONAR-AP19GF239 | Fixing Aluminium Doors - AP#19 (GF - inside Boxes) | 4 | 2025-08-06 | 2025-08-11
IN FRONT OF LIFT SHAFT |  | 111 | 2025-06-15 | 2025-09-04
R7S1ONAR-AP19GF241 | Flooring - AP#19 (GF - Front of Lift Shaft) | 3 | 2025-06-15 | 2025-06-17
R7S1ONAR-AP19GF242 | Skirting & Thresholds - AP#19 (GF - Front of Lift Shaft) | 1 | 2025-06-17 | 2025-06-17
R7S1ONAR-AP19GF243 | Painting - Surface Prep., Primer & 1st Coat - AP#19 (GF - Front of Lift Shaft) | 4 | 2025-06-18 | 2025-06-22
R7S1ONAR-AP19GF240 | False Ceiling - 1st Fix - AP#19 (GF - Front of Lift Shaft) | 4 | 2025-06-23 | 2025-06-26
R7S1ONAR-AP19GF244 | False Ceiling - Final Fix - AP#19 (GF - Front of Lift Shaft) | 3 | 2025-06-28 | 2025-06-30
R7S1ONAR-AP19GF246 | Fixing Handrail - AP#19 (GF - Front of Lift Shaft) | 3 | 2025-07-01 | 2025-07-03
R7S1ONAR-AP19GF247 | Paint for Handrail - AP#19 (GF - Front of Lift Shaft) | 3 | 2025-07-05 | 2025-07-07
R7S1ONAR-AP19GF245 | Painting - Final Coat - AP#19 (GF - Front of Lift Shaft) | 3 | 2025-08-27 | 2025-08-31
R7S1ONAR-AP19GF249 | Fixing Wall Guard - AP#19 (GF - Front of Lift Shaft) | 2 | 2025-08-31 | 2025-09-02
R7S1ONAR-AP19GF248 | Fixing Floor Mat - AP#19 (GF - Front of Lift Shaft) | 2 | 2025-09-02 | 2025-09-04
GARBAGE ROOM |  | 2 | 2025-09-14 | 2025-09-15
R7S1ONAR-AP19GF250 | Paint Finishes and Touchups - Final Coat - AP#19 (GF - Garbage Room) | 2 | 2025-09-14 | 2025-09-15
MEP WORKS |  | 87 | 2025-07-05 | 2025-10-16
MECHANICAL |  | 84 | 2025-07-05 | 2025-10-14
CHILLED WATER |  | 54 | 2025-07-05 | 2025-07-31
R7S1ONME-AP19GF679 | Installation of Chilled water hanger and supports - AP#19 (GF - Corridor) | 4 | 2025-07-05 | 2025-07-09
R7S1ONME-AP19GF731 | Installation of CHWP connection for FCU with Valve package in Corridor, Electrical Room & ICT Room - AP#19 (GF) | 4 | 2025-07-05 | 2025-07-09
R7S1ONME-AP19GF681 | Installation of BTU Meter with valves - AP#19 (GF - Corridor) | 2 | 2025-07-10 | 2025-07-13
R7S1ONME-AP19GF680 | Installation of CHWP piping (connection between modular cages & modular to apartment) - AP#19 (GF - Corridor) | 4 | 2025-07-09 | 2025-07-14
R7S1ONME-AP19GF682 | CHWP piping risers connections - AP#19 (GF - Corridor) | 3 | 2025-07-21 | 2025-07-24
R7S1ONME-AP19GF683 | Pressure Testing of CHWP piping - AP#19 (GF - Corridor) | 1 | 2025-07-24 | 2025-07-26
R7S1ONME-AP19GF719 | CHWP Insulation - AP#19 (GF - Corridor) | 4 | 2025-07-26 | 2025-07-30
R7S1ONME-AP19GF1496 | CHWP Installation/Connections and Insulation (In Front of Lift Shaft) - AP#19 | 4 | 2025-07-28 | 2025-07-31
HVAC DUCTING |  | 84 | 2025-07-05 | 2025-10-13
R7S1ONME-AP19GF730 | Installation of FCU's & Duct Connection in Corridor, Electrical Room & ICT Room - AP#19 (GF) | 4 | 2025-07-05 | 2025-07-09
R7S1ONME-AP19GF732 | Installation of Ducting and insulation (connection between modular cages) - AP#19 (GF - Corridor) | 3 | 2025-07-09 | 2025-07-13
R7S1ONME-AP19GF684 | Duct Riser Continuation - AP#19 (GF - Corridor) | 4 | 2025-07-21 | 2025-07-26
R7S1ONME-AP19GF685 | A/C drain & Copper pipe connection in ELV room - AP#19 (GF) | 2 | 2025-07-26 | 2025-07-28
R7S1ONME-AP19GF720 | Installation of Duct & Grill in Garbage Room - AP#19 (GF - Garbage Room) | 2 | 2025-07-28 | 2025-07-30
R7S1ONME-AP19GF733 | Installation of Grilles in the Corridor - AP#19 (GF - Corridor) | 2 | 2025-10-12 | 2025-10-13
FIRE FIGHTING |  | 79 | 2025-07-21 | 2025-10-14
R7S1ONME-AP19GF686 | Riser Continuity in corridor - AP#19 (GF - Corridor) | 4 | 2025-07-21 | 2025-07-26
R7S1ONME-AP19GF687 | Continuitu of FF pipes & ZC Valves (connection between modular cages & modular to apartment) - AP#19 (GF - Corridor) | 4 | 2025-07-21 | 2025-07-26
R7S1ONME-AP19GF1706 | Installation of F.F Pipes, Testing & Final Fixtures (In Front of Lift Shaft) - AP19 | 3 | 2025-08-02 | 2025-08-04
R7S1ONME-AP19GF688 | Installation of Sprinklers drops in corridor - AP#19 (GF - Corridor) | 4 | 2025-08-03 | 2025-08-07
R7S1ONME-AP19GF689 | Pressure Test for FF Piping in corridor - AP#19 (GF - Corridor) | 4 | 2025-08-07 | 2025-08-12
R7S1ONME-AP19GF721 | Installation of Pipe & sprinkler in Garbage Room - AP#19 (GF - Garbage Room) | 1 | 2025-08-21 | 2025-08-21
R7S1ONME-AP19GF734 | FF Flushing network - AP#19 (GF - Corridor) | 1 | 2025-09-09 | 2025-09-09
R7S1ONME-AP19GF691 | Installation of Alarm check valve, Fire Extinguishers & Blanket - AP#19 (GF - Corridor) | 2 | 2025-10-12 | 2025-10-13
R7S1ONME-AP19GF690 | Installation of Sprinklers in corridor - AP#19 (GF - Corridor) | 3 | 2025-10-12 | 2025-10-14
WATER SUPPLY |  | 67 | 2025-07-05 | 2025-09-20
R7S1ONME-AP19GF722 | Installation of WS Pipe in Garbage Room - AP#19 (GF - Garbage Room) | 2 | 2025-07-05 | 2025-07-07
R7S1ONME-AP19GF723 | Installation of Sanitary Fixtures in Janitor Room - AP#19 (GF - Janitor Room) | 2 | 2025-07-05 | 2025-07-07
R7S1ONME-AP19GF693 | WS High Level Pipe continuation & Insulation works - AP#19 (GF - Corridor) | 4 | 2025-07-05 | 2025-07-09
R7S1ONME-AP19GF694 | Installation of Cold, Hot water line & Hot water return - AP#19 (GF - Corridor) | 4 | 2025-07-09 | 2025-07-14
R7S1ONME-AP19GF695 | Water Meter Installation - AP#19 (GF - Corridor) | 4 | 2025-07-14 | 2025-07-19
R7S1ONME-AP19GF692 | Riser Continuity in Shafts - AP#19 (GF - Corridor) | 4 | 2025-07-21 | 2025-07-26
R7S1ONME-AP19GF696 | Pressure Test for WS - AP#19 (GF - Corridor) | 4 | 2025-09-11 | 2025-09-15
R7S1ONME-AP19GF735 | Insulation for Hot water line & Hot water return - AP#19 (GF - Corridor) | 4 | 2025-09-16 | 2025-09-20
DRAINAGE |  | 51 | 2025-07-05 | 2025-09-15
R7S1ONME-AP19GF698 | Installation of Clean-outs, Floor drain in balcony - AP#19 (GF - Corridor) | 4 | 2025-07-05 | 2025-07-09
R7S1ONME-AP19GF699 | Rain Water Riser continuation in Shafts - AP#19 (GF - Corridor) | 4 | 2025-07-21 | 2025-07-26
R7S1ONME-AP19GF700 | Drainage Riser continuation in Shafts - AP#19 (GF - Corridor) | 4 | 2025-07-21 | 2025-07-26
R7S1ONME-AP19GF701 | Testing for Rain Water Riser - AP#19 (GF - Corridor) | 4 | 2025-09-11 | 2025-09-15
R7S1ONME-AP19GF702 | Testing for Drainage Riser1 - AP#19 (GF - Corridor) | 4 | 2025-09-11 | 2025-09-15
ELECTRICAL |  | 80 | 2025-07-05 | 2025-10-16
POWER & LIGHTING |  | 80 | 2025-07-05 | 2025-10-16
R7S1ONME-AP19GF703 | Contiuation of Cable Trays & apartment branches - AP#19 (GF - Corridor) | 4 | 2025-07-05 | 2025-07-09
R7S1ONME-AP19GF704 | Contiuation of Cable Trunking with Flexible conduits for Lights - AP#19 (GF - Corridor) | 4 | 2025-07-05 | 2025-07-09
R7S1ONME-AP19GF705 | Installation of EMT pipes - AP#19 (GF - Corridor) | 5 | 2025-07-05 | 2025-07-10
R7S1ONME-AP19GF706 | Installation of Busbar, Electrical Meter & Tap-off - AP#19 (GF - Corridor) | 3 | 2025-07-09 | 2025-07-13
R7S1ONME-AP19GF729 | Termination of Tap-off with Electrical Meter in the apartments - AP#19 (GF - Corridor) | 3 | 2025-07-13 | 2025-07-16
R7S1ONME-AP19GF707 | Corridor Wire Pulling - AP#19 (GF - Corridor) | 6 | 2025-07-10 | 2025-07-17
R7S1ONME-AP19GF1916 | Continuation of Cable Tray/Trunking with Flexible conduits for Lights (In Front of Lift Shaft) - AP#19 | 4 | 2025-08-05 | 2025-08-09
R7S1ONME-AP19GF708 | Electrical Room - Installation of Cable trays, SMDB & Termination - AP#19 (GF - Corridor) | 6 | 2025-08-20 | 2025-08-27
R7S1ONME-AP19GF710 | Installation, Termination of Emergeny & Exit Lights with contiuity - AP#19 (GF - Corridor) | 2 | 2025-10-12 | 2025-10-13
R7S1ONME-AP19GF709 | Installation, Termination of Light Fixtures with continuity test - AP#19 (GF - Corridor & Balconies) | 3 | 2025-10-12 | 2025-10-14
R7S1ONME-AP19GF711 | Installation, Termination of PIR sensors with continuity test - AP#19 (GF - Corridor) | 2 | 2025-10-15 | 2025-10-16
LOW CURRENT SYSTEM |  | 79 | 2025-07-05 | 2025-10-15
R7S1ONME-AP19GF736 | CBS System cable installation - AP#19 (GF - Corridor) | 3 | 2025-07-05 | 2025-07-08
R7S1ONME-AP19GF712 | Installation of Basket trays for BMS, CCTV, Access Control - AP#19 (GF - Corridor) | 4 | 2025-07-05 | 2025-07-09
R7S1ONME-AP19GF714 | Fire alarm cable installation - AP#19 (GF - Corridor) | 3 | 2025-07-06 | 2025-07-09
R7S1ONME-AP19GF713 | Voice Evacuation cable installation - AP#19 (GF - Corridor) | 3 | 2025-07-08 | 2025-07-12
R7S1ONME-AP19GF715 | Fibre optic Cable pulling & Termination with OTO (in corridors to ONU) - AP#19 (GF - Corridor) | 2 | 2025-09-11 | 2025-09-13
R7S1ONME-AP19GF716 | BMS, CCTV & Access control Cable installation - AP#19 (GF - Corridor) | 2 | 2025-09-11 | 2025-09-13
R7S1ONME-AP19GF2126 | Installation of Basket trays for Low Current, Cable Installation (In Front of Lift Shaft) - AP#19 | 4 | 2025-09-09 | 2025-09-13
R7S1ONME-AP19GF717 | Low Current Works including BMS Panel in ICT Room - AP#19 (GF - Corridor) | 10 | 2025-09-07 | 2025-09-17
R7S1ONME-AP19GF728 | Fluke test for CCTV & Fibre Optic Cable - AP#19 (GF - Corridor) (Ceiling 1st Fix) | 2 | 2025-09-16 | 2025-09-17
R7S1ONME-AP19GF725 | Installation & Termination of Access control system for Electrical Room - AP#19 (GF) | 2 | 2025-09-17 | 2025-09-18
R7S1ONME-AP19GF724 | Installation & Termination of CCTV Cameras - AP#19 (GF - Corridor) | 2 | 2025-10-12 | 2025-10-13
R7S1ONME-AP19GF727 | Installation & Termination of Wireless Gateway & RF Node in corridors - AP#19 (GF - Corridor) | 2 | 2025-10-12 | 2025-10-13
R7S1ONME-AP19GF718 | Installation & Termination of Fire alarm devices & Speakers - AP#19 (GF - Corridor) | 4 | 2025-10-12 | 2025-10-15
R7S1ONME-AP19GF726 | Installation & Termination of Active Components & UPS installation in ICT Room - AP#19 (GF - Corridor) | 2 | 2025-10-14 | 2025-10-15
FIRST FLOOR |  | 129 | 2025-07-28 | 2025-10-23
ARCH./ CIVIL WORKS |  | 129 | 2025-07-28 | 2025-10-23
CORRIDOR AREA |  | 65 | 2025-07-28 | 2025-10-23
R7S1ONAR-AP19FF330 | Flooring in Corridor - AP#19 (FF - Corridor) | 6 | 2025-07-28 | 2025-08-04
R7S1ONAR-AP19FF331 | Corridor Skirting - AP#19 (FF - Corridor) | 2 | 2025-08-03 | 2025-08-05
R7S1ONAR-AP19FF328 | False Ceiling - 1st Fix - AP#19 (FF - Corridor) | 4 | 2025-08-05 | 2025-08-10
R7S1ONAR-AP19FF329 | Gypsum Wall Cladding (Shafts) - AP#19 (FF - Corridor) | 6 | 2025-09-27 | 2025-10-02
R7S1ONAR-AP19FF332 | Gypsum Wall Cladding (Shafts) -2nd Fix - AP#19 (FF Corridor) | 4 | 2025-10-04 | 2025-10-07
R7S1ONAR-AP19FF336 | Fixing Architrave - AP#19 (FF Corridor) | 2 | 2025-10-08 | 2025-10-09
R7S1ONAR-AP19FF337 | Fixing Aluminium Doors - AP#19 (FF Corridor) | 2 | 2025-10-11 | 2025-10-12
R7S1ONAR-AP19FF333 | False Ceiling - 2nd Fix (Closing the Ceiling) - AP#19 (FF Corridor) | 3 | 2025-10-13 | 2025-10-15
R7S1ONAR-AP19FF334 | Painting - Surface Prep., Primer & 1st Coat for Walls - AP#19 (FF Corridor) | 8 | 2025-10-08 | 2025-10-16
R7S1ONAR-AP19FF357 | Painting - Surface Prep., Primer & 1st Coat for Ceiling - AP#19 (FF Corridor) | 4 | 2025-10-16 | 2025-10-20
R7S1ONAR-AP19FF335 | Painting - Final Coat (Ceiling + Walls) - AP#19 (FF Corridor) | 3 | 2025-10-21 | 2025-10-23
INSIDE BOXES |  | 12 | 2025-08-28 | 2025-09-10
R7S1ONAR-AP19FF338 | Fixing Thresholds (Joining the Room) - AP#19 (FF - inside Boxes) | 4 | 2025-08-28 | 2025-09-01
R7S1ONAR-AP19FF339 | Fixing Wooden Doors - AP#19 (FF - inside Boxes) | 4 | 2025-09-02 | 2025-09-06
R7S1ONAR-AP19FF340 | Fixing Aluminium Doors (Next Floor) - AP#19 (FF - inside Boxes) | 4 | 2025-09-07 | 2025-09-10
IN FRONT OF LIFT SHAFT |  | 113 | 2025-07-28 | 2025-09-17
R7S1ONAR-AP19FF342 | Flooring - AP#19 (FF - Front of Lift Shaft) | 4 | 2025-07-28 | 2025-07-31
R7S1ONAR-AP19FF343 | Skirting & Thresholds - AP#19 (FF - Front of Lift Shaft) | 1 | 2025-07-31 | 2025-07-31
R7S1ONAR-AP19FF344 | Painting - Surface Prep., Primer & 1st Coat - AP#19 (FF - Front of Lift Shaft) | 4 | 2025-08-02 | 2025-08-05
R7S1ONAR-AP19FF341 | False Ceiling - 1st Fix - AP#19 (FF - Front of Lift Shaft) | 4 | 2025-08-06 | 2025-08-10
R7S1ONAR-AP19FF345 | False Ceiling - Final Fix - AP#19 (FF - Front of Lift Shaft) | 3 | 2025-09-02 | 2025-09-04
R7S1ONAR-AP19FF347 | Fixing Handrail - AP#19 (FF - Front of Lift Shaft) | 3 | 2025-09-06 | 2025-09-08
R7S1ONAR-AP19FF348 | Paint for Handrail - AP#19 (FF - Front of Lift Shaft) | 3 | 2025-09-09 | 2025-09-11
R7S1ONAR-AP19FF346 | Painting - 2nd Coat - AP#19 (FF - Front of Lift Shaft) | 3 | 2025-09-13 | 2025-09-15
R7S1ONAR-AP19FF349 | Fixing Floor Mat - AP#19 (FF - Front of Lift Shaft) | 2 | 2025-09-16 | 2025-09-17
R7S1ONAR-AP19FF350 | Fixing Wall Guard - AP#19 (FF - Front of Lift Shaft) | 2 | 2025-09-16 | 2025-09-17
GARBAGE ROOM |  | 8 | 2025-09-02 | 2025-09-13
R7S1ONAR-AP19FF351 | Installation of Dry Walls - First Fix - AP#19 (FF - Garbage Room) | 2 | 2025-09-02 | 2025-09-03
R7S1ONAR-AP19FF352 | Installation of Dry Walls - Final Fix - AP#19 (FF - Garbage Room) | 2 | 2025-09-03 | 2025-09-04
R7S1ONAR-AP19FF353 | Garbage Rooms - Wall Tile Finishes (One Side) - AP#19 (FF - Garbage Room) | 2 | 2025-09-04 | 2025-09-06
R7S1ONAR-AP19FF354 | Paint Works of Dry Walls - First Coat - AP#19 (FF - Garbage Room) | 2 | 2025-09-07 | 2025-09-08
R7S1ONAR-AP19FF355 | Installation of the Garbage Chute Door - AP#19 (FF - Garbage Room) | 2 | 2025-09-09 | 2025-09-10
R7S1ONAR-AP19FF356 | Paint Finishes and Touchups - Final Coat - AP#19 (FF - Garbage Room) | 2 | 2025-09-11 | 2025-09-13
MEP WORKS |  | 52 | 2025-07-28 | 2025-10-21
MECHANICAL |  | 48 | 2025-07-28 | 2025-10-19
CHILLED WATER |  | 25 | 2025-07-28 | 2025-09-17
R7S1ONME-AP19FF416 | Installation of Chilled water hanger and supports - AP#19 (FF Corridor) | 4 | 2025-07-28 | 2025-07-31
R7S1ONME-AP19FF466 | Installation of CHWP connection for FCU with Valve package in Corridor, Electrical Room & ICT Room | 4 | 2025-07-28 | 2025-07-31
R7S1ONME-AP19FF418 | Installation of BTU Meter with valves - AP#19 (FF Corridor) | 2 | 2025-08-03 | 2025-08-04
R7S1ONME-AP19FF417 | Installation of CHWP piping (connection between modular cages & modular to apartment) - AP#19 -(FF Corridor) | 4 | 2025-08-02 | 2025-08-05
R7S1ONME-AP19FF419 | CHWP piping risers connections - AP#19 (FF Corridor) | 3 | 2025-08-19 | 2025-08-21
R7S1ONME-AP19FF420 | Pressure Testing of CHWP piping - AP#19 (FF Corridor) | 1 | 2025-08-23 | 2025-08-23
R7S1ONME-AP19FF455 | CHWP Insulation - AP#19 (FF Corridor) | 4 | 2025-08-24 | 2025-08-27
R7S1ONME-AP19FF1506 | CHWP Installation/Connections and Insulation (In Front of Lift Shaft) - AP#19 | 4 | 2025-09-14 | 2025-09-17
HVAC DUCTING |  | 43 | 2025-07-28 | 2025-10-18
R7S1ONME-AP19FF467 | Installation of FCU's & Duct Connection in Corridor, Electrical Room & ICT Room - AP#19 (FF Corridor) | 4 | 2025-07-28 | 2025-07-31
R7S1ONME-AP19FF421 | Duct Riser Continuation - AP#19 (FF Corridor) | 4 | 2025-08-19 | 2025-08-23
R7S1ONME-AP19FF422 | A/C drain & Copper pipe connection in ELV room - AP#19 (FF Corridor) | 2 | 2025-08-24 | 2025-08-25
R7S1ONME-AP19FF468 | Installation of Ducting and insulation (connection between modular cages) - AP#19 (FF Corridor) | 3 | 2025-08-24 | 2025-08-26
R7S1ONME-AP19FF456 | Installation of Duct & Grill in Garbage Room - AP#19 (FF Corridor) | 2 | 2025-08-26 | 2025-08-27
R7S1ONME-AP19FF469 | Installation of Grilles in the Corridor - AP#19 (FF Corridor) | 2 | 2025-10-16 | 2025-10-18
FIRE FIGHTING |  | 48 | 2025-08-19 | 2025-10-19
R7S1ONME-AP19FF457 | Installation of Pipe & sprinkler in Garbage Room - AP#19 (FF Corridor) | 1 | 2025-08-21 | 2025-08-21
R7S1ONME-AP19FF423 | Riser Continuity in corridor - AP#19 (FF Corridor) | 4 | 2025-08-19 | 2025-08-23
R7S1ONME-AP19FF424 | Continuation of FF pipes & ZC Valves (connection between modular cages & modular to apartment) - AP#19 (FF Corridor) | 4 | 2025-08-19 | 2025-08-23
R7S1ONME-AP19FF425 | Installation of Sprinklers drops in corridor - AP#19 (FF Corridor) | 4 | 2025-08-24 | 2025-08-27
R7S1ONME-AP19FF426 | Pressure Test for FF Piping in corridor - AP#19 (FF Corridor) | 4 | 2025-08-28 | 2025-09-01
R7S1ONME-AP19FF470 | FF Flushing network - AP#19 (FF Corridor) | 4 | 2025-09-09 | 2025-09-13
R7S1ONME-AP19FF1716 | Installation of F.F Pipes, Testing & Final Fixtures (In Front of Lift Shaft) - AP19 | 3 | 2025-09-18 | 2025-09-21
R7S1ONME-AP19FF428 | Installation of Alarm check valve, Fire Extinguishers & Blanket (Last Stage of the Building) - AP#19 (FF Corridor) | 2 | 2025-10-16 | 2025-10-18
R7S1ONME-AP19FF427 | Installation of Sprinklers in corridor - AP#19 (FF Corridor) | 3 | 2025-10-16 | 2025-10-19
WATER SUPPLY |  | 31 | 2025-07-28 | 2025-09-25
R7S1ONME-AP19FF458 | Installation of WS Pipe in Garbage Room - AP#19 (FF Corridor) | 2 | 2025-07-28 | 2025-07-29
R7S1ONME-AP19FF459 | Installation of Sanitary Fixtures in Janitor Room - AP#19 (FF Corridor) | 2 | 2025-07-28 | 2025-07-29
R7S1ONME-AP19FF430 | WS High Level Pipe continuation & Insulation works in Corridor - AP#19 (FF Corridor) | 4 | 2025-07-28 | 2025-07-31
R7S1ONME-AP19FF431 | Installation of Cold, Hot water line & Hot water return in corridor - AP#19 (FF Corridor) | 4 | 2025-08-02 | 2025-08-05
R7S1ONME-AP19FF432 | Water Meter Installation in Corridor - AP#19 (FF Corridor) | 4 | 2025-08-06 | 2025-08-10
R7S1ONME-AP19FF429 | Riser Continuity in Shafts - AP#19 (FF Corridor) | 4 | 2025-08-19 | 2025-08-23
R7S1ONME-AP19FF433 | Pressure Test for WS - AP#19 (FF Corridor) | 4 | 2025-09-11 | 2025-09-15
R7S1ONME-AP19FF471 | Insulation for Hot water line & Hot water return in corridor - AP#19 (FF Corridor) | 4 | 2025-09-21 | 2025-09-25
DRAINAGE |  | 11 | 2025-07-28 | 2025-09-15
R7S1ONME-AP19FF434 | Installation of Clean-outs, Floor drain in balcony - AP#19 (FF Corridor) | 4 | 2025-07-28 | 2025-07-31
R7S1ONME-AP19FF435 | Rain Water Riser continuation in Shafts - AP#19 (FF Corridor) | 4 | 2025-08-19 | 2025-08-23
R7S1ONME-AP19FF436 | Drainage Riser continuation in Shafts - AP#19 (FF Corridor) | 4 | 2025-08-19 | 2025-08-23
R7S1ONME-AP19FF437 | Testing for Rain Water Riser - AP#19 (FF Corridor) | 4 | 2025-09-11 | 2025-09-15
R7S1ONME-AP19FF438 | Testing for Drainage Riser - AP#19 (FF Corridor) | 4 | 2025-09-11 | 2025-09-15
ELECTRICAL |  | 52 | 2025-07-28 | 2025-10-21
POWER & LIGHTING |  | 46 | 2025-07-28 | 2025-10-21
R7S1ONME-AP19FF439 | Contiuation of Cable Trays & apartment branches - AP#19 (FF Corridor) | 4 | 2025-07-28 | 2025-07-31
R7S1ONME-AP19FF440 | Contiuation of Cable Trunking with Flexible conduits for Lights - AP#19 (FF Corridor) | 4 | 2025-07-28 | 2025-07-31
R7S1ONME-AP19FF441 | Installation of EMT pipes - AP#19 (FF Corridor) | 5 | 2025-07-28 | 2025-08-02
R7S1ONME-AP19FF442 | Installation of Busbar, Electrical Meter & Tap-off - AP#19 (FF Corridor) | 3 | 2025-08-02 | 2025-08-04
R7S1ONME-AP19FF465 | Termination of Tap-off with Electrical Meter in the apartments - AP#19 (FF Corridor) | 3 | 2025-08-05 | 2025-08-07
R7S1ONME-AP19FF443 | Corridor Wire Pulling - AP#19 (FF Corridor) | 6 | 2025-08-03 | 2025-08-09
R7S1ONME-AP19FF444 | Electrical Room - Installation of Cable trays, SMDB & Termination - AP#19 (FF Corridor) | 6 | 2025-08-10 | 2025-08-16
R7S1ONME-AP19FF1926 | Continuation of Cable Tray/Trunking with Flexible conduits for Lights (In Front of Lift Shaft) - AP#19 | 4 | 2025-09-22 | 2025-09-27
R7S1ONME-AP19FF446 | Installation, Termination of Emergeny & Exit Lights with contiuity - AP#19 (FF Corridor) | 2 | 2025-10-16 | 2025-10-18
R7S1ONME-AP19FF445 | Installation, Termination of Light Fixtures with continuity test - AP#19 (FF - Corridor & Balconies) | 3 | 2025-10-16 | 2025-10-19
R7S1ONME-AP19FF447 | Installation, Termination of PIR sensors with continuity test - AP#19 (FF Corridor) | 2 | 2025-10-20 | 2025-10-21
LOW CURRENT SYSTEM |  | 52 | 2025-07-28 | 2025-10-20
R7S1ONME-AP19FF472 | CBS System cable installation - AP#19 (FF Corridor) | 3 | 2025-07-28 | 2025-07-30
R7S1ONME-AP19FF448 | Installation of Basket trays for BMS, CCTV, Access Control - AP#19 (FF Corridor) | 4 | 2025-07-28 | 2025-07-31
R7S1ONME-AP19FF450 | Fire alarm cable installation - AP#19 (FF Corridor) | 3 | 2025-07-29 | 2025-07-31
R7S1ONME-AP19FF449 | Voice Evacuation cable installation - AP#19 (FF Corridor) | 3 | 2025-07-31 | 2025-08-03
R7S1ONME-AP19FF451 | Fibre optic Cable pulling & Termination with OTO (in corridors to ONU) - AP#19 (FF Corridor) | 2 | 2025-09-14 | 2025-09-15
R7S1ONME-AP19FF452 | BMS, CCTV & Access control Cable installation - AP#19 (FF Corridor) | 2 | 2025-09-14 | 2025-09-15
R7S1ONME-AP19FF453 | Low Current Works including BMS Panel in ICT Room - AP#19 (FF Corridor) | 10 | 2025-09-09 | 2025-09-20
R7S1ONME-AP19FF464 | Fluke test for CCTV & Fibre Optic Cable - AP#19 (FF Corridor) | 2 | 2025-09-18 | 2025-09-20
R7S1ONME-AP19FF2136 | Installation of Basket trays for Low Current, Cable Installation (In Front of Lift Shaft) - AP#19 | 4 | 2025-09-28 | 2025-10-01
R7S1ONME-AP19FF460 | Installation & Termination of CCTV Cameras - AP#19 (FF Corridor) | 2 | 2025-10-16 | 2025-10-18
R7S1ONME-AP19FF461 | Installation & Termination of Access control system for Electrical Room - AP#19 (FF Corridor) | 2 | 2025-10-16 | 2025-10-18
R7S1ONME-AP19FF463 | Installation & Termination of Wireless Gateway & RF Node - AP#19 (FF Corridor) | 2 | 2025-10-16 | 2025-10-18
R7S1ONME-AP19FF454 | Installation & Termination of Fire alarm devices & Speakers - AP#19 (FF Corridor) | 4 | 2025-10-16 | 2025-10-20
R7S1ONME-AP19FF462 | Installation & Termination of Active Components & UPS installation in ICT Room | 2 | 2025-10-19 | 2025-10-20
SECOND FLOOR |  | 117 | 2025-08-02 | 2025-11-25
ARCH./ CIVIL WORKS |  | 111 | 2025-08-04 | 2025-11-25
CORRIDOR AREA |  | 53 | 2025-08-04 | 2025-11-25
R7S1ONAR-AP19SF229 | Flooring in Corridor - AP#19 (SF Corridor) | 6 | 2025-08-04 | 2025-08-11
R7S1ONAR-AP19SF230 | Corridor Skirting - AP#19 (SF Corridor) | 2 | 2025-08-10 | 2025-08-12
R7S1ONAR-AP19SF227 | False Ceiling - 1st Fix - AP#19 (SF Corridor) | 4 | 2025-08-12 | 2025-08-17
R7S1ONAR-AP19SF228 | Gypsum Wall Cladding (Shafts) - AP#19 (SF Corridor) | 6 | 2025-10-28 | 2025-11-03
R7S1ONAR-AP19SF231 | Gypsum Wall Cladding (Shafts) -2nd Fix - AP#19 (SF Corridor) | 4 | 2025-11-04 | 2025-11-08
R7S1ONAR-AP19SF235 | Fixing Architrave - AP#19 (SF Corridor) | 2 | 2025-11-09 | 2025-11-10
R7S1ONAR-AP19SF236 | Fixing Aluminium Doors - AP#19 (SF Corridor) | 2 | 2025-11-11 | 2025-11-12
R7S1ONAR-AP19SF232 | False Ceiling - 2nd Fix (Closing the Ceiling) - AP#19 (SF Corridor) | 3 | 2025-11-13 | 2025-11-16
R7S1ONAR-AP19SF233 | Painting - Surface Prep., Primer & 1st Coat - AP#19 (SF Corridor) | 8 | 2025-11-09 | 2025-11-17
R7S1ONAR-AP19SF257 | Painting - Surface Prep., Primer & 1st Coat - AP#19 (SF Corridor) | 4 | 2025-11-17 | 2025-11-20
R7S1ONAR-AP19SF234 | Painting - Final Coat (Ceiling + Walls) - AP#19 (SF Corridor) | 3 | 2025-11-23 | 2025-11-25
INSIDE BOXES |  | 12 | 2025-08-28 | 2025-09-10
R7S1ONAR-AP19SF237 | Fixing Thresholds (Joining the Room) - AP#19 (SF - inside Boxes) | 4 | 2025-08-28 | 2025-09-01
R7S1ONAR-AP19SF238 | Fixing Wooden Doors - AP#19 (SF - inside Boxes) | 4 | 2025-09-02 | 2025-09-06
R7S1ONAR-AP19SF239 | Fixing Aluminium Doors (Next Floor) - AP#19 (SF - inside Boxes) | 4 | 2025-09-07 | 2025-09-10
IN FRONT OF LIFT SHAFT |  | 94 | 2025-08-28 | 2025-11-03
R7S1ONAR-AP19SF241 | Flooring - AP#19 (SF - Front of Lift Shaft) | 4 | 2025-08-28 | 2025-09-01
R7S1ONAR-AP19SF242 | Skirting & Thresholds - AP#19 (SF - Front of Lift Shaft) | 2 | 2025-09-02 | 2025-09-03
R7S1ONAR-AP19SF243 | Painting - Surface Prep., Primer & 1st Coat - AP#19 (SF - Front of Lift Shaft) | 4 | 2025-09-04 | 2025-09-08
R7S1ONAR-AP19SF240 | False Ceiling - 1st Fix - AP#19 (SF - Front of Lift Shaft) | 4 | 2025-09-09 | 2025-09-13
R7S1ONAR-AP19SF244 | False Ceiling - Final Fix - AP#19 (SF - Front of Lift Shaft) | 3 | 2025-09-14 | 2025-09-16
R7S1ONAR-AP19SF246 | Fixing Handrail - AP#19 (SF - Front of Lift Shaft) | 3 | 2025-09-17 | 2025-09-20
R7S1ONAR-AP19SF247 | Paint for Handrail - AP#19 (SF - Front of Lift Shaft) | 3 | 2025-09-21 | 2025-09-24
R7S1ONAR-AP19SF245 | Painting - 2nd Coat - AP#19 (SF - Front of Lift Shaft) | 3 | 2025-10-29 | 2025-11-01
R7S1ONAR-AP19SF248 | Fixing Floor Mat - AP#19 (SF - Front of Lift Shaft) | 2 | 2025-11-02 | 2025-11-03
R7S1ONAR-AP19SF249 | Fixing Wall Guard - AP#19 (SF - Front of Lift Shaft) | 2 | 2025-11-02 | 2025-11-03
GARBAGE ROOM |  | 30 | 2025-08-11 | 2025-11-20
R7S1ONAR-AP19SF256 | Installation of Garbage Chute Full System from GF to 2nd Floor - AP#19 (SF - Garbage Room) | 10 | 2025-08-11 | 2025-08-21
R7S1ONAR-AP19SF250 | Installation of Dry Walls - First Fix - AP#19 (SF - Garbage Room) | 2 | 2025-08-23 | 2025-08-24
R7S1ONAR-AP19SF251 | Installation of Dry Walls - Final Fix - AP#19 (SF - Garbage Room) | 2 | 2025-08-25 | 2025-08-26
R7S1ONAR-AP19SF252 | Garbage Rooms - Wall Tile Finishes (One Side) - AP#19 (SF - Garbage Room) | 2 | 2025-08-26 | 2025-08-27
R7S1ONAR-AP19SF253 | Paint Works of Dry Walls - First Coat - AP#19 (SF - Garbage Room) | 2 | 2025-08-28 | 2025-08-30
R7S1ONAR-AP19SF254 | Installation of the Garbage Chute Door - AP#19 (SF - Garbage Room) | 2 | 2025-08-31 | 2025-09-01
R7S1ONAR-AP19SF255 | Paint Finishes and Touchups - Final Coat - AP#19 (SF - Garbage Room) | 2 | 2025-11-19 | 2025-11-20
MEP WORKS |  | 70 | 2025-08-02 | 2025-11-22
MECHANICAL |  | 70 | 2025-08-02 | 2025-11-20
CHILLED WATER |  | 23 | 2025-08-02 | 2025-09-14
R7S1ONME-AP19SF1516 | CHWP Installation/Connections and Insulation (In Front of Lift Shaft) - AP#19 | 4 | 2025-08-02 | 2025-08-05
R7S1ONME-AP19SF386 | Installation of Chilled water hanger and supports - AP#19 (SF Corridor) | 4 | 2025-08-28 | 2025-09-01
R7S1ONME-AP19SF436 | Installation of CHWP connection for FCU with Valve package in Corridor, Electrical Room & ICT Room | 4 | 2025-08-28 | 2025-09-01
R7S1ONME-AP19SF388 | Installation of BTU Meter with valves - AP#19 (SF Corridor) | 2 | 2025-09-03 | 2025-09-04
R7S1ONME-AP19SF387 | Installation of CHWP piping (connection between modular cages & modular to apartment) - AP#19 (SF Corridor) | 4 | 2025-09-02 | 2025-09-06
R7S1ONME-AP19SF389 | CHWP piping risers connections - AP#19 (SF Corridor) | 3 | 2025-09-06 | 2025-09-08
R7S1ONME-AP19SF390 | Pressure Testing of CHWP piping - AP#19 (SF Corridor) | 1 | 2025-09-09 | 2025-09-09
R7S1ONME-AP19SF425 | CHWP Insulation - AP#19 (SF Corridor) | 4 | 2025-09-10 | 2025-09-14
HVAC DUCTING |  | 70 | 2025-08-28 | 2025-11-18
R7S1ONME-AP19SF391 | Duct Riser Continuation - AP#19 (SF Corridor) | 4 | 2025-08-28 | 2025-09-01
R7S1ONME-AP19SF437 | Installation of FCU's & Duct Connection in Corridor, Electrical Room & ICT Room - AP#19 (SF Corridor) | 4 | 2025-08-28 | 2025-09-01
R7S1ONME-AP19SF392 | A/C drain & Copper pipe connection in ELV room - AP#19 (SF Corridor) | 2 | 2025-09-02 | 2025-09-03
R7S1ONME-AP19SF438 | Installation of Ducting and insulation (connection between modular cages) - AP#19 (SF Corridor) | 3 | 2025-09-02 | 2025-09-04
R7S1ONME-AP19SF426 | Installation of Duct & Grill in Garbage Room - AP#19 (SF Corridor) | 2 | 2025-11-17 | 2025-11-18
R7S1ONME-AP19SF439 | Installation of Grilles in the Corridor - AP#19 (SF Corridor) | 2 | 2025-11-17 | 2025-11-18
FIRE FIGHTING |  | 57 | 2025-08-03 | 2025-11-20
R7S1ONME-AP19SF1726 | Installation of F.F Pipes, Testing & Final Fixtures (In Front of Lift Shaft) - AP19 | 3 | 2025-08-03 | 2025-08-05
R7S1ONME-AP19SF393 | Riser Continuity Succ - Closing of Gysum Boards on shaft - AP#19 (SF Corridor) | 4 | 2025-08-28 | 2025-09-01
R7S1ONME-AP19SF394 | FF Contiuation on High Level with Valves - AP#19 (SF Corridor) | 4 | 2025-08-28 | 2025-09-01
R7S1ONME-AP19SF395 | Installation of Sprinklers drops - AP#19 (SF Corridor) | 4 | 2025-09-02 | 2025-09-06
R7S1ONME-AP19SF396 | Pressure Test for FF Piping - AP#19 (SF Corridor) | 2 | 2025-09-07 | 2025-09-08
R7S1ONME-AP19SF427 | Installation of Pipe & sprinkler in Garbage Room - AP#19 (SF Corridor) | 2 | 2025-11-17 | 2025-11-18
R7S1ONME-AP19SF398 | Installation of Fire Extinguishers - AP#19 (SF Corridor) | 3 | 2025-11-17 | 2025-11-19
R7S1ONME-AP19SF397 | Installation of Sprinklers - AP#19 (SF Corridor) | 4 | 2025-11-17 | 2025-11-20
WATER SUPPLY |  | 29 | 2025-08-28 | 2025-09-30
R7S1ONME-AP19SF428 | Installation of WS Pipe in Garbage Room - AP#19 (SF Corridor) | 2 | 2025-08-28 | 2025-08-30
R7S1ONME-AP19SF429 | Installation of Sanitary Fixtures in Janitor Room - AP#19 (SF Corridor) | 2 | 2025-08-28 | 2025-08-30
R7S1ONME-AP19SF399 | Riser Continuity - AP#19 (SF Corridor) | 4 | 2025-08-28 | 2025-09-01
R7S1ONME-AP19SF400 | WS High Level Pipe continuation & Insulation works - AP#19 (SF Corridor) | 4 | 2025-08-28 | 2025-09-01
R7S1ONME-AP19SF401 | Instalation of Hot water line in corridor - AP#19 (SF Corridor) | 4 | 2025-09-02 | 2025-09-06
R7S1ONME-AP19SF402 | Water Meter Installation - AP#19 (SF Corridor) | 4 | 2025-09-07 | 2025-09-10
R7S1ONME-AP19SF403 | Pressure Test for WS - AP#19 (SF Corridor) | 4 | 2025-09-16 | 2025-09-20
R7S1ONME-AP19FF473 | Insulation for Hot water line & Hot water return in corridor - AP#19 (SF Corridor) | 4 | 2025-09-27 | 2025-09-30
DRAINAGE |  | 14 | 2025-08-28 | 2025-09-15
R7S1ONME-AP19SF404 | Installation of Clean-outs - AP#19 (SF Corridor) | 4 | 2025-08-28 | 2025-09-01
R7S1ONME-AP19SF405 | Rain Water Riser continuation - AP#19 (SF Corridor) | 4 | 2025-08-28 | 2025-09-01
R7S1ONME-AP19SF406 | Drainage Riser continuation - AP#19 (SF Corridor) | 4 | 2025-08-28 | 2025-09-01
R7S1ONME-AP19SF408 | Testing for Drainage Riser - AP#19 (SF Corridor) | 4 | 2025-09-02 | 2025-09-06
R7S1ONME-AP19SF407 | Testing for Rain Water Riser - AP#19 (SF Corridor) | 4 | 2025-09-11 | 2025-09-15
ELECTRICAL |  | 51 | 2025-08-02 | 2025-11-22
POWER & LIGHTING |  | 42 | 2025-08-02 | 2025-11-22
R7S1ONME-AP19SF1936 | Continuation of Cable Tray/Trunking with Flexible conduits for Lights (In Front of Lift Shaft) - AP#19 | 4 | 2025-08-02 | 2025-08-05
R7S1ONME-AP19SF409 | Contiuation of Cable Trays & apartment branches - AP#19 (SF Corridor) | 4 | 2025-08-28 | 2025-09-01
R7S1ONME-AP19SF410 | Contiuation of Cable Trunking with Flexible conduits for Lights - AP#19 (SF Corridor) | 4 | 2025-08-28 | 2025-09-01
R7S1ONME-AP19SF411 | Installation of EMT pipes - AP#19 (SF Corridor) | 5 | 2025-08-28 | 2025-09-02
R7S1ONME-AP19SF412 | Installation of Busbar, Electrical Meter & Tap-off in Corridor - AP#19 (SF Corridor) | 3 | 2025-09-02 | 2025-09-04
R7S1ONME-AP19SF435 | Termination of Tap-off with Electrical Meter in the apartments - AP#19 (SF Corridor) | 3 | 2025-09-06 | 2025-09-08
R7S1ONME-AP19SF413 | Corridor Wire Pulling - AP#19 (SF Corridor) | 6 | 2025-09-03 | 2025-09-09
R7S1ONME-AP19SF414 | Electrical Room - Installation of Cable trays, SMDB & Termination - AP#19 (SF Corridor) | 6 | 2025-10-22 | 2025-10-28
R7S1ONME-AP19SF416 | Installation, Termination of Emergeny & Exit Lights with contiuity - AP#19 (SF Corridor) | 2 | 2025-11-17 | 2025-11-18
R7S1ONME-AP19SF415 | Installation, Termination of Light Fixtures with continuity test - AP#19 (SF - Corridor & Balconies) | 3 | 2025-11-17 | 2025-11-19
R7S1ONME-AP19SF417 | Installation, Termination of PIR sensors with continuity test - AP#19 (SF Corridor) | 2 | 2025-11-20 | 2025-11-22
LOW CURRENT SYSTEM |  | 51 | 2025-08-28 | 2025-11-20
R7S1ONME-AP19SF440 | CBS System cable installation - AP#19 (SF Corridor) | 3 | 2025-08-28 | 2025-08-31
R7S1ONME-AP19SF418 | Installation of Basket trays for BMS, CCTV, Access Control - AP#19 (SF Corridor) | 4 | 2025-08-28 | 2025-09-01
R7S1ONME-AP19SF420 | Fire alarm cable installation - AP#19 (SF Corridor) | 3 | 2025-08-30 | 2025-09-01
R7S1ONME-AP19SF419 | Voice Evacuation cable installation - AP#19 (SF Corridor) | 3 | 2025-09-01 | 2025-09-03
R7S1ONME-AP19SF421 | Fibre optic Cable pulling & Termination with OTO (in corridors to ONU) - AP#19 (SF Corridor) | 2 | 2025-09-16 | 2025-09-17
R7S1ONME-AP19SF422 | BMS, CCTV & Access control Cable installation - AP#19 (SF Corridor) | 2 | 2025-09-16 | 2025-09-17
R7S1ONME-AP19SF2146 | Installation of Basket trays for Low Current, Cable Installation (In Front of Lift Shaft) - AP#19 | 4 | 2025-10-02 | 2025-10-06
R7S1ONME-AP19SF423 | Low Current Works including BMS Panel in ICT Room - AP#19 (SF Corridor) | 10 | 2025-10-16 | 2025-10-27
R7S1ONME-AP19SF434 | Fluke test for CCTV & Fibre Optic Cable - AP#19 (SF Corridor) | 2 | 2025-10-26 | 2025-10-27
R7S1ONME-AP19SF430 | Installation & Termination of CCTV Cameras - AP#19 (SF Corridor) | 2 | 2025-11-17 | 2025-11-18
R7S1ONME-AP19SF431 | Installation & Termination of Access control system for Electrical Room - AP#19 (SF Corridor) | 2 | 2025-11-17 | 2025-11-18
R7S1ONME-AP19SF433 | Installation & Termination of Wireless Gateway & RF Node in corridors - AP#19 (SF Corridor) | 2 | 2025-11-17 | 2025-11-18
R7S1ONME-AP19SF424 | Installation & Termination of Fire alarm devices & Speakers - AP#19 (SF Corridor) | 4 | 2025-11-17 | 2025-11-20
R7S1ONME-AP19SF432 | Installation & Termination of Active Components & UPS installation in ICT Room - AP#19 (SF Corridor) | 2 | 2025-11-19 | 2025-11-20
ROOF WORKS |  | 64 | 2025-09-11 | 2025-11-17
ARCH./ CIVIL WORKS |  | 64 | 2025-09-11 | 2025-11-17
R7S1ONME-AP19RF386 | Installation of Roof Drains - AP#19 (Roof) | 3 | 2025-09-14 | 2025-09-16
R7S1ONAR-AP19RF59 | Roof Box Stiching (Concrete Works) - AP#19 (Roof) | 7 | 2025-09-11 | 2025-09-18
R7S1ONAR-AP19RF60 | Roof Waterproofing Works with testing - AP#19 (Roof) | 20 | 2025-09-20 | 2025-10-13
R7S1ONAR-AP19RF61 | Laying of Gravel - AP#19 (Roof) | 2 | 2025-10-14 | 2025-10-15
R7S1ONAR-AP19RF62 | Surface Preparation & Primer for Parapets - AP#19 (Roof) | 6 | 2025-10-16 | 2025-10-22
R7S1ONAR-AP19RF63 | 1st Coat Paint for Parapets - AP#19 (Roof) | 2 | 2025-10-21 | 2025-10-22
R7S1ONAR-AP19RF64 | 2nd Coat Paint for Parapets - AP#19 (Roof) | 2 | 2025-10-23 | 2025-10-25
R7S1ONAR-AP19RF66 | Fixing Fall Arrest System - AP#19 (Roof) | 2 | 2025-10-30 | 2025-11-01
R7S1ONAR-AP19RF65 | Crossover Bridges Installation & application of Sealant on MEP penetrations - AP#19 (Roof) | 12 | 2025-11-04 | 2025-11-17
MECHANICAL |  | 36 | 2025-10-16 | 2025-11-08
HVAC |  | 30 | 2025-10-16 | 2025-11-01
R7S1ONME-AP19RF350 | Modular Installation - AP#19 (Roof) | 5 | 2025-10-16 | 2025-10-21
R7S1ONME-AP19RF351 | Continuation of Roof duct works/FAHU Connections - AP#19 (Roof) | 5 | 2025-10-19 | 2025-10-23
R7S1ONME-AP19RF353 | Insulations for ducts - AP#19 (Roof) | 5 | 2025-10-20 | 2025-10-25
R7S1ONME-AP19RF355 | Installation of FAHU - AP#19 (Roof) | 2 | 2025-10-25 | 2025-10-26
R7S1ONME-AP19RF360 | Installation of Outdoor VRF/DX Units - AP#19 (Roof) | 2 | 2025-10-26 | 2025-10-27
R7S1ONME-AP19RF361 | Installation & Insulation of the Condensation Drain - AP#19 (Roof) | 1 | 2025-10-27 | 2025-10-27
R7S1ONME-AP19RF363 | Installation of Ventilation Fans - AP#19 (Roof) | 3 | 2025-10-25 | 2025-10-27
R7S1ONME-AP19RF358 | Chilled Water System Continuation and Connections with Valve package of FAHU - AP#19 (Roof) | 4 | 2025-10-25 | 2025-10-28
R7S1ONME-AP19RF365 | Installation of Louvers - AP#19 (Roof) | 2 | 2025-10-28 | 2025-10-29
R7S1ONME-AP19RF368 | Installation & Testing of Copper Pipes - AP#19 (Roof) | 2 | 2025-10-28 | 2025-10-29
R7S1ONME-AP19RF369 | Miscellaneous Works for Mechanical Connections (Fire & Volume Dampers etc.) - AP#19 (Roof) | 2 | 2025-10-30 | 2025-11-01
WATERSUPPLY & DRAINAGE |  | 23 | 2025-10-22 | 2025-11-06
R7S1ONME-AP19RF349 | Testing for the Rain Water Risers - AP#19 (Roof) | 2 | 2025-10-25 | 2025-10-26
R7S1ONME-AP19RF352 | Installation & Continuation of Water supply pipes (connection between modular cages & modular to Shaft Riser) - AP#19 | 4 | 2025-10-22 | 2025-10-26
R7S1ONME-AP19RF356 | Installation of Air Vent & Pressure Guage with Valves at Roof - AP#19 (Roof) | 4 | 2025-10-25 | 2025-10-28
R7S1ONME-AP19RF357 | Vertical Continuation of Vent Pipes To The Roof (Drainage) - AP#19 (Roof) | 4 | 2025-10-26 | 2025-10-29
R7S1ONME-AP19RF359 | Installation of Rain Water outlet - AP#19 (Roof) | 3 | 2025-10-27 | 2025-10-29
R7S1ONME-AP19RF354 | Installation of Air Vent with Valve for Water Supply - AP#19 (Roof) | 4 | 2025-10-27 | 2025-10-30
R7S1ONME-AP19RF362 | Testing of Water Supply Pipes - AP#19 (Roof) | 2 | 2025-11-01 | 2025-11-02
R7S1ONME-AP19RF364 | Insulation of Roof Water Line - AP#19 (Roof) | 2 | 2025-11-02 | 2025-11-03
R7S1ONME-AP19RF366 | Testing for the Drainage Pipes Risers - AP#19 (Roof) | 2 | 2025-11-04 | 2025-11-05
R7S1ONME-AP19RF367 | Installation of Vent Cowl - AP#19 (Roof) | 1 | 2025-11-06 | 2025-11-06
SOLAR HEATER |  | 26 | 2025-10-27 | 2025-11-08
R7S1ONME-AP19RF381 | Installation of Solar water pumps and circulation pumps with valves(For Water Only) - AP#19 (Roof) | 2 | 2025-10-28 | 2025-10-29
R7S1ONME-AP19RF379 | Installation of Structure and Solar Panels (For Water Only) - AP#19 (Roof) | 5 | 2025-10-27 | 2025-11-01
R7S1ONME-AP19RF380 | Installation of Solar Calorifier Tank & Air cooler (For Water Only) - AP#19 (Roof) | 5 | 2025-10-28 | 2025-11-02
R7S1ONME-AP19RF382 | Installation of Solar Pipes Primary Loop - AP#19 (Roof) | 5 | 2025-10-28 | 2025-11-02
R7S1ONME-AP19RF383 | Testing of Solar Pipes Primary Loop - AP#19 (Roof) | 1 | 2025-11-03 | 2025-11-03
R7S1ONME-AP19RF384 | Insulation of Solar Pipes Primary Loop - AP#19 (Roof) | 1 | 2025-11-03 | 2025-11-03
R7S1ONME-AP19RF385 | Aluminum Cladding of Solar Pipes Primary Loop - AP#19 (Roof) | 4 | 2025-11-04 | 2025-11-08
ELECTRICAL |  | 32 | 2025-10-22 | 2025-11-11
POWER & LOW CURRENT |  | 32 | 2025-10-22 | 2025-11-11
R7S1ONME-AP19RF370 | Installation of Cables for Fire Alarm system - AP#19 (Roof) | 3 | 2025-10-22 | 2025-10-25
R7S1ONME-AP19RF371 | Installation of Cables for BMS - AP#19 (Roof) | 3 | 2025-10-22 | 2025-10-25
R7S1ONME-AP19RF372 | Installation of Fire Alarm Devices - AP#19 (Roof) | 3 | 2025-10-22 | 2025-10-25
R7S1ONME-AP19RF374 | Installation of Roof Light Fixtures - AP#19 (Roof) | 3 | 2025-10-22 | 2025-10-25
R7S1ONME-AP19RF345 | Installation of Isolators and Machine Connections - AP#19 (Roof) | 4 | 2025-10-22 | 2025-10-26
R7S1ONME-AP19RF373 | Installation of BMS Devices - AP#19 (Roof) | 4 | 2025-10-23 | 2025-10-27
R7S1ONME-AP19RF344 | Lightening Protection & Earthing System - AP#19 (Roof) | 7 | 2025-10-22 | 2025-10-29
R7S1ONME-AP19RF346 | Installation of Electrical Containments for BMS - AP#19 (Roof) | 7 | 2025-10-22 | 2025-10-29
R7S1ONME-AP19RF376 | Termination for BMS System - AP#19 (Roof) | 1 | 2025-10-30 | 2025-10-30
R7S1ONME-AP19RF388 | Termination of Primary & Secondary pump for Solar system - AP#19 (Roof) | 1 | 2025-10-30 | 2025-10-30
R7S1ONME-AP19RF347 | Installation of Fire Alarm Containment for FAHU, Fans - AP#19 (Roof) | 4 | 2025-10-30 | 2025-11-03
R7S1ONME-AP19RF377 | Termination for Fire Alarm Device - AP#19 (Roof) | 1 | 2025-11-04 | 2025-11-04
R7S1ONME-AP19RF348 | Installation of LV Power Cables for Roof Equipment - AP#19 (Roof) | 5 | 2025-11-04 | 2025-11-09
R7S1ONME-AP19RF375 | Termination for LV Cables - AP#19 (Roof) | 1 | 2025-11-10 | 2025-11-10
R7S1ONME-AP19RF378 | Megger Test for the Power Cables - AP#19 (Roof) | 1 | 2025-11-11 | 2025-11-11
R7S1ONME-AP19RF387 | Installation & Termination of Solar System Panel - AP#19 (Roof) | 3 | 2025-11-09 | 2025-11-11
STAIR CASE |  | 101 | 2025-09-11 | 2025-11-10
CIVIL WORKS |  | 72 | 2025-09-20 | 2025-11-05
STAIR CASE (MAIN WITH LIFT) |  | 72 | 2025-09-20 | 2025-10-18
R7S1ONST-AP19RG428 | Stair Flooring (Roof to GF) - AP#19 (Main Stair) | 7 | 2025-09-20 | 2025-09-28
R7S1ONST-AP19RG429 | Stair Hand Rails (Roof to GF) - AP#19 (Main Stair) | 6 | 2025-09-29 | 2025-10-05
R7S1ONST-AP19RG430 | Stair Paint - Primer & 1st Coat (Roof to GF)- AP#19 (Main Stair) | 7 | 2025-10-06 | 2025-10-13
R7S1ONST-AP19RG431 | Stair Paint - Final Coat (Roof to GF)- AP#19 (Main Stair) | 4 | 2025-10-14 | 2025-10-18
STAIR CASE (LEFT SIDE) |  | 42 | 2025-09-29 | 2025-10-23
R7S1ONST-AP19RG438 | Stair Flooring (Roof to GF) - AP#19 Left Side Stair | 7 | 2025-09-29 | 2025-10-06
R7S1ONST-AP19RG439 | Stair Hand Rails (Roof to GF) - AP#19 Left Side Stair | 6 | 2025-10-07 | 2025-10-13
R7S1ONST-AP19RG440 | Stair Paint - Primer & 1st Coat (Roof to GF) - AP#19 Left Side Stair | 6 | 2025-10-14 | 2025-10-20
R7S1ONST-AP19RG441 | Stair Paint - Final Coat (Roof to GF) - AP#19 Left Side Stair | 3 | 2025-10-21 | 2025-10-23
STAIR CASE (RIGHT SIDE) |  | 36 | 2025-10-07 | 2025-11-05
R7S1ONST-AP19RG442 | Stair Flooring (Roof to GF) - AP#19 Right Side Stair | 8 | 2025-10-07 | 2025-10-15
R7S1ONST-AP19RG443 | Stair Hand Rails (Roof to GF) - AP#19 Right Side Stair | 7 | 2025-10-16 | 2025-10-23
R7S1ONST-AP19RG444 | Stair Paint - Primer & 1st Coat (Roof to GF) - AP#19 Right Side Stair | 7 | 2025-10-25 | 2025-11-01
R7S1ONST-AP19RG445 | Stair Paint - Final Coat (Roof to GF) - AP#19 Right Side Stair | 4 | 2025-11-02 | 2025-11-05
MEP WORKS |  | 72 | 2025-09-11 | 2025-11-10
STAIR CASE (MAIN WITH LIFT) |  | 57 | 2025-09-11 | 2025-10-22
R7S1ONST-AP19RG427 | Main Staircase Wire Pulling - AP#19 (Main Stair) | 3 | 2025-09-11 | 2025-09-14
R7S1ONST-AP19RG446 | Final fix - Main Staircase Lights Fixtures & Motion Sensor - AP#19 (Main Stair) | 2 | 2025-10-19 | 2025-10-20
R7S1ONST-AP19RG447 | Final fix - Main Staircase Emergency Lights Fixtures - AP#19 (Main Stair) | 2 | 2025-10-21 | 2025-10-22
STAIR CASE (LEFT SIDE) |  | 59 | 2025-09-15 | 2025-10-28
R7S1ONST-AP19RG432 | Left Staircase Wire Pulling - AP#19 (Main Stair) | 3 | 2025-09-15 | 2025-09-17
R7S1ONST-AP19RG434 | Final fix - Left Staircase Lights Fixtures & Motion Sensor - AP#19 (Main Stair) | 2 | 2025-10-25 | 2025-10-26
R7S1ONST-AP19RG436 | Final fix - Left Staircase Emergency Lights Fixtures - AP#19 (Main Stair) | 2 | 2025-10-27 | 2025-10-28
STAIR CASE (RIGHT SIDE) |  | 66 | 2025-09-18 | 2025-11-10
R7S1ONST-AP19RG433 | Right Staircase Wire Pulling - AP#19 (Main Stair) | 3 | 2025-09-18 | 2025-09-21
R7S1ONST-AP19RG435 | Final fix - Right Staircase Lights Fixtures & Motion Sensor - AP#19 (Main Stair) | 2 | 2025-11-06 | 2025-11-08
R7S1ONST-AP19RG437 | Final fix - Right Staircase Emergency Lights Fixtures - AP#19 (Main Stair) | 2 | 2025-11-09 | 2025-11-10
ELEVATOR WORKS |  | 20 | 2025-09-20 | 2025-10-15
R7S1ONEL-AP19GR637 | Installation of Rails - AP#19 (Elevator Works) | 6 | 2025-09-20 | 2025-09-27
R7S1ONEL-AP19GR638 | Assembly of Cabin - AP#19 (Elevator Works) | 4 | 2025-09-28 | 2025-10-01
R7S1ONEL-AP19GR639 | Installation of Motor - AP#19 (Elevator Works) | 4 | 2025-10-02 | 2025-10-06
R7S1ONEL-AP19GR640 | Installation of Main Cables - AP#19 (Elevator Works) | 4 | 2025-10-07 | 2025-10-11
R7S1ONEL-AP19GR641 | Installation of Doors, Indicator, Push Button - AP#19 (Elevator Works) | 2 | 2025-10-12 | 2025-10-13
R7S1ONEL-AP19GR642 | Interior Finishes - AP#19 (Elevator Works) | 2 | 2025-10-14 | 2025-10-15
EXTERNAL ELEVATIONS |  | 98 | 2025-09-29 | 2025-11-01
ARCH./ CIVIL WORKS |  | 98 | 2025-09-29 | 2025-11-01
R7S1ONEE-AP19GR525 | External Selant Works - For Boxes - AP#19 (External Elevations) | 15 | 2025-09-29 | 2025-10-15
R7S1ONEE-AP19GR526 | Final Finishes & Touchups - AP#19 (External Elevations) | 15 | 2025-10-06 | 2025-10-22
R7S1ONME-AP19GF697 | Installation of rain water outlet - External façade - AP#19 (External Elevations) | 2 | 2025-10-23 | 2025-10-25
R7S1ONEE-AP19GR528 | Installation of External Signages - AP#19 (External Elevations) | 4 | 2025-10-26 | 2025-10-29
R7S1ONEE-AP19GR527 | Fixing Cage Ladder - AP#19 (External Elevations) | 2 | 2025-10-30 | 2025-11-01
EXTERNAL - CIVIL WORKS |  | 34 | 2025-10-01 | 2025-10-26
DRAINAGE |  | 15 | 2025-10-01 | 2025-10-12
R7S1ONECW-AP19-379 | Excavation Works & Sand Bedding - AP#19 (External Drainage) | 3 | 2025-10-01 | 2025-10-04
R7S1ONECW-AP19-380 | Drainage Manholes - AP#19 | 6 | 2025-10-01 | 2025-10-07
R7S1ONECW-AP19-381 | Drainage Backfilling - AP#19 | 2 | 2025-10-11 | 2025-10-12
WATERSUPPLY |  | 15 | 2025-10-01 | 2025-10-26
R7S1ONECW-AP19-382 | Excavation Works & Sand Bedding - Watersupply - AP#19 (External Watersupply Civil) | 3 | 2025-10-01 | 2025-10-04
R7S1ONECW-AP19-383 | Watersupply Manholes - AP#19 | 6 | 2025-10-05 | 2025-10-11
R7S1ONECW-AP19-384 | Watersupply Backfilling - AP#19 | 2 | 2025-10-25 | 2025-10-26
CHILLED WATER |  | 19 | 2025-10-05 | 2025-10-16
R7S1ONECW-AP19-388 | Excavation Works & Sand Bedding - AP#19 (External Chilled Water Civil) | 3 | 2025-10-05 | 2025-10-07
R7S1ONECW-AP19-389 | Chilled Water Manholes - AP#19 | 6 | 2025-10-08 | 2025-10-14
R7S1ONECW-AP19-390 | Chilled Water Backfilling - AP#19 | 2 | 2025-10-15 | 2025-10-16
FIRE FIGHTING |  | 15 | 2025-10-05 | 2025-10-22
R7S1ONECW-AP19-385 | Excavation Works & Sand Bedding - AP#19 (External Chilled Water Civil) | 3 | 2025-10-05 | 2025-10-07
R7S1ONECW-AP19-386 | Fire Fighting Manholes - AP#19 | 6 | 2025-10-08 | 2025-10-14
R7S1ONECW-AP19-387 | Fire Fighting Backfilling - AP#19 | 2 | 2025-10-21 | 2025-10-22
POWER |  | 25 | 2025-10-08 | 2025-10-25
R7S1ONECW-AP19-391 | Excavation Works & Sand Bedding - AP#19 (External Power Civil) | 3 | 2025-10-08 | 2025-10-11
R7S1ONECW-AP19-392 | Power Manholes - AP#19 | 3 | 2025-10-12 | 2025-10-14
R7S1ONECW-AP19-393 | Power Backfilling - AP#19 | 2 | 2025-10-23 | 2025-10-25
LOW CURRENT |  | 25 | 2025-10-08 | 2025-10-16
R7S1ONECW-AP19-394 | Excavation Works & Sand Bedding - AP#19 (External Low Current Civil) | 3 | 2025-10-08 | 2025-10-11
R7S1ONECW-AP19-395 | Low Current Manholes - AP#19 | 3 | 2025-10-12 | 2025-10-14
R7S1ONECW-AP19-396 | Low Current Backfilling - AP#19 | 2 | 2025-10-15 | 2025-10-16
EXTERNAL - MEP SERVICES |  | 32 | 2025-10-08 | 2025-10-26
DRAINAGE |  | 4 | 2025-10-08 | 2025-10-12
R7S1ONEME-AP19-251 | External Drainage Network - AP#19 (External Drainage MEP) | 4 | 2025-10-08 | 2025-10-12
WATERSUPPLY |  | 10 | 2025-10-12 | 2025-10-26
R7S1ONEME-AP19-252 | PRV statiuon assembly including meters- AP#19 (External WS MEP) | 4 | 2025-10-12 | 2025-10-15
R7S1ONEME-AP19-254 | Installation of valve station incl. BTU meter- AP#19 (External WS MEP) | 3 | 2025-10-23 | 2025-10-26
CHILLED WATER |  | 7 | 2025-10-16 | 2025-10-23
R7S1ONEME-AP19-253 | Installation of Chilled water line- AP#19 (External CWP MEP) | 6 | 2025-10-16 | 2025-10-22
R7S1ONEME-AP19-255 | Pressure Test for chilled water line- AP#19 (External CWP MEP) | 1 | 2025-10-23 | 2025-10-23
FIRE FIGHTING |  | 11 | 2025-10-08 | 2025-10-20
R7S1ONEME-AP19-256 | Installation of External FF network - AP#19 (External FF MEP) | 6 | 2025-10-08 | 2025-10-14
R7S1ONEME-AP19-257 | Installation of Alarm check valves- AP#19 (External FF MEP) | 3 | 2025-10-15 | 2025-10-18
R7S1ONEME-AP19-258 | Testing of External FF - AP#19 (External FF MEP) | 2 | 2025-10-19 | 2025-10-20
POWER |  | 1 | 2025-10-22 | 2025-10-22
R7S1ONEME-AP19-259 | Cable pulling from Manhole to the building MDB - AP#19 (External Power MEP) | 1 | 2025-10-22 | 2025-10-22
LOW CURRENT |  | 3 | 2025-10-12 | 2025-10-14
R7S1ONEME-AP19-260 | Low Current Cable pulling- AP#19 (External FF MEP) | 3 | 2025-10-12 | 2025-10-14
BUILDING # AP05 (MEDIUM STUDIO) |  | 328 | 2024-12-22 | 2025-11-27
SUB-STRUCTURE |  | 109 | 2024-12-22 | 2025-05-03
R7S1-ONSB-AP05-259 | Site Setting Out Works - AP#05 | 3 | 2024-12-22 | 2024-12-24
R7S1-ONSB-AP05-256 | Site levelling & earthworks - AP#05 | 7 | 2024-12-24 | 2024-12-31
R7S1-ONSB-AP05-260 | Anti-termite & Polythene Sheet Works - AP#05 | 8 | 2025-01-02 | 2025-01-11
R7S1-ONSB-AP05-257 | Blinding PCC - AP#05 | 3 | 2025-01-11 | 2025-01-13
R7S1-ONSB-AP05-258 | Waterproofing for Blinding PCC (Bitumen Paint) - AP#05 | 1 | 2025-01-14 | 2025-01-14
R7S1-ONSB-AP05-265 | Installation of MEP U/G services below Boxes - AP#05 | 2 | 2025-01-14 | 2025-01-15
R7S1-ONSB-AP05-261 | Foundations/Upstands - Rebar - AP#05 | 81 | 2025-01-15 | 2025-04-24
R7S1-ONSB-AP05-262 | Foundations/Upstands - Shuttering (Including dowel Works) - AP#05 | 81 | 2025-01-15 | 2025-04-24
R7S1-ONSB-AP05-263 | Foundations/Upstands - Casting - AP#05 | 2 | 2025-04-26 | 2025-04-27
R7S1-ONSB-AP05-264 | Waterproofing For Foundations/Upstands - AP#05 | 2 | 2025-04-27 | 2025-04-28
R7S1-ONSB-AP05-266 | Backfilling & Compaction - AP#05 | 5 | 2025-04-28 | 2025-05-03
SLAB-ON-GRADE & UG MEP WORKS (in Corridor) |  | 20 | 2025-06-18 | 2025-07-08
LEFT SIDE |  | 20 | 2025-06-18 | 2025-07-05
R7S1-ONSG-AP05-400 | Backfilling & SOG (In Front of Lift Shaft) - AP#05 | 3 | 2025-06-18 | 2025-06-21
R7S1-ONSG-AP05-316 | Block Work below Corridor area - AP#05 | 1 | 2025-06-26 | 2025-06-28
R7S1-ONSG-AP05-322 | Backfilling upto Pipe Level - AP#05 | 1 | 2025-06-28 | 2025-06-29
R7S1-ONSG-AP05-330 | Plaster Work for Blockwork - AP#05 | 1 | 2025-06-28 | 2025-06-29
R7S1-ONSG-AP05-317 | UG MEP Works (Laying of Pipes) - AP#05 | 2 | 2025-06-28 | 2025-06-30
R7S1-ONSG-AP05-318 | Backfilling Works after Pipe Laying - AP#05 | 1 | 2025-06-30 | 2025-07-01
R7S1-ONSG-AP05-319 | Antitermite Works - AP#05 | 1 | 2025-06-30 | 2025-07-01
R7S1-ONSG-AP05-320 | Polythene & Rebar Mesh Works - AP#05 | 2 | 2025-07-01 | 2025-07-03
R7S1-ONSG-AP05-321 | Pouring SOG Concrete - AP#05 | 1 | 2025-07-03 | 2025-07-05
RIGHT SIDE |  | 8 | 2025-06-30 | 2025-07-08
R7S1-ONSG-AP05-323 | Block Work below Corridor area - AP#05 | 1 | 2025-06-30 | 2025-07-01
R7S1-ONSG-AP05-329 | Backfilling upto Pipe Level - AP#05 | 1 | 2025-07-01 | 2025-07-02
R7S1-ONSG-AP05-324 | UG MEP Works (Laying of Pipes) - AP#05 | 2 | 2025-07-02 | 2025-07-05
R7S1-ONSG-AP05-325 | Backfilling Works after Pipe Laying - AP#05 | 1 | 2025-07-05 | 2025-07-06
R7S1-ONSG-AP05-326 | Antitermite Works - AP#05 | 1 | 2025-07-05 | 2025-07-06
R7S1-ONSG-AP05-327 | Polythene & Rebar Mesh Works - AP#05 | 1 | 2025-07-06 | 2025-07-07
R7S1-ONSG-AP05-328 | Pouring SOG Concrete - AP#05 | 1 | 2025-07-07 | 2025-07-08
ERECTION WORKS |  | 66 | 2025-06-16 | 2025-09-14
GROUND FLOOR |  | 16 | 2025-06-16 | 2025-07-12
R7S1ONER-AP05GF532 | Erection of Columns/Beams Frame & Slab/Loose Elements (In Front of Lift Shaft) - AP#05 | 2 | 2025-06-16 | 2025-06-17
R7S1ONER-AP05GF181 | Erection of GF Boxes (Left Side) including Lift Box & Staircase - AP#05 - Medium Studio | 3 | 2025-06-23 | 2025-06-26
R7S1ONER-AP05GF182 | Erection of GF Boxes (Right Side) - AP#05 - Medium Studio | 3 | 2025-06-26 | 2025-06-30
R7S1ONER-AP05GF183 | Erection of GF MEP Modular Cages (Left Side) - AP#05 | 2 | 2025-07-05 | 2025-07-07
R7S1ONER-AP05GF184 | Erection of GF Corridor Slabs (Left Side) - AP#05 | 2 | 2025-07-06 | 2025-07-08
R7S1ONER-AP05GF185 | Erection of GF MEP Modular Cages (Right Side) - AP#05 | 2 | 2025-07-08 | 2025-07-10
R7S1ONER-AP05GF186 | Erection of GF Corridor Slabs Right Side) - AP#05 | 2 | 2025-07-09 | 2025-07-12
FIRST FLOOR |  | 15 | 2025-06-18 | 2025-07-30
R7S1ONER-AP05FF542 | Erection of Columns/Beams Frame & Slab/Loose Elements (In Front of Lift Shaft) - AP#05 | 2 | 2025-06-18 | 2025-06-19
R7S1ONER-AP05FF181 | Erection of FF Boxes (Left Side) - AP#05 - Medium Studio | 2 | 2025-07-23 | 2025-07-24
R7S1ONER-AP05FF182 | Erection of FF Boxes (Right Side) - AP#05 - Medium Studio | 2 | 2025-07-24 | 2025-07-26
R7S1ONER-AP05FF183 | Erection of FF MEP Modular Cages (Left Side) - AP#05 | 2 | 2025-07-24 | 2025-07-27
R7S1ONER-AP05FF185 | Erection of FF MEP Modular Cages (Right Side) - AP#05 | 2 | 2025-07-27 | 2025-07-28
R7S1ONER-AP05FF184 | Erection of FF Corridor Slabs (Left Side) - AP#05 | 2 | 2025-07-27 | 2025-07-29
R7S1ONER-AP05FF186 | Erection of FF Corridor Slabs Right Side) - AP#05 | 2 | 2025-07-29 | 2025-07-30
SECOND FLOOR |  | 8 | 2025-06-21 | 2025-08-31
R7S1ONER-AP05SF552 | Erection of Columns/Beams Frame & Slab/Loose Elements (In Front of Lift Shaft) - AP#05 | 2 | 2025-06-21 | 2025-06-22
R7S1ONER-AP05SF181 | Erection of SF Boxes (Left Side) - AP#05 - Medium Studio | 2 | 2025-08-20 | 2025-08-21
R7S1ONER-AP05SF182 | Erection of SF Boxes (Right Side) - AP#05 - Medium Studio | 1 | 2025-08-23 | 2025-08-24
R7S1ONER-AP05SF183 | Erection of SF MEP Modular Cages (Left Side) - AP#05 | 3 | 2025-08-23 | 2025-08-25
R7S1ONER-AP05SF184 | Erection of SF Corridor Slabs (Left Side) - AP#05 | 2 | 2025-08-26 | 2025-08-27
R7S1ONER-AP05SF185 | Erection of SF MEP Modular Cages (Right Side) - AP#05 | 2 | 2025-08-27 | 2025-08-28
R7S1ONER-AP05SF186 | Erection of SF Corridor Slabs Right Side) - AP#05 | 2 | 2025-08-30 | 2025-08-31
ROOF |  | 12 | 2025-09-01 | 2025-09-14
R7S1ONER-AP05RF106 | Erection of Loose Roof Parapets, Shaft Covers, MEP Foundation etc. - AP#05 Roof | 12 | 2025-09-01 | 2025-09-14
MEP WORKS & FINISHES |  | 138 | 2025-06-22 | 2025-11-27
GROUND FLOOR |  | 136 | 2025-06-22 | 2025-11-09
ARCH./ CIVIL WORKS |  | 136 | 2025-06-22 | 2025-11-09
CORRIDOR AREA |  | 78 | 2025-07-21 | 2025-11-09
R7S1ONAR-AP05GF198 | Flooring in Corridor - AP#05 (GF Corridor) | 6 | 2025-07-21 | 2025-07-28
R7S1ONAR-AP05GF199 | Corridor Skirting - AP#05 (GF Corridor) | 2 | 2025-07-27 | 2025-07-29
R7S1ONAR-AP05GF196 | False Ceiling - 1st Fix - AP#05 (GF - Corridor) | 4 | 2025-07-29 | 2025-08-03
R7S1ONAR-AP05GF197 | Gypsum Wall Cladding - 1st Fix (Shafts) - AP#05 (GF Corridor) | 6 | 2025-10-12 | 2025-10-18
R7S1ONAR-AP05GF200 | Gypsum Wall Cladding (Shafts) -2nd Fix - AP#05 (GF Corridor) | 4 | 2025-10-19 | 2025-10-22
R7S1ONAR-AP05GF204 | Fixing Architrave - AP#05 (GF Corridor) | 2 | 2025-10-23 | 2025-10-25
R7S1ONAR-AP05GF205 | Fixing Aluminium Doors - AP#05 (GF Corridor) | 2 | 2025-10-26 | 2025-10-27
R7S1ONAR-AP05GF201 | False Ceiling - 2nd Fix (Closing the Ceiling) - AP#05 (GF Corridor) | 3 | 2025-10-28 | 2025-10-30
R7S1ONAR-AP05GF202 | Painting - Surface Prep., Primer & 1st Coat - AP#05 (GF Corridor) | 8 | 2025-10-23 | 2025-11-01
R7S1ONAR-AP05GF226 | Painting - Surface Prep., Primer & 1st Coat for Ceiling - AP#05 (GF Corridor) | 4 | 2025-11-01 | 2025-11-04
R7S1ONAR-AP05GF203 | Painting - Final Coat (Ceiling + Walls) - AP#05 (GF Corridor) | 3 | 2025-11-06 | 2025-11-09
INSIDE BOXES |  | 12 | 2025-09-15 | 2025-09-29
R7S1ONAR-AP05GF206 | Fixing Thresholds (Joining the Room) - AP#05 (GF - inside Boxes) | 4 | 2025-09-15 | 2025-09-18
R7S1ONAR-AP05GF207 | Fixing Wooden Doors - AP#05 (GF - inside Boxes) | 4 | 2025-09-20 | 2025-09-24
R7S1ONAR-AP05GF208 | Fixing Aluminium Doors - AP#05 (GF - inside Boxes) | 4 | 2025-09-25 | 2025-09-29
IN FRONT OF LIFT SHAFT |  | 91 | 2025-06-22 | 2025-10-13
R7S1ONAR-AP05GF210 | Flooring - AP#05 (GF - Front of Lift Shaft) | 3 | 2025-06-22 | 2025-06-24
R7S1ONAR-AP05GF211 | Skirting & Thresholds - AP#05 (GF - Front of Lift Shaft) | 1 | 2025-06-24 | 2025-06-24
R7S1ONAR-AP05GF212 | Painting - Surface Prep., Primer & 1st Coat - AP#05 (GF - Front of Lift Shaft) | 4 | 2025-06-25 | 2025-06-29
R7S1ONAR-AP05GF209 | False Ceiling - 1st Fix - AP#05 (GF - Front of Lift Shaft) | 4 | 2025-06-30 | 2025-07-03
R7S1ONAR-AP05GF213 | False Ceiling - Final Fix - AP#05 (GF - Front of Lift Shaft) | 3 | 2025-07-05 | 2025-07-07
R7S1ONAR-AP05GF215 | Fixing Handrail - AP#05 (GF - Front of Lift Shaft) | 3 | 2025-07-08 | 2025-07-10
R7S1ONAR-AP05GF216 | Paint for Handrail - AP#05 (GF - Front of Lift Shaft) | 3 | 2025-07-12 | 2025-07-14
R7S1ONAR-AP05GF214 | Painting - Final Coat - AP#05 (GF - Front of Lift Shaft) | 3 | 2025-10-06 | 2025-10-08
R7S1ONAR-AP05GF218 | Fixing Wall Guard - AP#05 (GF - Front of Lift Shaft) | 2 | 2025-10-09 | 2025-10-11
R7S1ONAR-AP05GF217 | Fixing Floor Mat - AP#05 (GF - Front of Lift Shaft) | 2 | 2025-10-12 | 2025-10-13
GARBAGE ROOM |  | 2 | 2025-10-02 | 2025-10-04
R7S1ONAR-AP05GF219 | Paint Finishes and Touchups - Final Coat - AP#05 (GF - Garbage Room) | 2 | 2025-10-02 | 2025-10-04
MEP WORKS |  | 61 | 2025-08-05 | 2025-11-05
MECHANICAL |  | 43 | 2025-08-06 | 2025-11-03
CHILLED WATER |  | 10 | 2025-08-06 | 2025-10-02
R7S1ONME-AP05GF1526 | CHWP Installation/Connections and Insulation (In Front of Lift Shaft) - AP#05 | 4 | 2025-08-06 | 2025-08-10
R7S1ONME-AP05GF621 | Installation of Chilled water hanger and supports - AP#05 (GF - Corridor) | 4 | 2025-09-15 | 2025-09-18
R7S1ONME-AP05GF673 | Installation of CHWP connection for FCU with Valve package in Corridor, Electrical Room & ICT Room - AP#05 (GF) | 4 | 2025-09-15 | 2025-09-18
R7S1ONME-AP05GF623 | Installation of BTU Meter with valves - AP#05 (GF - Corridor) | 2 | 2025-09-21 | 2025-09-22
R7S1ONME-AP05GF622 | Installation of CHWP piping (connection between modular cages & modular to apartment) - AP#05 (GF - Corridor) | 4 | 2025-09-20 | 2025-09-24
R7S1ONME-AP05GF624 | CHWP piping risers connections - AP#05 (GF - Corridor) | 3 | 2025-09-24 | 2025-09-27
R7S1ONME-AP05GF625 | Pressure Testing of CHWP piping - AP#05 (GF - Corridor) | 1 | 2025-09-28 | 2025-09-28
R7S1ONME-AP05GF661 | CHWP Insulation - AP#05 (GF - Corridor) | 4 | 2025-09-29 | 2025-10-02
HVAC DUCTING |  | 42 | 2025-09-15 | 2025-11-02
R7S1ONME-AP05GF626 | Duct Riser Continuation - AP#05 (GF - Corridor) | 4 | 2025-09-15 | 2025-09-18
R7S1ONME-AP05GF672 | Installation of FCU's & Duct Connection in Corridor, Electrical Room & ICT Room - AP#05 (GF) | 4 | 2025-09-15 | 2025-09-18
R7S1ONME-AP05GF627 | A/C drain & Copper pipe connection in ELV room - AP#05 (GF) | 2 | 2025-09-20 | 2025-09-21
R7S1ONME-AP05GF674 | Installation of Ducting and insulation (connection between modular cages) - AP#05 (GF - Corridor) | 3 | 2025-09-20 | 2025-09-22
R7S1ONME-AP05GF662 | Installation of Duct & Grill in Garbage Room - AP#05 (GF - Garbage Room) | 2 | 2025-09-22 | 2025-09-24
R7S1ONME-AP05GF675 | Installation of Grilles in the Corridor - AP#05 (GF - Corridor) | 2 | 2025-11-01 | 2025-11-02
FIRE FIGHTING |  | 35 | 2025-08-06 | 2025-11-03
R7S1ONME-AP05GF1736 | Installation of F.F Pipes, Testing & Final Fixtures (In Front of Lift Shaft) - AP05 | 3 | 2025-08-06 | 2025-08-09
R7S1ONME-AP05GF628 | Riser Continuity in corridor - AP#05 (GF - Corridor) | 4 | 2025-09-15 | 2025-09-18
R7S1ONME-AP05GF629 | Continuitu of FF pipes & ZC Valves (connection between modular cages & modular to apartment) - AP#05 (GF - Corridor) | 4 | 2025-09-15 | 2025-09-18
R7S1ONME-AP05GF663 | Installation of Pipe & sprinkler in Garbage Room - AP#05 (GF - Garbage Room) | 4 | 2025-09-15 | 2025-09-18
R7S1ONME-AP05GF630 | Installation of Sprinklers drops in corridor - AP#05 (GF - Corridor) | 4 | 2025-09-20 | 2025-09-24
R7S1ONME-AP05GF631 | Pressure Test for FF Piping in corridor - AP#05 (GF - Corridor) | 2 | 2025-09-25 | 2025-09-27
R7S1ONME-AP05GF676 | FF Flushing network - AP#05 (GF - Corridor) | 1 | 2025-10-11 | 2025-10-11
R7S1ONME-AP05GF633 | Installation of Alarm check valve, Fire Extinguishers & Blanket - AP#05 (GF - Corridor) | 2 | 2025-11-01 | 2025-11-02
R7S1ONME-AP05GF632 | Installation of Sprinklers in corridor - AP#05 (GF - Corridor) | 3 | 2025-11-01 | 2025-11-03
WATER SUPPLY |  | 17 | 2025-09-15 | 2025-10-08
R7S1ONME-AP05GF664 | Installation of WS Pipe in Garbage Room - AP#05 (GF - Garbage Room) | 2 | 2025-09-15 | 2025-09-16
R7S1ONME-AP05GF665 | Installation of Sanitary Fixtures in Janitor Room - AP#05 (GF - Janitor Room) | 2 | 2025-09-15 | 2025-09-16
R7S1ONME-AP05GF634 | Riser Continuity in Shafts - AP#05 (GF - Corridor) | 4 | 2025-09-15 | 2025-09-18
R7S1ONME-AP05GF635 | WS High Level Pipe continuation & Insulation works - AP#05 (GF - Corridor) | 4 | 2025-09-15 | 2025-09-18
R7S1ONME-AP05GF636 | Installation of Cold, Hot water line & Hot water return - AP#05 (GF - Corridor) | 4 | 2025-09-20 | 2025-09-24
R7S1ONME-AP05GF637 | Water Meter Installation - AP#05 (GF - Corridor) | 4 | 2025-09-25 | 2025-09-29
R7S1ONME-AP05GF638 | Pressure Test for WS - AP#05 (GF - Corridor) | 4 | 2025-09-30 | 2025-10-04
R7S1ONME-AP05GF677 | Insulation for Hot water line & Hot water return - AP#05 (GF - Corridor) | 4 | 2025-10-05 | 2025-10-08
DRAINAGE |  | 13 | 2025-09-15 | 2025-09-24
R7S1ONME-AP05GF640 | Installation of Clean-outs, Floor drain in balcony - AP#05 (GF - Corridor) | 4 | 2025-09-15 | 2025-09-18
R7S1ONME-AP05GF641 | Rain Water Riser continuation in Shafts - AP#05 (GF - Corridor) | 4 | 2025-09-15 | 2025-09-18
R7S1ONME-AP05GF642 | Drainage Riser continuation in Shafts - AP#05 (GF - Corridor) | 4 | 2025-09-15 | 2025-09-18
R7S1ONME-AP05GF643 | Testing for Rain Water Riser - AP#05 (GF - Corridor) | 4 | 2025-09-20 | 2025-09-24
R7S1ONME-AP05GF644 | Testing for Drainage Riser1 - AP#05 (GF - Corridor) | 4 | 2025-09-20 | 2025-09-24
ELECTRICAL |  | 56 | 2025-08-05 | 2025-11-05
POWER & LIGHTING |  | 56 | 2025-08-05 | 2025-11-05
R7S1ONME-AP05GF1946 | Continuation of Cable Tray/Trunking with Flexible conduits for Lights (In Front of Lift Shaft) - AP#05 | 4 | 2025-08-05 | 2025-08-09
R7S1ONME-AP05GF645 | Contiuation of Cable Trays & apartment branches - AP#05 (GF - Corridor) | 4 | 2025-09-15 | 2025-09-18
R7S1ONME-AP05GF646 | Contiuation of Cable Trunking with Flexible conduits for Lights - AP#05 (GF - Corridor) | 4 | 2025-09-15 | 2025-09-18
R7S1ONME-AP05GF647 | Installation of EMT pipes - AP#05 (GF - Corridor) | 5 | 2025-09-15 | 2025-09-20
R7S1ONME-AP05GF648 | Installation of Busbar, Electrical Meter & Tap-off - AP#05 (GF - Corridor) | 3 | 2025-09-20 | 2025-09-22
R7S1ONME-AP05GF671 | Termination of Tap-off with Electrical Meter in the apartments - AP#05 (GF - Corridor) | 3 | 2025-09-24 | 2025-09-27
R7S1ONME-AP05GF649 | Corridor Wire Pulling - AP#05 (GF - Corridor) | 6 | 2025-09-21 | 2025-09-28
R7S1ONME-AP05GF650 | Electrical Room - Installation of Cable trays, SMDB & Termination - AP#05 (GF - Corridor) | 6 | 2025-09-29 | 2025-10-05
R7S1ONME-AP05GF652 | Installation, Termination of Emergeny & Exit Lights with contiuity - AP#05 (GF - Corridor) | 2 | 2025-11-01 | 2025-11-02
R7S1ONME-AP05GF651 | Installation, Termination of Light Fixtures with continuity test - AP#05 (GF - Corridor & Balconies) | 3 | 2025-11-01 | 2025-11-03
R7S1ONME-AP05GF653 | Installation, Termination of PIR sensors with continuity test - AP#05 (GF - Corridor) | 2 | 2025-11-04 | 2025-11-05
LOW CURRENT SYSTEM |  | 47 | 2025-09-01 | 2025-11-04
R7S1ONME-AP05GF654 | Installation of Basket trays for BMS, CCTV, Access Control - AP#05 (GF - Corridor) | 4 | 2025-09-01 | 2025-09-04
R7S1ONME-AP05GF656 | Fire alarm cable installation - AP#05 (GF - Corridor) | 3 | 2025-09-02 | 2025-09-04
R7S1ONME-AP05GF657 | Fibre optic Cable pulling & Termination with OTO (in corridors to ONU) - AP#05 (GF - Corridor) | 2 | 2025-09-04 | 2025-09-06
R7S1ONME-AP05GF655 | Voice Evacuation cable installation - AP#05 (GF - Corridor) | 3 | 2025-09-04 | 2025-09-07
R7S1ONME-AP05GF678 | CBS System cable installation - AP#05 (GF - Corridor) | 3 | 2025-09-15 | 2025-09-17
R7S1ONME-AP05GF658 | BMS, CCTV & Access control Cable installation - AP#05 (GF - Corridor) | 2 | 2025-09-18 | 2025-09-20
R7S1ONME-AP05GF659 | Low Current Works including BMS Panel in ICT Room - AP#05 (GF - Corridor) | 10 | 2025-09-15 | 2025-09-27
R7S1ONME-AP05GF670 | Fluke test for CCTV & Fibre Optic Cable - AP#05 (GF - Corridor) (Ceiling 1st Fix) | 2 | 2025-09-25 | 2025-09-27
R7S1ONME-AP05GF667 | Installation & Termination of Access control system for Electrical Room - AP#05 (GF) | 2 | 2025-09-27 | 2025-09-28
R7S1ONME-AP05GF2156 | Installation of Basket trays for Low Current, Cable Installation (In Front of Lift Shaft) - AP#05 | 4 | 2025-10-07 | 2025-10-11
R7S1ONME-AP05GF666 | Installation & Termination of CCTV Cameras - AP#05 (GF - Corridor) | 2 | 2025-11-01 | 2025-11-02
R7S1ONME-AP05GF669 | Installation & Termination of Wireless Gateway & RF Node in corridors - AP#05 (GF - Corridor) | 2 | 2025-11-01 | 2025-11-02
R7S1ONME-AP05GF660 | Installation & Termination of Fire alarm devices & Speakers - AP#05 (GF - Corridor) | 4 | 2025-11-01 | 2025-11-04
R7S1ONME-AP05GF668 | Installation & Termination of Active Components & UPS installation in ICT Room - AP#05 (GF - Corridor) | 2 | 2025-11-03 | 2025-11-04
FIRST FLOOR |  | 132 | 2025-07-28 | 2025-11-10
ARCH./ CIVIL WORKS |  | 132 | 2025-07-28 | 2025-11-10
CORRIDOR AREA |  | 73 | 2025-07-28 | 2025-11-10
R7S1ONAR-AP05FF288 | Flooring in Corridor - AP#05 (FF - Corridor) | 6 | 2025-07-28 | 2025-08-04
R7S1ONAR-AP05FF289 | Corridor Skirting - AP#05 (FF - Corridor) | 2 | 2025-08-03 | 2025-08-05
R7S1ONAR-AP05FF286 | False Ceiling - 1st Fix - AP#05 (FF - Corridor) | 6 | 2025-08-03 | 2025-08-10
R7S1ONAR-AP05FF287 | Gypsum Wall Cladding (Shafts) - AP#05 (FF - Corridor) | 6 | 2025-10-14 | 2025-10-20
R7S1ONAR-AP05FF290 | Gypsum Wall Cladding (Shafts) -2nd Fix - AP#05 (FF Corridor) | 4 | 2025-10-21 | 2025-10-25
R7S1ONAR-AP05FF294 | Fixing Architrave - AP#05 (FF Corridor) | 2 | 2025-10-26 | 2025-10-27
R7S1ONAR-AP05FF295 | Fixing Aluminium Doors - AP#05 (FF Corridor) | 2 | 2025-10-28 | 2025-10-29
R7S1ONAR-AP05FF291 | False Ceiling - 2nd Fix (Closing the Ceiling) - AP#05 (FF Corridor) | 3 | 2025-10-30 | 2025-11-02
R7S1ONAR-AP05FF292 | Painting - Surface Prep., Primer & 1st Coat for Walls - AP#05 (FF Corridor) | 8 | 2025-10-26 | 2025-11-03
R7S1ONAR-AP05FF327 | Painting - Surface Prep., Primer & 1st Coat for Ceiling - AP#05 (FF Corridor) | 4 | 2025-11-03 | 2025-11-06
R7S1ONAR-AP05FF293 | Painting - Final Coat (Ceiling + Walls) - AP#05 (FF Corridor) | 3 | 2025-11-08 | 2025-11-10
INSIDE BOXES |  | 12 | 2025-09-01 | 2025-09-14
R7S1ONAR-AP05FF296 | Fixing Thresholds (Joining the Room) - AP#05 (FF - inside Boxes) | 4 | 2025-09-01 | 2025-09-04
R7S1ONAR-AP05FF297 | Fixing Wooden Doors - AP#05 (FF - inside Boxes) | 4 | 2025-09-06 | 2025-09-09
R7S1ONAR-AP05FF298 | Fixing Aluminium Doors (Next Floor) - AP#05 (FF - inside Boxes) | 4 | 2025-09-10 | 2025-09-14
IN FRONT OF LIFT SHAFT |  | 116 | 2025-07-31 | 2025-10-21
R7S1ONAR-AP05FF300 | Flooring - AP#05 (FF - Front of Lift Shaft) | 3 | 2025-07-31 | 2025-08-03
R7S1ONAR-AP05FF301 | Skirting & Thresholds - AP#05 (FF - Front of Lift Shaft) | 1 | 2025-08-03 | 2025-08-03
R7S1ONAR-AP05FF302 | Painting - Surface Prep., Primer & 1st Coat - AP#05 (FF - Front of Lift Shaft) | 4 | 2025-08-04 | 2025-08-07
R7S1ONAR-AP05FF299 | False Ceiling - 1st Fix - AP#05 (FF - Front of Lift Shaft) | 4 | 2025-08-09 | 2025-08-12
R7S1ONAR-AP05FF303 | False Ceiling - Final Fix - AP#05 (FF - Front of Lift Shaft) | 4 | 2025-10-05 | 2025-10-08
R7S1ONAR-AP05FF305 | Fixing Handrail - AP#05 (FF - Front of Lift Shaft) | 3 | 2025-10-09 | 2025-10-12
R7S1ONAR-AP05FF306 | Paint for Handrail - AP#05 (FF - Front of Lift Shaft) | 3 | 2025-10-13 | 2025-10-15
R7S1ONAR-AP05FF304 | Painting - 2nd Coat - AP#05 (FF - Front of Lift Shaft) | 3 | 2025-10-16 | 2025-10-19
R7S1ONAR-AP05FF307 | Fixing Floor Mat - AP#05 (FF - Front of Lift Shaft) | 2 | 2025-10-20 | 2025-10-21
R7S1ONAR-AP05FF308 | Fixing Wall Guard - AP#05 (FF - Front of Lift Shaft) | 2 | 2025-10-20 | 2025-10-21
GARBAGE ROOM |  | 16 | 2025-09-06 | 2025-10-01
R7S1ONAR-AP05FF309 | Installation of Dry Walls - First Fix - AP#05 (FF - Garbage Room) | 2 | 2025-09-06 | 2025-09-07
R7S1ONAR-AP05FF310 | Installation of Dry Walls - Final Fix - AP#05 (FF - Garbage Room) | 2 | 2025-09-07 | 2025-09-08
R7S1ONAR-AP05FF311 | Garbage Rooms - Wall Tile Finishes (One Side) - AP#05 (FF - Garbage Room) | 2 | 2025-09-08 | 2025-09-09
R7S1ONAR-AP05FF312 | Paint Works of Dry Walls - First Coat - AP#05 (FF - Garbage Room) | 2 | 2025-09-10 | 2025-09-11
R7S1ONAR-AP05FF313 | Installation of the Garbage Chute Door - AP#05 (FF - Garbage Room) | 2 | 2025-09-13 | 2025-09-14
R7S1ONAR-AP05FF314 | Paint Finishes and Touchups - Final Coat - AP#05 (FF - Garbage Room) | 2 | 2025-09-30 | 2025-10-01
MEP WORKS |  | 44 | 2025-08-05 | 2025-11-08
MECHANICAL |  | 39 | 2025-08-06 | 2025-11-05
CHILLED WATER |  | 17 | 2025-08-06 | 2025-10-07
R7S1ONME-AP05FF1536 | CHWP Installation/Connections and Insulation (In Front of Lift Shaft) - AP#05 | 4 | 2025-08-06 | 2025-08-10
R7S1ONME-AP05FF358 | Installation of Chilled water hanger and supports - AP#05 (FF Corridor) | 4 | 2025-09-20 | 2025-09-24
R7S1ONME-AP05FF408 | Installation of CHWP connection for FCU with Valve package in Corridor, Electrical Room & ICT Room | 4 | 2025-09-20 | 2025-09-24
R7S1ONME-AP05FF360 | Installation of BTU Meter with valves - AP#05 (FF Corridor) | 2 | 2025-09-27 | 2025-09-28
R7S1ONME-AP05FF359 | Installation of CHWP piping (connection between modular cages & modular to apartment) - AP#05 -(FF Corridor) | 4 | 2025-09-25 | 2025-09-29
R7S1ONME-AP05FF361 | CHWP piping risers connections - AP#05 (FF Corridor) | 3 | 2025-09-29 | 2025-10-01
R7S1ONME-AP05FF362 | Pressure Testing of CHWP piping - AP#05 (FF Corridor) | 1 | 2025-10-02 | 2025-10-02
R7S1ONME-AP05FF397 | CHWP Insulation - AP#05 (FF Corridor) | 4 | 2025-10-04 | 2025-10-07
HVAC DUCTING |  | 28 | 2025-09-20 | 2025-11-04
R7S1ONME-AP05FF363 | Duct Riser Continuation - AP#05 (FF Corridor) | 4 | 2025-09-20 | 2025-09-24
R7S1ONME-AP05FF409 | Installation of FCU's & Duct Connection in Corridor, Electrical Room & ICT Room - AP#05 (FF Corridor) | 4 | 2025-09-20 | 2025-09-24
R7S1ONME-AP05FF364 | A/C drain & Copper pipe connection in ELV room - AP#05 (FF Corridor) | 2 | 2025-09-25 | 2025-09-27
R7S1ONME-AP05FF410 | Installation of Ducting and insulation (connection between modular cages) - AP#05 (FF Corridor) | 3 | 2025-09-25 | 2025-09-28
R7S1ONME-AP05FF398 | Installation of Duct & Grill in Garbage Room - AP#05 (FF Corridor) | 2 | 2025-09-28 | 2025-09-29
R7S1ONME-AP05FF411 | Installation of Grilles in the Corridor - AP#05 (FF Corridor) | 2 | 2025-11-03 | 2025-11-04
FIRE FIGHTING |  | 31 | 2025-08-06 | 2025-11-05
R7S1ONME-AP05FF1746 | Installation of F.F Pipes, Testing & Final Fixtures (In Front of Lift Shaft) - AP05 | 3 | 2025-08-06 | 2025-08-09
R7S1ONME-AP05FF399 | Installation of Pipe & sprinkler in Garbage Room - AP#05 (FF Corridor) | 1 | 2025-09-20 | 2025-09-20
R7S1ONME-AP05FF365 | Riser Continuity in corridor - AP#05 (FF Corridor) | 4 | 2025-09-20 | 2025-09-24
R7S1ONME-AP05FF366 | Continuation of FF pipes & ZC Valves (connection between modular cages & modular to apartment) - AP#05 (FF Corridor) | 4 | 2025-09-20 | 2025-09-24
R7S1ONME-AP05FF367 | Installation of Sprinklers drops in corridor - AP#05 (FF Corridor) | 4 | 2025-09-25 | 2025-09-29
R7S1ONME-AP05FF368 | Pressure Test for FF Piping in corridor - AP#05 (FF Corridor) | 4 | 2025-09-30 | 2025-10-04
R7S1ONME-AP05FF412 | FF Flushing network - AP#05 (FF Corridor) | 1 | 2025-10-11 | 2025-10-11
R7S1ONME-AP05FF370 | Installation of Alarm check valve, Fire Extinguishers & Blanket (Last Stage of the Building) - AP#05 (FF Corridor) | 2 | 2025-11-03 | 2025-11-04
R7S1ONME-AP05FF369 | Installation of Sprinklers in corridor - AP#05 (FF Corridor) | 3 | 2025-11-03 | 2025-11-05
WATER SUPPLY |  | 10 | 2025-09-20 | 2025-10-13
R7S1ONME-AP05FF371 | Riser Continuity in Shafts - AP#05 (FF Corridor) | 4 | 2025-09-20 | 2025-09-24
R7S1ONME-AP05FF372 | WS High Level Pipe continuation & Insulation works in Corridor - AP#05 (FF Corridor) | 4 | 2025-09-20 | 2025-09-24
R7S1ONME-AP05FF400 | Installation of WS Pipe in Garbage Room - AP#05 (FF Corridor) | 2 | 2025-09-25 | 2025-09-27
R7S1ONME-AP05FF373 | Installation of Cold, Hot water line & Hot water return in corridor - AP#05 (FF Corridor) | 4 | 2025-09-25 | 2025-09-29
R7S1ONME-AP05FF374 | Water Meter Installation in Corridor - AP#05 (FF Corridor) | 2 | 2025-09-30 | 2025-10-01
R7S1ONME-AP05FF401 | Installation of Sanitary Fixtures in Janitor Room - AP#05 (FF Corridor) | 4 | 2025-09-28 | 2025-10-01
R7S1ONME-AP05FF375 | Pressure Test for WS - AP#05 (FF Corridor) | 4 | 2025-10-02 | 2025-10-06
R7S1ONME-AP05FF413 | Insulation for Hot water line & Hot water return in corridor - AP#05 (FF Corridor) | 4 | 2025-10-09 | 2025-10-13
DRAINAGE |  | 12 | 2025-09-20 | 2025-09-29
R7S1ONME-AP05FF376 | Installation of Clean-outs, Floor drain in balcony - AP#05 (FF Corridor) | 4 | 2025-09-20 | 2025-09-24
R7S1ONME-AP05FF377 | Rain Water Riser continuation in Shafts - AP#05 (FF Corridor) | 4 | 2025-09-20 | 2025-09-24
R7S1ONME-AP05FF378 | Drainage Riser continuation in Shafts - AP#05 (FF Corridor) | 4 | 2025-09-20 | 2025-09-24
R7S1ONME-AP05FF379 | Testing for Rain Water Riser - AP#05 (FF Corridor) | 4 | 2025-09-25 | 2025-09-29
R7S1ONME-AP05FF380 | Testing for Drainage Riser - AP#05 (FF Corridor) | 4 | 2025-09-25 | 2025-09-29
ELECTRICAL |  | 44 | 2025-08-05 | 2025-11-08
POWER & LIGHTING |  | 42 | 2025-08-05 | 2025-11-08
R7S1ONME-AP05FF1956 | Continuation of Cable Tray/Trunking with Flexible conduits for Lights (In Front of Lift Shaft) - AP#05 | 4 | 2025-08-05 | 2025-08-09
R7S1ONME-AP05FF381 | Contiuation of Cable Trays & apartment branches - AP#05 (FF Corridor) | 4 | 2025-09-20 | 2025-09-24
R7S1ONME-AP05FF382 | Contiuation of Cable Trunking with Flexible conduits for Lights - AP#05 (FF Corridor) | 4 | 2025-09-20 | 2025-09-24
R7S1ONME-AP05FF383 | Installation of EMT pipes - AP#05 (FF Corridor) | 5 | 2025-09-21 | 2025-09-27
R7S1ONME-AP05FF384 | Installation of Busbar, Electrical Meter & Tap-off - AP#05 (FF Corridor) | 3 | 2025-09-25 | 2025-09-28
R7S1ONME-AP05FF407 | Termination of Tap-off with Electrical Meter in the apartments - AP#05 (FF Corridor) | 3 | 2025-09-29 | 2025-10-01
R7S1ONME-AP05FF385 | Corridor Wire Pulling - AP#05 (FF Corridor) | 6 | 2025-09-28 | 2025-10-04
R7S1ONME-AP05FF386 | Electrical Room - Installation of Cable trays, SMDB & Termination - AP#05 (FF Corridor) | 6 | 2025-10-05 | 2025-10-11
R7S1ONME-AP05FF388 | Installation, Termination of Emergeny & Exit Lights with contiuity - AP#05 (FF Corridor) | 2 | 2025-11-03 | 2025-11-04
R7S1ONME-AP05FF387 | Installation, Termination of Light Fixtures with continuity test - AP#05 (FF - Corridor & Balconies) | 3 | 2025-11-03 | 2025-11-05
R7S1ONME-AP05FF389 | Installation, Termination of PIR sensors with continuity test - AP#05 (FF Corridor) | 2 | 2025-11-06 | 2025-11-08
LOW CURRENT SYSTEM |  | 43 | 2025-09-06 | 2025-11-06
R7S1ONME-AP05FF390 | Installation of Basket trays for BMS, CCTV, Access Control - AP#05 (FF Corridor) | 4 | 2025-09-06 | 2025-09-09
R7S1ONME-AP05FF392 | Fire alarm cable installation - AP#05 (FF Corridor) | 3 | 2025-09-07 | 2025-09-09
R7S1ONME-AP05FF391 | Voice Evacuation cable installation - AP#05 (FF Corridor) | 3 | 2025-09-09 | 2025-09-11
R7S1ONME-AP05FF414 | CBS System cable installation - AP#05 (FF Corridor) | 3 | 2025-09-18 | 2025-09-21
R7S1ONME-AP05FF393 | Fibre optic Cable pulling & Termination with OTO (in corridors to ONU) - AP#05 (FF Corridor) | 2 | 2025-09-21 | 2025-09-22
R7S1ONME-AP05FF394 | BMS, CCTV & Access control Cable installation - AP#05 (FF Corridor) | 2 | 2025-09-21 | 2025-09-22
R7S1ONME-AP05FF395 | Low Current Works including BMS Panel in ICT Room - AP#05 (FF Corridor) | 10 | 2025-09-16 | 2025-09-28
R7S1ONME-AP05FF406 | Fluke test for CCTV & Fibre Optic Cable - AP#05 (FF Corridor) | 2 | 2025-09-27 | 2025-09-28
R7S1ONME-AP05FF2166 | Installation of Basket trays for Low Current, Cable Installation (In Front of Lift Shaft) - AP#05 | 4 | 2025-10-07 | 2025-10-11
R7S1ONME-AP05FF402 | Installation & Termination of CCTV Cameras - AP#05 (FF Corridor) | 2 | 2025-11-03 | 2025-11-04
R7S1ONME-AP05FF403 | Installation & Termination of Access control system for Electrical Room - AP#05 (FF Corridor) | 2 | 2025-11-03 | 2025-11-04
R7S1ONME-AP05FF405 | Installation & Termination of Wireless Gateway & RF Node - AP#05 (FF Corridor) | 2 | 2025-11-03 | 2025-11-04
R7S1ONME-AP05FF396 | Installation & Termination of Fire alarm devices & Speakers - AP#05 (FF Corridor) | 4 | 2025-11-03 | 2025-11-06
R7S1ONME-AP05FF404 | Installation & Termination of Active Components & UPS installation in ICT Room | 2 | 2025-11-05 | 2025-11-06
SECOND FLOOR |  | 114 | 2025-06-22 | 2025-11-27
ARCH./ CIVIL WORKS |  | 114 | 2025-06-22 | 2025-11-27
CORRIDOR AREA |  | 59 | 2025-08-04 | 2025-11-27
R7S1ONAR-AP05SF198 | Flooring in Corridor - AP#05 (SF Corridor) | 6 | 2025-08-04 | 2025-08-11
R7S1ONAR-AP05SF199 | Corridor Skirting - AP#05 (SF Corridor) | 2 | 2025-08-10 | 2025-08-12
R7S1ONAR-AP05SF196 | False Ceiling - 1st Fix - AP#05 (SF Corridor) | 4 | 2025-08-12 | 2025-08-17
R7S1ONAR-AP05SF197 | Gypsum Wall Cladding (Shafts) - AP#05 (SF Corridor) | 6 | 2025-11-01 | 2025-11-06
R7S1ONAR-AP05SF200 | Gypsum Wall Cladding (Shafts) -2nd Fix - AP#05 (SF Corridor) | 4 | 2025-11-08 | 2025-11-11
R7S1ONAR-AP05SF204 | Fixing Architrave - AP#05 (SF Corridor) | 2 | 2025-11-12 | 2025-11-13
R7S1ONAR-AP05SF205 | Fixing Aluminium Doors - AP#05 (SF Corridor) | 2 | 2025-11-15 | 2025-11-16
R7S1ONAR-AP05SF201 | False Ceiling - 2nd Fix (Closing the Ceiling) - AP#05 (SF Corridor) | 2 | 2025-11-17 | 2025-11-18
R7S1ONAR-AP05SF202 | Painting - Surface Prep., Primer & 1st Coat - AP#05 (SF Corridor) | 8 | 2025-11-12 | 2025-11-20
R7S1ONAR-AP05SF226 | Painting - Surface Prep., Primer & 1st Coat - AP#05 (SF Corridor) | 4 | 2025-11-19 | 2025-11-23
R7S1ONAR-AP05SF203 | Painting - Final Coat (Ceiling + Walls) - AP#05 (SF Corridor) | 3 | 2025-11-25 | 2025-11-27
INSIDE BOXES |  | 12 | 2025-09-01 | 2025-09-14
R7S1ONAR-AP05SF206 | Fixing Thresholds (Joining the Room) - AP#05 (SF - inside Boxes) | 4 | 2025-09-01 | 2025-09-04
R7S1ONAR-AP05SF207 | Fixing Wooden Doors - AP#05 (SF - inside Boxes) | 4 | 2025-09-06 | 2025-09-09
R7S1ONAR-AP05SF208 | Fixing Aluminium Doors (Next Floor) - AP#05 (SF - inside Boxes) | 4 | 2025-09-10 | 2025-09-14
IN FRONT OF LIFT SHAFT |  | 114 | 2025-06-22 | 2025-11-06
R7S1ONAR-AP05SF210 | Flooring - AP#05 (SF - Front of Lift Shaft) | 3 | 2025-06-22 | 2025-06-24
R7S1ONAR-AP05SF211 | Skirting & Thresholds - AP#05 (SF - Front of Lift Shaft) | 2 | 2025-06-25 | 2025-06-26
R7S1ONAR-AP05SF212 | Painting - Surface Prep., Primer & 1st Coat - AP#05 (SF - Front of Lift Shaft) | 4 | 2025-06-28 | 2025-07-01
R7S1ONAR-AP05SF209 | False Ceiling - 1st Fix - AP#05 (SF - Front of Lift Shaft) | 4 | 2025-09-01 | 2025-09-04
R7S1ONAR-AP05SF213 | False Ceiling - Final Fix - AP#05 (SF - Front of Lift Shaft) | 3 | 2025-10-11 | 2025-10-13
R7S1ONAR-AP05SF215 | Fixing Handrail - AP#05 (SF - Front of Lift Shaft) | 3 | 2025-10-14 | 2025-10-16
R7S1ONAR-AP05SF216 | Paint for Handrail - AP#05 (SF - Front of Lift Shaft) | 3 | 2025-10-18 | 2025-10-20
R7S1ONAR-AP05SF214 | Painting - 2nd Coat - AP#05 (SF - Front of Lift Shaft) | 3 | 2025-11-02 | 2025-11-04
R7S1ONAR-AP05SF217 | Fixing Floor Mat - AP#05 (SF - Front of Lift Shaft) | 2 | 2025-11-05 | 2025-11-06
R7S1ONAR-AP05SF218 | Fixing Wall Guard - AP#05 (SF - Front of Lift Shaft) | 2 | 2025-11-05 | 2025-11-06
GARBAGE ROOM |  | 29 | 2025-08-17 | 2025-11-24
R7S1ONAR-AP05SF225 | Installation of Garbage Chute Full System from GF to 2nd Floor - AP#05 (SF - Garbage Room) | 10 | 2025-08-17 | 2025-08-27
R7S1ONAR-AP05SF219 | Installation of Dry Walls - First Fix - AP#05 (SF - Garbage Room) | 1 | 2025-08-28 | 2025-08-28
R7S1ONAR-AP05SF220 | Installation of Dry Walls - Final Fix - AP#05 (SF - Garbage Room) | 1 | 2025-08-30 | 2025-08-30
R7S1ONAR-AP05SF221 | Garbage Rooms - Wall Tile Finishes (One Side) - AP#05 (SF - Garbage Room) | 1 | 2025-08-31 | 2025-08-31
R7S1ONAR-AP05SF222 | Paint Works of Dry Walls - First Coat - AP#05 (SF - Garbage Room) | 1 | 2025-09-01 | 2025-09-01
R7S1ONAR-AP05SF223 | Installation of the Garbage Chute Door - AP#05 (SF - Garbage Room) | 1 | 2025-09-02 | 2025-09-02
R7S1ONAR-AP05SF224 | Paint Finishes and Touchups - Final Coat - AP#05 (SF - Garbage Room) | 2 | 2025-11-23 | 2025-11-24
MEP WORKS |  | 55 | 2025-09-10 | 2025-11-24
MECHANICAL |  | 55 | 2025-09-25 | 2025-11-22
CHILLED WATER |  | 12 | 2025-09-25 | 2025-10-12
R7S1ONME-AP05SF331 | Installation of Chilled water hanger and supports - AP#05 (SF Corridor) | 4 | 2025-09-25 | 2025-09-29
R7S1ONME-AP05SF381 | Installation of CHWP connection for FCU with Valve package in Corridor, Electrical Room & ICT Room | 4 | 2025-09-25 | 2025-09-29
R7S1ONME-AP05SF333 | Installation of BTU Meter with valves - AP#05 (SF Corridor) | 2 | 2025-10-01 | 2025-10-02
R7S1ONME-AP05SF332 | Installation of CHWP piping (connection between modular cages & modular to apartment) - AP#05 (SF Corridor) | 4 | 2025-09-30 | 2025-10-04
R7S1ONME-AP05SF334 | CHWP piping risers connections - AP#05 (SF Corridor) | 3 | 2025-10-04 | 2025-10-06
R7S1ONME-AP05SF335 | Pressure Testing of CHWP piping - AP#05 (SF Corridor) | 1 | 2025-10-07 | 2025-10-07
R7S1ONME-AP05SF1546 | CHWP Installation/Connections and Insulation (In Front of Lift Shaft) - AP#05 | 4 | 2025-10-07 | 2025-10-11
R7S1ONME-AP05SF370 | CHWP Insulation - AP#05 (SF Corridor) | 4 | 2025-10-08 | 2025-10-12
HVAC DUCTING |  | 51 | 2025-09-25 | 2025-11-20
R7S1ONME-AP05SF336 | Duct Riser Continuation - AP#05 (SF Corridor) | 4 | 2025-09-25 | 2025-09-29
R7S1ONME-AP05SF382 | Installation of FCU's & Duct Connection in Corridor, Electrical Room & ICT Room - AP#05 (SF Corridor) | 4 | 2025-09-25 | 2025-09-29
R7S1ONME-AP05SF337 | A/C drain & Copper pipe connection in ELV room - AP#05 (SF Corridor) | 2 | 2025-09-30 | 2025-10-01
R7S1ONME-AP05SF383 | Installation of Ducting and insulation (connection between modular cages) - AP#05 (SF Corridor) | 3 | 2025-09-30 | 2025-10-02
R7S1ONME-AP05SF371 | Installation of Duct & Grill in Garbage Room - AP#05 (SF Corridor) | 2 | 2025-11-19 | 2025-11-20
R7S1ONME-AP05SF384 | Installation of Grilles in the Corridor - AP#05 (SF Corridor) | 2 | 2025-11-19 | 2025-11-20
FIRE FIGHTING |  | 41 | 2025-09-25 | 2025-11-22
R7S1ONME-AP05SF338 | Riser Continuity Succ - Closing of Gysum Boards on shaft - AP#05 (SF Corridor) | 4 | 2025-09-25 | 2025-09-29
R7S1ONME-AP05SF339 | FF Contiuation on High Level with Valves - AP#05 (SF Corridor) | 4 | 2025-09-30 | 2025-10-04
R7S1ONME-AP05SF340 | Installation of Sprinklers drops - AP#05 (SF Corridor) | 4 | 2025-10-05 | 2025-10-08
R7S1ONME-AP05SF341 | Pressure Test for FF Piping - AP#05 (SF Corridor) | 1 | 2025-10-09 | 2025-10-09
R7S1ONME-AP05SF1756 | Installation of F.F Pipes, Testing & Final Fixtures (In Front of Lift Shaft) - AP05 | 3 | 2025-10-07 | 2025-10-09
R7S1ONME-AP05SF343 | Installation of Fire Extinguishers - AP#05 (SF Corridor) | 2 | 2025-11-19 | 2025-11-20
R7S1ONME-AP05SF342 | Installation of Sprinklers - AP#05 (SF Corridor) | 3 | 2025-11-19 | 2025-11-22
R7S1ONME-AP05SF372 | Installation of Pipe & sprinkler in Garbage Room - AP#05 (SF Corridor) | 3 | 2025-11-19 | 2025-11-22
WATER SUPPLY |  | 12 | 2025-09-25 | 2025-10-18
R7S1ONME-AP05SF344 | Riser Continuity - AP#05 (SF Corridor) | 4 | 2025-09-25 | 2025-09-29
R7S1ONME-AP05SF345 | WS High Level Pipe continuation & Insulation works - AP#05 (SF Corridor) | 4 | 2025-09-25 | 2025-09-29
R7S1ONME-AP05SF373 | Installation of WS Pipe in Garbage Room - AP#05 (SF Corridor) | 2 | 2025-09-28 | 2025-09-29
R7S1ONME-AP05SF346 | Instalation of Hot water line in corridor - AP#05 (SF Corridor) | 4 | 2025-09-30 | 2025-10-04
R7S1ONME-AP05SF374 | Installation of Sanitary Fixtures in Janitor Room - AP#05 (SF Corridor) | 2 | 2025-10-02 | 2025-10-04
R7S1ONME-AP05SF347 | Water Meter Installation - AP#05 (SF Corridor) | 4 | 2025-10-05 | 2025-10-08
R7S1ONME-AP05SF348 | Pressure Test for WS - AP#05 (SF Corridor) | 4 | 2025-10-09 | 2025-10-13
R7S1ONME-AP05FF415 | Insulation for Hot water line & Hot water return in corridor - AP#05 (SF Corridor) | 4 | 2025-10-14 | 2025-10-18
DRAINAGE |  | 13 | 2025-09-25 | 2025-10-04
R7S1ONME-AP05SF349 | Installation of Clean-outs - AP#05 (SF Corridor) | 4 | 2025-09-25 | 2025-09-29
R7S1ONME-AP05SF350 | Rain Water Riser continuation - AP#05 (SF Corridor) | 4 | 2025-09-25 | 2025-09-29
R7S1ONME-AP05SF351 | Drainage Riser continuation - AP#05 (SF Corridor) | 4 | 2025-09-25 | 2025-09-29
R7S1ONME-AP05SF352 | Testing for Rain Water Riser - AP#05 (SF Corridor) | 4 | 2025-09-30 | 2025-10-04
R7S1ONME-AP05SF353 | Testing for Drainage Riser - AP#05 (SF Corridor) | 4 | 2025-09-30 | 2025-10-04
ELECTRICAL |  | 37 | 2025-09-10 | 2025-11-24
POWER & LIGHTING |  | 37 | 2025-09-25 | 2025-11-24
R7S1ONME-AP05SF354 | Contiuation of Cable Trays & apartment branches - AP#05 (SF Corridor) | 4 | 2025-09-25 | 2025-09-29
R7S1ONME-AP05SF355 | Contiuation of Cable Trunking with Flexible conduits for Lights - AP#05 (SF Corridor) | 4 | 2025-09-25 | 2025-09-29
R7S1ONME-AP05SF356 | Installation of EMT pipes - AP#05 (SF Corridor) | 5 | 2025-09-28 | 2025-10-02
R7S1ONME-AP05SF357 | Installation of Busbar, Electrical Meter & Tap-off in Corridor - AP#05 (SF Corridor) | 3 | 2025-09-30 | 2025-10-02
R7S1ONME-AP05SF380 | Termination of Tap-off with Electrical Meter in the apartments - AP#05 (SF Corridor) | 3 | 2025-10-04 | 2025-10-06
R7S1ONME-AP05SF358 | Corridor Wire Pulling - AP#05 (SF Corridor) | 6 | 2025-10-04 | 2025-10-09
R7S1ONME-AP05SF1966 | Continuation of Cable Tray/Trunking with Flexible conduits for Lights (In Front of Lift Shaft) - AP#05 | 4 | 2025-10-06 | 2025-10-09
R7S1ONME-AP05SF359 | Electrical Room - Installation of Cable trays, SMDB & Termination - AP#05 (SF Corridor) | 6 | 2025-10-26 | 2025-11-01
R7S1ONME-AP05SF361 | Installation, Termination of Emergeny & Exit Lights with contiuity - AP#05 (SF Corridor) | 2 | 2025-11-19 | 2025-11-20
R7S1ONME-AP05SF360 | Installation, Termination of Light Fixtures with continuity test - AP#05 (SF - Corridor & Balconies) | 3 | 2025-11-19 | 2025-11-22
R7S1ONME-AP05SF362 | Installation, Termination of PIR sensors with continuity test - AP#05 (SF Corridor) | 2 | 2025-11-23 | 2025-11-24
LOW CURRENT SYSTEM |  | 34 | 2025-09-10 | 2025-11-23
R7S1ONME-AP05SF363 | Installation of Basket trays for BMS, CCTV, Access Control - AP#05 (SF Corridor) | 4 | 2025-09-10 | 2025-09-14
R7S1ONME-AP05SF365 | Fire alarm cable installation - AP#05 (SF Corridor) | 3 | 2025-09-11 | 2025-09-14
R7S1ONME-AP05SF364 | Voice Evacuation cable installation - AP#05 (SF Corridor) | 3 | 2025-09-14 | 2025-09-16
R7S1ONME-AP05SF366 | Fibre optic Cable pulling & Termination with OTO (in corridors to ONU) - AP#05 (SF Corridor) | 2 | 2025-09-24 | 2025-09-25
R7S1ONME-AP05SF367 | BMS, CCTV & Access control Cable installation - AP#05 (SF Corridor) | 2 | 2025-09-24 | 2025-09-25
R7S1ONME-AP05SF385 | CBS System cable installation - AP#05 (SF Corridor) | 3 | 2025-09-22 | 2025-09-25
R7S1ONME-AP05SF2176 | Installation of Basket trays for Low Current, Cable Installation (In Front of Lift Shaft) - AP#05 | 4 | 2025-10-06 | 2025-10-09
R7S1ONME-AP05SF368 | Low Current Works including BMS Panel in ICT Room - AP#05 (SF Corridor) | 10 | 2025-10-20 | 2025-10-30
R7S1ONME-AP05SF379 | Fluke test for CCTV & Fibre Optic Cable - AP#05 (SF Corridor) | 2 | 2025-10-29 | 2025-10-30
R7S1ONME-AP05SF375 | Installation & Termination of CCTV Cameras - AP#05 (SF Corridor) | 2 | 2025-11-19 | 2025-11-20
R7S1ONME-AP05SF376 | Installation & Termination of Access control system for Electrical Room - AP#05 (SF Corridor) | 2 | 2025-11-19 | 2025-11-20
R7S1ONME-AP05SF378 | Installation & Termination of Wireless Gateway & RF Node in corridors - AP#05 (SF Corridor) | 2 | 2025-11-19 | 2025-11-20
R7S1ONME-AP05SF369 | Installation & Termination of Fire alarm devices & Speakers - AP#05 (SF Corridor) | 4 | 2025-11-19 | 2025-11-23
R7S1ONME-AP05SF377 | Installation & Termination of Active Components & UPS installation in ICT Room - AP#05 (SF Corridor) | 2 | 2025-11-22 | 2025-11-23
ROOF WORKS |  | 75 | 2025-09-15 | 2025-11-19
ARCH./ CIVIL WORKS |  | 75 | 2025-09-15 | 2025-11-19
R7S1ONAR-AP05RF51 | Roof Box Stiching (Concrete Works) - AP#05 (Roof) | 6 | 2025-09-15 | 2025-09-21
R7S1ONME-AP05RF341 | Installation of Roof Drains - AP#05 (Roof) | 2 | 2025-09-20 | 2025-09-21
R7S1ONAR-AP05RF52 | Roof Waterproofing Works with testing - AP#05 (Roof) | 20 | 2025-09-24 | 2025-10-16
R7S1ONAR-AP05RF53 | Laying of Gravel - AP#05 (Roof) | 2 | 2025-10-18 | 2025-10-19
R7S1ONAR-AP05RF54 | Surface Preparation & Primer for Parapets - AP#05 (Roof) | 6 | 2025-11-06 | 2025-11-12
R7S1ONAR-AP05RF55 | 1st Coat Paint for Parapets - AP#05 (Roof) | 2 | 2025-11-13 | 2025-11-15
R7S1ONAR-AP05RF57 | Crossover Bridges Installation & application of Sealant on MEP penetrations - AP#05 (Roof) | 12 | 2025-11-03 | 2025-11-16
R7S1ONAR-AP05RF56 | 2nd Coat Paint for Parapets - AP#05 (Roof) | 2 | 2025-11-16 | 2025-11-17
R7S1ONAR-AP05RF58 | Fixing Fall Arrest System - AP#05 (Roof) | 2 | 2025-11-18 | 2025-11-19
MECHANICAL |  | 49 | 2025-10-20 | 2025-11-11
HVAC |  | 31 | 2025-10-20 | 2025-11-04
R7S1ONME-AP05RF305 | Modular Installation - AP#05 (Roof) | 5 | 2025-10-20 | 2025-10-25
R7S1ONME-AP05RF306 | Continuation of Roof duct works/FAHU Connections - AP#05 (Roof) | 5 | 2025-10-22 | 2025-10-27
R7S1ONME-AP05RF308 | Insulations for ducts - AP#05 (Roof) | 5 | 2025-10-23 | 2025-10-28
R7S1ONME-AP05RF310 | Installation of FAHU - AP#05 (Roof) | 2 | 2025-10-28 | 2025-10-29
R7S1ONME-AP05RF315 | Installation of Outdoor VRF/DX Units - AP#05 (Roof) | 2 | 2025-10-29 | 2025-10-30
R7S1ONME-AP05RF316 | Installation & Insulation of the Condensation Drain - AP#05 (Roof) | 1 | 2025-10-30 | 2025-10-30
R7S1ONME-AP05RF318 | Installation of Ventilation Fans - AP#05 (Roof) | 3 | 2025-10-28 | 2025-10-30
R7S1ONME-AP05RF313 | Chilled Water System Continuation and Connections with Valve package of FAHU - AP#05 (Roof) | 4 | 2025-10-28 | 2025-11-01
R7S1ONME-AP05RF320 | Installation of Louvers - AP#05 (Roof) | 2 | 2025-11-01 | 2025-11-02
R7S1ONME-AP05RF323 | Installation & Testing of Copper Pipes - AP#05 (Roof) | 2 | 2025-11-01 | 2025-11-02
R7S1ONME-AP05RF324 | Miscellaneous Works for Mechanical Connections (Fire & Volume Dampers etc.) - AP#05 (Roof) | 2 | 2025-11-03 | 2025-11-04
WATERSUPPLY & DRAINAGE |  | 26 | 2025-10-26 | 2025-11-10
R7S1ONME-AP05RF304 | Testing for the Rain Water Risers - AP#05 (Roof) | 2 | 2025-10-28 | 2025-10-29
R7S1ONME-AP05RF307 | Installation & Continuation of Water supply pipes (connection between modular cages & modular to Shaft Riser) - AP#05 | 4 | 2025-10-26 | 2025-10-29
R7S1ONME-AP05RF311 | Installation of Air Vent & Pressure Guage with Valves at Roof - AP#05 (Roof) | 4 | 2025-10-28 | 2025-11-01
R7S1ONME-AP05RF312 | Vertical Continuation of Vent Pipes To The Roof (Drainage) - AP#05 (Roof) | 4 | 2025-10-29 | 2025-11-02
R7S1ONME-AP05RF314 | Installation of Rain Water outlet - AP#05 (Roof) | 3 | 2025-10-30 | 2025-11-02
R7S1ONME-AP05RF309 | Installation of Air Vent with Valve for Water Supply - AP#05 (Roof) | 4 | 2025-10-30 | 2025-11-03
R7S1ONME-AP05RF317 | Testing of Water Supply Pipes - AP#05 (Roof) | 2 | 2025-11-04 | 2025-11-05
R7S1ONME-AP05RF319 | Insulation of Roof Water Line - AP#05 (Roof) | 2 | 2025-11-05 | 2025-11-06
R7S1ONME-AP05RF321 | Testing for the Drainage Pipes Risers - AP#05 (Roof) | 2 | 2025-11-08 | 2025-11-09
R7S1ONME-AP05RF322 | Installation of Vent Cowl - AP#05 (Roof) | 1 | 2025-11-10 | 2025-11-10
SOLAR HEATER |  | 39 | 2025-10-30 | 2025-11-11
R7S1ONME-AP05RF336 | Installation of Solar water pumps and circulation pumps with valves(For Water Only) - AP#05 (Roof) | 2 | 2025-11-01 | 2025-11-02
R7S1ONME-AP05RF334 | Installation of Structure and Solar Panels (For Water Only) - AP#05 (Roof) | 5 | 2025-10-30 | 2025-11-04
R7S1ONME-AP05RF335 | Installation of Solar Calorifier Tank & Air cooler (For Water Only) - AP#05 (Roof) | 5 | 2025-11-01 | 2025-11-05
R7S1ONME-AP05RF337 | Installation of Solar Pipes Primary Loop - AP#05 (Roof) | 5 | 2025-11-01 | 2025-11-05
R7S1ONME-AP05RF338 | Testing of Solar Pipes Primary Loop - AP#05 (Roof) | 1 | 2025-11-06 | 2025-11-06
R7S1ONME-AP05RF339 | Insulation of Solar Pipes Primary Loop - AP#05 (Roof) | 1 | 2025-11-06 | 2025-11-06
R7S1ONME-AP05RF340 | Aluminum Cladding of Solar Pipes Primary Loop - AP#05 (Roof) | 4 | 2025-11-08 | 2025-11-11
ELECTRICAL |  | 38 | 2025-10-20 | 2025-11-15
POWER & LOW CURRENT |  | 38 | 2025-10-20 | 2025-11-15
R7S1ONME-AP05RF299 | Lightening Protection & Earthing System - AP#05 (Roof) | 7 | 2025-10-20 | 2025-10-27
R7S1ONME-AP05RF325 | Installation of Cables for Fire Alarm system - AP#05 (Roof) | 3 | 2025-10-26 | 2025-10-28
R7S1ONME-AP05RF326 | Installation of Cables for BMS - AP#05 (Roof) | 3 | 2025-10-26 | 2025-10-28
R7S1ONME-AP05RF327 | Installation of Fire Alarm Devices - AP#05 (Roof) | 3 | 2025-10-26 | 2025-10-28
R7S1ONME-AP05RF329 | Installation of Roof Light Fixtures - AP#05 (Roof) | 3 | 2025-10-26 | 2025-10-28
R7S1ONME-AP05RF300 | Installation of Isolators and Machine Connections - AP#05 (Roof) | 4 | 2025-10-26 | 2025-10-29
R7S1ONME-AP05RF328 | Installation of BMS Devices - AP#05 (Roof) | 4 | 2025-10-27 | 2025-10-30
R7S1ONME-AP05RF302 | Installation of Fire Alarm Containment for FAHU, Fans - AP#05 (Roof) | 4 | 2025-10-28 | 2025-11-01
R7S1ONME-AP05RF301 | Installation of Electrical Containments for BMS - AP#05 (Roof) | 7 | 2025-10-26 | 2025-11-02
R7S1ONME-AP05RF332 | Termination for Fire Alarm Device - AP#05 (Roof) | 1 | 2025-11-02 | 2025-11-02
R7S1ONME-AP05RF331 | Termination for BMS System - AP#05 (Roof) | 1 | 2025-11-03 | 2025-11-03
R7S1ONME-AP05RF343 | Termination of Primary & Secondary pump for Solar system - AP#05 (Roof) | 1 | 2025-11-03 | 2025-11-03
R7S1ONME-AP05RF303 | Installation of LV Power Cables for Roof Equipment - AP#05 (Roof) | 5 | 2025-11-02 | 2025-11-06
R7S1ONME-AP05RF330 | Termination for LV Cables - AP#05 (Roof) | 1 | 2025-11-08 | 2025-11-08
R7S1ONME-AP05RF333 | Megger Test for the Power Cables - AP#05 (Roof) | 1 | 2025-11-09 | 2025-11-09
R7S1ONME-AP05RF342 | Installation & Termination of Solar System Panel - AP#05 (Roof) | 3 | 2025-11-12 | 2025-11-15
STAIR CASE |  | 99 | 2025-09-22 | 2025-11-12
CIVIL WORKS |  | 78 | 2025-09-22 | 2025-11-08
STAIR CASE (MAIN WITH LIFT) |  | 72 | 2025-09-22 | 2025-10-20
R7S1ONST-AP05RG407 | Stair Flooring (Roof to GF) - AP#05 (Main Stair) | 7 | 2025-09-22 | 2025-09-30
R7S1ONST-AP05RG408 | Stair Hand Rails (Roof to GF) - AP#05 (Main Stair) | 6 | 2025-10-01 | 2025-10-07
R7S1ONST-AP05RG409 | Stair Paint - Primer & 1st Coat (Roof to GF)- AP#05 (Main Stair) | 7 | 2025-10-08 | 2025-10-15
R7S1ONST-AP05RG410 | Stair Paint - Final Coat (Roof to GF)- AP#05 (Main Stair) | 4 | 2025-10-16 | 2025-10-20
STAIR CASE (LEFT SIDE) |  | 50 | 2025-10-01 | 2025-10-26
R7S1ONST-AP05RG417 | Stair Flooring (Roof to GF) - AP#05 Left Side Stair | 7 | 2025-10-01 | 2025-10-08
R7S1ONST-AP05RG418 | Stair Hand Rails (Roof to GF) - AP#05 Left Side Stair | 6 | 2025-10-09 | 2025-10-15
R7S1ONST-AP05RG419 | Stair Paint - Primer & 1st Coat (Roof to GF) - AP#05 Left Side Stair | 6 | 2025-10-16 | 2025-10-22
R7S1ONST-AP05RG420 | Stair Paint - Final Coat (Roof to GF) - AP#05 Left Side Stair | 3 | 2025-10-23 | 2025-10-26
STAIR CASE (RIGHT SIDE) |  | 47 | 2025-10-09 | 2025-11-08
R7S1ONST-AP05RG421 | Stair Flooring (Roof to GF) - AP#05 Right Side Stair | 8 | 2025-10-09 | 2025-10-18
R7S1ONST-AP05RG422 | Stair Hand Rails (Roof to GF) - AP#05 Right Side Stair | 7 | 2025-10-19 | 2025-10-26
R7S1ONST-AP05RG423 | Stair Paint - Primer & 1st Coat (Roof to GF) - AP#05 Right Side Stair | 7 | 2025-10-27 | 2025-11-03
R7S1ONST-AP05RG424 | Stair Paint - Final Coat (Roof to GF) - AP#05 Right Side Stair | 4 | 2025-11-04 | 2025-11-08
MEP WORKS |  | 79 | 2025-09-29 | 2025-11-12
STAIR CASE (MAIN WITH LIFT) |  | 55 | 2025-09-29 | 2025-10-25
R7S1ONST-AP05RG406 | Main Staircase Wire Pulling - AP#05 (Main Stair) | 3 | 2025-09-29 | 2025-10-01
R7S1ONST-AP05RG425 | Final fix - Main Staircase Lights Fixtures & Motion Sensor - AP#05 (Main Stair) | 2 | 2025-10-21 | 2025-10-22
R7S1ONST-AP05RG426 | Final fix - Main Staircase Emergency Lights Fixtures - AP#05 (Main Stair) | 2 | 2025-10-23 | 2025-10-25
STAIR CASE (LEFT SIDE) |  | 60 | 2025-10-02 | 2025-10-30
R7S1ONST-AP05RG411 | Left Staircase Wire Pulling - AP#05 (Main Stair) | 3 | 2025-10-02 | 2025-10-05
R7S1ONST-AP05RG413 | Final fix - Left Staircase Lights Fixtures & Motion Sensor - AP#05 (Main Stair) | 2 | 2025-10-27 | 2025-10-28
R7S1ONST-AP05RG415 | Final fix - Left Staircase Emergency Lights Fixtures - AP#05 (Main Stair) | 2 | 2025-10-29 | 2025-10-30
STAIR CASE (RIGHT SIDE) |  | 73 | 2025-10-06 | 2025-11-12
R7S1ONST-AP05RG412 | Right Staircase Wire Pulling - AP#05 (Main Stair) | 3 | 2025-10-06 | 2025-10-08
R7S1ONST-AP05RG414 | Final fix - Right Staircase Lights Fixtures & Motion Sensor - AP#05 (Main Stair) | 2 | 2025-11-09 | 2025-11-10
R7S1ONST-AP05RG416 | Final fix - Right Staircase Emergency Lights Fixtures - AP#05 (Main Stair) | 2 | 2025-11-11 | 2025-11-12
ELEVATOR WORKS |  | 43 | 2025-09-22 | 2025-10-18
R7S1ONEL-AP05GR631 | Installation of Rails - AP#05 (Elevator Works) | 6 | 2025-09-22 | 2025-09-29
R7S1ONEL-AP05GR632 | Assembly of Cabin - AP#05 (Elevator Works) | 4 | 2025-09-30 | 2025-10-04
R7S1ONEL-AP05GR633 | Installation of Motor - AP#05 (Elevator Works) | 4 | 2025-10-05 | 2025-10-08
R7S1ONEL-AP05GR634 | Installation of Main Cables - AP#05 (Elevator Works) | 4 | 2025-10-09 | 2025-10-13
R7S1ONEL-AP05GR635 | Installation of Doors, Indicator, Push Button - AP#05 (Elevator Works) | 2 | 2025-10-14 | 2025-10-15
R7S1ONEL-AP05GR636 | Interior Finishes - AP#05 (Elevator Works) | 2 | 2025-10-16 | 2025-10-18
EXTERNAL ELEVATIONS |  | 91 | 2025-10-20 | 2025-11-20
ARCH./ CIVIL WORKS |  | 91 | 2025-10-20 | 2025-11-20
R7S1ONEE-AP05GR521 | External Selant Works - For Boxes - AP#05 (External Elevations) | 15 | 2025-10-20 | 2025-11-05
R7S1ONME-AP05GF639 | Installation of rain water outlet - External façade - AP#05 (External Elevations) | 2 | 2025-11-15 | 2025-11-16
R7S1ONEE-AP05GR522 | Final Finishes & Touchups - AP#05 (External Elevations) | 20 | 2025-10-25 | 2025-11-16
R7S1ONEE-AP05GR523 | Fixing Cage Ladder - AP#05 (External Elevations) | 2 | 2025-11-19 | 2025-11-20
R7S1ONEE-AP05GR524 | Installation of External Signages - AP#05 (External Elevations) | 4 | 2025-11-17 | 2025-11-20
EXTERNAL - CIVIL WORKS |  | 27 | 2025-10-11 | 2025-11-04
DRAINAGE |  | 9 | 2025-10-11 | 2025-10-19
R7S1ONECW-AP05-361 | Excavation Works & Sand Bedding - AP#05 (External Drainage) | 3 | 2025-10-11 | 2025-10-13
R7S1ONECW-AP05-362 | Drainage Manholes - AP#05 | 6 | 2025-10-11 | 2025-10-16
R7S1ONECW-AP05-363 | Drainage Backfilling - AP#05 | 2 | 2025-10-18 | 2025-10-19
WATERSUPPLY |  | 21 | 2025-10-11 | 2025-11-04
R7S1ONECW-AP05-364 | Excavation Works & Sand Bedding - Watersupply - AP#05 (External Watersupply Civil) | 3 | 2025-10-11 | 2025-10-13
R7S1ONECW-AP05-365 | Watersupply Manholes - AP#05 | 6 | 2025-10-14 | 2025-10-20
R7S1ONECW-AP05-366 | Watersupply Backfilling - AP#05 | 2 | 2025-11-03 | 2025-11-04
CHILLED WATER |  | 20 | 2025-10-14 | 2025-10-26
R7S1ONECW-AP05-370 | Excavation Works & Sand Bedding - AP#05 (External Chilled Water Civil) | 3 | 2025-10-14 | 2025-10-16
R7S1ONECW-AP05-371 | Chilled Water Manholes - AP#05 | 6 | 2025-10-18 | 2025-10-23
R7S1ONECW-AP05-372 | Chilled Water Backfilling - AP#05 | 2 | 2025-10-25 | 2025-10-26
FIRE FIGHTING |  | 16 | 2025-10-14 | 2025-11-01
R7S1ONECW-AP05-367 | Excavation Works & Sand Bedding - AP#05 (External Chilled Water Civil) | 3 | 2025-10-14 | 2025-10-16
R7S1ONECW-AP05-368 | Fire Fighting Manholes - AP#05 | 6 | 2025-10-18 | 2025-10-23
R7S1ONECW-AP05-369 | Fire Fighting Backfilling - AP#05 | 2 | 2025-10-30 | 2025-11-01
POWER |  | 10 | 2025-10-18 | 2025-10-26
R7S1ONECW-AP05-373 | Excavation Works & Sand Bedding - AP#05 (External Power Civil) | 3 | 2025-10-18 | 2025-10-20
R7S1ONECW-AP05-374 | Power Manholes - AP#05 | 3 | 2025-10-21 | 2025-10-23
R7S1ONECW-AP05-375 | Power Backfilling - AP#05 | 2 | 2025-10-25 | 2025-10-26
LOW CURRENT |  | 12 | 2025-10-18 | 2025-10-26
R7S1ONECW-AP05-376 | Excavation Works & Sand Bedding - AP#05 (External Low Current Civil) | 3 | 2025-10-18 | 2025-10-20
R7S1ONECW-AP05-377 | Low Current Manholes - AP#05 | 3 | 2025-10-21 | 2025-10-23
R7S1ONECW-AP05-378 | Low Current Backfilling - AP#05 | 2 | 2025-10-25 | 2025-10-26
EXTERNAL - MEP SERVICES |  | 33 | 2025-10-14 | 2025-11-04
DRAINAGE |  | 4 | 2025-10-14 | 2025-10-18
R7S1ONEME-AP05-241 | External Drainage Network - AP#05 (External Drainage MEP) | 4 | 2025-10-14 | 2025-10-18
WATERSUPPLY |  | 13 | 2025-10-21 | 2025-11-04
R7S1ONEME-AP05-242 | PRV statiuon assembly including meters- AP#05 (External WS MEP) | 4 | 2025-10-21 | 2025-10-25
R7S1ONEME-AP05-244 | Installation of valve station incl. BTU meter- AP#05 (External WS MEP) | 3 | 2025-11-02 | 2025-11-04
CHILLED WATER |  | 7 | 2025-10-26 | 2025-11-02
R7S1ONEME-AP05-243 | Installation of Chilled water line- AP#05 (External CWP MEP) | 6 | 2025-10-26 | 2025-11-01
R7S1ONEME-AP05-245 | Pressure Test for chilled water line- AP#05 (External CWP MEP) | 1 | 2025-11-02 | 2025-11-02
FIRE FIGHTING |  | 11 | 2025-10-18 | 2025-10-29
R7S1ONEME-AP05-246 | Installation of External FF network - AP#05 (External FF MEP) | 6 | 2025-10-18 | 2025-10-23
R7S1ONEME-AP05-247 | Installation of Alarm check valves- AP#05 (External FF MEP) | 3 | 2025-10-25 | 2025-10-27
R7S1ONEME-AP05-248 | Testing of External FF - AP#05 (External FF MEP) | 2 | 2025-10-28 | 2025-10-29
POWER |  | 1 | 2025-10-23 | 2025-10-23
R7S1ONEME-AP05-249 | Cable pulling from Manhole to the building MDB - AP#05 (External Power MEP) | 1 | 2025-10-23 | 2025-10-23
LOW CURRENT |  | 3 | 2025-10-21 | 2025-10-23
R7S1ONEME-AP05-250 | Low Current Cable pulling- AP#05 (External FF MEP) | 3 | 2025-10-21 | 2025-10-23
BUILDING # AP14 (LARGE STUDIO) |  | 334 | 2024-12-14 | 2025-12-02
SUB-STRUCTURE |  | 114 | 2024-12-14 | 2025-04-30
R7S1-ONSB-AP14-303 | Site Setting Out Works - AP#14 | 2 | 2024-12-14 | 2024-12-15
R7S1-ONSB-AP14-300 | Site levelling & earthworks - AP#14 | 5 | 2024-12-15 | 2024-12-19
R7S1-ONSB-AP14-304 | Anti-termite & Polythene Sheet Works - AP#14 | 1 | 2025-01-27 | 2025-01-27
R7S1-ONSB-AP14-301 | Blinding PCC - AP#14 | 3 | 2025-01-28 | 2025-01-30
R7S1-ONSB-AP14-302 | Waterproofing for Blinding PCC (Bitumen Paint) - AP#14 | 2 | 2025-02-01 | 2025-02-02
R7S1-ONSB-AP14-309 | Installation of MEP U/G services below Boxes - AP#14 | 17 | 2025-03-17 | 2025-04-09
R7S1-ONSB-AP14-305 | Foundations/Upstands - Rebar - AP#14 | 27 | 2025-03-09 | 2025-04-13
R7S1-ONSB-AP14-306 | Foundations/Upstands - Shuttering (Including dowel Works) - AP#14 | 26 | 2025-03-10 | 2025-04-13
R7S1-ONSB-AP14-307 | Foundations/Upstands - Casting - AP#14 | 17 | 2025-03-20 | 2025-04-13
R7S1-ONSB-AP14-308 | Waterproofing For Foundations/Upstands - AP#14 | 10 | 2025-04-19 | 2025-04-29
R7S1-ONSB-AP14-310 | Backfilling & Compaction - AP#14 | 5 | 2025-04-26 | 2025-04-30
SLAB-ON-GRADE & UG MEP WORKS (in Corridor) |  | 21 | 2025-06-25 | 2025-07-13
LEFT SIDE |  | 21 | 2025-06-25 | 2025-07-10
R7S1-ONSG-AP14-370 | Backfilling & SOG (In Front of Lift Shaft) - AP#14 | 3 | 2025-06-25 | 2025-06-28
R7S1-ONSG-AP14-376 | Block Work below Corridor area - AP#14 | 1 | 2025-07-02 | 2025-07-03
R7S1-ONSG-AP14-382 | Backfilling upto Pipe Level - AP#14 | 1 | 2025-07-03 | 2025-07-05
R7S1-ONSG-AP14-390 | Plaster Work for Blockwork - AP#14 | 1 | 2025-07-03 | 2025-07-05
R7S1-ONSG-AP14-377 | UG MEP Works (Laying of Pipes) - AP#14 | 2 | 2025-07-03 | 2025-07-06
R7S1-ONSG-AP14-378 | Backfilling Works after Pipe Laying - AP#14 | 1 | 2025-07-06 | 2025-07-07
R7S1-ONSG-AP14-379 | Antitermite Works - AP#14 | 1 | 2025-07-06 | 2025-07-07
R7S1-ONSG-AP14-380 | Polythene & Rebar Mesh Works - AP#14 | 2 | 2025-07-07 | 2025-07-09
R7S1-ONSG-AP14-381 | Pouring SOG Concrete - AP#14 | 1 | 2025-07-09 | 2025-07-10
RIGHT SIDE |  | 6 | 2025-07-05 | 2025-07-13
R7S1-ONSG-AP14-383 | Block Work below Corridor area - AP#14 | 2 | 2025-07-05 | 2025-07-07
R7S1-ONSG-AP14-389 | Backfilling upto Pipe Level - AP#14 | 1 | 2025-07-07 | 2025-07-08
R7S1-ONSG-AP14-384 | UG MEP Works (Laying of Pipes) - AP#14 | 1 | 2025-07-08 | 2025-07-09
R7S1-ONSG-AP14-385 | Backfilling Works after Pipe Laying - AP#14 | 1 | 2025-07-09 | 2025-07-10
R7S1-ONSG-AP14-386 | Antitermite Works - AP#14 | 1 | 2025-07-09 | 2025-07-10
R7S1-ONSG-AP14-387 | Polythene & Rebar Mesh Works - AP#14 | 1 | 2025-07-10 | 2025-07-12
R7S1-ONSG-AP14-388 | Pouring SOG Concrete - AP#14 | 1 | 2025-07-12 | 2025-07-13
ERECTION WORKS |  | 65 | 2025-06-23 | 2025-09-14
GROUND FLOOR |  | 24 | 2025-06-23 | 2025-07-16
R7S1ONER-AP14GF442 | Erection of Columns/Beams Frame & Slab/Loose Elements (In Front of Lift Shaft) - AP#14 | 2 | 2025-06-23 | 2025-06-24
R7S1ONER-AP14GF205 | Erection of GF Boxes (Left Side) including Lift Box & Staircase - AP#14 - Large Studio | 2 | 2025-06-30 | 2025-07-02
R7S1ONER-AP14GF206 | Erection of GF Boxes (Right Side) - AP#14 - Large Studio | 2 | 2025-07-02 | 2025-07-05
R7S1ONER-AP14GF207 | Erection of GF MEP Modular Cages (Left Side) - AP#14 | 2 | 2025-07-10 | 2025-07-13
R7S1ONER-AP14GF208 | Erection of GF Corridor Slabs (Left Side) - AP#14 | 2 | 2025-07-12 | 2025-07-14
R7S1ONER-AP14GF209 | Erection of GF MEP Modular Cages (Right Side) - AP#14 | 2 | 2025-07-13 | 2025-07-15
R7S1ONER-AP14GF210 | Erection of GF Corridor Slabs Right Side) - AP#14 | 2 | 2025-07-14 | 2025-07-16
FIRST FLOOR |  | 15 | 2025-06-25 | 2025-08-03
R7S1ONER-AP14FF452 | Erection of Columns/Beams Frame & Slab/Loose Elements (In Front of Lift Shaft) - AP#14 | 2 | 2025-06-25 | 2025-06-26
R7S1ONER-AP14FF205 | Erection of FF Boxes (Left Side) - AP#14 - Large Studio | 2 | 2025-07-27 | 2025-07-28
R7S1ONER-AP14FF206 | Erection of FF Boxes (Right Side) - AP#14 - Large Studio | 2 | 2025-07-28 | 2025-07-29
R7S1ONER-AP14FF207 | Erection of FF MEP Modular Cages (Left Side) - AP#14 | 2 | 2025-07-28 | 2025-07-30
R7S1ONER-AP14FF209 | Erection of FF MEP Modular Cages (Right Side) - AP#14 | 2 | 2025-07-30 | 2025-07-31
R7S1ONER-AP14FF208 | Erection of FF Corridor Slabs (Left Side) - AP#14 | 2 | 2025-07-30 | 2025-08-02
R7S1ONER-AP14FF210 | Erection of FF Corridor Slabs Right Side) - AP#14 | 2 | 2025-08-02 | 2025-08-03
SECOND FLOOR |  | 14 | 2025-06-28 | 2025-09-03
R7S1ONER-AP14SF462 | Erection of Columns/Beams Frame & Slab/Loose Elements (In Front of Lift Shaft) - AP#14 | 2 | 2025-06-28 | 2025-06-29
R7S1ONER-AP14SF205 | Erection of SF Boxes (Left Side) - AP#14 - Large Studio | 2 | 2025-08-24 | 2025-08-25
R7S1ONER-AP14SF206 | Erection of SF Boxes (Right Side) - AP#14 - Large Studio | 1 | 2025-08-26 | 2025-08-27
R7S1ONER-AP14SF207 | Erection of SF MEP Modular Cages (Left Side) - AP#14 | 3 | 2025-08-26 | 2025-08-28
R7S1ONER-AP14SF208 | Erection of SF Corridor Slabs (Left Side) - AP#14 | 2 | 2025-08-30 | 2025-08-31
R7S1ONER-AP14SF209 | Erection of SF MEP Modular Cages (Right Side) - AP#14 | 2 | 2025-08-31 | 2025-09-01
R7S1ONER-AP14SF210 | Erection of SF Corridor Slabs Right Side) - AP#14 | 2 | 2025-09-02 | 2025-09-03
ROOF |  | 9 | 2025-09-04 | 2025-09-14
R7S1ONER-AP14RF110 | Erection of Loose Roof Parapets, Shaft Covers, MEP Foundation etc. - AP#14 Roof | 9 | 2025-09-04 | 2025-09-14
MEP WORKS & FINISHES |  | 167 | 2025-06-29 | 2025-12-02
GROUND FLOOR |  | 165 | 2025-06-29 | 2025-11-09
ARCH./ CIVIL WORKS |  | 143 | 2025-06-29 | 2025-11-09
CORRIDOR AREA |  | 98 | 2025-07-21 | 2025-11-09
R7S1ONAR-AP14GF304 | Flooring in Corridor - AP#14 (GF Corridor) | 6 | 2025-07-21 | 2025-07-28
R7S1ONAR-AP14GF305 | Corridor Skirting - AP#14 (GF Corridor) | 2 | 2025-07-27 | 2025-07-29
R7S1ONAR-AP14GF302 | False Ceiling - 1st Fix - AP#14 (GF - Corridor) | 4 | 2025-07-29 | 2025-08-03
R7S1ONAR-AP14GF303 | Gypsum Wall Cladding - 1st Fix (Shafts) - AP#14 (GF Corridor) | 6 | 2025-10-13 | 2025-10-19
R7S1ONAR-AP14GF306 | Gypsum Wall Cladding (Shafts) -2nd Fix - AP#14 (GF Corridor) | 4 | 2025-10-20 | 2025-10-23
R7S1ONAR-AP14GF310 | Fixing Architrave - AP#14 (GF Corridor) | 2 | 2025-10-25 | 2025-10-26
R7S1ONAR-AP14GF311 | Fixing Aluminium Doors - AP#14 (GF Corridor) | 2 | 2025-10-27 | 2025-10-28
R7S1ONAR-AP14GF307 | False Ceiling - 2nd Fix (Closing the Ceiling) - AP#14 (GF Corridor) | 2 | 2025-10-29 | 2025-10-30
R7S1ONAR-AP14GF308 | Painting - Surface Prep., Primer & 1st Coat - AP#14 (GF Corridor) | 8 | 2025-10-25 | 2025-11-02
R7S1ONAR-AP14GF326 | Painting - Surface Prep., Primer & 1st Coat for Ceiling - AP#14 (GF Corridor) | 4 | 2025-11-01 | 2025-11-04
R7S1ONAR-AP14GF309 | Painting - Final Coat (Ceiling + Walls) - AP#14 (GF Corridor) | 3 | 2025-11-06 | 2025-11-09
INSIDE BOXES |  | 12 | 2025-07-28 | 2025-08-11
R7S1ONAR-AP14GF312 | Fixing Thresholds (Joining the Room) - AP#14 (GF - inside Boxes) | 4 | 2025-07-28 | 2025-08-02
R7S1ONAR-AP14GF313 | Fixing Wooden Doors - AP#14 (GF - inside Boxes) | 4 | 2025-08-02 | 2025-08-06
R7S1ONAR-AP14GF314 | Fixing Aluminium Doors - AP#14 (GF - inside Boxes) | 4 | 2025-08-06 | 2025-08-11
IN FRONT OF LIFT SHAFT |  | 90 | 2025-06-29 | 2025-09-10
R7S1ONAR-AP14GF316 | Flooring - AP#14 (GF - Front of Lift Shaft) | 4 | 2025-06-29 | 2025-07-02
R7S1ONAR-AP14GF317 | Skirting & Thresholds - AP#14 (GF - Front of Lift Shaft) | 1 | 2025-07-02 | 2025-07-02
R7S1ONAR-AP14GF318 | Painting - Surface Prep., Primer & 1st Coat - AP#14 (GF - Front of Lift Shaft) | 4 | 2025-07-03 | 2025-07-07
R7S1ONAR-AP14GF315 | False Ceiling - 1st Fix - AP#14 (GF - Front of Lift Shaft) | 4 | 2025-07-08 | 2025-07-12
R7S1ONAR-AP14GF319 | False Ceiling - Final Fix - AP#14 (GF - Front of Lift Shaft) | 3 | 2025-07-13 | 2025-07-15
R7S1ONAR-AP14GF321 | Fixing Handrail - AP#14 (GF - Front of Lift Shaft) | 3 | 2025-07-16 | 2025-07-19
R7S1ONAR-AP14GF322 | Paint for Handrail - AP#14 (GF - Front of Lift Shaft) | 3 | 2025-07-20 | 2025-07-22
R7S1ONAR-AP14GF320 | Painting - Final Coat - AP#14 (GF - Front of Lift Shaft) | 2 | 2025-09-03 | 2025-09-06
R7S1ONAR-AP14GF324 | Fixing Wall Guard - AP#14 (GF - Front of Lift Shaft) | 2 | 2025-09-06 | 2025-09-08
R7S1ONAR-AP14GF323 | Fixing Floor Mat - AP#14 (GF - Front of Lift Shaft) | 2 | 2025-09-08 | 2025-09-10
GARBAGE ROOM |  | 2 | 2025-09-21 | 2025-09-22
R7S1ONAR-AP14GF325 | Paint Finishes and Touchups - Final Coat - AP#14 (GF - Garbage Room) | 2 | 2025-09-21 | 2025-09-22
MEP WORKS |  | 106 | 2025-07-16 | 2025-11-05
MECHANICAL |  | 101 | 2025-07-16 | 2025-11-03
CHILLED WATER |  | 71 | 2025-07-16 | 2025-10-14
R7S1ONME-AP14GF853 | Installation of Chilled water hanger and supports - AP#14 (GF - Corridor) | 4 | 2025-07-16 | 2025-07-21
R7S1ONME-AP14GF905 | Installation of CHWP connection for FCU with Valve package in Corridor, Electrical Room & ICT Room - AP#14 (GF) | 4 | 2025-07-16 | 2025-07-21
R7S1ONME-AP14GF855 | Installation of BTU Meter with valves - AP#14 (GF - Corridor) | 2 | 2025-07-22 | 2025-07-24
R7S1ONME-AP14GF854 | Installation of CHWP piping (connection between modular cages & modular to apartment) - AP#14 (GF - Corridor) | 4 | 2025-07-21 | 2025-07-26
R7S1ONME-AP14GF856 | CHWP piping risers connections - AP#14 (GF - Corridor) | 3 | 2025-07-28 | 2025-07-31
R7S1ONME-AP14GF857 | Pressure Testing of CHWP piping - AP#14 (GF - Corridor) | 1 | 2025-07-31 | 2025-08-02
R7S1ONME-AP14GF893 | CHWP Insulation - AP#14 (GF - Corridor) | 4 | 2025-08-02 | 2025-08-06
R7S1ONME-AP14GF1436 | CHWP Installation/Connections and Insulation (In Front of Lift Shaft) - AP#14 | 4 | 2025-10-11 | 2025-10-14
HVAC DUCTING |  | 97 | 2025-07-16 | 2025-11-02
R7S1ONME-AP14GF904 | Installation of FCU's & Duct Connection in Corridor, Electrical Room & ICT Room - AP#14 (GF) | 4 | 2025-07-16 | 2025-07-21
R7S1ONME-AP14GF906 | Installation of Ducting and insulation (connection between modular cages) - AP#14 (GF - Corridor) | 3 | 2025-07-21 | 2025-07-24
R7S1ONME-AP14GF858 | Duct Riser Continuation - AP#14 (GF - Corridor) | 4 | 2025-07-28 | 2025-08-02
R7S1ONME-AP14GF859 | A/C drain & Copper pipe connection in ELV room - AP#14 (GF) | 2 | 2025-08-02 | 2025-08-04
R7S1ONME-AP14GF894 | Installation of Duct & Grill in Garbage Room - AP#14 (GF - Garbage Room) | 2 | 2025-08-04 | 2025-08-06
R7S1ONME-AP14GF907 | Installation of Grilles in the Corridor - AP#14 (GF - Corridor) | 2 | 2025-11-01 | 2025-11-02
FIRE FIGHTING |  | 87 | 2025-07-28 | 2025-11-03
R7S1ONME-AP14GF860 | Riser Continuity in corridor - AP#14 (GF - Corridor) | 4 | 2025-07-28 | 2025-08-02
R7S1ONME-AP14GF861 | Continuitu of FF pipes & ZC Valves (connection between modular cages & modular to apartment) - AP#14 (GF - Corridor) | 4 | 2025-07-28 | 2025-08-02
R7S1ONME-AP14GF862 | Installation of Sprinklers drops in corridor - AP#14 (GF - Corridor) | 4 | 2025-08-03 | 2025-08-07
R7S1ONME-AP14GF863 | Pressure Test for FF Piping in corridor - AP#14 (GF - Corridor) | 4 | 2025-08-07 | 2025-08-12
R7S1ONME-AP14GF895 | Installation of Pipe & sprinkler in Garbage Room - AP#14 (GF - Garbage Room) | 1 | 2025-09-02 | 2025-09-02
R7S1ONME-AP14GF908 | FF Flushing network - AP#14 (GF - Corridor) | 1 | 2025-09-16 | 2025-09-16
R7S1ONME-AP14GF1646 | Installation of F.F Pipes, Testing & Final Fixtures (In Front of Lift Shaft) - AP14 | 3 | 2025-10-12 | 2025-10-14
R7S1ONME-AP14GF864 | Installation of Sprinklers in corridor - AP#14 (GF - Corridor) | 3 | 2025-11-01 | 2025-11-03
R7S1ONME-AP14GF865 | Installation of Alarm check valve, Fire Extinguishers & Blanket - AP#14 (GF - Corridor) | 3 | 2025-11-01 | 2025-11-03
WATER SUPPLY |  | 72 | 2025-07-16 | 2025-09-24
R7S1ONME-AP14GF896 | Installation of WS Pipe in Garbage Room - AP#14 (GF - Garbage Room) | 2 | 2025-07-16 | 2025-07-19
R7S1ONME-AP14GF897 | Installation of Sanitary Fixtures in Janitor Room - AP#14 (GF - Janitor Room) | 2 | 2025-07-16 | 2025-07-19
R7S1ONME-AP14GF867 | WS High Level Pipe continuation & Insulation works - AP#14 (GF - Corridor) | 4 | 2025-07-16 | 2025-07-21
R7S1ONME-AP14GF868 | Installation of Cold, Hot water line & Hot water return - AP#14 (GF - Corridor) | 4 | 2025-07-21 | 2025-07-26
R7S1ONME-AP14GF869 | Water Meter Installation - AP#14 (GF - Corridor) | 4 | 2025-07-26 | 2025-07-30
R7S1ONME-AP14GF866 | Riser Continuity in Shafts - AP#14 (GF - Corridor) | 4 | 2025-07-28 | 2025-08-02
R7S1ONME-AP14GF870 | Pressure Test for WS - AP#14 (GF - Corridor) | 4 | 2025-09-15 | 2025-09-18
R7S1ONME-AP14GF909 | Insulation for Hot water line & Hot water return - AP#14 (GF - Corridor) | 4 | 2025-09-20 | 2025-09-24
DRAINAGE |  | 63 | 2025-07-16 | 2025-09-18
R7S1ONME-AP14GF872 | Installation of Clean-outs, Floor drain in balcony - AP#14 (GF - Corridor) | 4 | 2025-07-16 | 2025-07-21
R7S1ONME-AP14GF873 | Rain Water Riser continuation in Shafts - AP#14 (GF - Corridor) | 4 | 2025-07-28 | 2025-08-02
R7S1ONME-AP14GF874 | Drainage Riser continuation in Shafts - AP#14 (GF - Corridor) | 4 | 2025-07-28 | 2025-08-02
R7S1ONME-AP14GF875 | Testing for Rain Water Riser - AP#14 (GF - Corridor) | 4 | 2025-09-15 | 2025-09-18
R7S1ONME-AP14GF876 | Testing for Drainage Riser1 - AP#14 (GF - Corridor) | 4 | 2025-09-15 | 2025-09-18
ELECTRICAL |  | 104 | 2025-07-16 | 2025-11-05
POWER & LIGHTING |  | 103 | 2025-07-16 | 2025-11-05
R7S1ONME-AP14GF877 | Contiuation of Cable Trays & apartment branches - AP#14 (GF - Corridor) | 4 | 2025-07-16 | 2025-07-21
R7S1ONME-AP14GF878 | Contiuation of Cable Trunking with Flexible conduits for Lights - AP#14 (GF - Corridor) | 4 | 2025-07-16 | 2025-07-21
R7S1ONME-AP14GF879 | Installation of EMT pipes - AP#14 (GF - Corridor) | 5 | 2025-07-16 | 2025-07-22
R7S1ONME-AP14GF880 | Installation of Busbar, Electrical Meter & Tap-off - AP#14 (GF - Corridor) | 3 | 2025-07-21 | 2025-07-24
R7S1ONME-AP14GF903 | Termination of Tap-off with Electrical Meter in the apartments - AP#14 (GF - Corridor) | 3 | 2025-07-24 | 2025-07-28
R7S1ONME-AP14GF881 | Corridor Wire Pulling - AP#14 (GF - Corridor) | 6 | 2025-07-22 | 2025-07-29
R7S1ONME-AP14GF882 | Electrical Room - Installation of Cable trays, SMDB & Termination - AP#14 (GF - Corridor) | 6 | 2025-08-27 | 2025-09-03
R7S1ONME-AP14GF1856 | Continuation of Cable Tray/Trunking with Flexible conduits for Lights (In Front of Lift Shaft) - AP#14 | 4 | 2025-10-11 | 2025-10-14
R7S1ONME-AP14GF884 | Installation, Termination of Emergeny & Exit Lights with contiuity - AP#14 (GF - Corridor) | 2 | 2025-11-01 | 2025-11-02
R7S1ONME-AP14GF883 | Installation, Termination of Light Fixtures with continuity test - AP#14 (GF - Corridor & Balconies) | 3 | 2025-11-01 | 2025-11-03
R7S1ONME-AP14GF885 | Installation, Termination of PIR sensors with continuity test - AP#14 (GF - Corridor) | 2 | 2025-11-04 | 2025-11-05
LOW CURRENT SYSTEM |  | 104 | 2025-07-16 | 2025-11-04
R7S1ONME-AP14GF910 | CBS System cable installation - AP#14 (GF - Corridor) | 3 | 2025-07-16 | 2025-07-20
R7S1ONME-AP14GF886 | Installation of Basket trays for BMS, CCTV, Access Control - AP#14 (GF - Corridor) | 4 | 2025-07-16 | 2025-07-21
R7S1ONME-AP14GF888 | Fire alarm cable installation - AP#14 (GF - Corridor) | 3 | 2025-07-17 | 2025-07-21
R7S1ONME-AP14GF887 | Voice Evacuation cable installation - AP#14 (GF - Corridor) | 3 | 2025-07-20 | 2025-07-23
R7S1ONME-AP14GF889 | Fibre optic Cable pulling & Termination with OTO (in corridors to ONU) - AP#14 (GF - Corridor) | 2 | 2025-09-27 | 2025-09-28
R7S1ONME-AP14GF890 | BMS, CCTV & Access control Cable installation - AP#14 (GF - Corridor) | 2 | 2025-09-27 | 2025-09-28
R7S1ONME-AP14GF891 | Low Current Works including BMS Panel in ICT Room - AP#14 (GF - Corridor) | 10 | 2025-09-21 | 2025-10-02
R7S1ONME-AP14GF902 | Fluke test for CCTV & Fibre Optic Cable - AP#14 (GF - Corridor) (Ceiling 1st Fix) | 2 | 2025-10-01 | 2025-10-02
R7S1ONME-AP14GF899 | Installation & Termination of Access control system for Electrical Room - AP#14 (GF) | 2 | 2025-10-02 | 2025-10-04
R7S1ONME-AP14GF2066 | Installation of Basket trays for Low Current, Cable Installation (In Front of Lift Shaft) - AP#14 | 4 | 2025-10-11 | 2025-10-14
R7S1ONME-AP14GF898 | Installation & Termination of CCTV Cameras - AP#14 (GF - Corridor) | 2 | 2025-11-01 | 2025-11-02
R7S1ONME-AP14GF901 | Installation & Termination of Wireless Gateway & RF Node in corridors - AP#14 (GF - Corridor) | 2 | 2025-11-01 | 2025-11-02
R7S1ONME-AP14GF892 | Installation & Termination of Fire alarm devices & Speakers - AP#14 (GF - Corridor) | 4 | 2025-11-01 | 2025-11-04
R7S1ONME-AP14GF900 | Installation & Termination of Active Components & UPS installation in ICT Room - AP#14 (GF - Corridor) | 2 | 2025-11-03 | 2025-11-04
FIRST FLOOR |  | 137 | 2025-07-28 | 2025-11-27
ARCH./ CIVIL WORKS |  | 137 | 2025-07-28 | 2025-11-27
CORRIDOR AREA |  | 84 | 2025-07-28 | 2025-11-27
R7S1ONAR-AP14FF420 | Flooring in Corridor - AP#14 (FF - Corridor) | 6 | 2025-07-28 | 2025-08-04
R7S1ONAR-AP14FF421 | Corridor Skirting - AP#14 (FF - Corridor) | 2 | 2025-08-03 | 2025-08-05
R7S1ONAR-AP14FF418 | False Ceiling - 1st Fix - AP#14 (FF - Corridor) | 4 | 2025-08-05 | 2025-08-10
R7S1ONAR-AP14FF419 | Gypsum Wall Cladding (Shafts) - AP#14 (FF - Corridor) | 6 | 2025-10-06 | 2025-10-12
R7S1ONAR-AP14FF422 | Gypsum Wall Cladding (Shafts) -2nd Fix - AP#14 (FF Corridor) | 4 | 2025-10-13 | 2025-10-16
R7S1ONAR-AP14FF426 | Fixing Architrave - AP#14 (FF Corridor) | 2 | 2025-10-18 | 2025-10-19
R7S1ONAR-AP14FF427 | Fixing Aluminium Doors - AP#14 (FF Corridor) | 2 | 2025-10-20 | 2025-10-21
R7S1ONAR-AP14FF423 | False Ceiling - 2nd Fix (Closing the Ceiling) - AP#14 (FF Corridor) | 3 | 2025-10-22 | 2025-10-25
R7S1ONAR-AP14FF424 | Painting - Surface Prep., Primer & 1st Coat for Walls - AP#14 (FF Corridor) | 8 | 2025-10-18 | 2025-10-26
R7S1ONAR-AP14FF447 | Painting - Surface Prep., Primer & 1st Coat for Ceiling - AP#14 (FF Corridor) | 4 | 2025-10-26 | 2025-10-29
R7S1ONAR-AP14FF425 | Painting - Final Coat (Ceiling + Walls) - AP#14 (FF Corridor) | 3 | 2025-11-25 | 2025-11-27
INSIDE BOXES |  | 12 | 2025-09-04 | 2025-09-17
R7S1ONAR-AP14FF428 | Fixing Thresholds (Joining the Room) - AP#14 (FF - inside Boxes) | 4 | 2025-09-04 | 2025-09-08
R7S1ONAR-AP14FF429 | Fixing Wooden Doors - AP#14 (FF - inside Boxes) | 4 | 2025-09-09 | 2025-09-13
R7S1ONAR-AP14FF430 | Fixing Aluminium Doors (Next Floor) - AP#14 (FF - inside Boxes) | 4 | 2025-09-14 | 2025-09-17
IN FRONT OF LIFT SHAFT |  | 74 | 2025-10-27 | 2025-11-24
R7S1ONAR-AP14FF432 | Flooring - AP#14 (FF - Front of Lift Shaft) | 4 | 2025-10-27 | 2025-10-30
R7S1ONAR-AP14FF433 | Skirting & Thresholds - AP#14 (FF - Front of Lift Shaft) | 1 | 2025-10-30 | 2025-10-30
R7S1ONAR-AP14FF434 | Painting - Surface Prep., Primer & 1st Coat - AP#14 (FF - Front of Lift Shaft) | 4 | 2025-11-01 | 2025-11-04
R7S1ONAR-AP14FF431 | False Ceiling - 1st Fix - AP#14 (FF - Front of Lift Shaft) | 4 | 2025-11-05 | 2025-11-09
R7S1ONAR-AP14FF435 | False Ceiling - Final Fix - AP#14 (FF - Front of Lift Shaft) | 3 | 2025-11-10 | 2025-11-12
R7S1ONAR-AP14FF437 | Fixing Handrail - AP#14 (FF - Front of Lift Shaft) | 3 | 2025-11-13 | 2025-11-16
R7S1ONAR-AP14FF438 | Paint for Handrail - AP#14 (FF - Front of Lift Shaft) | 3 | 2025-11-17 | 2025-11-19
R7S1ONAR-AP14FF436 | Painting - 2nd Coat - AP#14 (FF - Front of Lift Shaft) | 2 | 2025-11-20 | 2025-11-22
R7S1ONAR-AP14FF439 | Fixing Floor Mat - AP#14 (FF - Front of Lift Shaft) | 2 | 2025-11-23 | 2025-11-24
R7S1ONAR-AP14FF440 | Fixing Wall Guard - AP#14 (FF - Front of Lift Shaft) | 2 | 2025-11-23 | 2025-11-24
GARBAGE ROOM |  | 16 | 2025-09-09 | 2025-09-20
R7S1ONAR-AP14FF441 | Installation of Dry Walls - First Fix - AP#14 (FF - Garbage Room) | 2 | 2025-09-09 | 2025-09-10
R7S1ONAR-AP14FF442 | Installation of Dry Walls - Final Fix - AP#14 (FF - Garbage Room) | 2 | 2025-09-10 | 2025-09-11
R7S1ONAR-AP14FF443 | Garbage Rooms - Wall Tile Finishes (One Side) - AP#14 (FF - Garbage Room) | 2 | 2025-09-11 | 2025-09-13
R7S1ONAR-AP14FF444 | Paint Works of Dry Walls - First Coat - AP#14 (FF - Garbage Room) | 2 | 2025-09-14 | 2025-09-15
R7S1ONAR-AP14FF445 | Installation of the Garbage Chute Door - AP#14 (FF - Garbage Room) | 2 | 2025-09-16 | 2025-09-17
R7S1ONAR-AP14FF446 | Paint Finishes and Touchups - Final Coat - AP#14 (FF - Garbage Room) | 2 | 2025-09-18 | 2025-09-20
MEP WORKS |  | 71 | 2025-08-04 | 2025-11-08
MECHANICAL |  | 70 | 2025-08-04 | 2025-11-06
CHILLED WATER |  | 45 | 2025-08-04 | 2025-10-19
R7S1ONME-AP14FF590 | Installation of Chilled water hanger and supports - AP#14 (FF Corridor) | 4 | 2025-08-04 | 2025-08-07
R7S1ONME-AP14FF640 | Installation of CHWP connection for FCU with Valve package in Corridor, Electrical Room & ICT Room | 4 | 2025-08-04 | 2025-08-07
R7S1ONME-AP14FF592 | Installation of BTU Meter with valves - AP#14 (FF Corridor) | 2 | 2025-08-10 | 2025-08-11
R7S1ONME-AP14FF591 | Installation of CHWP piping (connection between modular cages & modular to apartment) - AP#14 -(FF Corridor) | 4 | 2025-08-09 | 2025-08-12
R7S1ONME-AP14FF593 | CHWP piping risers connections - AP#14 (FF Corridor) | 3 | 2025-08-26 | 2025-08-28
R7S1ONME-AP14FF594 | Pressure Testing of CHWP piping - AP#14 (FF Corridor) | 1 | 2025-08-30 | 2025-08-30
R7S1ONME-AP14FF629 | CHWP Insulation - AP#14 (FF Corridor) | 4 | 2025-08-31 | 2025-09-03
R7S1ONME-AP14FF1446 | CHWP Installation/Connections and Insulation (In Front of Lift Shaft) - AP#14 | 4 | 2025-10-15 | 2025-10-19
HVAC DUCTING |  | 68 | 2025-08-04 | 2025-10-27
R7S1ONME-AP14FF641 | Installation of FCU's & Duct Connection in Corridor, Electrical Room & ICT Room - AP#14 (FF Corridor) | 4 | 2025-08-04 | 2025-08-07
R7S1ONME-AP14FF595 | Duct Riser Continuation - AP#14 (FF Corridor) | 4 | 2025-08-26 | 2025-08-30
R7S1ONME-AP14FF596 | A/C drain & Copper pipe connection in ELV room - AP#14 (FF Corridor) | 2 | 2025-08-31 | 2025-09-01
R7S1ONME-AP14FF642 | Installation of Ducting and insulation (connection between modular cages) - AP#14 (FF Corridor) | 3 | 2025-08-31 | 2025-09-02
R7S1ONME-AP14FF630 | Installation of Duct & Grill in Garbage Room - AP#14 (FF Corridor) | 2 | 2025-09-02 | 2025-09-03
R7S1ONME-AP14FF643 | Installation of Grilles in the Corridor - AP#14 (FF Corridor) | 2 | 2025-10-26 | 2025-10-27
FIRE FIGHTING |  | 58 | 2025-08-26 | 2025-11-06
R7S1ONME-AP14FF597 | Riser Continuity in corridor - AP#14 (FF Corridor) | 4 | 2025-08-26 | 2025-08-30
R7S1ONME-AP14FF598 | Continuation of FF pipes & ZC Valves (connection between modular cages & modular to apartment) - AP#14 (FF Corridor) | 4 | 2025-08-26 | 2025-08-30
R7S1ONME-AP14FF631 | Installation of Pipe & sprinkler in Garbage Room - AP#14 (FF Corridor) | 1 | 2025-09-02 | 2025-09-02
R7S1ONME-AP14FF599 | Installation of Sprinklers drops in corridor - AP#14 (FF Corridor) | 4 | 2025-08-31 | 2025-09-03
R7S1ONME-AP14FF600 | Pressure Test for FF Piping in corridor - AP#14 (FF Corridor) | 2 | 2025-09-04 | 2025-09-06
R7S1ONME-AP14FF644 | FF Flushing network - AP#14 (FF Corridor) | 2 | 2025-09-16 | 2025-09-17
R7S1ONME-AP14FF1656 | Installation of F.F Pipes, Testing & Final Fixtures (In Front of Lift Shaft) - AP14 | 3 | 2025-10-20 | 2025-10-22
R7S1ONME-AP14FF601 | Installation of Sprinklers in corridor - AP#14 (FF Corridor) | 4 | 2025-10-26 | 2025-10-29
R7S1ONME-AP14FF602 | Installation of Alarm check valve, Fire Extinguishers & Blanket (Last Stage of the Building) - AP#14 (FF Corridor) | 3 | 2025-11-04 | 2025-11-06
WATER SUPPLY |  | 39 | 2025-08-04 | 2025-09-29
R7S1ONME-AP14FF632 | Installation of WS Pipe in Garbage Room - AP#14 (FF Corridor) | 2 | 2025-08-04 | 2025-08-05
R7S1ONME-AP14FF633 | Installation of Sanitary Fixtures in Janitor Room - AP#14 (FF Corridor) | 2 | 2025-08-04 | 2025-08-05
R7S1ONME-AP14FF604 | WS High Level Pipe continuation & Insulation works in Corridor - AP#14 (FF Corridor) | 4 | 2025-08-04 | 2025-08-07
R7S1ONME-AP14FF605 | Installation of Cold, Hot water line & Hot water return in corridor - AP#14 (FF Corridor) | 4 | 2025-08-09 | 2025-08-12
R7S1ONME-AP14FF606 | Water Meter Installation in Corridor - AP#14 (FF Corridor) | 4 | 2025-08-13 | 2025-08-17
R7S1ONME-AP14FF603 | Riser Continuity in Shafts - AP#14 (FF Corridor) | 4 | 2025-08-26 | 2025-08-30
R7S1ONME-AP14FF607 | Pressure Test for WS - AP#14 (FF Corridor) | 4 | 2025-09-15 | 2025-09-18
R7S1ONME-AP14FF645 | Insulation for Hot water line & Hot water return in corridor - AP#14 (FF Corridor) | 4 | 2025-09-25 | 2025-09-29
DRAINAGE |  | 22 | 2025-08-04 | 2025-09-18
R7S1ONME-AP14FF608 | Installation of Clean-outs, Floor drain in balcony - AP#14 (FF Corridor) | 4 | 2025-08-04 | 2025-08-07
R7S1ONME-AP14FF609 | Rain Water Riser continuation in Shafts - AP#14 (FF Corridor) | 4 | 2025-08-26 | 2025-08-30
R7S1ONME-AP14FF610 | Drainage Riser continuation in Shafts - AP#14 (FF Corridor) | 4 | 2025-08-26 | 2025-08-30
R7S1ONME-AP14FF611 | Testing for Rain Water Riser - AP#14 (FF Corridor) | 4 | 2025-09-15 | 2025-09-18
R7S1ONME-AP14FF612 | Testing for Drainage Riser - AP#14 (FF Corridor) | 4 | 2025-09-15 | 2025-09-18
ELECTRICAL |  | 65 | 2025-08-04 | 2025-11-08
POWER & LIGHTING |  | 65 | 2025-08-04 | 2025-11-08
R7S1ONME-AP14FF613 | Contiuation of Cable Trays & apartment branches - AP#14 (FF Corridor) | 4 | 2025-08-04 | 2025-08-07
R7S1ONME-AP14FF614 | Contiuation of Cable Trunking with Flexible conduits for Lights - AP#14 (FF Corridor) | 4 | 2025-08-04 | 2025-08-07
R7S1ONME-AP14FF615 | Installation of EMT pipes - AP#14 (FF Corridor) | 5 | 2025-08-04 | 2025-08-09
R7S1ONME-AP14FF616 | Installation of Busbar, Electrical Meter & Tap-off - AP#14 (FF Corridor) | 3 | 2025-08-09 | 2025-08-11
R7S1ONME-AP14FF639 | Termination of Tap-off with Electrical Meter in the apartments - AP#14 (FF Corridor) | 3 | 2025-08-12 | 2025-08-14
R7S1ONME-AP14FF617 | Corridor Wire Pulling - AP#14 (FF Corridor) | 6 | 2025-08-10 | 2025-08-16
R7S1ONME-AP14FF618 | Electrical Room - Installation of Cable trays, SMDB & Termination - AP#14 (FF Corridor) | 6 | 2025-08-17 | 2025-08-23
R7S1ONME-AP14FF620 | Installation, Termination of Emergeny & Exit Lights with contiuity - AP#14 (FF Corridor) | 2 | 2025-10-26 | 2025-10-27
R7S1ONME-AP14FF1866 | Continuation of Cable Tray/Trunking with Flexible conduits for Lights (In Front of Lift Shaft) - AP#14 | 4 | 2025-10-23 | 2025-10-27
R7S1ONME-AP14FF619 | Installation, Termination of Light Fixtures with continuity test - AP#14 (FF - Corridor & Balconies) | 3 | 2025-10-26 | 2025-10-28
R7S1ONME-AP14FF621 | Installation, Termination of PIR sensors with continuity test - AP#14 (FF Corridor) | 2 | 2025-11-06 | 2025-11-08
LOW CURRENT SYSTEM |  | 64 | 2025-08-04 | 2025-11-01
R7S1ONME-AP14FF646 | CBS System cable installation - AP#14 (FF Corridor) | 3 | 2025-08-04 | 2025-08-06
R7S1ONME-AP14FF622 | Installation of Basket trays for BMS, CCTV, Access Control - AP#14 (FF Corridor) | 4 | 2025-08-04 | 2025-08-07
R7S1ONME-AP14FF624 | Fire alarm cable installation - AP#14 (FF Corridor) | 3 | 2025-08-05 | 2025-08-07
R7S1ONME-AP14FF623 | Voice Evacuation cable installation - AP#14 (FF Corridor) | 3 | 2025-08-07 | 2025-08-10
R7S1ONME-AP14FF625 | Fibre optic Cable pulling & Termination with OTO (in corridors to ONU) - AP#14 (FF Corridor) | 2 | 2025-09-29 | 2025-09-30
R7S1ONME-AP14FF626 | BMS, CCTV & Access control Cable installation - AP#14 (FF Corridor) | 2 | 2025-09-29 | 2025-09-30
R7S1ONME-AP14FF627 | Low Current Works including BMS Panel in ICT Room - AP#14 (FF Corridor) | 10 | 2025-09-24 | 2025-10-05
R7S1ONME-AP14FF638 | Fluke test for CCTV & Fibre Optic Cable - AP#14 (FF Corridor) | 2 | 2025-10-04 | 2025-10-05
R7S1ONME-AP14FF634 | Installation & Termination of CCTV Cameras - AP#14 (FF Corridor) | 2 | 2025-10-26 | 2025-10-27
R7S1ONME-AP14FF635 | Installation & Termination of Access control system for Electrical Room - AP#14 (FF Corridor) | 2 | 2025-10-26 | 2025-10-27
R7S1ONME-AP14FF637 | Installation & Termination of Wireless Gateway & RF Node - AP#14 (FF Corridor) | 2 | 2025-10-26 | 2025-10-27
R7S1ONME-AP14FF628 | Installation & Termination of Fire alarm devices & Speakers - AP#14 (FF Corridor) | 4 | 2025-10-26 | 2025-10-29
R7S1ONME-AP14FF636 | Installation & Termination of Active Components & UPS installation in ICT Room | 2 | 2025-10-28 | 2025-10-29
R7S1ONME-AP14FF2076 | Installation of Basket trays for Low Current, Cable Installation (In Front of Lift Shaft) - AP#14 | 4 | 2025-10-28 | 2025-11-01
SECOND FLOOR |  | 116 | 2025-08-04 | 2025-12-02
ARCH./ CIVIL WORKS |  | 111 | 2025-08-04 | 2025-12-02
CORRIDOR AREA |  | 68 | 2025-08-04 | 2025-12-02
R7S1ONAR-AP14SF322 | Flooring in Corridor - AP#14 (SF Corridor) | 6 | 2025-08-04 | 2025-08-11
R7S1ONAR-AP14SF323 | Corridor Skirting - AP#14 (SF Corridor) | 2 | 2025-08-10 | 2025-08-12
R7S1ONAR-AP14SF320 | False Ceiling - 1st Fix - AP#14 (SF Corridor) | 4 | 2025-08-12 | 2025-08-17
R7S1ONAR-AP14SF321 | Gypsum Wall Cladding (Shafts) - AP#14 (SF Corridor) | 6 | 2025-10-27 | 2025-11-02
R7S1ONAR-AP14SF324 | Gypsum Wall Cladding (Shafts) -2nd Fix - AP#14 (SF Corridor) | 4 | 2025-11-03 | 2025-11-06
R7S1ONAR-AP14SF328 | Fixing Architrave - AP#14 (SF Corridor) | 2 | 2025-11-08 | 2025-11-09
R7S1ONAR-AP14SF329 | Fixing Aluminium Doors - AP#14 (SF Corridor) | 2 | 2025-11-10 | 2025-11-11
R7S1ONAR-AP14SF325 | False Ceiling - 2nd Fix (Closing the Ceiling) - AP#14 (SF Corridor) | 3 | 2025-11-12 | 2025-11-15
R7S1ONAR-AP14SF326 | Painting - Surface Prep., Primer & 1st Coat - AP#14 (SF Corridor) | 8 | 2025-11-08 | 2025-11-16
R7S1ONAR-AP14SF350 | Painting - Surface Prep., Primer & 1st Coat - AP#14 (SF Corridor) | 4 | 2025-11-16 | 2025-11-19
R7S1ONAR-AP14SF327 | Painting - Final Coat (Ceiling + Walls) - AP#14 (SF Corridor) | 3 | 2025-11-30 | 2025-12-02
INSIDE BOXES |  | 12 | 2025-09-04 | 2025-09-17
R7S1ONAR-AP14SF330 | Fixing Thresholds (Joining the Room) - AP#14 (SF - inside Boxes) | 4 | 2025-09-04 | 2025-09-08
R7S1ONAR-AP14SF331 | Fixing Wooden Doors - AP#14 (SF - inside Boxes) | 4 | 2025-09-09 | 2025-09-13
R7S1ONAR-AP14SF332 | Fixing Aluminium Doors (Next Floor) - AP#14 (SF - inside Boxes) | 4 | 2025-09-14 | 2025-09-17
IN FRONT OF LIFT SHAFT |  | 56 | 2025-11-12 | 2025-12-02
R7S1ONAR-AP14SF334 | Flooring - AP#14 (SF - Front of Lift Shaft) | 4 | 2025-11-12 | 2025-11-16
R7S1ONAR-AP14SF335 | Skirting & Thresholds - AP#14 (SF - Front of Lift Shaft) | 2 | 2025-11-17 | 2025-11-18
R7S1ONAR-AP14SF336 | Painting - Surface Prep., Primer & 1st Coat - AP#14 (SF - Front of Lift Shaft) | 4 | 2025-11-19 | 2025-11-23
R7S1ONAR-AP14SF333 | False Ceiling - 1st Fix - AP#14 (SF - Front of Lift Shaft) | 4 | 2025-11-20 | 2025-11-24
R7S1ONAR-AP14SF337 | False Ceiling - Final Fix - AP#14 (SF - Front of Lift Shaft) | 3 | 2025-11-25 | 2025-11-27
R7S1ONAR-AP14SF339 | Fixing Handrail - AP#14 (SF - Front of Lift Shaft) | 3 | 2025-11-25 | 2025-11-27
R7S1ONAR-AP14SF340 | Paint for Handrail - AP#14 (SF - Front of Lift Shaft) | 2 | 2025-11-29 | 2025-11-30
R7S1ONAR-AP14SF338 | Painting - 2nd Coat - AP#14 (SF - Front of Lift Shaft) | 2 | 2025-12-01 | 2025-12-02
R7S1ONAR-AP14SF341 | Fixing Floor Mat - AP#14 (SF - Front of Lift Shaft) | 2 | 2025-12-01 | 2025-12-02
R7S1ONAR-AP14SF342 | Fixing Wall Guard - AP#14 (SF - Front of Lift Shaft) | 2 | 2025-12-01 | 2025-12-02
GARBAGE ROOM |  | 44 | 2025-08-23 | 2025-11-19
R7S1ONAR-AP14SF349 | Installation of Garbage Chute Full System from GF to 2nd Floor - AP#14 (SF - Garbage Room) | 10 | 2025-08-23 | 2025-09-02
R7S1ONAR-AP14SF343 | Installation of Dry Walls - First Fix - AP#14 (SF - Garbage Room) | 2 | 2025-09-03 | 2025-09-04
R7S1ONAR-AP14SF344 | Installation of Dry Walls - Final Fix - AP#14 (SF - Garbage Room) | 2 | 2025-09-06 | 2025-09-07
R7S1ONAR-AP14SF345 | Garbage Rooms - Wall Tile Finishes (One Side) - AP#14 (SF - Garbage Room) | 2 | 2025-09-07 | 2025-09-08
R7S1ONAR-AP14SF346 | Paint Works of Dry Walls - First Coat - AP#14 (SF - Garbage Room) | 2 | 2025-09-09 | 2025-09-10
R7S1ONAR-AP14SF347 | Installation of the Garbage Chute Door - AP#14 (SF - Garbage Room) | 2 | 2025-09-11 | 2025-09-13
R7S1ONAR-AP14SF348 | Paint Finishes and Touchups - Final Coat - AP#14 (SF - Garbage Room) | 2 | 2025-11-18 | 2025-11-19
MEP WORKS |  | 72 | 2025-09-04 | 2025-11-20
MECHANICAL |  | 72 | 2025-09-04 | 2025-11-19
CHILLED WATER |  | 35 | 2025-09-04 | 2025-10-23
R7S1ONME-AP14SF551 | Installation of Chilled water hanger and supports - AP#14 (SF Corridor) | 4 | 2025-09-04 | 2025-09-08
R7S1ONME-AP14SF601 | Installation of CHWP connection for FCU with Valve package in Corridor, Electrical Room & ICT Room | 4 | 2025-09-04 | 2025-09-08
R7S1ONME-AP14SF553 | Installation of BTU Meter with valves - AP#14 (SF Corridor) | 2 | 2025-09-10 | 2025-09-11
R7S1ONME-AP14SF552 | Installation of CHWP piping (connection between modular cages & modular to apartment) - AP#14 (SF Corridor) | 4 | 2025-09-09 | 2025-09-13
R7S1ONME-AP14SF554 | CHWP piping risers connections - AP#14 (SF Corridor) | 3 | 2025-09-13 | 2025-09-15
R7S1ONME-AP14SF555 | Pressure Testing of CHWP piping - AP#14 (SF Corridor) | 1 | 2025-09-16 | 2025-09-16
R7S1ONME-AP14SF590 | CHWP Insulation - AP#14 (SF Corridor) | 4 | 2025-09-17 | 2025-09-21
R7S1ONME-AP14SF1456 | CHWP Installation/Connections and Insulation (In Front of Lift Shaft) - AP#14 | 4 | 2025-10-20 | 2025-10-23
HVAC DUCTING |  | 68 | 2025-09-04 | 2025-11-17
R7S1ONME-AP14SF556 | Duct Riser Continuation - AP#14 (SF Corridor) | 4 | 2025-09-04 | 2025-09-08
R7S1ONME-AP14SF602 | Installation of FCU's & Duct Connection in Corridor, Electrical Room & ICT Room - AP#14 (SF Corridor) | 4 | 2025-09-04 | 2025-09-08
R7S1ONME-AP14SF557 | A/C drain & Copper pipe connection in ELV room - AP#14 (SF Corridor) | 2 | 2025-09-09 | 2025-09-10
R7S1ONME-AP14SF603 | Installation of Ducting and insulation (connection between modular cages) - AP#14 (SF Corridor) | 3 | 2025-09-09 | 2025-09-11
R7S1ONME-AP14SF591 | Installation of Duct & Grill in Garbage Room - AP#14 (SF Corridor) | 2 | 2025-11-16 | 2025-11-17
R7S1ONME-AP14SF604 | Installation of Grilles in the Corridor - AP#14 (SF Corridor) | 2 | 2025-11-16 | 2025-11-17
FIRE FIGHTING |  | 67 | 2025-09-04 | 2025-11-19
R7S1ONME-AP14SF558 | Riser Continuity Succ - Closing of Gysum Boards on shaft - AP#14 (SF Corridor) | 4 | 2025-09-04 | 2025-09-08
R7S1ONME-AP14SF559 | FF Contiuation on High Level with Valves - AP#14 (SF Corridor) | 4 | 2025-09-04 | 2025-09-08
R7S1ONME-AP14SF560 | Installation of Sprinklers drops - AP#14 (SF Corridor) | 4 | 2025-09-09 | 2025-09-13
R7S1ONME-AP14SF561 | Pressure Test for FF Piping - AP#14 (SF Corridor) | 2 | 2025-09-14 | 2025-09-15
R7S1ONME-AP14SF1666 | Installation of F.F Pipes, Testing & Final Fixtures (In Front of Lift Shaft) - AP14 | 3 | 2025-10-25 | 2025-10-27
R7S1ONME-AP14SF592 | Installation of Pipe & sprinkler in Garbage Room - AP#14 (SF Corridor) | 2 | 2025-11-16 | 2025-11-17
R7S1ONME-AP14SF562 | Installation of Sprinklers - AP#14 (SF Corridor) | 4 | 2025-11-16 | 2025-11-19
R7S1ONME-AP14SF563 | Installation of Fire Extinguishers - AP#14 (SF Corridor) | 4 | 2025-11-16 | 2025-11-19
WATER SUPPLY |  | 25 | 2025-09-04 | 2025-10-04
R7S1ONME-AP14SF593 | Installation of WS Pipe in Garbage Room - AP#14 (SF Corridor) | 2 | 2025-09-04 | 2025-09-06
R7S1ONME-AP14SF594 | Installation of Sanitary Fixtures in Janitor Room - AP#14 (SF Corridor) | 2 | 2025-09-04 | 2025-09-06
R7S1ONME-AP14SF564 | Riser Continuity - AP#14 (SF Corridor) | 4 | 2025-09-04 | 2025-09-08
R7S1ONME-AP14SF565 | WS High Level Pipe continuation & Insulation works - AP#14 (SF Corridor) | 4 | 2025-09-04 | 2025-09-08
R7S1ONME-AP14SF566 | Instalation of Hot water line in corridor - AP#14 (SF Corridor) | 4 | 2025-09-09 | 2025-09-13
R7S1ONME-AP14SF567 | Water Meter Installation - AP#14 (SF Corridor) | 4 | 2025-09-11 | 2025-09-15
R7S1ONME-AP14SF568 | Pressure Test for WS - AP#14 (SF Corridor) | 4 | 2025-09-20 | 2025-09-24
R7S1ONME-AP14FF647 | Insulation for Hot water line & Hot water return in corridor - AP#14 (SF Corridor) | 4 | 2025-09-30 | 2025-10-04
DRAINAGE |  | 22 | 2025-09-04 | 2025-09-18
R7S1ONME-AP14SF569 | Installation of Clean-outs - AP#14 (SF Corridor) | 4 | 2025-09-04 | 2025-09-08
R7S1ONME-AP14SF570 | Rain Water Riser continuation - AP#14 (SF Corridor) | 4 | 2025-09-04 | 2025-09-08
R7S1ONME-AP14SF571 | Drainage Riser continuation - AP#14 (SF Corridor) | 4 | 2025-09-04 | 2025-09-08
R7S1ONME-AP14SF572 | Testing for Rain Water Riser - AP#14 (SF Corridor) | 4 | 2025-09-15 | 2025-09-18
R7S1ONME-AP14SF573 | Testing for Drainage Riser - AP#14 (SF Corridor) | 4 | 2025-09-15 | 2025-09-18
ELECTRICAL |  | 58 | 2025-09-04 | 2025-11-20
POWER & LIGHTING |  | 58 | 2025-09-04 | 2025-11-20
R7S1ONME-AP14SF574 | Contiuation of Cable Trays & apartment branches - AP#14 (SF Corridor) | 4 | 2025-09-04 | 2025-09-08
R7S1ONME-AP14SF575 | Contiuation of Cable Trunking with Flexible conduits for Lights - AP#14 (SF Corridor) | 4 | 2025-09-04 | 2025-09-08
R7S1ONME-AP14SF576 | Installation of EMT pipes - AP#14 (SF Corridor) | 5 | 2025-09-04 | 2025-09-09
R7S1ONME-AP14SF577 | Installation of Busbar, Electrical Meter & Tap-off in Corridor - AP#14 (SF Corridor) | 3 | 2025-09-09 | 2025-09-11
R7S1ONME-AP14SF600 | Termination of Tap-off with Electrical Meter in the apartments - AP#14 (SF Corridor) | 3 | 2025-09-13 | 2025-09-15
R7S1ONME-AP14SF578 | Corridor Wire Pulling - AP#14 (SF Corridor) | 6 | 2025-09-10 | 2025-09-16
R7S1ONME-AP14SF1876 | Continuation of Cable Tray/Trunking with Flexible conduits for Lights (In Front of Lift Shaft) - AP#14 | 4 | 2025-10-28 | 2025-11-01
R7S1ONME-AP14SF579 | Electrical Room - Installation of Cable trays, SMDB & Termination - AP#14 (SF Corridor) | 6 | 2025-10-28 | 2025-11-03
R7S1ONME-AP14SF581 | Installation, Termination of Emergeny & Exit Lights with contiuity - AP#14 (SF Corridor) | 2 | 2025-11-16 | 2025-11-17
R7S1ONME-AP14SF580 | Installation, Termination of Light Fixtures with continuity test - AP#14 (SF - Corridor & Balconies) | 3 | 2025-11-16 | 2025-11-18
R7S1ONME-AP14SF582 | Installation, Termination of PIR sensors with continuity test - AP#14 (SF Corridor) | 2 | 2025-11-19 | 2025-11-20
LOW CURRENT SYSTEM |  | 57 | 2025-09-04 | 2025-11-19
R7S1ONME-AP14SF605 | CBS System cable installation - AP#14 (SF Corridor) | 3 | 2025-09-04 | 2025-09-07
R7S1ONME-AP14SF583 | Installation of Basket trays for BMS, CCTV, Access Control - AP#14 (SF Corridor) | 4 | 2025-09-04 | 2025-09-08
R7S1ONME-AP14SF585 | Fire alarm cable installation - AP#14 (SF Corridor) | 3 | 2025-09-06 | 2025-09-08
R7S1ONME-AP14SF584 | Voice Evacuation cable installation - AP#14 (SF Corridor) | 3 | 2025-09-08 | 2025-09-10
R7S1ONME-AP14SF586 | Fibre optic Cable pulling & Termination with OTO (in corridors to ONU) - AP#14 (SF Corridor) | 2 | 2025-10-01 | 2025-10-02
R7S1ONME-AP14SF587 | BMS, CCTV & Access control Cable installation - AP#14 (SF Corridor) | 2 | 2025-10-01 | 2025-10-02
R7S1ONME-AP14SF2086 | Installation of Basket trays for Low Current, Cable Installation (In Front of Lift Shaft) - AP#14 | 4 | 2025-10-28 | 2025-11-01
R7S1ONME-AP14SF588 | Low Current Works including BMS Panel in ICT Room - AP#14 (SF Corridor) | 10 | 2025-10-22 | 2025-11-02
R7S1ONME-AP14SF599 | Fluke test for CCTV & Fibre Optic Cable - AP#14 (SF Corridor) | 2 | 2025-11-01 | 2025-11-02
R7S1ONME-AP14SF595 | Installation & Termination of CCTV Cameras - AP#14 (SF Corridor) | 2 | 2025-11-16 | 2025-11-17
R7S1ONME-AP14SF596 | Installation & Termination of Access control system for Electrical Room - AP#14 (SF Corridor) | 2 | 2025-11-16 | 2025-11-17
R7S1ONME-AP14SF598 | Installation & Termination of Wireless Gateway & RF Node in corridors - AP#14 (SF Corridor) | 2 | 2025-11-16 | 2025-11-17
R7S1ONME-AP14SF589 | Installation & Termination of Fire alarm devices & Speakers - AP#14 (SF Corridor) | 4 | 2025-11-16 | 2025-11-19
R7S1ONME-AP14SF597 | Installation & Termination of Active Components & UPS installation in ICT Room - AP#14 (SF Corridor) | 2 | 2025-11-18 | 2025-11-19
ROOF WORKS |  | 78 | 2025-09-15 | 2025-11-17
ARCH./ CIVIL WORKS |  | 78 | 2025-09-15 | 2025-11-17
R7S1ONAR-AP14RF83 | Roof Box Stiching (Concrete Works) - AP#14 (Roof) | 6 | 2025-09-15 | 2025-09-21
R7S1ONME-AP14RF521 | Installation of Roof Drains - AP#14 (Roof) | 2 | 2025-09-21 | 2025-09-22
R7S1ONAR-AP14RF84 | Roof Waterproofing Works with testing - AP#14 (Roof) | 20 | 2025-09-28 | 2025-10-20
R7S1ONAR-AP14RF85 | Laying of Gravel - AP#14 (Roof) | 2 | 2025-10-20 | 2025-10-21
R7S1ONAR-AP14RF86 | Surface Preparation & Primer for Parapets - AP#14 (Roof) | 6 | 2025-10-22 | 2025-10-28
R7S1ONAR-AP14RF87 | 1st Coat Paint for Parapets - AP#14 (Roof) | 2 | 2025-10-29 | 2025-10-30
R7S1ONAR-AP14RF88 | 2nd Coat Paint for Parapets - AP#14 (Roof) | 2 | 2025-11-01 | 2025-11-02
R7S1ONAR-AP14RF90 | Fixing Fall Arrest System - AP#14 (Roof) | 2 | 2025-11-05 | 2025-11-06
R7S1ONAR-AP14RF89 | Crossover Bridges Installation & application of Sealant on MEP penetrations - AP#14 (Roof) | 9 | 2025-11-08 | 2025-11-17
MECHANICAL |  | 45 | 2025-10-22 | 2025-11-13
HVAC |  | 27 | 2025-10-22 | 2025-11-06
R7S1ONME-AP14RF485 | Modular Installation - AP#14 (Roof) | 5 | 2025-10-22 | 2025-10-27
R7S1ONME-AP14RF486 | Continuation of Roof duct works/FAHU Connections - AP#14 (Roof) | 5 | 2025-10-25 | 2025-10-29
R7S1ONME-AP14RF488 | Insulations for ducts - AP#14 (Roof) | 5 | 2025-10-26 | 2025-10-30
R7S1ONME-AP14RF490 | Installation of FAHU - AP#14 (Roof) | 2 | 2025-10-30 | 2025-11-01
R7S1ONME-AP14RF495 | Installation of Outdoor VRF/DX Units - AP#14 (Roof) | 2 | 2025-11-01 | 2025-11-02
R7S1ONME-AP14RF496 | Installation & Insulation of the Condensation Drain - AP#14 (Roof) | 1 | 2025-11-02 | 2025-11-02
R7S1ONME-AP14RF498 | Installation of Ventilation Fans - AP#14 (Roof) | 3 | 2025-10-30 | 2025-11-02
R7S1ONME-AP14RF493 | Chilled Water System Continuation and Connections with Valve package of FAHU - AP#14 (Roof) | 4 | 2025-10-30 | 2025-11-03
R7S1ONME-AP14RF500 | Installation of Louvers - AP#14 (Roof) | 2 | 2025-11-03 | 2025-11-04
R7S1ONME-AP14RF503 | Installation & Testing of Copper Pipes - AP#14 (Roof) | 2 | 2025-11-03 | 2025-11-04
R7S1ONME-AP14RF504 | Miscellaneous Works for Mechanical Connections (Fire & Volume Dampers etc.) - AP#14 (Roof) | 2 | 2025-11-05 | 2025-11-06
WATERSUPPLY & DRAINAGE |  | 26 | 2025-10-28 | 2025-11-12
R7S1ONME-AP14RF484 | Testing for the Rain Water Risers - AP#14 (Roof) | 2 | 2025-10-30 | 2025-11-01
R7S1ONME-AP14RF487 | Installation & Continuation of Water supply pipes (connection between modular cages & modular to Shaft Riser) - AP#14 | 4 | 2025-10-28 | 2025-11-01
R7S1ONME-AP14RF491 | Installation of Air Vent & Pressure Guage with Valves at Roof - AP#14 (Roof) | 4 | 2025-10-30 | 2025-11-03
R7S1ONME-AP14RF492 | Vertical Continuation of Vent Pipes To The Roof (Drainage) - AP#14 (Roof) | 4 | 2025-11-01 | 2025-11-04
R7S1ONME-AP14RF494 | Installation of Rain Water outlet - AP#14 (Roof) | 3 | 2025-11-02 | 2025-11-04
R7S1ONME-AP14RF489 | Installation of Air Vent with Valve for Water Supply - AP#14 (Roof) | 4 | 2025-11-02 | 2025-11-05
R7S1ONME-AP14RF497 | Testing of Water Supply Pipes - AP#14 (Roof) | 2 | 2025-11-06 | 2025-11-08
R7S1ONME-AP14RF499 | Insulation of Roof Water Line - AP#14 (Roof) | 2 | 2025-11-08 | 2025-11-09
R7S1ONME-AP14RF501 | Testing for the Drainage Pipes Risers - AP#14 (Roof) | 2 | 2025-11-10 | 2025-11-11
R7S1ONME-AP14RF502 | Installation of Vent Cowl - AP#14 (Roof) | 1 | 2025-11-12 | 2025-11-12
SOLAR HEATER |  | 36 | 2025-11-02 | 2025-11-13
R7S1ONME-AP14RF516 | Installation of Solar water pumps and circulation pumps with valves(For Water Only) - AP#14 (Roof) | 2 | 2025-11-03 | 2025-11-04
R7S1ONME-AP14RF514 | Installation of Structure and Solar Panels (For Water Only) - AP#14 (Roof) | 5 | 2025-11-02 | 2025-11-06
R7S1ONME-AP14RF515 | Installation of Solar Calorifier Tank & Air cooler (For Water Only) - AP#14 (Roof) | 5 | 2025-11-03 | 2025-11-08
R7S1ONME-AP14RF517 | Installation of Solar Pipes Primary Loop - AP#14 (Roof) | 5 | 2025-11-03 | 2025-11-08
R7S1ONME-AP14RF518 | Testing of Solar Pipes Primary Loop - AP#14 (Roof) | 1 | 2025-11-09 | 2025-11-09
R7S1ONME-AP14RF519 | Insulation of Solar Pipes Primary Loop - AP#14 (Roof) | 1 | 2025-11-09 | 2025-11-09
R7S1ONME-AP14RF520 | Aluminum Cladding of Solar Pipes Primary Loop - AP#14 (Roof) | 4 | 2025-11-10 | 2025-11-13
ELECTRICAL |  | 26 | 2025-10-26 | 2025-11-17
POWER & LOW CURRENT |  | 26 | 2025-10-26 | 2025-11-17
R7S1ONME-AP14RF505 | Installation of Cables for Fire Alarm system - AP#14 (Roof) | 3 | 2025-10-28 | 2025-10-30
R7S1ONME-AP14RF506 | Installation of Cables for BMS - AP#14 (Roof) | 3 | 2025-10-28 | 2025-10-30
R7S1ONME-AP14RF507 | Installation of Fire Alarm Devices - AP#14 (Roof) | 3 | 2025-10-28 | 2025-10-30
R7S1ONME-AP14RF509 | Installation of Roof Light Fixtures - AP#14 (Roof) | 3 | 2025-10-28 | 2025-10-30
R7S1ONME-AP14RF480 | Installation of Isolators and Machine Connections - AP#14 (Roof) | 4 | 2025-10-28 | 2025-11-01
R7S1ONME-AP14RF479 | Lightening Protection & Earthing System - AP#14 (Roof) | 7 | 2025-10-26 | 2025-11-02
R7S1ONME-AP14RF508 | Installation of BMS Devices - AP#14 (Roof) | 4 | 2025-10-29 | 2025-11-02
R7S1ONME-AP14RF481 | Installation of Electrical Containments for BMS - AP#14 (Roof) | 7 | 2025-10-28 | 2025-11-04
R7S1ONME-AP14RF511 | Termination for BMS System - AP#14 (Roof) | 1 | 2025-11-05 | 2025-11-05
R7S1ONME-AP14RF523 | Termination of Primary & Secondary pump for Solar system - AP#14 (Roof) | 1 | 2025-11-05 | 2025-11-05
R7S1ONME-AP14RF482 | Installation of Fire Alarm Containment for FAHU, Fans - AP#14 (Roof) | 4 | 2025-11-03 | 2025-11-06
R7S1ONME-AP14RF512 | Termination for Fire Alarm Device - AP#14 (Roof) | 1 | 2025-11-08 | 2025-11-08
R7S1ONME-AP14RF483 | Installation of LV Power Cables for Roof Equipment - AP#14 (Roof) | 5 | 2025-11-08 | 2025-11-12
R7S1ONME-AP14RF510 | Termination for LV Cables - AP#14 (Roof) | 1 | 2025-11-13 | 2025-11-13
R7S1ONME-AP14RF513 | Megger Test for the Power Cables - AP#14 (Roof) | 1 | 2025-11-15 | 2025-11-15
R7S1ONME-AP14RF522 | Installation & Termination of Solar System Panel - AP#14 (Roof) | 3 | 2025-11-15 | 2025-11-17
STAIR CASE |  | 103 | 2025-09-15 | 2025-11-12
CIVIL WORKS |  | 72 | 2025-09-22 | 2025-11-08
STAIR CASE (MAIN WITH LIFT) |  | 66 | 2025-09-22 | 2025-10-20
R7S1ONST-AP14RG491 | Stair Flooring (Roof to GF) - AP#14 (Main Stair) | 7 | 2025-09-22 | 2025-09-30
R7S1ONST-AP14RG492 | Stair Hand Rails (Roof to GF) - AP#14 (Main Stair) | 6 | 2025-10-01 | 2025-10-07
R7S1ONST-AP14RG493 | Stair Paint - Primer & 1st Coat (Roof to GF)- AP#14 (Main Stair) | 7 | 2025-10-08 | 2025-10-15
R7S1ONST-AP14RG494 | Stair Paint - Final Coat (Roof to GF)- AP#14 (Main Stair) | 4 | 2025-10-16 | 2025-10-20
STAIR CASE (LEFT SIDE) |  | 44 | 2025-10-01 | 2025-10-26
R7S1ONST-AP14RG501 | Stair Flooring (Roof to GF) - AP#14 Left Side Stair | 7 | 2025-10-01 | 2025-10-08
R7S1ONST-AP14RG502 | Stair Hand Rails (Roof to GF) - AP#14 Left Side Stair | 6 | 2025-10-09 | 2025-10-15
R7S1ONST-AP14RG503 | Stair Paint - Primer & 1st Coat (Roof to GF) - AP#14 Left Side Stair | 6 | 2025-10-16 | 2025-10-22
R7S1ONST-AP14RG504 | Stair Paint - Final Coat (Roof to GF) - AP#14 Left Side Stair | 3 | 2025-10-23 | 2025-10-26
STAIR CASE (RIGHT SIDE) |  | 41 | 2025-10-09 | 2025-11-08
R7S1ONST-AP14RG505 | Stair Flooring (Roof to GF) - AP#14 Right Side Stair | 8 | 2025-10-09 | 2025-10-18
R7S1ONST-AP14RG506 | Stair Hand Rails (Roof to GF) - AP#14 Right Side Stair | 7 | 2025-10-19 | 2025-10-26
R7S1ONST-AP14RG507 | Stair Paint - Primer & 1st Coat (Roof to GF) - AP#14 Right Side Stair | 7 | 2025-10-27 | 2025-11-03
R7S1ONST-AP14RG508 | Stair Paint - Final Coat (Roof to GF) - AP#14 Right Side Stair | 4 | 2025-11-04 | 2025-11-08
MEP WORKS |  | 80 | 2025-09-15 | 2025-11-12
STAIR CASE (MAIN WITH LIFT) |  | 58 | 2025-09-15 | 2025-10-25
R7S1ONST-AP14RG490 | Main Staircase Wire Pulling - AP#14 (Main Stair) | 3 | 2025-09-15 | 2025-09-17
R7S1ONST-AP14RG509 | Final fix - Main Staircase Lights Fixtures & Motion Sensor - AP#14 (Main Stair) | 2 | 2025-10-21 | 2025-10-22
R7S1ONST-AP14RG510 | Final fix - Main Staircase Emergency Lights Fixtures - AP#14 (Main Stair) | 2 | 2025-10-23 | 2025-10-25
STAIR CASE (LEFT SIDE) |  | 66 | 2025-09-18 | 2025-10-30
R7S1ONST-AP14RG495 | Left Staircase Wire Pulling - AP#14 (Main Stair) | 3 | 2025-09-18 | 2025-09-21
R7S1ONST-AP14RG497 | Final fix - Left Staircase Lights Fixtures & Motion Sensor - AP#14 (Main Stair) | 2 | 2025-10-27 | 2025-10-28
R7S1ONST-AP14RG499 | Final fix - Left Staircase Emergency Lights Fixtures - AP#14 (Main Stair) | 2 | 2025-10-29 | 2025-10-30
STAIR CASE (RIGHT SIDE) |  | 74 | 2025-09-22 | 2025-11-12
R7S1ONST-AP14RG496 | Right Staircase Wire Pulling - AP#14 (Main Stair) | 3 | 2025-09-22 | 2025-09-25
R7S1ONST-AP14RG498 | Final fix - Right Staircase Lights Fixtures & Motion Sensor - AP#14 (Main Stair) | 2 | 2025-11-09 | 2025-11-10
R7S1ONST-AP14RG500 | Final fix - Right Staircase Emergency Lights Fixtures - AP#14 (Main Stair) | 2 | 2025-11-11 | 2025-11-12
ELEVATOR WORKS |  | 22 | 2025-09-22 | 2025-10-18
R7S1ONEL-AP14GR655 | Installation of Rails - AP#14 (Elevator Works) | 6 | 2025-09-22 | 2025-09-29
R7S1ONEL-AP14GR656 | Assembly of Cabin - AP#14 (Elevator Works) | 4 | 2025-09-30 | 2025-10-04
R7S1ONEL-AP14GR657 | Installation of Motor - AP#14 (Elevator Works) | 4 | 2025-10-05 | 2025-10-08
R7S1ONEL-AP14GR658 | Installation of Main Cables - AP#14 (Elevator Works) | 4 | 2025-10-09 | 2025-10-13
R7S1ONEL-AP14GR659 | Installation of Doors, Indicator, Push Button - AP#14 (Elevator Works) | 2 | 2025-10-14 | 2025-10-15
R7S1ONEL-AP14GR660 | Interior Finishes - AP#14 (Elevator Works) | 2 | 2025-10-16 | 2025-10-18
EXTERNAL ELEVATIONS |  | 86 | 2025-10-05 | 2025-11-02
ARCH./ CIVIL WORKS |  | 86 | 2025-10-05 | 2025-11-02
R7S1ONEE-AP14GR537 | External Selant Works - For Boxes - AP#14 (External Elevations) | 15 | 2025-10-05 | 2025-10-21
R7S1ONEE-AP14GR538 | Final Finishes & Touchups - AP#14 (External Elevations) | 15 | 2025-10-09 | 2025-10-26
R7S1ONME-AP14GF871 | Installation of rain water outlet - External façade - AP#14 (External Elevations) | 2 | 2025-10-27 | 2025-10-28
R7S1ONEE-AP14GR539 | Fixing Cage Ladder - AP#14 (External Elevations) | 2 | 2025-11-01 | 2025-11-02
R7S1ONEE-AP14GR540 | Installation of External Signages - AP#14 (External Elevations) | 4 | 2025-10-29 | 2025-11-02
EXTERNAL - CIVIL WORKS |  | 217 | 2025-02-23 | 2025-11-12
DRAINAGE |  | 8 | 2025-10-18 | 2025-10-26
R7S1ONECW-AP14-433 | Excavation Works & Sand Bedding - AP#14 (External Drainage) | 3 | 2025-10-18 | 2025-10-20
R7S1ONECW-AP14-434 | Drainage Manholes - AP#14 | 6 | 2025-10-18 | 2025-10-23
R7S1ONECW-AP14-435 | Drainage Backfilling - AP#14 | 2 | 2025-10-25 | 2025-10-26
WATERSUPPLY |  | 217 | 2025-02-23 | 2025-11-12
R7S1ONECW-AP14-436 | Excavation Works & Sand Bedding - Watersupply - AP#14 (External Watersupply Civil) | 197 | 2025-02-23 | 2025-10-21
R7S1ONECW-AP14-437 | Watersupply Manholes - AP#14 | 6 | 2025-10-21 | 2025-10-28
R7S1ONECW-AP14-438 | Watersupply Backfilling - AP#14 | 2 | 2025-11-10 | 2025-11-12
CHILLED WATER |  | 9 | 2025-10-21 | 2025-11-03
R7S1ONECW-AP14-442 | Excavation Works & Sand Bedding - AP#14 (External Chilled Water Civil) | 3 | 2025-10-21 | 2025-10-25
R7S1ONECW-AP14-443 | Chilled Water Manholes - AP#14 | 6 | 2025-10-25 | 2025-11-01
R7S1ONECW-AP14-444 | Chilled Water Backfilling - AP#14 | 2 | 2025-11-01 | 2025-11-03
FIRE FIGHTING |  | 209 | 2025-02-23 | 2025-11-03
R7S1ONECW-AP14-439 | Excavation Works & Sand Bedding - AP#14 (External Chilled Water Civil) | 200 | 2025-02-23 | 2025-10-25
R7S1ONECW-AP14-440 | Fire Fighting Manholes - AP#14 | 6 | 2025-10-25 | 2025-11-01
R7S1ONECW-AP14-441 | Fire Fighting Backfilling - AP#14 | 2 | 2025-11-01 | 2025-11-03
POWER |  | 13 | 2025-10-25 | 2025-11-03
R7S1ONECW-AP14-445 | Excavation Works & Sand Bedding - AP#14 (External Power Civil) | 3 | 2025-10-25 | 2025-10-28
R7S1ONECW-AP14-446 | Power Manholes - AP#14 | 3 | 2025-10-28 | 2025-11-01
R7S1ONECW-AP14-447 | Power Backfilling - AP#14 | 2 | 2025-11-01 | 2025-11-03
LOW CURRENT |  | 18 | 2025-10-25 | 2025-11-03
R7S1ONECW-AP14-448 | Excavation Works & Sand Bedding - AP#14 (External Low Current Civil) | 3 | 2025-10-25 | 2025-10-28
R7S1ONECW-AP14-449 | Low Current Manholes - AP#14 | 3 | 2025-10-28 | 2025-11-01
R7S1ONECW-AP14-450 | Low Current Backfilling - AP#14 | 2 | 2025-11-01 | 2025-11-03
EXTERNAL - MEP SERVICES |  | 208 | 2025-02-24 | 2025-11-12
DRAINAGE |  | 4 | 2025-10-21 | 2025-10-25
R7S1ONEME-AP14-281 | External Drainage Network - AP#14 (External Drainage MEP) | 4 | 2025-10-21 | 2025-10-25
WATERSUPPLY |  | 7 | 2025-10-28 | 2025-11-12
R7S1ONEME-AP14-282 | PRV statiuon assembly including meters- AP#14 (External WS MEP) | 4 | 2025-10-28 | 2025-11-02
R7S1ONEME-AP14-284 | Installation of valve station incl. BTU meter- AP#14 (External WS MEP) | 3 | 2025-11-09 | 2025-11-12
CHILLED WATER |  | 7 | 2025-11-02 | 2025-11-10
R7S1ONEME-AP14-283 | Installation of Chilled water line- AP#14 (External CWP MEP) | 6 | 2025-11-02 | 2025-11-09
R7S1ONEME-AP14-285 | Pressure Test for chilled water line- AP#14 (External CWP MEP) | 1 | 2025-11-09 | 2025-11-10
FIRE FIGHTING |  | 199 | 2025-02-24 | 2025-10-30
R7S1ONEME-AP14-286 | Installation of External FF network - AP#14 (External FF MEP) | 199 | 2025-02-24 | 2025-10-25
R7S1ONEME-AP14-287 | Installation of Alarm check valves- AP#14 (External FF MEP) | 3 | 2025-10-25 | 2025-10-28
R7S1ONEME-AP14-288 | Testing of External FF - AP#14 (External FF MEP) | 2 | 2025-10-28 | 2025-10-30
POWER |  | 1 | 2025-10-28 | 2025-10-29
R7S1ONEME-AP14-289 | Cable pulling from Manhole to the building MDB - AP#14 (External Power MEP) | 1 | 2025-10-28 | 2025-10-29
LOW CURRENT |  | 3 | 2025-10-28 | 2025-11-01
R7S1ONEME-AP14-290 | Low Current Cable pulling- AP#14 (External FF MEP) | 3 | 2025-10-28 | 2025-11-01
BUILDING # AP15 (LARGE STUDIO) |  | 330 | 2024-12-22 | 2025-12-02
SUB-STRUCTURE |  | 109 | 2024-12-22 | 2025-05-03
R7S1-ONSB-AP15-314 | Site Setting Out Works - AP#15 | 4 | 2024-12-22 | 2024-12-25
R7S1-ONSB-AP15-311 | Site levelling & earthworks - AP#15 | 16 | 2024-12-25 | 2025-01-12
R7S1-ONSB-AP15-315 | Anti-termite & Polythene Sheet Works - AP#15 | 1 | 2025-01-13 | 2025-01-13
R7S1-ONSB-AP15-312 | Blinding PCC - AP#15 | 19 | 2025-01-13 | 2025-02-03
R7S1-ONSB-AP15-313 | Waterproofing for Blinding PCC (Bitumen Paint) - AP#15 | 2 | 2025-02-03 | 2025-02-04
R7S1-ONSB-AP15-316 | Foundations/Upstands - Rebar - AP#15 | 24 | 2025-03-16 | 2025-04-16
R7S1-ONSB-AP15-317 | Foundations/Upstands - Shuttering (Including dowel Works) - AP#15 | 24 | 2025-03-17 | 2025-04-17
R7S1-ONSB-AP15-318 | Foundations/Upstands - Casting - AP#15 | 15 | 2025-03-27 | 2025-04-17
R7S1-ONSB-AP15-320 | Installation of MEP U/G services below Boxes - AP#15 | 18 | 2025-03-24 | 2025-04-17
R7S1-ONSB-AP15-321 | Backfilling & Compaction - AP#15 | 5 | 2025-04-26 | 2025-04-30
R7S1-ONSB-AP15-319 | Waterproofing For Foundations/Upstands - AP#15 | 14 | 2025-04-17 | 2025-05-03
SLAB-ON-GRADE & UG MEP WORKS (in Corridor) |  | 27 | 2025-07-02 | 2025-07-17
LEFT SIDE |  | 27 | 2025-07-02 | 2025-07-15
R7S1-ONSG-AP15-380 | Backfilling & SOG (In Front of Lift Shaft) - AP#15 | 3 | 2025-07-02 | 2025-07-05
R7S1-ONSG-AP15-391 | Block Work below Corridor area - AP#15 | 1 | 2025-07-07 | 2025-07-08
R7S1-ONSG-AP15-397 | Backfilling upto Pipe Level - AP#15 | 1 | 2025-07-08 | 2025-07-09
R7S1-ONSG-AP15-405 | Plaster Work for Blockwork - AP#15 | 1 | 2025-07-08 | 2025-07-09
R7S1-ONSG-AP15-392 | UG MEP Works (Laying of Pipes) - AP#15 | 2 | 2025-07-08 | 2025-07-10
R7S1-ONSG-AP15-393 | Backfilling Works after Pipe Laying - AP#15 | 1 | 2025-07-10 | 2025-07-12
R7S1-ONSG-AP15-394 | Antitermite Works - AP#15 | 1 | 2025-07-10 | 2025-07-12
R7S1-ONSG-AP15-395 | Polythene & Rebar Mesh Works - AP#15 | 2 | 2025-07-12 | 2025-07-14
R7S1-ONSG-AP15-396 | Pouring SOG Concrete - AP#15 | 1 | 2025-07-14 | 2025-07-15
RIGHT SIDE |  | 5 | 2025-07-09 | 2025-07-17
R7S1-ONSG-AP15-398 | Block Work below Corridor area - AP#15 | 2 | 2025-07-09 | 2025-07-12
R7S1-ONSG-AP15-404 | Backfilling upto Pipe Level - AP#15 | 1 | 2025-07-12 | 2025-07-13
R7S1-ONSG-AP15-399 | UG MEP Works (Laying of Pipes) - AP#15 | 1 | 2025-07-13 | 2025-07-14
R7S1-ONSG-AP15-400 | Backfilling Works after Pipe Laying - AP#15 | 1 | 2025-07-14 | 2025-07-15
R7S1-ONSG-AP15-401 | Antitermite Works - AP#15 | 1 | 2025-07-14 | 2025-07-15
R7S1-ONSG-AP15-402 | Polythene & Rebar Mesh Works - AP#15 | 1 | 2025-07-15 | 2025-07-16
R7S1-ONSG-AP15-403 | Pouring SOG Concrete - AP#15 | 1 | 2025-07-16 | 2025-07-17
ERECTION WORKS |  | 67 | 2025-06-30 | 2025-09-21
GROUND FLOOR |  | 43 | 2025-06-30 | 2025-07-21
R7S1ONER-AP15GF472 | Erection of Columns/Beams Frame & Slab/Loose Elements (In Front of Lift Shaft) - AP#15 | 2 | 2025-06-30 | 2025-07-01
R7S1ONER-AP15GF211 | Erection of GF Boxes (Left Side) including Lift Box & Staircase - AP#15 - Large Studio | 2 | 2025-07-05 | 2025-07-07
R7S1ONER-AP15GF212 | Erection of GF Boxes (Right Side) - AP#15 - Large Studio | 2 | 2025-07-07 | 2025-07-09
R7S1ONER-AP15GF213 | Erection of GF MEP Modular Cages (Left Side) - AP#15 | 2 | 2025-07-15 | 2025-07-17
R7S1ONER-AP15GF214 | Erection of GF Corridor Slabs (Left Side) - AP#15 | 2 | 2025-07-16 | 2025-07-19
R7S1ONER-AP15GF215 | Erection of GF MEP Modular Cages (Right Side) - AP#15 | 2 | 2025-07-17 | 2025-07-20
R7S1ONER-AP15GF216 | Erection of GF Corridor Slabs Right Side) - AP#15 | 2 | 2025-07-19 | 2025-07-21
FIRST FLOOR |  | 23 | 2025-07-02 | 2025-08-07
R7S1ONER-AP15FF482 | Erection of Columns/Beams Frame & Slab/Loose Elements (In Front of Lift Shaft) - AP#15 | 2 | 2025-07-02 | 2025-07-03
R7S1ONER-AP15FF211 | Erection of FF Boxes (Left Side) - AP#15 - Large Studio | 2 | 2025-07-30 | 2025-07-31
R7S1ONER-AP15FF212 | Erection of FF Boxes (Right Side) - AP#15 - Large Studio | 2 | 2025-08-02 | 2025-08-03
R7S1ONER-AP15FF213 | Erection of FF MEP Modular Cages (Left Side) - AP#15 | 2 | 2025-07-31 | 2025-08-03
R7S1ONER-AP15FF214 | Erection of FF Corridor Slabs (Left Side) - AP#15 | 2 | 2025-08-03 | 2025-08-05
R7S1ONER-AP15FF215 | Erection of FF MEP Modular Cages (Right Side) - AP#15 | 2 | 2025-08-03 | 2025-08-05
R7S1ONER-AP15FF216 | Erection of FF Corridor Slabs Right Side) - AP#15 | 2 | 2025-08-05 | 2025-08-07
SECOND FLOOR |  | 9 | 2025-07-05 | 2025-09-07
R7S1ONER-AP15SF492 | Erection of Columns/Beams Frame & Slab/Loose Elements (In Front of Lift Shaft) - AP#15 | 2 | 2025-07-05 | 2025-07-06
R7S1ONER-AP15SF211 | Erection of SF Boxes (Left Side) - AP#15 - Large Studio | 2 | 2025-08-27 | 2025-08-28
R7S1ONER-AP15SF212 | Erection of SF Boxes (Right Side) - AP#15 - Large Studio | 2 | 2025-08-30 | 2025-08-31
R7S1ONER-AP15SF213 | Erection of SF MEP Modular Cages (Left Side) - AP#15 | 3 | 2025-08-30 | 2025-09-01
R7S1ONER-AP15SF214 | Erection of SF Corridor Slabs (Left Side) - AP#15 | 2 | 2025-09-02 | 2025-09-03
R7S1ONER-AP15SF215 | Erection of SF MEP Modular Cages (Right Side) - AP#15 | 2 | 2025-09-03 | 2025-09-04
R7S1ONER-AP15SF216 | Erection of SF Corridor Slabs Right Side) - AP#15 | 2 | 2025-09-06 | 2025-09-07
ROOF |  | 12 | 2025-09-08 | 2025-09-21
R7S1ONER-AP15RF111 | Erection of Loose Roof Parapets, Shaft Covers, MEP Foundation etc. - AP#15 Roof | 12 | 2025-09-08 | 2025-09-21
MEP WORKS & FINISHES |  | 164 | 2025-07-06 | 2025-12-02
GROUND FLOOR |  | 162 | 2025-07-06 | 2025-11-16
ARCH./ CIVIL WORKS |  | 127 | 2025-07-06 | 2025-11-16
CORRIDOR AREA |  | 82 | 2025-07-21 | 2025-11-16
R7S1ONAR-AP15GF329 | Flooring in Corridor - AP#15 (GF Corridor) | 6 | 2025-07-21 | 2025-07-28
R7S1ONAR-AP15GF330 | Corridor Skirting - AP#15 (GF Corridor) | 2 | 2025-07-27 | 2025-07-29
R7S1ONAR-AP15GF327 | False Ceiling - 1st Fix - AP#15 (GF - Corridor) | 4 | 2025-07-29 | 2025-08-03
R7S1ONAR-AP15GF328 | Gypsum Wall Cladding - 1st Fix (Shafts) - AP#15 (GF Corridor) | 6 | 2025-10-19 | 2025-10-26
R7S1ONAR-AP15GF331 | Gypsum Wall Cladding (Shafts) -2nd Fix - AP#15 (GF Corridor) | 4 | 2025-10-26 | 2025-10-30
R7S1ONAR-AP15GF335 | Fixing Architrave - AP#15 (GF Corridor) | 2 | 2025-10-30 | 2025-11-02
R7S1ONAR-AP15GF336 | Fixing Aluminium Doors - AP#15 (GF Corridor) | 2 | 2025-11-02 | 2025-11-04
R7S1ONAR-AP15GF332 | False Ceiling - 2nd Fix (Closing the Ceiling) - AP#15 (GF Corridor) | 3 | 2025-11-03 | 2025-11-06
R7S1ONAR-AP15GF333 | Painting - Surface Prep., Primer & 1st Coat - AP#15 (GF Corridor) | 8 | 2025-10-30 | 2025-11-09
R7S1ONAR-AP15GF351 | Painting - Surface Prep., Primer & 1st Coat for Ceiling - AP#15 (GF Corridor) | 4 | 2025-11-06 | 2025-11-11
R7S1ONAR-AP15GF334 | Painting - Final Coat (Ceiling + Walls) - AP#15 (GF Corridor) | 3 | 2025-11-12 | 2025-11-16
INSIDE BOXES |  | 12 | 2025-07-31 | 2025-08-14
R7S1ONAR-AP15GF337 | Fixing Thresholds (Joining the Room) - AP#15 (GF - inside Boxes) | 4 | 2025-07-31 | 2025-08-05
R7S1ONAR-AP15GF338 | Fixing Wooden Doors - AP#15 (GF - inside Boxes) | 4 | 2025-08-05 | 2025-08-10
R7S1ONAR-AP15GF339 | Fixing Aluminium Doors - AP#15 (GF - inside Boxes) | 4 | 2025-08-10 | 2025-08-14
IN FRONT OF LIFT SHAFT |  | 92 | 2025-07-06 | 2025-10-09
R7S1ONAR-AP15GF341 | Flooring - AP#15 (GF - Front of Lift Shaft) | 4 | 2025-07-06 | 2025-07-09
R7S1ONAR-AP15GF342 | Skirting & Thresholds - AP#15 (GF - Front of Lift Shaft) | 2 | 2025-07-08 | 2025-07-09
R7S1ONAR-AP15GF343 | Painting - Surface Prep., Primer & 1st Coat - AP#15 (GF - Front of Lift Shaft) | 4 | 2025-07-10 | 2025-07-14
R7S1ONAR-AP15GF340 | False Ceiling - 1st Fix - AP#15 (GF - Front of Lift Shaft) | 4 | 2025-07-15 | 2025-07-19
R7S1ONAR-AP15GF344 | False Ceiling - Final Fix - AP#15 (GF - Front of Lift Shaft) | 3 | 2025-07-20 | 2025-07-22
R7S1ONAR-AP15GF346 | Fixing Handrail - AP#15 (GF - Front of Lift Shaft) | 3 | 2025-07-23 | 2025-07-26
R7S1ONAR-AP15GF347 | Paint for Handrail - AP#15 (GF - Front of Lift Shaft) | 3 | 2025-07-27 | 2025-07-29
R7S1ONAR-AP15GF345 | Painting - Final Coat - AP#15 (GF - Front of Lift Shaft) | 3 | 2025-10-01 | 2025-10-05
R7S1ONAR-AP15GF349 | Fixing Wall Guard - AP#15 (GF - Front of Lift Shaft) | 2 | 2025-10-05 | 2025-10-07
R7S1ONAR-AP15GF348 | Fixing Floor Mat - AP#15 (GF - Front of Lift Shaft) | 2 | 2025-10-07 | 2025-10-09
GARBAGE ROOM |  | 2 | 2025-09-27 | 2025-09-28
R7S1ONAR-AP15GF350 | Paint Finishes and Touchups - Final Coat - AP#15 (GF - Garbage Room) | 2 | 2025-09-27 | 2025-09-28
MEP WORKS |  | 106 | 2025-07-21 | 2025-11-12
MECHANICAL |  | 105 | 2025-07-21 | 2025-11-11
CHILLED WATER |  | 79 | 2025-07-21 | 2025-10-28
R7S1ONME-AP15GF911 | Installation of Chilled water hanger and supports - AP#15 (GF - Corridor) | 4 | 2025-07-21 | 2025-07-26
R7S1ONME-AP15GF963 | Installation of CHWP connection for FCU with Valve package in Corridor, Electrical Room & ICT Room - AP#15 (GF) | 4 | 2025-07-21 | 2025-07-26
R7S1ONME-AP15GF913 | Installation of BTU Meter with valves - AP#15 (GF - Corridor) | 2 | 2025-07-27 | 2025-07-29
R7S1ONME-AP15GF912 | Installation of CHWP piping (connection between modular cages & modular to apartment) - AP#15 (GF - Corridor) | 4 | 2025-07-26 | 2025-07-30
R7S1ONME-AP15GF914 | CHWP piping risers connections - AP#15 (GF - Corridor) | 3 | 2025-07-31 | 2025-08-04
R7S1ONME-AP15GF915 | Pressure Testing of CHWP piping - AP#15 (GF - Corridor) | 1 | 2025-08-04 | 2025-08-05
R7S1ONME-AP15GF951 | CHWP Insulation - AP#15 (GF - Corridor) | 4 | 2025-08-05 | 2025-08-10
R7S1ONME-AP15GF1466 | CHWP Installation/Connections and Insulation (In Front of Lift Shaft) - AP#15 | 4 | 2025-10-25 | 2025-10-28
HVAC DUCTING |  | 103 | 2025-07-21 | 2025-11-09
R7S1ONME-AP15GF962 | Installation of FCU's & Duct Connection in Corridor, Electrical Room & ICT Room - AP#15 (GF) | 4 | 2025-07-21 | 2025-07-26
R7S1ONME-AP15GF964 | Installation of Ducting and insulation (connection between modular cages) - AP#15 (GF - Corridor) | 3 | 2025-07-26 | 2025-07-29
R7S1ONME-AP15GF916 | Duct Riser Continuation - AP#15 (GF - Corridor) | 4 | 2025-07-31 | 2025-08-05
R7S1ONME-AP15GF917 | A/C drain & Copper pipe connection in ELV room - AP#15 (GF) | 2 | 2025-08-05 | 2025-08-07
R7S1ONME-AP15GF952 | Installation of Duct & Grill in Garbage Room - AP#15 (GF - Garbage Room) | 2 | 2025-08-07 | 2025-08-10
R7S1ONME-AP15GF965 | Installation of Grilles in the Corridor - AP#15 (GF - Corridor) | 2 | 2025-11-06 | 2025-11-09
FIRE FIGHTING |  | 87 | 2025-07-31 | 2025-11-11
R7S1ONME-AP15GF918 | Riser Continuity in corridor - AP#15 (GF - Corridor) | 4 | 2025-07-31 | 2025-08-05
R7S1ONME-AP15GF919 | Continuitu of FF pipes & ZC Valves (connection between modular cages & modular to apartment) - AP#15 (GF - Corridor) | 4 | 2025-07-31 | 2025-08-05
R7S1ONME-AP15GF920 | Installation of Sprinklers drops in corridor - AP#15 (GF - Corridor) | 4 | 2025-08-05 | 2025-08-10
R7S1ONME-AP15GF921 | Pressure Test for FF Piping in corridor - AP#15 (GF - Corridor) | 2 | 2025-08-10 | 2025-08-12
R7S1ONME-AP15GF953 | Installation of Pipe & sprinkler in Garbage Room - AP#15 (GF - Garbage Room) | 1 | 2025-09-08 | 2025-09-08
R7S1ONME-AP15GF966 | FF Flushing network - AP#15 (GF - Corridor) | 1 | 2025-10-18 | 2025-10-19
R7S1ONME-AP15GF1676 | Installation of F.F Pipes, Testing & Final Fixtures (In Front of Lift Shaft) - AP15 | 3 | 2025-10-29 | 2025-11-01
R7S1ONME-AP15GF923 | Installation of Alarm check valve, Fire Extinguishers & Blanket - AP#15 (GF - Corridor) | 2 | 2025-11-06 | 2025-11-09
R7S1ONME-AP15GF922 | Installation of Sprinklers in corridor - AP#15 (GF - Corridor) | 4 | 2025-11-06 | 2025-11-11
WATER SUPPLY |  | 69 | 2025-07-21 | 2025-10-01
R7S1ONME-AP15GF954 | Installation of WS Pipe in Garbage Room - AP#15 (GF - Garbage Room) | 2 | 2025-07-21 | 2025-07-23
R7S1ONME-AP15GF955 | Installation of Sanitary Fixtures in Janitor Room - AP#15 (GF - Janitor Room) | 2 | 2025-07-21 | 2025-07-23
R7S1ONME-AP15GF925 | WS High Level Pipe continuation & Insulation works - AP#15 (GF - Corridor) | 4 | 2025-07-21 | 2025-07-26
R7S1ONME-AP15GF926 | Installation of Cold, Hot water line & Hot water return - AP#15 (GF - Corridor) | 4 | 2025-07-26 | 2025-07-30
R7S1ONME-AP15GF927 | Water Meter Installation - AP#15 (GF - Corridor) | 4 | 2025-07-30 | 2025-08-04
R7S1ONME-AP15GF924 | Riser Continuity in Shafts - AP#15 (GF - Corridor) | 4 | 2025-07-31 | 2025-08-05
R7S1ONME-AP15GF928 | Pressure Test for WS - AP#15 (GF - Corridor) | 4 | 2025-09-22 | 2025-09-27
R7S1ONME-AP15GF967 | Insulation for Hot water line & Hot water return - AP#15 (GF - Corridor) | 4 | 2025-09-28 | 2025-10-01
DRAINAGE |  | 49 | 2025-07-21 | 2025-09-27
R7S1ONME-AP15GF930 | Installation of Clean-outs, Floor drain in balcony - AP#15 (GF - Corridor) | 4 | 2025-07-21 | 2025-07-26
R7S1ONME-AP15GF931 | Rain Water Riser continuation in Shafts - AP#15 (GF - Corridor) | 4 | 2025-07-31 | 2025-08-05
R7S1ONME-AP15GF932 | Drainage Riser continuation in Shafts - AP#15 (GF - Corridor) | 4 | 2025-07-31 | 2025-08-05
R7S1ONME-AP15GF933 | Testing for Rain Water Riser - AP#15 (GF - Corridor) | 4 | 2025-09-22 | 2025-09-27
R7S1ONME-AP15GF934 | Testing for Drainage Riser1 - AP#15 (GF - Corridor) | 4 | 2025-09-22 | 2025-09-27
ELECTRICAL |  | 106 | 2025-07-21 | 2025-11-12
POWER & LIGHTING |  | 106 | 2025-07-21 | 2025-11-12
R7S1ONME-AP15GF935 | Contiuation of Cable Trays & apartment branches - AP#15 (GF - Corridor) | 4 | 2025-07-21 | 2025-07-26
R7S1ONME-AP15GF936 | Contiuation of Cable Trunking with Flexible conduits for Lights - AP#15 (GF - Corridor) | 4 | 2025-07-21 | 2025-07-26
R7S1ONME-AP15GF937 | Installation of EMT pipes - AP#15 (GF - Corridor) | 5 | 2025-07-21 | 2025-07-27
R7S1ONME-AP15GF938 | Installation of Busbar, Electrical Meter & Tap-off - AP#15 (GF - Corridor) | 3 | 2025-07-26 | 2025-07-29
R7S1ONME-AP15GF961 | Termination of Tap-off with Electrical Meter in the apartments - AP#15 (GF - Corridor) | 3 | 2025-07-29 | 2025-08-02
R7S1ONME-AP15GF939 | Corridor Wire Pulling - AP#15 (GF - Corridor) | 6 | 2025-07-27 | 2025-08-03
R7S1ONME-AP15GF940 | Electrical Room - Installation of Cable trays, SMDB & Termination - AP#15 (GF - Corridor) | 6 | 2025-09-24 | 2025-10-01
R7S1ONME-AP15GF1886 | Continuation of Cable Tray/Trunking with Flexible conduits for Lights (In Front of Lift Shaft) - AP#15 | 4 | 2025-11-02 | 2025-11-05
R7S1ONME-AP15GF942 | Installation, Termination of Emergeny & Exit Lights with contiuity - AP#15 (GF - Corridor) | 2 | 2025-11-06 | 2025-11-09
R7S1ONME-AP15GF941 | Installation, Termination of Light Fixtures with continuity test - AP#15 (GF - Corridor & Balconies) | 3 | 2025-11-06 | 2025-11-10
R7S1ONME-AP15GF943 | Installation, Termination of PIR sensors with continuity test - AP#15 (GF - Corridor) | 2 | 2025-11-10 | 2025-11-12
LOW CURRENT SYSTEM |  | 105 | 2025-07-21 | 2025-11-11
R7S1ONME-AP15GF968 | CBS System cable installation - AP#15 (GF - Corridor) | 3 | 2025-07-21 | 2025-07-24
R7S1ONME-AP15GF944 | Installation of Basket trays for BMS, CCTV, Access Control - AP#15 (GF - Corridor) | 4 | 2025-07-21 | 2025-07-26
R7S1ONME-AP15GF946 | Fire alarm cable installation - AP#15 (GF - Corridor) | 3 | 2025-07-22 | 2025-07-26
R7S1ONME-AP15GF945 | Voice Evacuation cable installation - AP#15 (GF - Corridor) | 3 | 2025-07-24 | 2025-07-28
R7S1ONME-AP15GF947 | Fibre optic Cable pulling & Termination with OTO (in corridors to ONU) - AP#15 (GF - Corridor) | 2 | 2025-10-04 | 2025-10-05
R7S1ONME-AP15GF948 | BMS, CCTV & Access control Cable installation - AP#15 (GF - Corridor) | 2 | 2025-10-04 | 2025-10-05
R7S1ONME-AP15GF949 | Low Current Works including BMS Panel in ICT Room - AP#15 (GF - Corridor) | 10 | 2025-09-29 | 2025-10-09
R7S1ONME-AP15GF960 | Fluke test for CCTV & Fibre Optic Cable - AP#15 (GF - Corridor) (Ceiling 1st Fix) | 2 | 2025-10-08 | 2025-10-09
R7S1ONME-AP15GF957 | Installation & Termination of Access control system for Electrical Room - AP#15 (GF) | 2 | 2025-10-09 | 2025-10-11
R7S1ONME-AP15GF2096 | Installation of Basket trays for Low Current, Cable Installation (In Front of Lift Shaft) - AP#15 | 4 | 2025-11-02 | 2025-11-05
R7S1ONME-AP15GF956 | Installation & Termination of CCTV Cameras - AP#15 (GF - Corridor) | 2 | 2025-11-06 | 2025-11-09
R7S1ONME-AP15GF959 | Installation & Termination of Wireless Gateway & RF Node in corridors - AP#15 (GF - Corridor) | 2 | 2025-11-06 | 2025-11-09
R7S1ONME-AP15GF950 | Installation & Termination of Fire alarm devices & Speakers - AP#15 (GF - Corridor) | 4 | 2025-11-06 | 2025-11-11
R7S1ONME-AP15GF958 | Installation & Termination of Active Components & UPS installation in ICT Room - AP#15 (GF - Corridor) | 2 | 2025-11-09 | 2025-11-11
FIRST FLOOR |  | 135 | 2025-07-28 | 2025-11-19
ARCH./ CIVIL WORKS |  | 123 | 2025-07-28 | 2025-11-19
CORRIDOR AREA |  | 81 | 2025-07-28 | 2025-11-19
R7S1ONAR-AP15FF450 | Flooring in Corridor - AP#15 (FF - Corridor) | 6 | 2025-07-28 | 2025-08-04
R7S1ONAR-AP15FF451 | Corridor Skirting - AP#15 (FF - Corridor) | 2 | 2025-08-03 | 2025-08-05
R7S1ONAR-AP15FF448 | False Ceiling - 1st Fix - AP#15 (FF - Corridor) | 4 | 2025-08-05 | 2025-08-10
R7S1ONAR-AP15FF449 | Gypsum Wall Cladding (Shafts) - AP#15 (FF - Corridor) | 6 | 2025-10-22 | 2025-10-29
R7S1ONAR-AP15FF452 | Gypsum Wall Cladding (Shafts) -2nd Fix - AP#15 (FF Corridor) | 4 | 2025-10-29 | 2025-11-03
R7S1ONAR-AP15FF456 | Fixing Architrave - AP#15 (FF Corridor) | 2 | 2025-11-03 | 2025-11-05
R7S1ONAR-AP15FF457 | Fixing Aluminium Doors - AP#15 (FF Corridor) | 2 | 2025-11-05 | 2025-11-08
R7S1ONAR-AP15FF453 | False Ceiling - 2nd Fix (Closing the Ceiling) - AP#15 (FF Corridor) | 3 | 2025-11-08 | 2025-11-11
R7S1ONAR-AP15FF454 | Painting - Surface Prep., Primer & 1st Coat for Walls - AP#15 (FF Corridor) | 8 | 2025-11-03 | 2025-11-12
R7S1ONAR-AP15FF477 | Painting - Surface Prep., Primer & 1st Coat for Ceiling - AP#15 (FF Corridor) | 4 | 2025-11-11 | 2025-11-16
R7S1ONAR-AP15FF455 | Painting - Final Coat (Ceiling + Walls) - AP#15 (FF Corridor) | 3 | 2025-11-16 | 2025-11-19
INSIDE BOXES |  | 12 | 2025-09-08 | 2025-09-21
R7S1ONAR-AP15FF458 | Fixing Thresholds (Joining the Room) - AP#15 (FF - inside Boxes) | 4 | 2025-09-08 | 2025-09-11
R7S1ONAR-AP15FF459 | Fixing Wooden Doors - AP#15 (FF - inside Boxes) | 4 | 2025-09-13 | 2025-09-16
R7S1ONAR-AP15FF460 | Fixing Aluminium Doors (Next Floor) - AP#15 (FF - inside Boxes) | 4 | 2025-09-17 | 2025-09-21
IN FRONT OF LIFT SHAFT |  | 117 | 2025-08-07 | 2025-10-12
R7S1ONAR-AP15FF462 | Flooring - AP#15 (FF - Front of Lift Shaft) | 4 | 2025-08-07 | 2025-08-12
R7S1ONAR-AP15FF463 | Skirting & Thresholds - AP#15 (FF - Front of Lift Shaft) | 2 | 2025-08-10 | 2025-08-12
R7S1ONAR-AP15FF464 | Painting - Surface Prep., Primer & 1st Coat - AP#15 (FF - Front of Lift Shaft) | 4 | 2025-08-12 | 2025-08-17
R7S1ONAR-AP15FF461 | False Ceiling - 1st Fix - AP#15 (FF - Front of Lift Shaft) | 4 | 2025-08-17 | 2025-08-21
R7S1ONAR-AP15FF465 | False Ceiling - Final Fix - AP#15 (FF - Front of Lift Shaft) | 3 | 2025-09-10 | 2025-09-13
R7S1ONAR-AP15FF467 | Fixing Handrail - AP#15 (FF - Front of Lift Shaft) | 3 | 2025-09-14 | 2025-09-16
R7S1ONAR-AP15FF468 | Paint for Handrail - AP#15 (FF - Front of Lift Shaft) | 3 | 2025-09-17 | 2025-09-20
R7S1ONAR-AP15FF466 | Painting - 2nd Coat - AP#15 (FF - Front of Lift Shaft) | 2 | 2025-10-01 | 2025-10-04
R7S1ONAR-AP15FF470 | Fixing Wall Guard - AP#15 (FF - Front of Lift Shaft) | 2 | 2025-10-07 | 2025-10-09
R7S1ONAR-AP15FF469 | Fixing Floor Mat - AP#15 (FF - Front of Lift Shaft) | 2 | 2025-10-09 | 2025-10-12
GARBAGE ROOM |  | 10 | 2025-09-14 | 2025-09-25
R7S1ONAR-AP15FF471 | Installation of Dry Walls - First Fix - AP#15 (FF - Garbage Room) | 2 | 2025-09-14 | 2025-09-15
R7S1ONAR-AP15FF472 | Installation of Dry Walls - Final Fix - AP#15 (FF - Garbage Room) | 2 | 2025-09-15 | 2025-09-16
R7S1ONAR-AP15FF473 | Garbage Rooms - Wall Tile Finishes (One Side) - AP#15 (FF - Garbage Room) | 2 | 2025-09-16 | 2025-09-17
R7S1ONAR-AP15FF474 | Paint Works of Dry Walls - First Coat - AP#15 (FF - Garbage Room) | 2 | 2025-09-18 | 2025-09-20
R7S1ONAR-AP15FF475 | Installation of the Garbage Chute Door - AP#15 (FF - Garbage Room) | 2 | 2025-09-21 | 2025-09-22
R7S1ONAR-AP15FF476 | Paint Finishes and Touchups - Final Coat - AP#15 (FF - Garbage Room) | 2 | 2025-09-24 | 2025-09-25
MEP WORKS |  | 80 | 2025-08-07 | 2025-11-17
MECHANICAL |  | 68 | 2025-08-07 | 2025-11-16
CHILLED WATER |  | 34 | 2025-08-07 | 2025-11-02
R7S1ONME-AP15FF648 | Installation of Chilled water hanger and supports - AP#15 (FF Corridor) | 4 | 2025-08-07 | 2025-08-12
R7S1ONME-AP15FF698 | Installation of CHWP connection for FCU with Valve package in Corridor, Electrical Room & ICT Room | 4 | 2025-08-07 | 2025-08-12
R7S1ONME-AP15FF650 | Installation of BTU Meter with valves - AP#15 (FF Corridor) | 2 | 2025-08-13 | 2025-08-16
R7S1ONME-AP15FF649 | Installation of CHWP piping (connection between modular cages & modular to apartment) - AP#15 -(FF Corridor) | 4 | 2025-08-12 | 2025-08-17
R7S1ONME-AP15FF651 | CHWP piping risers connections - AP#15 (FF Corridor) | 3 | 2025-08-30 | 2025-09-01
R7S1ONME-AP15FF652 | Pressure Testing of CHWP piping - AP#15 (FF Corridor) | 1 | 2025-09-02 | 2025-09-02
R7S1ONME-AP15FF687 | CHWP Insulation - AP#15 (FF Corridor) | 4 | 2025-09-03 | 2025-09-07
R7S1ONME-AP15FF1476 | CHWP Installation/Connections and Insulation (In Front of Lift Shaft) - AP#15 | 4 | 2025-10-29 | 2025-11-02
HVAC DUCTING |  | 65 | 2025-08-07 | 2025-11-13
R7S1ONME-AP15FF699 | Installation of FCU's & Duct Connection in Corridor, Electrical Room & ICT Room - AP#15 (FF Corridor) | 4 | 2025-08-07 | 2025-08-12
R7S1ONME-AP15FF653 | Duct Riser Continuation - AP#15 (FF Corridor) | 4 | 2025-08-30 | 2025-09-02
R7S1ONME-AP15FF654 | A/C drain & Copper pipe connection in ELV room - AP#15 (FF Corridor) | 2 | 2025-09-03 | 2025-09-04
R7S1ONME-AP15FF700 | Installation of Ducting and insulation (connection between modular cages) - AP#15 (FF Corridor) | 3 | 2025-09-03 | 2025-09-06
R7S1ONME-AP15FF688 | Installation of Duct & Grill in Garbage Room - AP#15 (FF Corridor) | 2 | 2025-09-06 | 2025-09-07
R7S1ONME-AP15FF701 | Installation of Grilles in the Corridor - AP#15 (FF Corridor) | 2 | 2025-11-11 | 2025-11-13
FIRE FIGHTING |  | 62 | 2025-08-30 | 2025-11-16
R7S1ONME-AP15FF655 | Riser Continuity in corridor - AP#15 (FF Corridor) | 4 | 2025-08-30 | 2025-09-02
R7S1ONME-AP15FF656 | Continuation of FF pipes & ZC Valves (connection between modular cages & modular to apartment) - AP#15 (FF Corridor) | 4 | 2025-08-30 | 2025-09-02
R7S1ONME-AP15FF657 | Installation of Sprinklers drops in corridor - AP#15 (FF Corridor) | 4 | 2025-09-03 | 2025-09-07
R7S1ONME-AP15FF689 | Installation of Pipe & sprinkler in Garbage Room - AP#15 (FF Corridor) | 1 | 2025-09-08 | 2025-09-08
R7S1ONME-AP15FF658 | Pressure Test for FF Piping in corridor - AP#15 (FF Corridor) | 2 | 2025-09-08 | 2025-09-09
R7S1ONME-AP15FF702 | FF Flushing network - AP#15 (FF Corridor) | 4 | 2025-10-18 | 2025-10-22
R7S1ONME-AP15FF1686 | Installation of F.F Pipes, Testing & Final Fixtures (In Front of Lift Shaft) - AP15 | 3 | 2025-11-03 | 2025-11-05
R7S1ONME-AP15FF660 | Installation of Alarm check valve, Fire Extinguishers & Blanket (Last Stage of the Building) - AP#15 (FF Corridor) | 2 | 2025-11-11 | 2025-11-13
R7S1ONME-AP15FF659 | Installation of Sprinklers in corridor - AP#15 (FF Corridor) | 4 | 2025-11-11 | 2025-11-16
WATER SUPPLY |  | 37 | 2025-08-07 | 2025-10-06
R7S1ONME-AP15FF690 | Installation of WS Pipe in Garbage Room - AP#15 (FF Corridor) | 2 | 2025-08-07 | 2025-08-10
R7S1ONME-AP15FF691 | Installation of Sanitary Fixtures in Janitor Room - AP#15 (FF Corridor) | 2 | 2025-08-07 | 2025-08-10
R7S1ONME-AP15FF662 | WS High Level Pipe continuation & Insulation works in Corridor - AP#15 (FF Corridor) | 4 | 2025-08-07 | 2025-08-12
R7S1ONME-AP15FF663 | Installation of Cold, Hot water line & Hot water return in corridor - AP#15 (FF Corridor) | 4 | 2025-08-12 | 2025-08-17
R7S1ONME-AP15FF664 | Water Meter Installation in Corridor - AP#15 (FF Corridor) | 4 | 2025-08-17 | 2025-08-21
R7S1ONME-AP15FF661 | Riser Continuity in Shafts - AP#15 (FF Corridor) | 4 | 2025-08-30 | 2025-09-02
R7S1ONME-AP15FF665 | Pressure Test for WS - AP#15 (FF Corridor) | 4 | 2025-09-22 | 2025-09-27
R7S1ONME-AP15FF703 | Insulation for Hot water line & Hot water return in corridor - AP#15 (FF Corridor) | 4 | 2025-10-02 | 2025-10-06
DRAINAGE |  | 33 | 2025-08-07 | 2025-09-27
R7S1ONME-AP15FF666 | Installation of Clean-outs, Floor drain in balcony - AP#15 (FF Corridor) | 4 | 2025-08-07 | 2025-08-12
R7S1ONME-AP15FF667 | Rain Water Riser continuation in Shafts - AP#15 (FF Corridor) | 4 | 2025-08-30 | 2025-09-02
R7S1ONME-AP15FF668 | Drainage Riser continuation in Shafts - AP#15 (FF Corridor) | 4 | 2025-08-30 | 2025-09-02
R7S1ONME-AP15FF669 | Testing for Rain Water Riser - AP#15 (FF Corridor) | 4 | 2025-09-22 | 2025-09-27
R7S1ONME-AP15FF670 | Testing for Drainage Riser - AP#15 (FF Corridor) | 4 | 2025-09-22 | 2025-09-27
ELECTRICAL |  | 75 | 2025-08-07 | 2025-11-17
POWER & LIGHTING |  | 75 | 2025-08-07 | 2025-11-17
R7S1ONME-AP15FF671 | Contiuation of Cable Trays & apartment branches - AP#15 (FF Corridor) | 4 | 2025-08-07 | 2025-08-12
R7S1ONME-AP15FF672 | Contiuation of Cable Trunking with Flexible conduits for Lights - AP#15 (FF Corridor) | 4 | 2025-08-07 | 2025-08-12
R7S1ONME-AP15FF673 | Installation of EMT pipes - AP#15 (FF Corridor) | 5 | 2025-08-07 | 2025-08-13
R7S1ONME-AP15FF674 | Installation of Busbar, Electrical Meter & Tap-off - AP#15 (FF Corridor) | 3 | 2025-08-12 | 2025-08-16
R7S1ONME-AP15FF697 | Termination of Tap-off with Electrical Meter in the apartments - AP#15 (FF Corridor) | 3 | 2025-08-16 | 2025-08-19
R7S1ONME-AP15FF675 | Corridor Wire Pulling - AP#15 (FF Corridor) | 6 | 2025-08-13 | 2025-08-20
R7S1ONME-AP15FF676 | Electrical Room - Installation of Cable trays, SMDB & Termination - AP#15 (FF Corridor) | 6 | 2025-09-24 | 2025-10-01
R7S1ONME-AP15FF1896 | Continuation of Cable Tray/Trunking with Flexible conduits for Lights (In Front of Lift Shaft) - AP#15 | 4 | 2025-11-06 | 2025-11-10
R7S1ONME-AP15FF678 | Installation, Termination of Emergeny & Exit Lights with contiuity - AP#15 (FF Corridor) | 2 | 2025-11-11 | 2025-11-13
R7S1ONME-AP15FF677 | Installation, Termination of Light Fixtures with continuity test - AP#15 (FF - Corridor & Balconies) | 3 | 2025-11-11 | 2025-11-15
R7S1ONME-AP15FF679 | Installation, Termination of PIR sensors with continuity test - AP#15 (FF Corridor) | 2 | 2025-11-15 | 2025-11-17
LOW CURRENT SYSTEM |  | 68 | 2025-08-07 | 2025-11-16
R7S1ONME-AP15FF704 | CBS System cable installation - AP#15 (FF Corridor) | 3 | 2025-08-07 | 2025-08-11
R7S1ONME-AP15FF680 | Installation of Basket trays for BMS, CCTV, Access Control - AP#15 (FF Corridor) | 4 | 2025-08-07 | 2025-08-12
R7S1ONME-AP15FF682 | Fire alarm cable installation - AP#15 (FF Corridor) | 3 | 2025-08-09 | 2025-08-12
R7S1ONME-AP15FF681 | Voice Evacuation cable installation - AP#15 (FF Corridor) | 3 | 2025-08-11 | 2025-08-14
R7S1ONME-AP15FF683 | Fibre optic Cable pulling & Termination with OTO (in corridors to ONU) - AP#15 (FF Corridor) | 2 | 2025-10-06 | 2025-10-07
R7S1ONME-AP15FF684 | BMS, CCTV & Access control Cable installation - AP#15 (FF Corridor) | 2 | 2025-10-06 | 2025-10-07
R7S1ONME-AP15FF685 | Low Current Works including BMS Panel in ICT Room - AP#15 (FF Corridor) | 10 | 2025-10-01 | 2025-10-12
R7S1ONME-AP15FF696 | Fluke test for CCTV & Fibre Optic Cable - AP#15 (FF Corridor) | 2 | 2025-10-11 | 2025-10-12
R7S1ONME-AP15FF2106 | Installation of Basket trays for Low Current, Cable Installation (In Front of Lift Shaft) - AP#15 | 4 | 2025-11-06 | 2025-11-10
R7S1ONME-AP15FF692 | Installation & Termination of CCTV Cameras - AP#15 (FF Corridor) | 2 | 2025-11-11 | 2025-11-13
R7S1ONME-AP15FF693 | Installation & Termination of Access control system for Electrical Room - AP#15 (FF Corridor) | 2 | 2025-11-11 | 2025-11-13
R7S1ONME-AP15FF695 | Installation & Termination of Wireless Gateway & RF Node - AP#15 (FF Corridor) | 2 | 2025-11-11 | 2025-11-13
R7S1ONME-AP15FF686 | Installation & Termination of Fire alarm devices & Speakers - AP#15 (FF Corridor) | 4 | 2025-11-11 | 2025-11-16
R7S1ONME-AP15FF694 | Installation & Termination of Active Components & UPS installation in ICT Room | 2 | 2025-11-13 | 2025-11-16
SECOND FLOOR |  | 115 | 2025-08-28 | 2025-12-02
ARCH./ CIVIL WORKS |  | 115 | 2025-08-28 | 2025-12-02
CORRIDOR AREA |  | 76 | 2025-09-18 | 2025-12-02
R7S1ONAR-AP15SF353 | Flooring in Corridor - AP#15 (SF Corridor) | 6 | 2025-09-18 | 2025-09-25
R7S1ONAR-AP15SF354 | Corridor Skirting - AP#15 (SF Corridor) | 2 | 2025-09-25 | 2025-09-27
R7S1ONAR-AP15SF351 | False Ceiling - 1st Fix - AP#15 (SF Corridor) | 4 | 2025-10-06 | 2025-10-11
R7S1ONAR-AP15SF352 | Gypsum Wall Cladding (Shafts) - AP#15 (SF Corridor) | 6 | 2025-11-06 | 2025-11-12
R7S1ONAR-AP15SF355 | Gypsum Wall Cladding (Shafts) -2nd Fix - AP#15 (SF Corridor) | 4 | 2025-11-13 | 2025-11-17
R7S1ONAR-AP15SF359 | Fixing Architrave - AP#15 (SF Corridor) | 2 | 2025-11-18 | 2025-11-19
R7S1ONAR-AP15SF360 | Fixing Aluminium Doors - AP#15 (SF Corridor) | 2 | 2025-11-18 | 2025-11-19
R7S1ONAR-AP15SF356 | False Ceiling - 2nd Fix (Closing the Ceiling) - AP#15 (SF Corridor) | 3 | 2025-11-20 | 2025-11-23
R7S1ONAR-AP15SF357 | Painting - Surface Prep., Primer & 1st Coat - AP#15 (SF Corridor) | 8 | 2025-11-18 | 2025-11-26
R7S1ONAR-AP15SF381 | Painting - Surface Prep., Primer & 1st Coat - AP#15 (SF Corridor) | 4 | 2025-11-24 | 2025-11-27
R7S1ONAR-AP15SF358 | Painting - Final Coat (Ceiling + Walls) - AP#15 (SF Corridor) | 3 | 2025-11-30 | 2025-12-02
INSIDE BOXES |  | 12 | 2025-09-27 | 2025-10-09
R7S1ONAR-AP15SF361 | Fixing Thresholds (Joining the Room) - AP#15 (SF - inside Boxes) | 4 | 2025-09-27 | 2025-09-30
R7S1ONAR-AP15SF362 | Fixing Wooden Doors - AP#15 (SF - inside Boxes) | 4 | 2025-10-01 | 2025-10-05
R7S1ONAR-AP15SF363 | Fixing Aluminium Doors (Next Floor) - AP#15 (SF - inside Boxes) | 4 | 2025-10-06 | 2025-10-09
IN FRONT OF LIFT SHAFT |  | 114 | 2025-09-08 | 2025-11-12
R7S1ONAR-AP15SF365 | Flooring - AP#15 (SF - Front of Lift Shaft) | 4 | 2025-09-08 | 2025-09-11
R7S1ONAR-AP15SF366 | Skirting & Thresholds - AP#15 (SF - Front of Lift Shaft) | 4 | 2025-09-13 | 2025-09-16
R7S1ONAR-AP15SF367 | Painting - Surface Prep., Primer & 1st Coat - AP#15 (SF - Front of Lift Shaft) | 4 | 2025-09-17 | 2025-09-21
R7S1ONAR-AP15SF364 | False Ceiling - 1st Fix - AP#15 (SF - Front of Lift Shaft) | 3 | 2025-09-22 | 2025-09-25
R7S1ONAR-AP15SF368 | False Ceiling - Final Fix - AP#15 (SF - Front of Lift Shaft) | 3 | 2025-10-18 | 2025-10-21
R7S1ONAR-AP15SF370 | Fixing Handrail - AP#15 (SF - Front of Lift Shaft) | 3 | 2025-10-21 | 2025-10-25
R7S1ONAR-AP15SF371 | Paint for Handrail - AP#15 (SF - Front of Lift Shaft) | 3 | 2025-10-25 | 2025-10-28
R7S1ONAR-AP15SF369 | Painting - 2nd Coat - AP#15 (SF - Front of Lift Shaft) | 2 | 2025-11-09 | 2025-11-10
R7S1ONAR-AP15SF372 | Fixing Floor Mat - AP#15 (SF - Front of Lift Shaft) | 2 | 2025-11-11 | 2025-11-12
R7S1ONAR-AP15SF373 | Fixing Wall Guard - AP#15 (SF - Front of Lift Shaft) | 2 | 2025-11-11 | 2025-11-12
GARBAGE ROOM |  | 36 | 2025-08-28 | 2025-11-27
R7S1ONAR-AP15SF380 | Installation of Garbage Chute Full System from GF to 2nd Floor - AP#15 (SF - Garbage Room) | 10 | 2025-08-28 | 2025-09-08
R7S1ONAR-AP15SF374 | Installation of Dry Walls - First Fix - AP#15 (SF - Garbage Room) | 2 | 2025-09-09 | 2025-09-10
R7S1ONAR-AP15SF375 | Installation of Dry Walls - Final Fix - AP#15 (SF - Garbage Room) | 2 | 2025-09-11 | 2025-09-13
R7S1ONAR-AP15SF376 | Garbage Rooms - Wall Tile Finishes (One Side) - AP#15 (SF - Garbage Room) | 2 | 2025-09-13 | 2025-09-14
R7S1ONAR-AP15SF377 | Paint Works of Dry Walls - First Coat - AP#15 (SF - Garbage Room) | 2 | 2025-09-15 | 2025-09-16
R7S1ONAR-AP15SF378 | Installation of the Garbage Chute Door - AP#15 (SF - Garbage Room) | 2 | 2025-09-17 | 2025-09-18
R7S1ONAR-AP15SF379 | Paint Finishes and Touchups - Final Coat - AP#15 (SF - Garbage Room) | 2 | 2025-11-26 | 2025-11-27
MEP WORKS |  | 85 | 2025-09-08 | 2025-11-29
MECHANICAL |  | 85 | 2025-09-08 | 2025-11-27
CHILLED WATER |  | 35 | 2025-09-08 | 2025-11-06
R7S1ONME-AP15SF606 | Installation of Chilled water hanger and supports - AP#15 (SF Corridor) | 4 | 2025-09-08 | 2025-09-11
R7S1ONME-AP15SF656 | Installation of CHWP connection for FCU with Valve package in Corridor, Electrical Room & ICT Room | 4 | 2025-09-08 | 2025-09-11
R7S1ONME-AP15SF608 | Installation of BTU Meter with valves - AP#15 (SF Corridor) | 2 | 2025-09-14 | 2025-09-15
R7S1ONME-AP15SF607 | Installation of CHWP piping (connection between modular cages & modular to apartment) - AP#15 (SF Corridor) | 4 | 2025-09-13 | 2025-09-16
R7S1ONME-AP15SF609 | CHWP piping risers connections - AP#15 (SF Corridor) | 3 | 2025-09-16 | 2025-09-18
R7S1ONME-AP15SF610 | Pressure Testing of CHWP piping - AP#15 (SF Corridor) | 1 | 2025-09-20 | 2025-09-20
R7S1ONME-AP15SF645 | CHWP Insulation - AP#15 (SF Corridor) | 4 | 2025-09-21 | 2025-09-25
R7S1ONME-AP15SF1486 | CHWP Installation/Connections and Insulation (In Front of Lift Shaft) - AP#15 | 4 | 2025-11-03 | 2025-11-06
HVAC DUCTING |  | 66 | 2025-09-08 | 2025-11-25
R7S1ONME-AP15SF611 | Duct Riser Continuation - AP#15 (SF Corridor) | 4 | 2025-09-08 | 2025-09-11
R7S1ONME-AP15SF657 | Installation of FCU's & Duct Connection in Corridor, Electrical Room & ICT Room - AP#15 (SF Corridor) | 4 | 2025-09-08 | 2025-09-11
R7S1ONME-AP15SF612 | A/C drain & Copper pipe connection in ELV room - AP#15 (SF Corridor) | 2 | 2025-09-13 | 2025-09-14
R7S1ONME-AP15SF658 | Installation of Ducting and insulation (connection between modular cages) - AP#15 (SF Corridor) | 3 | 2025-09-13 | 2025-09-15
R7S1ONME-AP15SF646 | Installation of Duct & Grill in Garbage Room - AP#15 (SF Corridor) | 2 | 2025-11-24 | 2025-11-25
R7S1ONME-AP15SF659 | Installation of Grilles in the Corridor - AP#15 (SF Corridor) | 2 | 2025-11-24 | 2025-11-25
FIRE FIGHTING |  | 73 | 2025-09-08 | 2025-11-27
R7S1ONME-AP15SF613 | Riser Continuity Succ - Closing of Gysum Boards on shaft - AP#15 (SF Corridor) | 4 | 2025-09-08 | 2025-09-11
R7S1ONME-AP15SF614 | FF Contiuation on High Level with Valves - AP#15 (SF Corridor) | 4 | 2025-09-08 | 2025-09-11
R7S1ONME-AP15SF615 | Installation of Sprinklers drops - AP#15 (SF Corridor) | 4 | 2025-10-11 | 2025-10-15
R7S1ONME-AP15SF616 | Pressure Test for FF Piping - AP#15 (SF Corridor) | 2 | 2025-10-15 | 2025-10-18
R7S1ONME-AP15SF1696 | Installation of F.F Pipes, Testing & Final Fixtures (In Front of Lift Shaft) - AP15 | 3 | 2025-11-06 | 2025-11-09
R7S1ONME-AP15SF618 | Installation of Fire Extinguishers - AP#15 (SF Corridor) | 2 | 2025-11-24 | 2025-11-25
R7S1ONME-AP15SF647 | Installation of Pipe & sprinkler in Garbage Room - AP#15 (SF Corridor) | 2 | 2025-11-24 | 2025-11-25
R7S1ONME-AP15SF617 | Installation of Sprinklers - AP#15 (SF Corridor) | 4 | 2025-11-24 | 2025-11-27
WATER SUPPLY |  | 29 | 2025-09-08 | 2025-10-11
R7S1ONME-AP15SF648 | Installation of WS Pipe in Garbage Room - AP#15 (SF Corridor) | 2 | 2025-09-08 | 2025-09-09
R7S1ONME-AP15SF649 | Installation of Sanitary Fixtures in Janitor Room - AP#15 (SF Corridor) | 2 | 2025-09-08 | 2025-09-09
R7S1ONME-AP15SF619 | Riser Continuity - AP#15 (SF Corridor) | 4 | 2025-09-08 | 2025-09-11
R7S1ONME-AP15SF620 | WS High Level Pipe continuation & Insulation works - AP#15 (SF Corridor) | 4 | 2025-09-08 | 2025-09-11
R7S1ONME-AP15SF621 | Instalation of Hot water line in corridor - AP#15 (SF Corridor) | 4 | 2025-09-13 | 2025-09-16
R7S1ONME-AP15SF622 | Water Meter Installation - AP#15 (SF Corridor) | 4 | 2025-09-17 | 2025-09-21
R7S1ONME-AP15SF623 | Pressure Test for WS - AP#15 (SF Corridor) | 4 | 2025-09-28 | 2025-10-01
R7S1ONME-AP15FF705 | Insulation for Hot water line & Hot water return in corridor - AP#15 (SF Corridor) | 4 | 2025-10-07 | 2025-10-11
DRAINAGE |  | 27 | 2025-09-08 | 2025-09-27
R7S1ONME-AP15SF624 | Installation of Clean-outs - AP#15 (SF Corridor) | 4 | 2025-09-08 | 2025-09-11
R7S1ONME-AP15SF625 | Rain Water Riser continuation - AP#15 (SF Corridor) | 4 | 2025-09-08 | 2025-09-11
R7S1ONME-AP15SF626 | Drainage Riser continuation - AP#15 (SF Corridor) | 4 | 2025-09-08 | 2025-09-11
R7S1ONME-AP15SF627 | Testing for Rain Water Riser - AP#15 (SF Corridor) | 4 | 2025-09-22 | 2025-09-27
R7S1ONME-AP15SF628 | Testing for Drainage Riser - AP#15 (SF Corridor) | 4 | 2025-09-22 | 2025-09-27
ELECTRICAL |  | 59 | 2025-09-08 | 2025-11-29
POWER & LIGHTING |  | 59 | 2025-09-08 | 2025-11-29
R7S1ONME-AP15SF629 | Contiuation of Cable Trays & apartment branches - AP#15 (SF Corridor) | 4 | 2025-09-08 | 2025-09-11
R7S1ONME-AP15SF630 | Contiuation of Cable Trunking with Flexible conduits for Lights - AP#15 (SF Corridor) | 4 | 2025-09-08 | 2025-09-11
R7S1ONME-AP15SF631 | Installation of EMT pipes - AP#15 (SF Corridor) | 5 | 2025-09-08 | 2025-09-13
R7S1ONME-AP15SF632 | Installation of Busbar, Electrical Meter & Tap-off in Corridor - AP#15 (SF Corridor) | 3 | 2025-09-13 | 2025-09-15
R7S1ONME-AP15SF655 | Termination of Tap-off with Electrical Meter in the apartments - AP#15 (SF Corridor) | 3 | 2025-09-16 | 2025-09-18
R7S1ONME-AP15SF633 | Corridor Wire Pulling - AP#15 (SF Corridor) | 6 | 2025-09-14 | 2025-09-20
R7S1ONME-AP15SF634 | Electrical Room - Installation of Cable trays, SMDB & Termination - AP#15 (SF Corridor) | 6 | 2025-11-02 | 2025-11-08
R7S1ONME-AP15SF1906 | Continuation of Cable Tray/Trunking with Flexible conduits for Lights (In Front of Lift Shaft) - AP#15 | 4 | 2025-11-06 | 2025-11-10
R7S1ONME-AP15SF636 | Installation, Termination of Emergeny & Exit Lights with contiuity - AP#15 (SF Corridor) | 2 | 2025-11-24 | 2025-11-25
R7S1ONME-AP15SF635 | Installation, Termination of Light Fixtures with continuity test - AP#15 (SF - Corridor & Balconies) | 3 | 2025-11-24 | 2025-11-26
R7S1ONME-AP15SF637 | Installation, Termination of PIR sensors with continuity test - AP#15 (SF Corridor) | 2 | 2025-11-27 | 2025-11-29
LOW CURRENT SYSTEM |  | 58 | 2025-09-08 | 2025-11-27
R7S1ONME-AP15SF660 | CBS System cable installation - AP#15 (SF Corridor) | 3 | 2025-09-08 | 2025-09-10
R7S1ONME-AP15SF638 | Installation of Basket trays for BMS, CCTV, Access Control - AP#15 (SF Corridor) | 4 | 2025-09-08 | 2025-09-11
R7S1ONME-AP15SF640 | Fire alarm cable installation - AP#15 (SF Corridor) | 3 | 2025-09-09 | 2025-09-11
R7S1ONME-AP15SF639 | Voice Evacuation cable installation - AP#15 (SF Corridor) | 3 | 2025-09-11 | 2025-09-14
R7S1ONME-AP15SF641 | Fibre optic Cable pulling & Termination with OTO (in corridors to ONU) - AP#15 (SF Corridor) | 2 | 2025-10-06 | 2025-10-07
R7S1ONME-AP15SF642 | BMS, CCTV & Access control Cable installation - AP#15 (SF Corridor) | 2 | 2025-10-06 | 2025-10-07
R7S1ONME-AP15SF643 | Low Current Works including BMS Panel in ICT Room - AP#15 (SF Corridor) | 10 | 2025-10-26 | 2025-11-05
R7S1ONME-AP15SF654 | Fluke test for CCTV & Fibre Optic Cable - AP#15 (SF Corridor) | 2 | 2025-11-04 | 2025-11-05
R7S1ONME-AP15SF2116 | Installation of Basket trays for Low Current, Cable Installation (In Front of Lift Shaft) - AP#15 | 4 | 2025-11-06 | 2025-11-10
R7S1ONME-AP15SF650 | Installation & Termination of CCTV Cameras - AP#15 (SF Corridor) | 2 | 2025-11-24 | 2025-11-25
R7S1ONME-AP15SF651 | Installation & Termination of Access control system for Electrical Room - AP#15 (SF Corridor) | 2 | 2025-11-24 | 2025-11-25
R7S1ONME-AP15SF653 | Installation & Termination of Wireless Gateway & RF Node in corridors - AP#15 (SF Corridor) | 2 | 2025-11-24 | 2025-11-25
R7S1ONME-AP15SF644 | Installation & Termination of Fire alarm devices & Speakers - AP#15 (SF Corridor) | 4 | 2025-11-24 | 2025-11-27
R7S1ONME-AP15SF652 | Installation & Termination of Active Components & UPS installation in ICT Room - AP#15 (SF Corridor) | 2 | 2025-11-26 | 2025-11-27
ROOF WORKS |  | 89 | 2025-09-22 | 2025-11-17
ARCH./ CIVIL WORKS |  | 89 | 2025-09-22 | 2025-11-12
R7S1ONAR-AP15RF91 | Roof Box Stiching (Concrete Works) - AP#15 (Roof) | 6 | 2025-09-22 | 2025-09-29
R7S1ONME-AP15RF566 | Installation of Roof Drains - AP#15 (Roof) | 2 | 2025-09-28 | 2025-09-29
R7S1ONAR-AP15RF92 | Roof Waterproofing Works with testing - AP#15 (Roof) | 20 | 2025-10-01 | 2025-10-23
R7S1ONAR-AP15RF93 | Laying of Gravel - AP#15 (Roof) | 2 | 2025-10-25 | 2025-10-26
R7S1ONAR-AP15RF94 | Surface Preparation & Primer for Parapets - AP#15 (Roof) | 4 | 2025-10-27 | 2025-10-30
R7S1ONAR-AP15RF95 | 1st Coat Paint for Parapets - AP#15 (Roof) | 2 | 2025-11-01 | 2025-11-02
R7S1ONAR-AP15RF96 | 2nd Coat Paint for Parapets - AP#15 (Roof) | 2 | 2025-11-03 | 2025-11-04
R7S1ONAR-AP15RF98 | Fixing Fall Arrest System - AP#15 (Roof) | 2 | 2025-11-08 | 2025-11-09
R7S1ONAR-AP15RF97 | Crossover Bridges Installation & application of Sealant on MEP penetrations - AP#15 (Roof) | 6 | 2025-11-06 | 2025-11-12
MECHANICAL |  | 46 | 2025-10-27 | 2025-11-16
HVAC |  | 20 | 2025-10-27 | 2025-11-09
R7S1ONME-AP15RF530 | Modular Installation - AP#15 (Roof) | 5 | 2025-10-27 | 2025-11-01
R7S1ONME-AP15RF531 | Continuation of Roof duct works/FAHU Connections - AP#15 (Roof) | 5 | 2025-10-29 | 2025-11-03
R7S1ONME-AP15RF535 | Installation of FAHU - AP#15 (Roof) | 2 | 2025-11-02 | 2025-11-03
R7S1ONME-AP15RF533 | Insulations for ducts - AP#15 (Roof) | 5 | 2025-10-30 | 2025-11-04
R7S1ONME-AP15RF540 | Installation of Outdoor VRF/DX Units - AP#15 (Roof) | 2 | 2025-11-03 | 2025-11-04
R7S1ONME-AP15RF541 | Installation & Insulation of the Condensation Drain - AP#15 (Roof) | 1 | 2025-11-04 | 2025-11-04
R7S1ONME-AP15RF543 | Installation of Ventilation Fans - AP#15 (Roof) | 3 | 2025-11-02 | 2025-11-04
R7S1ONME-AP15RF538 | Chilled Water System Continuation and Connections with Valve package of FAHU - AP#15 (Roof) | 4 | 2025-11-02 | 2025-11-05
R7S1ONME-AP15RF545 | Installation of Louvers - AP#15 (Roof) | 2 | 2025-11-05 | 2025-11-06
R7S1ONME-AP15RF548 | Installation & Testing of Copper Pipes - AP#15 (Roof) | 2 | 2025-11-05 | 2025-11-06
R7S1ONME-AP15RF549 | Miscellaneous Works for Mechanical Connections (Fire & Volume Dampers etc.) - AP#15 (Roof) | 2 | 2025-11-08 | 2025-11-09
WATERSUPPLY & DRAINAGE |  | 28 | 2025-11-01 | 2025-11-16
R7S1ONME-AP15RF532 | Installation & Continuation of Water supply pipes (connection between modular cages & modular to Shaft Riser) - AP#15 | 4 | 2025-11-01 | 2025-11-04
R7S1ONME-AP15RF529 | Testing for the Rain Water Risers - AP#15 (Roof) | 2 | 2025-11-04 | 2025-11-05
R7S1ONME-AP15RF536 | Installation of Air Vent & Pressure Guage with Valves at Roof - AP#15 (Roof) | 4 | 2025-11-02 | 2025-11-05
R7S1ONME-AP15RF537 | Vertical Continuation of Vent Pipes To The Roof (Drainage) - AP#15 (Roof) | 4 | 2025-11-03 | 2025-11-06
R7S1ONME-AP15RF534 | Installation of Air Vent with Valve for Water Supply - AP#15 (Roof) | 4 | 2025-11-05 | 2025-11-09
R7S1ONME-AP15RF539 | Installation of Rain Water outlet - AP#15 (Roof) | 3 | 2025-11-06 | 2025-11-09
R7S1ONME-AP15RF542 | Testing of Water Supply Pipes - AP#15 (Roof) | 2 | 2025-11-10 | 2025-11-11
R7S1ONME-AP15RF544 | Insulation of Roof Water Line - AP#15 (Roof) | 2 | 2025-11-11 | 2025-11-12
R7S1ONME-AP15RF546 | Testing for the Drainage Pipes Risers - AP#15 (Roof) | 2 | 2025-11-13 | 2025-11-15
R7S1ONME-AP15RF547 | Installation of Vent Cowl - AP#15 (Roof) | 1 | 2025-11-16 | 2025-11-16
SOLAR HEATER |  | 41 | 2025-11-02 | 2025-11-15
R7S1ONME-AP15RF561 | Installation of Solar water pumps and circulation pumps with valves(For Water Only) - AP#15 (Roof) | 2 | 2025-11-04 | 2025-11-05
R7S1ONME-AP15RF559 | Installation of Structure and Solar Panels (For Water Only) - AP#15 (Roof) | 5 | 2025-11-02 | 2025-11-06
R7S1ONME-AP15RF560 | Installation of Solar Calorifier Tank & Air cooler (For Water Only) - AP#15 (Roof) | 5 | 2025-11-04 | 2025-11-09
R7S1ONME-AP15RF562 | Installation of Solar Pipes Primary Loop - AP#15 (Roof) | 5 | 2025-11-04 | 2025-11-09
R7S1ONME-AP15RF563 | Testing of Solar Pipes Primary Loop - AP#15 (Roof) | 1 | 2025-11-10 | 2025-11-10
R7S1ONME-AP15RF564 | Insulation of Solar Pipes Primary Loop - AP#15 (Roof) | 1 | 2025-11-10 | 2025-11-10
R7S1ONME-AP15RF565 | Aluminum Cladding of Solar Pipes Primary Loop - AP#15 (Roof) | 4 | 2025-11-11 | 2025-11-15
ELECTRICAL |  | 26 | 2025-10-27 | 2025-11-17
POWER & LOW CURRENT |  | 26 | 2025-10-27 | 2025-11-17
R7S1ONME-AP15RF551 | Installation of Cables for BMS - AP#15 (Roof) | 3 | 2025-10-27 | 2025-10-29
R7S1ONME-AP15RF524 | Lightening Protection & Earthing System - AP#15 (Roof) | 7 | 2025-10-28 | 2025-11-04
R7S1ONME-AP15RF527 | Installation of Fire Alarm Containment for FAHU, Fans - AP#15 (Roof) | 4 | 2025-11-01 | 2025-11-04
R7S1ONME-AP15RF550 | Installation of Cables for Fire Alarm system - AP#15 (Roof) | 3 | 2025-11-02 | 2025-11-04
R7S1ONME-AP15RF552 | Installation of Fire Alarm Devices - AP#15 (Roof) | 3 | 2025-11-02 | 2025-11-04
R7S1ONME-AP15RF554 | Installation of Roof Light Fixtures - AP#15 (Roof) | 3 | 2025-11-02 | 2025-11-04
R7S1ONME-AP15RF526 | Installation of Electrical Containments for BMS - AP#15 (Roof) | 7 | 2025-10-29 | 2025-11-05
R7S1ONME-AP15RF553 | Installation of BMS Devices - AP#15 (Roof) | 4 | 2025-11-02 | 2025-11-05
R7S1ONME-AP15RF557 | Termination for Fire Alarm Device - AP#15 (Roof) | 1 | 2025-11-05 | 2025-11-05
R7S1ONME-AP15RF525 | Installation of Isolators and Machine Connections - AP#15 (Roof) | 5 | 2025-11-02 | 2025-11-06
R7S1ONME-AP15RF556 | Termination for BMS System - AP#15 (Roof) | 1 | 2025-11-06 | 2025-11-06
R7S1ONME-AP15RF568 | Termination of Primary & Secondary pump for Solar system - AP#15 (Roof) | 1 | 2025-11-06 | 2025-11-06
R7S1ONME-AP15RF528 | Installation of LV Power Cables for Roof Equipment - AP#15 (Roof) | 3 | 2025-11-05 | 2025-11-08
R7S1ONME-AP15RF555 | Termination for LV Cables - AP#15 (Roof) | 1 | 2025-11-09 | 2025-11-09
R7S1ONME-AP15RF558 | Megger Test for the Power Cables - AP#15 (Roof) | 1 | 2025-11-10 | 2025-11-10
R7S1ONME-AP15RF567 | Installation & Termination of Solar System Panel - AP#15 (Roof) | 3 | 2025-11-15 | 2025-11-17
STAIR CASE |  | 91 | 2025-09-22 | 2025-11-19
CIVIL WORKS |  | 70 | 2025-09-30 | 2025-11-15
STAIR CASE (MAIN WITH LIFT) |  | 66 | 2025-09-30 | 2025-10-27
R7S1ONST-AP15RG512 | Stair Flooring (Roof to GF) - AP#15 (Main Stair) | 7 | 2025-09-30 | 2025-10-07
R7S1ONST-AP15RG513 | Stair Hand Rails (Roof to GF) - AP#15 (Main Stair) | 6 | 2025-10-08 | 2025-10-14
R7S1ONST-AP15RG514 | Stair Paint - Primer & 1st Coat (Roof to GF)- AP#15 (Main Stair) | 7 | 2025-10-15 | 2025-10-22
R7S1ONST-AP15RG515 | Stair Paint - Final Coat (Roof to GF)- AP#15 (Main Stair) | 4 | 2025-10-23 | 2025-10-27
STAIR CASE (LEFT SIDE) |  | 61 | 2025-10-08 | 2025-11-02
R7S1ONST-AP15RG522 | Stair Flooring (Roof to GF) - AP#15 Left Side Stair | 7 | 2025-10-08 | 2025-10-15
R7S1ONST-AP15RG523 | Stair Hand Rails (Roof to GF) - AP#15 Left Side Stair | 6 | 2025-10-16 | 2025-10-22
R7S1ONST-AP15RG524 | Stair Paint - Primer & 1st Coat (Roof to GF) - AP#15 Left Side Stair | 6 | 2025-10-23 | 2025-10-29
R7S1ONST-AP15RG525 | Stair Paint - Final Coat (Roof to GF) - AP#15 Left Side Stair | 3 | 2025-10-30 | 2025-11-02
STAIR CASE (RIGHT SIDE) |  | 57 | 2025-10-16 | 2025-11-15
R7S1ONST-AP15RG526 | Stair Flooring (Roof to GF) - AP#15 Right Side Stair | 8 | 2025-10-16 | 2025-10-25
R7S1ONST-AP15RG527 | Stair Hand Rails (Roof to GF) - AP#15 Right Side Stair | 7 | 2025-10-26 | 2025-11-02
R7S1ONST-AP15RG528 | Stair Paint - Primer & 1st Coat (Roof to GF) - AP#15 Right Side Stair | 7 | 2025-11-03 | 2025-11-10
R7S1ONST-AP15RG529 | Stair Paint - Final Coat (Roof to GF) - AP#15 Right Side Stair | 4 | 2025-11-11 | 2025-11-15
MEP WORKS |  | 60 | 2025-09-22 | 2025-11-19
STAIR CASE (MAIN WITH LIFT) |  | 54 | 2025-09-22 | 2025-11-01
R7S1ONST-AP15RG511 | Main Staircase Wire Pulling - AP#15 (Main Stair) | 3 | 2025-09-22 | 2025-09-25
R7S1ONST-AP15RG530 | Final fix - Main Staircase Lights Fixtures & Motion Sensor - AP#15 (Main Stair) | 2 | 2025-10-28 | 2025-10-29
R7S1ONST-AP15RG531 | Final fix - Main Staircase Emergency Lights Fixtures - AP#15 (Main Stair) | 2 | 2025-10-30 | 2025-11-01
STAIR CASE (LEFT SIDE) |  | 53 | 2025-09-27 | 2025-11-06
R7S1ONST-AP15RG516 | Left Staircase Wire Pulling - AP#15 (Main Stair) | 3 | 2025-09-27 | 2025-09-29
R7S1ONST-AP15RG518 | Final fix - Left Staircase Lights Fixtures & Motion Sensor - AP#15 (Main Stair) | 2 | 2025-11-03 | 2025-11-04
R7S1ONST-AP15RG520 | Final fix - Left Staircase Emergency Lights Fixtures - AP#15 (Main Stair) | 2 | 2025-11-05 | 2025-11-06
STAIR CASE (RIGHT SIDE) |  | 54 | 2025-09-30 | 2025-11-19
R7S1ONST-AP15RG517 | Right Staircase Wire Pulling - AP#15 (Main Stair) | 3 | 2025-09-30 | 2025-10-02
R7S1ONST-AP15RG519 | Final fix - Right Staircase Lights Fixtures & Motion Sensor - AP#15 (Main Stair) | 2 | 2025-11-16 | 2025-11-17
R7S1ONST-AP15RG521 | Final fix - Right Staircase Emergency Lights Fixtures - AP#15 (Main Stair) | 2 | 2025-11-18 | 2025-11-19
ELEVATOR WORKS |  | 32 | 2025-09-30 | 2025-10-25
R7S1ONEL-AP15GR661 | Installation of Rails - AP#15 (Elevator Works) | 6 | 2025-09-30 | 2025-10-06
R7S1ONEL-AP15GR662 | Assembly of Cabin - AP#15 (Elevator Works) | 4 | 2025-10-07 | 2025-10-11
R7S1ONEL-AP15GR663 | Installation of Motor - AP#15 (Elevator Works) | 4 | 2025-10-12 | 2025-10-15
R7S1ONEL-AP15GR664 | Installation of Main Cables - AP#15 (Elevator Works) | 4 | 2025-10-16 | 2025-10-20
R7S1ONEL-AP15GR665 | Installation of Doors, Indicator, Push Button - AP#15 (Elevator Works) | 2 | 2025-10-21 | 2025-10-22
R7S1ONEL-AP15GR666 | Interior Finishes - AP#15 (Elevator Works) | 2 | 2025-10-23 | 2025-10-25
EXTERNAL ELEVATIONS |  | 89 | 2025-10-09 | 2025-11-06
ARCH./ CIVIL WORKS |  | 89 | 2025-10-09 | 2025-11-06
R7S1ONEE-AP15GR541 | External Selant Works - For Boxes - AP#15 (External Elevations) | 15 | 2025-10-09 | 2025-10-26
R7S1ONME-AP15GF929 | Installation of rain water outlet - External façade - AP#15 (External Elevations) | 2 | 2025-11-01 | 2025-11-02
R7S1ONEE-AP15GR542 | Final Finishes & Touchups - AP#15 (External Elevations) | 15 | 2025-10-16 | 2025-11-02
R7S1ONEE-AP15GR543 | Fixing Cage Ladder - AP#15 (External Elevations) | 2 | 2025-11-05 | 2025-11-06
R7S1ONEE-AP15GR544 | Installation of External Signages - AP#15 (External Elevations) | 4 | 2025-11-03 | 2025-11-06
EXTERNAL - CIVIL WORKS |  | 27 | 2025-10-25 | 2025-11-11
DRAINAGE |  | 6 | 2025-10-25 | 2025-11-06
R7S1ONECW-AP15-451 | Excavation Works & Sand Bedding - AP#15 (External Drainage) | 3 | 2025-10-25 | 2025-10-27
R7S1ONECW-AP15-452 | Drainage Manholes - AP#15 | 6 | 2025-10-25 | 2025-10-30
R7S1ONECW-AP15-453 | Drainage Backfilling - AP#15 | 2 | 2025-11-05 | 2025-11-06
WATERSUPPLY |  | 7 | 2025-10-25 | 2025-11-10
R7S1ONECW-AP15-454 | Excavation Works & Sand Bedding - Watersupply - AP#15 (External Watersupply Civil) | 3 | 2025-10-25 | 2025-10-27
R7S1ONECW-AP15-455 | Watersupply Manholes - AP#15 | 6 | 2025-10-25 | 2025-10-30
R7S1ONECW-AP15-456 | Watersupply Backfilling - AP#15 | 2 | 2025-11-09 | 2025-11-10
CHILLED WATER |  | 8 | 2025-10-25 | 2025-11-02
R7S1ONECW-AP15-460 | Excavation Works & Sand Bedding - AP#15 (External Chilled Water Civil) | 3 | 2025-10-25 | 2025-10-27
R7S1ONECW-AP15-461 | Chilled Water Manholes - AP#15 | 6 | 2025-10-25 | 2025-10-30
R7S1ONECW-AP15-462 | Chilled Water Backfilling - AP#15 | 2 | 2025-11-01 | 2025-11-02
FIRE FIGHTING |  | 8 | 2025-10-25 | 2025-11-11
R7S1ONECW-AP15-457 | Excavation Works & Sand Bedding - AP#15 (External Chilled Water Civil) | 3 | 2025-10-25 | 2025-10-27
R7S1ONECW-AP15-458 | Fire Fighting Manholes - AP#15 | 6 | 2025-10-25 | 2025-10-30
R7S1ONECW-AP15-459 | Fire Fighting Backfilling - AP#15 | 2 | 2025-11-10 | 2025-11-11
POWER |  | 16 | 2025-10-25 | 2025-11-02
R7S1ONECW-AP15-463 | Excavation Works & Sand Bedding - AP#15 (External Power Civil) | 3 | 2025-10-25 | 2025-10-27
R7S1ONECW-AP15-464 | Power Manholes - AP#15 | 3 | 2025-10-25 | 2025-10-27
R7S1ONECW-AP15-465 | Power Backfilling - AP#15 | 2 | 2025-10-30 | 2025-11-02
LOW CURRENT |  | 25 | 2025-10-28 | 2025-11-05
R7S1ONECW-AP15-466 | Excavation Works & Sand Bedding - AP#15 (External Low Current Civil) | 3 | 2025-10-28 | 2025-10-30
R7S1ONECW-AP15-467 | Low Current Manholes - AP#15 | 3 | 2025-10-28 | 2025-10-30
R7S1ONECW-AP15-468 | Low Current Backfilling - AP#15 | 2 | 2025-11-04 | 2025-11-05
EXTERNAL - MEP SERVICES |  | 23 | 2025-10-28 | 2025-11-10
DRAINAGE |  | 4 | 2025-11-01 | 2025-11-04
R7S1ONEME-AP15-291 | External Drainage Network - AP#15 (External Drainage MEP) | 4 | 2025-11-01 | 2025-11-04
WATERSUPPLY |  | 4 | 2025-11-01 | 2025-11-10
R7S1ONEME-AP15-292 | PRV statiuon assembly including meters- AP#15 (External WS MEP) | 4 | 2025-11-01 | 2025-11-04
R7S1ONEME-AP15-294 | Installation of valve station incl. BTU meter- AP#15 (External WS MEP) | 3 | 2025-11-08 | 2025-11-10
CHILLED WATER |  | 7 | 2025-11-01 | 2025-11-08
R7S1ONEME-AP15-293 | Installation of Chilled water line- AP#15 (External CWP MEP) | 6 | 2025-11-01 | 2025-11-06
R7S1ONEME-AP15-295 | Pressure Test for chilled water line- AP#15 (External CWP MEP) | 1 | 2025-11-08 | 2025-11-08
FIRE FIGHTING |  | 11 | 2025-10-28 | 2025-11-09
R7S1ONEME-AP15-296 | Installation of External FF network - AP#15 (External FF MEP) | 6 | 2025-10-28 | 2025-11-03
R7S1ONEME-AP15-297 | Installation of Alarm check valves- AP#15 (External FF MEP) | 3 | 2025-11-04 | 2025-11-06
R7S1ONEME-AP15-298 | Testing of External FF - AP#15 (External FF MEP) | 2 | 2025-11-08 | 2025-11-09
POWER |  | 1 | 2025-10-29 | 2025-10-30
R7S1ONEME-AP15-299 | Cable pulling from Manhole to the building MDB - AP#15 (External Power MEP) | 1 | 2025-10-29 | 2025-10-30
LOW CURRENT |  | 3 | 2025-11-01 | 2025-11-03
R7S1ONEME-AP15-300 | Low Current Cable pulling- AP#15 (External FF MEP) | 3 | 2025-11-01 | 2025-11-03
INFRA WORKS INCLUDE HUBS |  | 293 | 2025-02-11 | 2025-12-22
EV - 16 HUB (SECONDARY) |  | 205 | 2025-04-26 | 2025-12-22
SUB-STRUCTURE |  | 33 | 2025-04-26 | 2025-05-22
R7S1-ONSB-EV16-250 | Site Setting Out Works - EV16 | 1 | 2025-04-26 | 2025-04-26
R7S1-ONSB-EV16-220 | Site levelling & earthworks - EV16 | 3 | 2025-04-27 | 2025-04-29
R7S1-ONSB-EV16-260 | Anti-termite & Polythene Sheet Works - EV16 | 2 | 2025-04-29 | 2025-04-30
R7S1-ONSB-EV16-230 | Blinding PCC - EV16 | 4 | 2025-04-30 | 2025-05-04
R7S1-ONSB-EV16-240 | Waterproofing for Blinding PCC (Bitumen Paint) - EV16 | 2 | 2025-05-04 | 2025-05-05
R7S1-ONSB-EV16-270 | Foundations/Trenches - Rebar - EV16 | 6 | 2025-05-05 | 2025-05-11
R7S1-ONSB-EV16-280 | Foundations/Trenches - Shuttering (Including dowel Works) - EV16 | 6 | 2025-05-08 | 2025-05-14
R7S1-ONSB-EV16-310 | Installation of MEP U/G services below Boxes - EV16 | 4 | 2025-05-13 | 2025-05-17
R7S1-ONSB-EV16-290 | Foundations/Upstands - Casting - EV16 | 1 | 2025-05-18 | 2025-05-18
R7S1-ONSB-EV16-300 | Waterproofing For Foundations/Upstands - EV16 | 1 | 2025-05-19 | 2025-05-19
R7S1-ONSB-EV16-320 | Backfilling/Subbase & Compaction - EV16 | 3 | 2025-05-20 | 2025-05-22
TRENCH WORKS OUTSIDE THE HUB |  | 18 | 2025-09-02 | 2025-09-30
R7S1-ONSB-EV16-330 | Earthworks for Trenches - EV16 | 2 | 2025-09-02 | 2025-09-04
R7S1-ONSB-EV16-340 | Blinding PCC for Trenches - EV16 | 2 | 2025-09-04 | 2025-09-07
R7S1-ONSB-EV16-350 | Foundations/Trenches - Rebar - EV16 | 6 | 2025-09-07 | 2025-09-14
R7S1-ONSB-EV16-360 | MEP UG Services - EV16 | 6 | 2025-09-08 | 2025-09-15
R7S1-ONSB-EV16-370 | Trenches - Shuttering - EV16 | 6 | 2025-09-10 | 2025-09-17
R7S1-ONSB-EV16-380 | Trenches - Concrete - EV16 | 1 | 2025-09-17 | 2025-09-18
R7S1-ONSB-EV16-390 | Waterproofing For Trenches - EV16 | 1 | 2025-09-18 | 2025-09-20
R7S1-ONSB-EV16-400 | Backfilling - EV16 | 3 | 2025-09-20 | 2025-09-24
R7S1-ONSB-EV16-410 | Slab on Grade works - EV16 | 5 | 2025-09-24 | 2025-09-30
ERECTION WORKS |  | 8 | 2025-08-31 | 2025-09-09
R7S1-ONER-EV16-120 | Erection of Boxes - EV16 | 2 | 2025-08-31 | 2025-09-02
R7S1-ONER-EV16-130 | Erection of Loose Loose Elements - EV16 | 6 | 2025-09-02 | 2025-09-09
INSIDE HUBS (MEP & CIVIL FINISHES) |  | 113 | 2025-09-09 | 2025-11-08
CIVIL WORKS / FINISHES INSIDE THE HUB & ROOF |  | 113 | 2025-09-09 | 2025-11-08
R7S1-ONFIN-EV16-230 | Roof Stiching Works - EV16 | 8 | 2025-09-09 | 2025-09-18
R7S1-ONFIN-EV16-270 | Installation of Roof Drain Works - EV16 | 3 | 2025-09-18 | 2025-09-22
R7S1-ONFIN-EV16-220 | Roof Waterproofing works & Test - EV16 | 15 | 2025-09-18 | 2025-10-07
R7S1-ONFIN-EV16-280 | Installation of Roof Water pipes - EV16 | 2 | 2025-10-07 | 2025-10-09
R7S1-ONFIN-EV16-240 | Internal final paint - EV16 | 8 | 2025-10-07 | 2025-10-16
R7S1-ONFIN-EV16-250 | External final paint (including parapets) - EV16 | 10 | 2025-10-25 | 2025-11-05
R7S1-ONFIN-EV16-260 | Installation of Cage Ladder - EV16 | 2 | 2025-11-05 | 2025-11-08
MEP WORKS |  | 101 | 2025-09-18 | 2025-11-05
MECHANICAL |  | 37 | 2025-09-18 | 2025-10-23
CHILLED WATER |  | 37 | 2025-09-18 | 2025-10-19
R7S1-MECH-EV16-600 | Chilled water pump connection Works - EV16 | 5 | 2025-09-18 | 2025-09-25
R7S1-MECH-EV16-610 | Chemical Dosing unit connection Work - EV16 | 5 | 2025-09-21 | 2025-09-28
R7S1-MECH-EV16-620 | Pressurization unit -connection Work - EV16 | 5 | 2025-09-25 | 2025-10-01
R7S1-MECH-EV16-625 | Installation of Expansion Tank - EV16 | 6 | 2025-09-24 | 2025-10-01
R7S1-MECH-EV16-628 | Installation of Air Separator - EV16 | 6 | 2025-09-25 | 2025-10-02
R7S1-MECH-EV16-770 | Installation of EX-Fan - EV16 | 1 | 2025-10-02 | 2025-10-04
R7S1-MECH-EV16-730 | Installation of External Out door unit for DX Split A/C - EV16 | 6 | 2025-09-30 | 2025-10-07
R7S1-MECH-EV16-630 | Installation of CHW Pipes/Valves/Fittings - EV16 | 18 | 2025-09-28 | 2025-10-19
WATER SUPPLY |  | 23 | 2025-09-18 | 2025-10-19
R7S1-MECH-EV16-640 | Installation of GRP Tank - EV16 | 10 | 2025-09-18 | 2025-10-01
R7S1-MECH-EV16-650 | Booster Pumps connection Works - EV16 | 4 | 2025-09-27 | 2025-10-01
R7S1-MECH-EV16-660 | Ionization Filter connection Works - EV16 | 4 | 2025-10-01 | 2025-10-06
R7S1-MECH-EV16-670 | Connection of WS Pipes/Valves/Fittings - EV16 | 18 | 2025-09-28 | 2025-10-19
DRAINAGE |  | 24 | 2025-09-30 | 2025-10-23
R7S1-MECH-EV16-750 | Installation of Trench drain - EV16 | 4 | 2025-09-30 | 2025-10-05
R7S1-MECH-EV16-760 | Installation of External Manhole & UPVC pipes - EV16 | 4 | 2025-09-30 | 2025-10-05
R7S1-MECH-EV16-720 | Installation of PVC pipes for A/C drain with insulation - EV16 | 6 | 2025-10-07 | 2025-10-14
R7S1-MECH-EV16-740 | Installation of UPVC pipes for GRP tank overflow drain with valves - EV16 | 4 | 2025-10-19 | 2025-10-23
FIRE FIGHTING |  | 22 | 2025-09-18 | 2025-10-11
R7S1-MECH-EV16-680 | Fire Fighting Piping installation - EV16 | 8 | 2025-09-18 | 2025-09-29
R7S1-MECH-EV16-710 | NOVEC system installation - EV16 | 6 | 2025-09-29 | 2025-10-06
R7S1-MECH-EV16-690 | Sprinkler installation - EV16 | 2 | 2025-10-06 | 2025-10-08
R7S1-MECH-EV16-700 | FHRC / FE's Installation - EV16 | 2 | 2025-10-08 | 2025-10-11
ELECTRICAL |  | 101 | 2025-09-18 | 2025-11-05
POWER & LIGHTING |  | 101 | 2025-09-18 | 2025-10-25
R7S1-ELEC-EV16-390 | Cable Tray / Trunking continuation (for power & Low current) - EV16 | 6 | 2025-09-18 | 2025-09-27
R7S1-ELEC-EV16-400 | Pulling of wires - EV16 | 6 | 2025-09-21 | 2025-09-29
R7S1-ELEC-EV16-500 | Installation of Harmonic Filters - EV16 | 4 | 2025-09-29 | 2025-10-04
R7S1-ELEC-EV16-510 | Installation of Capacitor Banks - EV16 | 4 | 2025-09-29 | 2025-10-04
R7S1-ELEC-EV16-420 | Wiring Accessories installation - EV16 | 6 | 2025-09-29 | 2025-10-06
R7S1-ELEC-EV16-410 | Installation of DBs/MDBs/SMDBs (Electrical Power) - EV16 | 6 | 2025-09-30 | 2025-10-07
R7S1-ELEC-EV16-540 | Installation of DBs/MDBs/SMDBs for Chilled Water Pumps - EV16 | 6 | 2025-09-30 | 2025-10-07
R7S1-ELEC-EV16-550 | Installation of DBs/MDBs/SMDBs for Booster Pumps - EV16 | 6 | 2025-10-02 | 2025-10-09
R7S1-ELEC-EV16-470 | Electrical Cables Installation for SMDBS- EV16 | 6 | 2025-10-04 | 2025-10-11
R7S1-ELEC-EV16-480 | Electrical Cable Termination - EV16 | 3 | 2025-10-11 | 2025-10-14
R7S1-ELEC-EV16-490 | Installation of Light Fittings - EV16 | 2 | 2025-10-14 | 2025-10-16
R7S1-ELEC-EV16-520 | Termination of Harmonic Filters - EV16 | 3 | 2025-10-14 | 2025-10-18
R7S1-ELEC-EV16-530 | Termination of Capacitor Banks - EV16 | 3 | 2025-10-14 | 2025-10-18
R7S1-ELEC-EV16-620 | Installation of Louvers - EV16 | 6 | 2025-10-18 | 2025-10-25
EARTHING |  | 8 | 2025-10-02 | 2025-10-14
R7S1-ELEC-EV16-590 | Installation of Copper Tape at Roof - EV16 | 6 | 2025-10-02 | 2025-10-09
R7S1-ELEC-EV16-600 | Installation of Earth Pit with SS rod - EV16 | 6 | 2025-10-05 | 2025-10-12
R7S1-ELEC-EV16-610 | Installation of Grounding Conductor with Equipment termination - EV16 | 6 | 2025-10-07 | 2025-10-14
LOW CURRENT SYSTEM |  | 48 | 2025-09-27 | 2025-11-05
R7S1-ELEC-EV16-430 | Installation of ICT Pipes & ICT Cables - EV16 | 12 | 2025-09-27 | 2025-10-11
R7S1-ELEC-EV16-630 | Installation of Firalarm Conduits - EV16 | 12 | 2025-09-27 | 2025-10-11
R7S1-ELEC-EV16-560 | Installation of Security System Pipes & ICT Cables - EV16 | 12 | 2025-09-28 | 2025-10-12
R7S1-ELEC-EV16-570 | Installation of BMS Pipes & Cables - EV16 | 12 | 2025-10-01 | 2025-10-15
R7S1-ELEC-EV16-640 | Installation of Firalarm Devices with Termination - EV16 | 12 | 2025-10-04 | 2025-10-18
R7S1-ELEC-EV16-660 | Installation of BMS DDC Panel with Termination - EV16 | 12 | 2025-10-08 | 2025-10-22
R7S1-ELEC-EV16-440 | ICT Equipment with Racks installation - EV16 | 12 | 2025-10-11 | 2025-10-25
R7S1-ELEC-EV16-650 | Installation of Monitor Module/Control Module with Termination - EV16 | 6 | 2025-10-18 | 2025-10-25
R7S1-ELEC-EV16-450 | Security System installation & Termination - EV16 | 12 | 2025-10-12 | 2025-10-26
R7S1-ELEC-EV16-460 | Access control installation - EV16 | 12 | 2025-10-19 | 2025-11-02
R7S1-ELEC-EV16-580 | Termination of BMS Cables with Field Device - EV16 | 12 | 2025-10-22 | 2025-11-05
EXTERNAL CIVIL & MEP WORKS |  | 18 | 2025-09-24 | 2025-10-15
R7S2-MECH-EV16-610 | External MEP & Civil Works - EV16 | 18 | 2025-09-24 | 2025-10-15
TESTING & COMMISSIONING |  | 78 | 2025-10-14 | 2025-12-04
ELECTRICAL |  | 78 | 2025-10-14 | 2025-12-04
POWER/SMDBs |  | 7 | 2025-10-14 | 2025-10-23
R7S1ONTCE-EV16-270 | T&C - Earthing & Lightening System - EV16 | 4 | 2025-10-14 | 2025-10-19
R7S1ONTCE-EV16-260 | T&C - LV Panel/SMDB & Energizing Panel (Power-On) - EV16 | 4 | 2025-10-19 | 2025-10-23
FIRE ALARM SYSTEM |  | 6 | 2025-10-25 | 2025-11-01
R7S1ONTCE-EV16-280 | T&C - Fire Alarm System - EV16 | 6 | 2025-10-25 | 2025-11-01
ICT SYSTEM |  | 6 | 2025-11-27 | 2025-12-04
R7S1ONTCE-EV16-290 | T&C - ICT System - EV16 | 6 | 2025-11-27 | 2025-12-04
SECURITY SYSTEM |  | 64 | 2025-10-28 | 2025-11-12
R7S1ONTCE-EV16-300 | T&C - Security System - EV16 | 6 | 2025-10-28 | 2025-11-03
R7S1ONTCE-EV16-310 | T&C - Access Control System - EV16 | 6 | 2025-11-02 | 2025-11-09
R7S1ONTCE-EV16-320 | T&C - BMS System - EV16 | 6 | 2025-11-05 | 2025-11-12
MECHANICAL |  | 59 | 2025-10-23 | 2025-11-25
CHILLED WATER |  | 32 | 2025-10-23 | 2025-11-25
R7S1ONTCM-EV16-290 | T&C - Chilled Water Pump - EV16 | 4 | 2025-10-23 | 2025-10-28
R7S1ONTCM-EV16-300 | T&C - CHW Flushing - EV16 | 18 | 2025-10-28 | 2025-11-18
R7S1ONTCM-EV16-280 | T&C - CHW Final Chemical - EV16 | 3 | 2025-11-18 | 2025-11-22
R7S1ONTCM-EV16-310 | T&C - CHW - Water Balancing - EV16 | 6 | 2025-11-18 | 2025-11-25
WATER SUPPLY |  | 58 | 2025-10-23 | 2025-11-13
R7S1ONTCM-EV16-330 | T&C - WS Pump - EV16 | 6 | 2025-10-23 | 2025-10-30
R7S1ONTCM-EV16-340 | T&C - WS Flushing - EV16 | 4 | 2025-10-30 | 2025-11-04
R7S1ONTCM-EV16-320 | T&C - WS Disinfection - EV16 | 6 | 2025-11-04 | 2025-11-11
R7S1ONTCM-EV16-350 | T&C - WS - Water Balancing (Mustadam) - EV16 | 8 | 2025-11-04 | 2025-11-13
DRAINAGE |  | 4 | 2025-10-23 | 2025-10-28
R7S1ONTCM-EV16-360 | T&C - Drainage System - EV16 | 4 | 2025-10-23 | 2025-10-28
FIRE FIGHTING |  | 37 | 2025-10-23 | 2025-11-03
R7S1ONTCM-EV16-370 | T&C - NOVEC (3 systems) - EV16 | 8 | 2025-10-23 | 2025-11-02
R7S1ONTCM-EV16-380 | T&C - Fire Fighting System - EV16 | 9 | 2025-10-23 | 2025-11-03
SNAGGING / DESNAGGING |  | 52 | 2025-12-04 | 2025-12-22
R7S1ONSNG-EV16-100 | Receipt of Preliminary Snag List From Employer - EV16 | 2 | 2025-12-04 | 2025-12-07
R7S1ONSNG-EV16-110 | De-Snagging of Preliminary Snags For Civil/MEP Activities - EV16 | 5 | 2025-12-07 | 2025-12-13
R7S1ONSNG-EV16-120 | O & M / Training - EV16 | 5 | 2025-12-10 | 2025-12-16
R7S1ONSNG-EV16-130 | Asbuilt - EV16 | 5 | 2025-12-13 | 2025-12-18
R7S1ONSNG-EV16-140 | Warranties / Guarantees / Spare Parts - EV16 | 5 | 2025-12-15 | 2025-12-21
R7S1ONSNG-EV16-150 | Acknowledgement of Final Snags Closure - EV16 | 4 | 2025-12-17 | 2025-12-22
INFRA WORKS (SECONDARY NETWORK) |  | 257 | 2025-02-11 | 2025-12-16
SECTION - 03 (AROUND AP-17,18 & 19) |  | 234 | 2025-02-11 | 2025-11-27
DRAINAGE WORKS |  | 54 | 2025-09-04 | 2025-11-08
R7S1-INF-SC3-DR-160 | Manhole Excavation (Section - 03 around AP-17,18 & 19) | 6 | 2025-09-04 | 2025-09-10
R7S1-INF-SC3-DR-170 | Maholes Construction (Section - 03 around AP-17,18 & 19) | 15 | 2025-09-08 | 2025-09-25
R7S1-INF-SC3-DR-180 | Excavation for Drainage line (Section - 03 around AP-17,18 & 19) | 15 | 2025-09-10 | 2025-09-28
R7S1-INF-SC3-DR-190 | Laying of Drainage Pipes & Connection (Section - 03 around AP-17,18 & 19) | 15 | 2025-09-13 | 2025-09-30
R7S1-INF-SC3-DR-200 | Testing (Section - 03 around AP-17,18 & 19) | 6 | 2025-09-27 | 2025-10-02
R7S1-INF-SC3-DR-210 | Backfilling+Warning Tape (Section - 03 around AP-17,18 & 19) | 9 | 2025-10-28 | 2025-11-08
CHILLED WATER WORKS |  | 66 | 2025-09-08 | 2025-11-18
R7S1-INF-SC3-CW-230 | Manhole Excavation (Section - 03 around AP-17,18 & 19) | 15 | 2025-09-08 | 2025-09-25
R7S1-INF-SC3-CW-240 | Maholes Construction (Section - 03 around AP-17,18 & 19) | 15 | 2025-09-11 | 2025-09-29
R7S1-INF-SC3-CW-250 | Excavation for CHWP line (Section - 03 around AP-17,18 & 19) | 15 | 2025-09-30 | 2025-10-16
R7S1-INF-SC3-CW-260 | Laying of CH Pipes & VALVES (Section - 03 around AP-17,18 & 19) | 15 | 2025-10-04 | 2025-10-20
R7S1-INF-SC3-CW-270 | Pressure Testing (Section - 03 around AP-17,18 & 19) | 6 | 2025-10-16 | 2025-10-22
R7S1-INF-SC3-CW-280 | Backfilling+Warning Tape (Section - 03 around AP-17,18 & 19) | 9 | 2025-10-18 | 2025-10-27
R7S1-INF-SC3-CW-290 | Chilled Water Pipes Flushing (Section - 03 around AP-17,18 & 19) | 18 | 2025-10-28 | 2025-11-18
WATER SUPPLY WORKS |  | 229 | 2025-02-11 | 2025-11-17
R7S1-INF-SC3-WS-160 | Manhole Excavation (Section - 03 around AP-17,18 & 19) | 15 | 2025-09-11 | 2025-09-29
R7S1-INF-SC3-WS-170 | Maholes Construction (Section - 03 around AP-17,18 & 19) | 15 | 2025-09-30 | 2025-10-16
R7S1-INF-SC3-WS-180 | Excavation for WS line (Section - 03 around AP-17,18 & 19) | 206 | 2025-02-11 | 2025-10-21
R7S1-INF-SC3-WS-190 | Laying of WS Pipes & VALVES (Section - 03 around AP-17,18 & 19) | 202 | 2025-02-16 | 2025-10-21
R7S1-INF-SC3-WS-200 | Pressure Testing (Section - 03 around AP-17,18 & 19) | 173 | 2025-03-25 | 2025-10-23
R7S1-INF-SC3-WS-210 | Backfilling+Warning Tape (Section - 03 around AP-17,18 & 19) | 187 | 2025-04-07 | 2025-11-17
FIRE PROTECTION WORKS |  | 217 | 2025-02-11 | 2025-11-03
R7S1-INF-SC3-FP-160 | Manhole Excavation (Section - 03 around AP-17,18 & 19) | 15 | 2025-09-15 | 2025-10-02
R7S1-INF-SC3-FP-170 | Maholes Construction (Section - 03 around AP-17,18 & 19) | 15 | 2025-09-18 | 2025-10-06
R7S1-INF-SC3-FP-180 | Excavation for FP line (Section - 03 around AP-17,18 & 19) | 197 | 2025-02-11 | 2025-10-11
R7S1-INF-SC3-FP-190 | Laying of FF Pipes & VALVES (Section - 03 around AP-17,18 & 19) | 196 | 2025-02-16 | 2025-10-14
R7S1-INF-SC3-FP-210 | Backfilling+Warning Tape (Section - 03 around AP-17,18 & 19) | 172 | 2025-04-07 | 2025-10-30
R7S1-INF-SC3-FP-200 | Pressure Testing (Section - 03 around AP-17,18 & 19) | 182 | 2025-03-25 | 2025-11-03
POWER - ELECTRICAL |  | 36 | 2025-09-18 | 2025-10-16
R7S1-INF-SC3-PO-150 | Manhole Excavation (Section - 03 around AP-17,18 & 19) | 15 | 2025-09-18 | 2025-10-06
R7S1-INF-SC3-PO-160 | Maholes Construction (Section - 03 around AP-17,18 & 19) | 15 | 2025-09-21 | 2025-10-08
R7S1-INF-SC3-PO-170 | Excavation for LV Cable (Section - 03 around AP-17,18 & 19) | 15 | 2025-09-24 | 2025-10-11
R7S1-INF-SC3-PO-180 | Laying of LV Cable (Section - 03 around AP-17,18 & 19) | 15 | 2025-09-28 | 2025-10-14
R7S1-INF-SC3-PO-190 | Backfilling+Warning Tape (Section - 03 around AP-17,18 & 19) | 12 | 2025-10-04 | 2025-10-16
SECURITY SYSTEM (CCTV & ACCESS CONTROL) - ELECTRICAL |  | 38 | 2025-09-27 | 2025-10-23
R7S1-INF-SC3-ELV-150 | Manhole Excavation (Section - 03 around AP-17,18 & 19) | 6 | 2025-09-27 | 2025-10-02
R7S1-INF-SC3-ELV-160 | Maholes Construction (Section - 03 around AP-17,18 & 19) | 15 | 2025-09-30 | 2025-10-16
R7S1-INF-SC3-ELV-170 | Excavation for ELV Cable (Section - 03 around AP-17,18 & 19) | 15 | 2025-10-02 | 2025-10-19
R7S1-INF-SC3-ELV-180 | Laying of ELV Cable (Section - 03 around AP-17,18 & 19) | 15 | 2025-10-05 | 2025-10-21
R7S1-INF-SC3-ELV-190 | Backfilling+Warning Tape (Section - 03 around AP-17,18 & 19) | 12 | 2025-10-11 | 2025-10-23
ICT - ELECTRICAL |  | 54 | 2025-10-04 | 2025-11-27
R7S1-INF-SC3-ICT-150 | Manhole Excavation (Section - 03 around AP-17,18 & 19) | 6 | 2025-10-04 | 2025-10-09
R7S1-INF-SC3-ICT-160 | Maholes Construction (Section - 03 around AP-17,18 & 19) | 15 | 2025-10-07 | 2025-10-23
R7S1-INF-SC3-ICT-170 | Excavation for ICT Cable (Section - 03 around AP-17,18 & 19) | 15 | 2025-10-09 | 2025-10-26
R7S1-INF-SC3-ICT-180 | Laying of Ducts, Road Crossings, ICT Cable Pulling (Section - 03 around AP-17,18 & 19) | 15 | 2025-10-12 | 2025-10-28
R7S1-INF-SC3-ICT-190 | Backfilling+Warning Tape (Section - 03 around AP-17,18 & 19) | 9 | 2025-11-17 | 2025-11-27
SECTION - 04 (AROUND AP-14,15 & 05) |  | 237 | 2025-02-13 | 2025-11-27
DRAINAGE WORKS |  | 47 | 2025-09-15 | 2025-11-17
R7S1-INF-SC4-DR-220 | Manhole Excavation (Section - 04 around AP-14,15 & 16) | 6 | 2025-09-15 | 2025-09-21
R7S1-INF-SC4-DR-230 | Maholes Construction (Section - 04 around AP-14,15 & 16) | 15 | 2025-09-18 | 2025-10-06
R7S1-INF-SC4-DR-240 | Excavation for Drainage line (Section - 04 around AP-14,15 & 16) | 15 | 2025-09-21 | 2025-10-08
R7S1-INF-SC4-DR-250 | Laying of Drainage Pipes (Section - 04 around AP-14,15 & 16) | 15 | 2025-09-24 | 2025-10-11
R7S1-INF-SC4-DR-260 | Testing (Section - 04 around AP-14,15 & 16) | 6 | 2025-10-07 | 2025-10-13
R7S1-INF-SC4-DR-270 | Backfilling+Warning Tape (Section - 04 around AP-14,15 & 16) | 9 | 2025-11-08 | 2025-11-17
CHILLED WATER WORKS |  | 63 | 2025-09-17 | 2025-11-18
R7S1-INF-SC4-CW-240 | Manhole Excavation (Section - 04 around AP-14,15 & 16) | 15 | 2025-09-17 | 2025-10-05
R7S1-INF-SC4-CW-250 | Maholes Construction (Section - 04 around AP-14,15 & 16) | 15 | 2025-09-21 | 2025-10-08
R7S1-INF-SC4-CW-260 | Excavation for CHWP line (Section - 04 around AP-14,15 & 16) | 15 | 2025-09-25 | 2025-10-12
R7S1-INF-SC4-CW-270 | Laying of CH Pipes & VALVES (Section - 04 around AP-14,15 & 16) | 15 | 2025-09-29 | 2025-10-15
R7S1-INF-SC4-CW-280 | Pressure Testing (Section - 04 around AP-14,15 & 16) | 6 | 2025-10-12 | 2025-10-18
R7S1-INF-SC4-CW-290 | Backfilling+Warning Tape (Section - 04 around AP-14,15 & 16) | 6 | 2025-10-13 | 2025-10-19
R7S1-INF-SC4-CW-300 | Chilled Water Pipes Flushing (Section - 04 around AP-14,15 & 16) | 18 | 2025-10-28 | 2025-11-18
WATER SUPPLY WORKS |  | 226 | 2025-02-13 | 2025-11-16
R7S1-INF-SC4-WS-220 | Manhole Excavation (Section - 04 around AP-14,15 & 16) | 15 | 2025-09-25 | 2025-10-12
R7S1-INF-SC4-WS-230 | Maholes Construction (Section - 04 around AP-14,15 & 16) | 15 | 2025-09-29 | 2025-10-15
R7S1-INF-SC4-WS-240 | Excavation for WS line (Section - 04 around AP-14,15 & 16) | 203 | 2025-02-13 | 2025-10-20
R7S1-INF-SC4-WS-250 | Laying of WS Pipes & VALVES (Section - 04 around AP-14,15 & 16) | 205 | 2025-02-15 | 2025-10-23
R7S1-INF-SC4-WS-260 | Pressure Testing (Section - 04 around AP-14,15 & 16) | 167 | 2025-04-08 | 2025-10-26
R7S1-INF-SC4-WS-270 | Backfilling+Warning Tape (Section - 04 around AP-14,15 & 05) | 183 | 2025-04-10 | 2025-11-16
FIRE PROTECTION WORKS |  | 221 | 2025-02-13 | 2025-11-10
R7S1-INF-SC4-FP-220 | Manhole Excavation (Section - 04 around AP-14,15 & 16) | 15 | 2025-10-02 | 2025-10-19
R7S1-INF-SC4-FP-230 | Maholes Construction (Section - 04 around AP-14,15 & 16) | 15 | 2025-10-05 | 2025-10-21
R7S1-INF-SC4-FP-240 | Excavation for FP line (Section - 04 around AP-14,15 & 16) | 207 | 2025-02-13 | 2025-10-25
R7S1-INF-SC4-FP-250 | Laying of FF Pipes & VALVES (Section - 04 around AP-14,15 & 16) | 208 | 2025-02-15 | 2025-10-27
R7S1-INF-SC4-FP-260 | Pressure Testing (Section - 04 around AP-14,15 & 16) | 174 | 2025-04-08 | 2025-11-03
R7S1-INF-SC4-FP-270 | Backfilling+Warning Tape (Section - 04 around AP-14,15 & 16) | 178 | 2025-04-10 | 2025-11-10
POWER - ELECTRICAL |  | 32 | 2025-09-25 | 2025-10-19
R7S1-INF-SC4-PO-200 | Manhole Excavation (Section - 04 around AP-14,15 & 16) | 14 | 2025-09-25 | 2025-10-11
R7S1-INF-SC4-PO-210 | Maholes Construction (Section - 04 around AP-14,15 & 16) | 14 | 2025-09-28 | 2025-10-13
R7S1-INF-SC4-PO-220 | Excavation for LV Cable (Section - 04 around AP-14,15 & 16) | 14 | 2025-09-30 | 2025-10-15
R7S1-INF-SC4-PO-230 | Laying of LV Cable (Section - 04 around AP-14,15 & 16) | 14 | 2025-10-02 | 2025-10-18
R7S1-INF-SC4-PO-240 | Backfilling+Warning Tape (Section - 04 around AP-14,15 & 16) | 9 | 2025-10-09 | 2025-10-19
SECURITY SYSTEM (CCTV & ACCESS CONTROL) - ELECTRICAL |  | 20 | 2025-10-09 | 2025-11-03
R7S1-INF-SC4-ELV-200 | Manhole Excavation (Section - 04 around AP-14,15 & 16) | 6 | 2025-10-09 | 2025-10-15
R7S1-INF-SC4-ELV-210 | Maholes Construction (Section - 04 around AP-14,15 & 16) | 15 | 2025-10-12 | 2025-10-28
R7S1-INF-SC4-ELV-220 | Excavation for ELV Cable (Section - 04 around AP-14,15 & 16) | 15 | 2025-10-13 | 2025-10-29
R7S1-INF-SC4-ELV-230 | Laying of ELV Cable (Section - 04 around AP-14,15 & 16) | 15 | 2025-10-15 | 2025-11-01
R7S1-INF-SC4-ELV-240 | Backfilling+Warning Tape (Section - 04 around AP-14,15 & 16) | 9 | 2025-10-25 | 2025-11-03
ICT - ELECTRICAL |  | 51 | 2025-10-16 | 2025-11-27
R7S1-INF-SC4-ICT-200 | Manhole Excavation (Section - 04 around AP-14,15 & 16) | 6 | 2025-10-16 | 2025-10-22
R7S1-INF-SC4-ICT-210 | Maholes Construction (Section - 04 around AP-14,15 & 16) | 15 | 2025-10-20 | 2025-11-05
R7S1-INF-SC4-ICT-220 | Excavation for LV Cable (Section - 04 around AP-14,15 & 16) | 15 | 2025-10-22 | 2025-11-08
R7S1-INF-SC4-ICT-230 | Laying of Ducts, Road Crossings, ICT Cable Pulling (Section - 04 around AP-14,15 & 16) | 15 | 2025-10-25 | 2025-11-10
R7S1-INF-SC4-ICT-240 | Backfilling+Warning Tape (Section - 04 around AP-14,15 & 16) | 9 | 2025-11-17 | 2025-11-27
TIE-IN CONNECTION (SECTION - 03 & 04) |  | 85 | 2025-08-20 | 2025-11-24
DRAINAGE |  | 50 | 2025-08-20 | 2025-11-11
R7S1-INF-TIE-DR-180 | Drainage Tie-in Connection Works - AP16 (MH-L1-20) | 4 | 2025-08-20 | 2025-08-24
R7S1-INF-TIE-DR-220 | Drainage Tie-in Connection Works - AP17 (MH-L5-10-10) | 4 | 2025-10-04 | 2025-10-07
R7S1-INF-TIE-DR-200 | Drainage Tie-in Connection Works - AP18 (MH-L5-10-4-2) | 4 | 2025-10-08 | 2025-10-12
R7S1-INF-TIE-DR-210 | Drainage Tie-in Connection Works - AP19 (MH-L5-10-4-2) | 4 | 2025-10-13 | 2025-10-16
R7S1-INF-TIE-DR-160 | Drainage Tie-in Connection Works - AP05 (MH-L4-8-2-1) | 4 | 2025-10-20 | 2025-10-23
R7S1-INF-TIE-DR-190 | Drainage Tie-in Connection Works - AP14 (MH-L5-10-11) | 4 | 2025-10-27 | 2025-10-30
R7S1-INF-TIE-DR-170 | Drainage Tie-in Connection Works - AP15 (MH-L1-20) | 4 | 2025-11-08 | 2025-11-11
CHILLED WATER |  | 60 | 2025-10-19 | 2025-11-24
R7S1-INF-TIE-CHW-200 | Connect Pipe from the Heat Exchanger to the Existing Valve Chamber near EV-16 | 2 | 2025-10-19 | 2025-10-21
R7S1-INF-TIE-CHW-210 | Connect Pipe from the Heat Exchanger to Chilled Waterpump | 2 | 2025-10-21 | 2025-10-23
R7S1-INF-TIE-CHW-220 | Open Valve to Flow to the Network (after Flushing) | 1 | 2025-11-23 | 2025-11-24
WATER SUPPLY |  | 4 | 2025-10-19 | 2025-10-23
R7S1-INF-TIE-WS-180 | Watersupply Pipe Laying & Connecting to the Existing Tank Primary Tank to Secondary GRP tank | 4 | 2025-10-19 | 2025-10-23
FIRE PROTECTION |  | 7 | 2025-11-03 | 2025-11-11
R7S1-INF-TIE-FF-170 | Close Valves (2 Nos) near AP15 & 14 | 1 | 2025-11-03 | 2025-11-04
R7S1-INF-TIE-FF-180 | Remove End Cap & Drain the Network | 2 | 2025-11-04 | 2025-11-06
R7S1-INF-TIE-FF-190 | Pipe Cinnections (tie-ins) and Filll Water (Network) & Open the Valve | 4 | 2025-11-06 | 2025-11-11
SECTION - 05 (ZONE-3) |  | 77 | 2025-09-22 | 2025-12-13
DRAINAGE WORKS |  | 43 | 2025-09-22 | 2025-11-17
R7S1-INF-SC5-DR-280 | Manhole Excavation (Section - 05 - ZONE:03) | 15 | 2025-09-22 | 2025-10-09
R7S1-INF-SC5-DR-290 | Maholes Construction (Section - 05 - ZONE:03) | 20 | 2025-09-30 | 2025-10-22
R7S1-INF-SC5-DR-300 | Excavation for Drainage line (Section - 05 - ZONE:03) | 20 | 2025-10-07 | 2025-10-29
R7S1-INF-SC5-DR-310 | Laying of Drainage Pipes (Section - 05 - ZONE:03) | 20 | 2025-10-14 | 2025-11-05
R7S1-INF-SC5-DR-320 | Testing (Section - 05 - ZONE:03) | 6 | 2025-11-06 | 2025-11-12
R7S1-INF-SC5-DR-330 | Backfilling+Warning Tape (Section - 05 - ZONE:03) | 9 | 2025-11-08 | 2025-11-17
CHILLED WATER WORKS |  | 69 | 2025-09-24 | 2025-12-13
R7S1-INF-SC5-CW-310 | Manhole Excavation (Section - 05 - ZONE:03) | 20 | 2025-09-24 | 2025-10-16
R7S1-INF-SC5-CW-320 | Maholes Construction (Section - 05 - ZONE:03) | 20 | 2025-10-12 | 2025-11-03
R7S1-INF-SC5-CW-330 | Excavation for CHWP line (Section - 05 - ZONE:03) | 20 | 2025-10-13 | 2025-11-04
R7S1-INF-SC5-CW-300 | Laying of CH Pipes & VALVES (Section - 05 - ZONE:03) | 20 | 2025-11-05 | 2025-11-27
R7S1-INF-SC5-CW-350 | Pressure Testing (Section - 05 - ZONE:03) | 6 | 2025-11-24 | 2025-11-30
R7S1-INF-SC5-CW-360 | Backfilling+Warning Tape (Section - 05 - ZONE:03) | 9 | 2025-11-25 | 2025-12-04
R7S1-INF-SC5-CW-370 | Chilled Water Pipes Flushing (Section - 05 - ZONE:03) | 15 | 2025-11-26 | 2025-12-13
WATER SUPPLY WORKS |  | 49 | 2025-09-25 | 2025-11-22
R7S1-INF-SC5-WS-280 | Manhole Excavation (Section - 05 - ZONE:03) | 20 | 2025-09-25 | 2025-10-18
R7S1-INF-SC5-WS-290 | Maholes Construction (Section - 05 - ZONE:03) | 20 | 2025-10-05 | 2025-10-27
R7S1-INF-SC5-WS-300 | Excavation for WS line (Section - 05 - ZONE:03) | 20 | 2025-10-14 | 2025-11-05
R7S1-INF-SC5-WS-310 | Laying of WS Pipes & VALVES (Section - 05 - ZONE:03) | 20 | 2025-10-23 | 2025-11-15
R7S1-INF-SC5-WS-320 | Pressure Testing (Section - 05 - ZONE:03) | 6 | 2025-11-11 | 2025-11-17
R7S1-INF-SC5-WS-330 | Backfilling+Warning Tape (Section - 05 - ZONE:03) | 9 | 2025-11-12 | 2025-11-22
FIRE PROTECTION WORKS |  | 45 | 2025-09-25 | 2025-11-17
R7S1-INF-SC5-FP-280 | Manhole Excavation (Section - 05 - ZONE:03) | 20 | 2025-09-25 | 2025-10-18
R7S1-INF-SC5-FP-290 | Maholes Construction (Section - 05 - ZONE:03) | 20 | 2025-10-05 | 2025-10-27
R7S1-INF-SC5-FP-300 | Excavation for FP line (Section - 05 - ZONE:03) | 20 | 2025-10-12 | 2025-11-03
R7S1-INF-SC5-FP-310 | Laying of FF Pipes & VALVES (Section - 05 - ZONE:03) | 20 | 2025-10-19 | 2025-11-10
R7S1-INF-SC5-FP-320 | Pressure Testing (Section - 05 - ZONE:03) | 6 | 2025-11-06 | 2025-11-12
R7S1-INF-SC5-FP-330 | Backfilling+Warning Tape (Section - 05 - ZONE:03) | 9 | 2025-11-08 | 2025-11-17
POWER - ELECTRICAL |  | 50 | 2025-10-13 | 2025-12-02
R7S1-INF-SC5-PO-250 | Manhole Excavation (Section - 05 - ZONE:03) | 20 | 2025-10-13 | 2025-11-04
R7S1-INF-SC5-PO-260 | Maholes Construction (Section - 05 - ZONE:03) | 20 | 2025-10-20 | 2025-11-11
R7S1-INF-SC5-PO-270 | Excavation for LV Cable (Section - 05 - ZONE:03) | 20 | 2025-10-27 | 2025-11-18
R7S1-INF-SC5-PO-280 | Laying of LV Cable (Section - 05 - ZONE:03) | 20 | 2025-11-03 | 2025-11-25
R7S1-INF-SC5-PO-290 | Backfilling+Warning Tape (Section - 05 - ZONE:03) | 20 | 2025-11-10 | 2025-12-02
SECURITY SYSTEM (CCTV & ACCESS CONTROL) - ELECTRICAL |  | 37 | 2025-10-30 | 2025-12-06
R7S1-INF-SC5-ELV-250 | Manhole Excavation (Section - 05 - ZONE:03) | 20 | 2025-10-30 | 2025-11-22
R7S1-INF-SC5-ELV-260 | Maholes Construction (Section - 05 - ZONE:03) | 20 | 2025-11-03 | 2025-11-25
R7S1-INF-SC5-ELV-270 | Excavation for ELV Cable (Section - 05 - ZONE:03) | 20 | 2025-11-06 | 2025-11-29
R7S1-INF-SC5-ELV-280 | Laying of ELV Cable (Section - 05 - ZONE:03) | 20 | 2025-11-10 | 2025-12-02
R7S1-INF-SC5-ELV-290 | Backfilling+Warning Tape (Section - 05 - ZONE:03) | 20 | 2025-11-13 | 2025-12-06
ICT - ELECTRICAL |  | 36 | 2025-11-05 | 2025-12-11
R7S1-INF-SC5-ICT-250 | Manhole Excavation (Section - 05 - ZONE:03) | 20 | 2025-11-05 | 2025-11-27
R7S1-INF-SC5-ICT-260 | Maholes Construction (Section - 05 - ZONE:03) | 20 | 2025-11-09 | 2025-12-01
R7S1-INF-SC5-ICT-270 | Excavation for LV Cable (Section - 05 - ZONE:03) | 20 | 2025-11-12 | 2025-12-04
R7S1-INF-SC5-ICT-280 | Laying of Ducts, Road Crossings, ICT Cable Pulling (Section - 05 - ZONE:03) | 20 | 2025-11-16 | 2025-12-08
R7S1-INF-SC5-ICT-290 | Backfilling+Warning Tape (Section - 05 - ZONE:03) | 20 | 2025-11-19 | 2025-12-11
TIE-IN CONNECTION (SECTION - 05 (ZONE-3) |  | 20 | 2025-11-18 | 2025-12-16
DRAINAGE |  | 20 | 2025-11-18 | 2025-12-15
R7S1-INF-TIE-DR-230 | Drainage Tie-in Connection Works - AP08 (ZUT-SR2-MH4) | 4 | 2025-11-18 | 2025-11-22
R7S1-INF-TIE-DR-280 | Drainage Tie-in Connection Works - AP09 (MH-L4-8) | 4 | 2025-11-23 | 2025-11-26
R7S1-INF-TIE-DR-270 | Drainage Tie-in Connection Works - AP10 (MH-L4-9) | 4 | 2025-11-27 | 2025-12-01
R7S1-INF-TIE-DR-290 | Drainage Tie-in Connection Works - AP11 (MH-L4-9) | 4 | 2025-12-02 | 2025-12-06
R7S1-INF-TIE-DR-260 | Drainage Tie-in Connection Works - AP12 (MH-L4-9) | 4 | 2025-12-07 | 2025-12-10
R7S1-INF-TIE-DR-240 | Drainage Tie-in Connection Works - AP13 (MH-L4-9) | 4 | 2025-12-11 | 2025-12-15
CHILLED WATER |  | 3 | 2025-12-14 | 2025-12-16
R7S1-INF-TIE-CHW-250 | Open Valve to Flow to the Network (after Flushing) | 3 | 2025-12-14 | 2025-12-16
WATER SUPPLY |  | 4 | 2025-11-23 | 2025-11-26
R7S1-INF-TIE-WS-190 | Watersupply Pipe Laying & Connecting to the Existing Tank Primary Tank to Secondary GRP tank | 4 | 2025-11-23 | 2025-11-26
FIRE PROTECTION |  | 7 | 2025-11-18 | 2025-11-25
R7S1-INF-TIE-FF-200 | Close Valves (ZUT-FP2-FS2) | 1 | 2025-11-18 | 2025-11-18
R7S1-INF-TIE-FF-210 | Remove End Cap & Drain the Network | 2 | 2025-11-19 | 2025-11-20
R7S1-INF-TIE-FF-220 | Pipe Cinnections (tie-ins) and Filll Water (Network) & Open the Valve | 4 | 2025-11-22 | 2025-11-25
TESTING & COMMISSIONING |  | 130 | 2025-07-22 | 2025-12-03
PRIORITY - 1 |  | 93 | 2025-07-22 | 2025-09-25
BUILDING # AP03 - TESTING & COMMISSIONING (MANAGEMENT) |  | 93 | 2025-08-11 | 2025-09-14
MECHANICAL |  | 93 | 2025-08-11 | 2025-09-14
R7S1ONTCM-AP03-451 | T&C - Water Supply System (Internal) - AP#03 | 4 | 2025-08-11 | 2025-08-16
R7S1ONTCM-AP03-466 | T&C - Flow test for Drainage System - AP#03 | 4 | 2025-08-14 | 2025-08-19
R7S1ONTCM-AP03-448 | T&C - Solar System - AP#03 | 4 | 2025-08-31 | 2025-09-03
R7S1ONTCM-AP03-465 | T&C - Startup of Equipment (FAHU/FCU/Exaust Fans) - AP#03 | 4 | 2025-08-31 | 2025-09-03
R7S1ONTCM-AP03-445 | T&C - Chilled Water System Flushing - AP#03 | 15 | 2025-08-18 | 2025-09-04
R7S1ONTCM-AP03-449 | T&C - HVAC Air Balancing (FCU & FAHU) - AP#03 | 4 | 2025-09-04 | 2025-09-08
R7S1ONTCM-AP03-450 | T&C - Hot Water System - Balancing - AP#03 | 4 | 2025-09-04 | 2025-09-08
R7S1ONTCM-AP03-446 | T&C - Chilled Water Balancing (FCU & FAHU) - AP#03 | 4 | 2025-09-04 | 2025-09-09
R7S1ONTCM-AP03-444 | T&C - Fire Fighting System - AP#03 | 4 | 2025-09-09 | 2025-09-14
R7S1ONTCM-AP03-452 | T&C - Water Supply System - Disinfection (All together) - AP#03 | 4 | 2025-09-09 | 2025-09-14
ELECTRICAL |  | 18 | 2025-08-21 | 2025-09-08
R7S1ONTCM-AP03-453 | T&C - Earthing & Lightning - AP#03 | 4 | 2025-08-21 | 2025-08-25
R7S1ONTCM-AP03-463 | T&C - BMS - AP#03 | 4 | 2025-08-25 | 2025-08-30
R7S1ONTCM-AP03-454 | T&C - Power System - AP#03 (Energization of Building MDB/SMDB of Building) | 4 | 2025-08-26 | 2025-08-30
R7S1ONTCM-AP03-459 | T&C - Lights System - AP#03 | 4 | 2025-08-28 | 2025-09-02
R7S1ONTCM-AP03-455 | T&C - Lifts/Elevators - AP#03 | 4 | 2025-08-31 | 2025-09-03
R7S1ONTCM-AP03-456 | T&C - CCTV - AP#03 | 4 | 2025-08-31 | 2025-09-03
R7S1ONTCM-AP03-457 | T&C - Acess Control - AP#03 | 4 | 2025-08-31 | 2025-09-03
R7S1ONTCM-AP03-460 | T&C - CBS System - AP#03 | 4 | 2025-08-31 | 2025-09-03
R7S1ONTCM-AP03-461 | T&C - UPS System - AP#03 | 4 | 2025-09-01 | 2025-09-06
R7S1ONTCM-AP03-462 | T&C - Fire Alarm System - AP#03 | 4 | 2025-09-01 | 2025-09-06
R7S1ONTCM-AP03-458 | T&C - HVAC Air Balancing - AP#03 | 4 | 2025-09-04 | 2025-09-08
BUILDING # AP02 - TESTING & COMMISSIONING (MANAGEMENT) |  | 81 | 2025-07-22 | 2025-09-15
MECHANICAL |  | 81 | 2025-07-22 | 2025-09-15
R7S1ONTCM-AP02-428 | T&C - Water Supply System (Internal) - AP#02 | 4 | 2025-07-22 | 2025-07-26
R7S1ONTCM-AP02-443 | T&C - Flow test for Drainage System - AP#02 | 4 | 2025-07-26 | 2025-07-29
R7S1ONTCM-AP02-425 | T&C - Solar System - AP#02 | 4 | 2025-08-31 | 2025-09-03
R7S1ONTCM-AP02-442 | T&C - Startup of Equipment (FAHU/FCU/Exaust Fans) - AP#02 | 4 | 2025-08-31 | 2025-09-03
R7S1ONTCM-AP02-422 | T&C - Chilled Water System Flushing - AP#02 | 15 | 2025-08-18 | 2025-09-04
R7S1ONTCM-AP02-426 | T&C - HVAC Air Balancing (FCU & FAHU) - AP#02 | 4 | 2025-09-04 | 2025-09-08
R7S1ONTCM-AP02-427 | T&C - Hot Water System - Balancing - AP#02 | 4 | 2025-09-04 | 2025-09-08
R7S1ONTCM-AP02-423 | T&C - Chilled Water Balancing (FCU & FAHU) - AP#02 | 4 | 2025-09-06 | 2025-09-10
R7S1ONTCM-AP02-429 | T&C - Water Supply System - Disinfection (All together) - AP#02 | 4 | 2025-09-07 | 2025-09-11
R7S1ONTCM-AP02-421 | T&C - Fire Fighting System - AP#02 | 5 | 2025-09-09 | 2025-09-15
ELECTRICAL |  | 12 | 2025-08-21 | 2025-09-08
R7S1ONTCM-AP02-430 | T&C - Earthing & Lightning - AP#02 | 4 | 2025-08-21 | 2025-08-25
R7S1ONTCM-AP02-440 | T&C - BMS - AP#02 | 4 | 2025-08-25 | 2025-08-30
R7S1ONTCM-AP02-431 | T&C - Power System - AP#02 (Energization of Building MDB/SMDB of Building) | 4 | 2025-08-26 | 2025-08-30
R7S1ONTCM-AP02-432 | T&C - Lifts/Elevators - AP#02 | 4 | 2025-08-31 | 2025-09-03
R7S1ONTCM-AP02-433 | T&C - CCTV - AP#02 | 4 | 2025-08-31 | 2025-09-03
R7S1ONTCM-AP02-434 | T&C - Acess Control - AP#02 | 4 | 2025-08-31 | 2025-09-03
R7S1ONTCM-AP02-437 | T&C - CBS System - AP#02 | 4 | 2025-08-31 | 2025-09-03
R7S1ONTCM-AP02-438 | T&C - UPS System - AP#02 | 4 | 2025-08-31 | 2025-09-03
R7S1ONTCM-AP02-439 | T&C - Fire Alarm System - AP#02 | 4 | 2025-08-31 | 2025-09-03
R7S1ONTCM-AP02-436 | T&C - Lights System - AP#02 | 4 | 2025-08-31 | 2025-09-04
R7S1ONTCM-AP02-435 | T&C - HVAC Air Balancing - AP#02 | 4 | 2025-09-04 | 2025-09-08
BUILDING # AP01 - TESTING & COMMISSIONING (MANAGEMENT) |  | 85 | 2025-07-30 | 2025-09-17
MECHANICAL |  | 85 | 2025-07-30 | 2025-09-17
R7S1ONTCM-AP01-270 | T&C - Water Supply System (Internal) - AP#01 | 4 | 2025-07-30 | 2025-08-03
R7S1ONTCM-AP01-420 | T&C - Flow test for Drainage System - AP#01 | 4 | 2025-08-03 | 2025-08-06
R7S1ONTCM-AP01-210 | T&C - Chilled Water System Flushing - AP#01 | 15 | 2025-08-14 | 2025-09-01
R7S1ONTCM-AP01-280 | T&C - Water Supply System - Disinfection (All together) - AP#01 | 4 | 2025-09-01 | 2025-09-06
R7S1ONTCM-AP01-240 | T&C - Solar System - AP#01 | 4 | 2025-09-02 | 2025-09-06
R7S1ONTCM-AP01-410 | T&C - Startup of Equipment (FAHU/FCU/Exaust Fans) - AP#01 | 4 | 2025-09-02 | 2025-09-06
R7S1ONTCM-AP01-250 | T&C - HVAC Air Balancing (FCU & FAHU) - AP#01 | 4 | 2025-09-07 | 2025-09-10
R7S1ONTCM-AP01-260 | T&C - Hot Water System - Balancing - AP#01 | 4 | 2025-09-07 | 2025-09-10
R7S1ONTCM-AP01-220 | T&C - Chilled Water Balancing (FCU & FAHU) - AP#01 | 4 | 2025-09-07 | 2025-09-11
R7S1ONTCM-AP01-200 | T&C - Fire Fighting System - AP#01 | 8 | 2025-09-08 | 2025-09-17
ELECTRICAL |  | 12 | 2025-08-21 | 2025-09-10
R7S1ONTCM-AP01-290 | T&C - Earthing & Lightning - AP#01 | 4 | 2025-08-21 | 2025-08-25
R7S1ONTCM-AP01-390 | T&C - BMS - AP#01 | 4 | 2025-08-25 | 2025-08-30
R7S1ONTCM-AP01-300 | T&C - Power System - AP#01 (Energization of Building MDB/SMDB of Building) | 4 | 2025-08-28 | 2025-09-01
R7S1ONTCM-AP01-370 | T&C - UPS System - AP#01 | 4 | 2025-09-01 | 2025-09-06
R7S1ONTCM-AP01-310 | T&C - Lifts/Elevators - AP#01 | 4 | 2025-09-02 | 2025-09-06
R7S1ONTCM-AP01-320 | T&C - CCTV - AP#01 | 4 | 2025-09-02 | 2025-09-06
R7S1ONTCM-AP01-330 | T&C - Acess Control - AP#01 | 4 | 2025-09-02 | 2025-09-06
R7S1ONTCM-AP01-360 | T&C - CBS System - AP#01 | 4 | 2025-09-02 | 2025-09-06
R7S1ONTCM-AP01-380 | T&C - Fire Alarm System - AP#01 | 4 | 2025-09-02 | 2025-09-06
R7S1ONTCM-AP01-350 | T&C - Lights System - AP#01 | 4 | 2025-09-02 | 2025-09-07
R7S1ONTCM-AP01-340 | T&C - HVAC Air Balancing - AP#01 | 4 | 2025-09-07 | 2025-09-10
BUILDING # AP04 - TESTING & COMMISSIONING (MANAGEMENT) |  | 77 | 2025-08-06 | 2025-09-22
MECHANICAL |  | 77 | 2025-08-06 | 2025-09-22
R7S1ONTCM-AP04-474 | T&C - Water Supply System (Internal) - AP#04 | 4 | 2025-08-06 | 2025-08-11
R7S1ONTCM-AP04-489 | T&C - Flow test for Drainage System - AP#04 | 4 | 2025-08-10 | 2025-08-14
R7S1ONTCM-AP04-468 | T&C - Chilled Water System Flushing - AP#04 | 15 | 2025-08-18 | 2025-09-04
R7S1ONTCM-AP04-475 | T&C - Water Supply System - Disinfection (All together) - AP#04 | 4 | 2025-09-07 | 2025-09-11
R7S1ONTCM-AP04-469 | T&C - Chilled Water Balancing (FCU & FAHU) - AP#04 | 4 | 2025-09-08 | 2025-09-13
R7S1ONTCM-AP04-471 | T&C - Solar System - AP#04 | 4 | 2025-09-13 | 2025-09-17
R7S1ONTCM-AP04-488 | T&C - Startup of Equipment (FAHU/FCU/Exaust Fans) - AP#04 | 4 | 2025-09-13 | 2025-09-17
R7S1ONTCM-AP04-467 | T&C - Fire Fighting System - AP#04 | 7 | 2025-09-10 | 2025-09-18
R7S1ONTCM-AP04-472 | T&C - HVAC Air Balancing (FCU & FAHU) - AP#04 | 4 | 2025-09-17 | 2025-09-22
R7S1ONTCM-AP04-473 | T&C - Hot Water System - Balancing - AP#04 | 4 | 2025-09-17 | 2025-09-22
ELECTRICAL |  | 13 | 2025-08-25 | 2025-09-22
R7S1ONTCM-AP04-486 | T&C - BMS - AP#04 | 4 | 2025-08-25 | 2025-08-30
R7S1ONTCM-AP04-476 | T&C - Earthing & Lightning - AP#04 | 4 | 2025-08-25 | 2025-08-30
R7S1ONTCM-AP04-477 | T&C - Power System - AP#04 (Energization of Building MDB/SMDB of Building) | 5 | 2025-09-07 | 2025-09-13
R7S1ONTCM-AP04-478 | T&C - Lifts/Elevators - AP#04 | 4 | 2025-09-13 | 2025-09-17
R7S1ONTCM-AP04-479 | T&C - CCTV - AP#04 | 4 | 2025-09-13 | 2025-09-17
R7S1ONTCM-AP04-480 | T&C - Acess Control - AP#04 | 4 | 2025-09-13 | 2025-09-17
R7S1ONTCM-AP04-482 | T&C - Lights System - AP#04 | 4 | 2025-09-13 | 2025-09-17
R7S1ONTCM-AP04-483 | T&C - CBS System - AP#04 | 4 | 2025-09-13 | 2025-09-17
R7S1ONTCM-AP04-484 | T&C - UPS System - AP#04 | 4 | 2025-09-13 | 2025-09-17
R7S1ONTCM-AP04-485 | T&C - Fire Alarm System - AP#04 | 4 | 2025-09-13 | 2025-09-17
R7S1ONTCM-AP04-481 | T&C - HVAC Air Balancing - AP#04 | 4 | 2025-09-17 | 2025-09-22
BUILDING # AP06 - TESTING & COMMISSIONING (MANAGEMENT) |  | 75 | 2025-08-12 | 2025-09-24
MECHANICAL |  | 75 | 2025-08-12 | 2025-09-24
R7S1ONTCM-AP06-497 | T&C - Water Supply System (Internal) - AP#06 | 4 | 2025-08-12 | 2025-08-17
R7S1ONTCM-AP06-512 | T&C - Flow test for Drainage System - AP#06 | 4 | 2025-08-16 | 2025-08-20
R7S1ONTCM-AP06-491 | T&C - Chilled Water System Flushing - AP#06 | 15 | 2025-08-18 | 2025-09-04
R7S1ONTCM-AP06-498 | T&C - Water Supply System - Disinfection (All together) - AP#06 | 4 | 2025-09-07 | 2025-09-11
R7S1ONTCM-AP06-492 | T&C - Chilled Water Balancing (FCU & FAHU) - AP#06 | 4 | 2025-09-09 | 2025-09-14
R7S1ONTCM-AP06-511 | T&C - Startup of Equipment (FAHU/FCU/Exaust Fans) - AP#06 | 4 | 2025-09-14 | 2025-09-18
R7S1ONTCM-AP06-490 | T&C - Fire Fighting System - AP#06 | 8 | 2025-09-10 | 2025-09-20
R7S1ONTCM-AP06-494 | T&C - Solar System - AP#06 | 4 | 2025-09-18 | 2025-09-24
R7S1ONTCM-AP06-495 | T&C - HVAC Air Balancing (FCU & FAHU) - AP#06 | 4 | 2025-09-18 | 2025-09-24
R7S1ONTCM-AP06-496 | T&C - Hot Water System - Balancing - AP#06 | 4 | 2025-09-18 | 2025-09-24
ELECTRICAL |  | 11 | 2025-08-25 | 2025-09-24
R7S1ONTCM-AP06-509 | T&C - BMS - AP#06 | 4 | 2025-08-25 | 2025-08-30
R7S1ONTCM-AP06-499 | T&C - Earthing & Lightning - AP#06 | 4 | 2025-08-31 | 2025-09-04
R7S1ONTCM-AP06-500 | T&C - Power System - AP#06 (Energization of Building MDB/SMDB of Building) | 5 | 2025-09-13 | 2025-09-18
R7S1ONTCM-AP06-501 | T&C - Lifts/Elevators - AP#06 | 4 | 2025-09-18 | 2025-09-24
R7S1ONTCM-AP06-502 | T&C - CCTV - AP#06 | 4 | 2025-09-18 | 2025-09-24
R7S1ONTCM-AP06-503 | T&C - Acess Control - AP#06 | 4 | 2025-09-18 | 2025-09-24
R7S1ONTCM-AP06-504 | T&C - HVAC Air Balancing - AP#06 | 4 | 2025-09-18 | 2025-09-24
R7S1ONTCM-AP06-505 | T&C - Lights System - AP#06 | 4 | 2025-09-18 | 2025-09-24
R7S1ONTCM-AP06-506 | T&C - CBS System - AP#06 | 4 | 2025-09-18 | 2025-09-24
R7S1ONTCM-AP06-507 | T&C - UPS System - AP#06 | 4 | 2025-09-18 | 2025-09-24
R7S1ONTCM-AP06-508 | T&C - Fire Alarm System - AP#06 | 4 | 2025-09-18 | 2025-09-24
BUILDING # AP07 - TESTING & COMMISSIONING (MANAGEMENT) |  | 66 | 2025-08-18 | 2025-09-25
MECHANICAL |  | 66 | 2025-08-18 | 2025-09-25
R7S1ONTCM-AP07-520 | T&C - Water Supply System (Internal) - AP#07 | 4 | 2025-08-20 | 2025-08-24
R7S1ONTCM-AP07-535 | T&C - Flow test for Drainage System - AP#07 | 4 | 2025-08-23 | 2025-08-27
R7S1ONTCM-AP07-514 | T&C - Chilled Water System Flushing- AP#07 | 15 | 2025-08-18 | 2025-09-04
R7S1ONTCM-AP07-521 | T&C - Water Supply System - Disinfection (All together) - AP#07 | 4 | 2025-09-07 | 2025-09-11
R7S1ONTCM-AP07-515 | T&C - Chilled Water Balancing (FCU & FAHU) - AP#07 | 4 | 2025-09-14 | 2025-09-18
R7S1ONTCM-AP07-517 | T&C - Solar System - AP#07 | 4 | 2025-09-15 | 2025-09-20
R7S1ONTCM-AP07-534 | T&C - Startup of Equipment (FAHU/FCU/Exaust Fans) - AP#07 | 4 | 2025-09-15 | 2025-09-20
R7S1ONTCM-AP07-513 | T&C - Fire Fighting System - AP#07 | 11 | 2025-09-08 | 2025-09-21
R7S1ONTCM-AP07-518 | T&C - HVAC Air Balancing (FCU & FAHU) - AP#07 | 4 | 2025-09-20 | 2025-09-25
R7S1ONTCM-AP07-519 | T&C - Hot Water System - Balancing - AP#07 | 4 | 2025-09-20 | 2025-09-25
ELECTRICAL |  | 11 | 2025-08-25 | 2025-09-25
R7S1ONTCM-AP07-532 | T&C - BMS - AP#07 | 4 | 2025-08-25 | 2025-08-30
R7S1ONTCM-AP07-522 | T&C - Earthing & Lightning - AP#07 | 4 | 2025-08-28 | 2025-09-02
R7S1ONTCM-AP07-523 | T&C - Power System - AP#07 (Energization of Building MDB/SMDB of Building) | 4 | 2025-09-10 | 2025-09-15
R7S1ONTCM-AP07-524 | T&C - Lifts/Elevators - AP#07 | 4 | 2025-09-15 | 2025-09-20
R7S1ONTCM-AP07-525 | T&C - CCTV - AP#07 | 4 | 2025-09-15 | 2025-09-20
R7S1ONTCM-AP07-526 | T&C - Acess Control - AP#07 | 4 | 2025-09-15 | 2025-09-20
R7S1ONTCM-AP07-528 | T&C - Lights System - AP#07 | 4 | 2025-09-15 | 2025-09-20
R7S1ONTCM-AP07-529 | T&C - CBS System - AP#07 | 4 | 2025-09-15 | 2025-09-20
R7S1ONTCM-AP07-530 | T&C - UPS System - AP#07 | 4 | 2025-09-15 | 2025-09-20
R7S1ONTCM-AP07-531 | T&C - Fire Alarm System - AP#07 | 4 | 2025-09-15 | 2025-09-20
R7S1ONTCM-AP07-527 | T&C - HVAC Air Balancing - AP#07 | 4 | 2025-09-20 | 2025-09-25
PRIORITY - 2 |  | 45 | 2025-10-19 | 2025-12-03
BUILDING # AP16 - TESTING & COMMISSIONING (LARGE STUDIO) |  | 36 | 2025-10-19 | 2025-11-24
MECHANICAL |  | 36 | 2025-10-19 | 2025-11-24
R7S1ONTCM-AP16-681 | T&C - Water Supply System (Internal) - AP#16 (Large) | 4 | 2025-10-19 | 2025-10-22
R7S1ONTCM-AP16-696 | T&C - Flow test for Drainage System - AP#16 (Large) | 4 | 2025-10-22 | 2025-10-26
R7S1ONTCM-AP16-678 | T&C - Solar System - AP#16 (Large) | 4 | 2025-11-01 | 2025-11-04
R7S1ONTCM-AP16-695 | T&C - Startup of Equipment (FAHU/FCU/Exaust Fans) - AP#16 (Large) | 4 | 2025-11-01 | 2025-11-04
R7S1ONTCM-AP16-679 | T&C - HVAC Air Balancing (FCU & FAHU) - AP#16 (Large) | 4 | 2025-11-05 | 2025-11-09
R7S1ONTCM-AP16-680 | T&C - Hot Water System - Balancing - AP#16 (Large) | 4 | 2025-11-05 | 2025-11-09
R7S1ONTCM-AP16-674 | T&C - Fire Fighting System - AP#16 (Large) | 4 | 2025-11-06 | 2025-11-11
R7S1ONTCM-AP16-675 | T&C - Chilled Water System Flushing - AP#16 (Large) | 18 | 2025-10-28 | 2025-11-18
R7S1ONTCM-AP16-682 | T&C - Water Supply System - Disinfection (All together) - AP#16 (Large) | 4 | 2025-11-16 | 2025-11-20
R7S1ONTCM-AP16-676 | T&C - Chilled Water Balancing (FCU & FAHU) - AP#16 (Large) | 4 | 2025-11-19 | 2025-11-24
ELECTRICAL |  | 29 | 2025-10-22 | 2025-11-17
R7S1ONTCM-AP16-683 | T&C - Earthing & Lightning - AP#16 (Large) | 4 | 2025-10-22 | 2025-10-26
R7S1ONTCM-AP16-684 | T&C - Power System - AP#16 (Energization of Building MDB/SMDB of Building) | 4 | 2025-10-27 | 2025-10-30
R7S1ONTCM-AP16-686 | T&C - CCTV - AP#16 (Large) | 4 | 2025-11-01 | 2025-11-04
R7S1ONTCM-AP16-687 | T&C - Acess Control - AP#16 (Large) | 4 | 2025-11-01 | 2025-11-04
R7S1ONTCM-AP16-690 | T&C - CBS System (Pred-Installation of CBS 1st Floor) - AP#16 (Large) | 4 | 2025-11-01 | 2025-11-04
R7S1ONTCM-AP16-685 | T&C - Lifts/Elevators - AP#16 (Large) | 4 | 2025-11-02 | 2025-11-05
R7S1ONTCM-AP16-688 | T&C - HVAC Air Balancing - AP#16 (Large) | 4 | 2025-11-05 | 2025-11-09
R7S1ONTCM-AP16-691 | T&C - UPS System - AP#16 (Large) | 4 | 2025-11-05 | 2025-11-09
R7S1ONTCM-AP16-692 | T&C - Fire Alarm System - AP#16 (Large) | 4 | 2025-11-05 | 2025-11-09
R7S1ONTCM-AP16-689 | T&C - Lights System - AP#16 (Large) | 4 | 2025-11-06 | 2025-11-10
R7S1ONTCM-AP16-693 | T&C - BMS - AP#16 | 4 | 2025-11-12 | 2025-11-17
BUILDING # AP17 - TESTING & COMMISSIONING (LARGE STUDIO) |  | 34 | 2025-10-27 | 2025-11-27
MECHANICAL |  | 34 | 2025-10-27 | 2025-11-27
R7S1ONTCM-AP17-612 | T&C - Water Supply System (Internal) - AP#17 (Large) | 4 | 2025-10-27 | 2025-10-30
R7S1ONTCM-AP17-627 | T&C - Flow test for Drainage System - AP#17 (Large) | 4 | 2025-10-30 | 2025-11-03
R7S1ONTCM-AP17-605 | T&C - Fire Fighting System - AP#17 (Large) | 4 | 2025-11-10 | 2025-11-13
R7S1ONTCM-AP17-613 | T&C - Water Supply System - Disinfection (All together) - AP#17 (Large) | 4 | 2025-11-17 | 2025-11-22
R7S1ONTCM-AP17-609 | T&C - Solar System - AP#17 (Large) | 4 | 2025-11-18 | 2025-11-22
R7S1ONTCM-AP17-626 | T&C - Startup of Equipment (FAHU/FCU/Exaust Fans) - AP#17 (Large) | 4 | 2025-11-18 | 2025-11-22
R7S1ONTCM-AP17-606 | T&C - Chilled Water System Flushing - AP#17 (Large) | 18 | 2025-11-02 | 2025-11-23
R7S1ONTCM-AP17-610 | T&C - HVAC Air Balancing (FCU & FAHU) - AP#17 (Large) | 4 | 2025-11-23 | 2025-11-26
R7S1ONTCM-AP17-611 | T&C - Hot Water System - Balancing - AP#17 (Large) | 4 | 2025-11-23 | 2025-11-26
R7S1ONTCM-AP17-607 | T&C - Chilled Water Balancing (FCU & FAHU) - AP#17 (Large) | 4 | 2025-11-23 | 2025-11-27
ELECTRICAL |  | 27 | 2025-11-01 | 2025-11-26
R7S1ONTCM-AP17-614 | T&C - Earthing & Lightning - AP#17 (Large) | 4 | 2025-11-01 | 2025-11-04
R7S1ONTCM-AP17-624 | T&C - BMS - AP#17 | 4 | 2025-11-12 | 2025-11-17
R7S1ONTCM-AP17-615 | T&C - Power System - AP#17 (Energization of Building MDB/SMDB of Building) | 4 | 2025-11-13 | 2025-11-17
R7S1ONTCM-AP17-616 | T&C - Lifts/Elevators - AP#17 (Large) | 4 | 2025-11-18 | 2025-11-22
R7S1ONTCM-AP17-617 | T&C - CCTV - AP#17 (Large) | 4 | 2025-11-18 | 2025-11-22
R7S1ONTCM-AP17-618 | T&C - Acess Control - AP#17 (Large) | 4 | 2025-11-18 | 2025-11-22
R7S1ONTCM-AP17-620 | T&C - Lights System - AP#17 (Large) | 4 | 2025-11-18 | 2025-11-22
R7S1ONTCM-AP17-621 | T&C - CBS System (Pred-Installation of CBS 1st Floor) - AP#17 (Large) | 4 | 2025-11-18 | 2025-11-22
R7S1ONTCM-AP17-622 | T&C - UPS System - AP#17 (Large) | 4 | 2025-11-18 | 2025-11-22
R7S1ONTCM-AP17-623 | T&C - Fire Alarm System - AP#17 (Large) | 4 | 2025-11-18 | 2025-11-22
R7S1ONTCM-AP17-619 | T&C - HVAC Air Balancing - AP#17 (Large) | 4 | 2025-11-23 | 2025-11-26
BUILDING # AP18 - TESTING & COMMISSIONING (LARGE STUDIO) |  | 34 | 2025-10-26 | 2025-11-29
MECHANICAL |  | 32 | 2025-10-30 | 2025-11-29
R7S1ONTCM-AP18-589 | T&C - Water Supply System (Internal) - AP#18 (Large) | 4 | 2025-10-30 | 2025-11-03
R7S1ONTCM-AP18-604 | T&C - Flow test for Drainage System - AP#18 (Large) | 4 | 2025-11-03 | 2025-11-06
R7S1ONTCM-AP18-586 | T&C - Solar System - AP#18 (Large) | 4 | 2025-11-12 | 2025-11-16
R7S1ONTCM-AP18-603 | T&C - Startup of Equipment (FAHU/FCU/Exaust Fans) - AP#18 (Large) | 4 | 2025-11-12 | 2025-11-16
R7S1ONTCM-AP18-582 | T&C - Fire Fighting System - AP#18 (Large) | 4 | 2025-11-15 | 2025-11-18
R7S1ONTCM-AP18-587 | T&C - HVAC Air Balancing (FCU & FAHU) - AP#18 (Large) | 4 | 2025-11-17 | 2025-11-20
R7S1ONTCM-AP18-588 | T&C - Hot Water System - Balancing - AP#18 (Large) | 4 | 2025-11-17 | 2025-11-20
R7S1ONTCM-AP18-590 | T&C - Water Supply System - Disinfection (All together) - AP#18 | 4 | 2025-11-17 | 2025-11-22
R7S1ONTCM-AP18-583 | T&C - Chilled Water System Flushing - AP#18 (Large) | 18 | 2025-11-02 | 2025-11-23
R7S1ONTCM-AP18-584 | T&C - Chilled Water Balancing (FCU & FAHU) - AP#18 (Large) | 4 | 2025-11-24 | 2025-11-29
ELECTRICAL |  | 32 | 2025-10-26 | 2025-11-22
R7S1ONTCM-AP18-591 | T&C - Earthing & Lightning - AP#18 (Large) | 4 | 2025-10-26 | 2025-10-29
R7S1ONTCM-AP18-592 | T&C - Power System - AP#18 (Energization of Building MDB/SMDB of Building) | 4 | 2025-11-08 | 2025-11-11
R7S1ONTCM-AP18-593 | T&C - Lifts/Elevators - AP#18 (Large) | 4 | 2025-11-12 | 2025-11-16
R7S1ONTCM-AP18-594 | T&C - CCTV - AP#18 (Large) | 4 | 2025-11-12 | 2025-11-16
R7S1ONTCM-AP18-595 | T&C - Acess Control - AP#18 (Large) | 4 | 2025-11-12 | 2025-11-16
R7S1ONTCM-AP18-598 | T&C - CBS System (Pred-Installation of CBS 1st Floor) - AP#18 (Large) | 4 | 2025-11-12 | 2025-11-16
R7S1ONTCM-AP18-601 | T&C - BMS - AP#18 | 4 | 2025-11-12 | 2025-11-17
R7S1ONTCM-AP18-596 | T&C - HVAC Air Balancing - AP#18 (Large) | 4 | 2025-11-17 | 2025-11-20
R7S1ONTCM-AP18-599 | T&C - UPS System - AP#18 (Large) | 4 | 2025-11-17 | 2025-11-20
R7S1ONTCM-AP18-600 | T&C - Fire Alarm System - AP#18 (Large) | 4 | 2025-11-17 | 2025-11-20
R7S1ONTCM-AP18-597 | T&C - Lights System - AP#18 (Large) | 4 | 2025-11-18 | 2025-11-22
BUILDING # AP19 - TESTING & COMMISSIONING (MEDIUM STUDIO) |  | 29 | 2025-10-30 | 2025-11-30
MECHANICAL |  | 28 | 2025-11-02 | 2025-11-30
R7S1ONTCM-AP19-566 | T&C - Water Supply System (Internal) - AP#19 | 4 | 2025-11-04 | 2025-11-08
R7S1ONTCM-AP19-581 | T&C - Flow test for Drainage System - AP#19 | 4 | 2025-11-08 | 2025-11-11
R7S1ONTCM-AP19-563 | T&C - Solar System - AP#19 | 4 | 2025-11-17 | 2025-11-20
R7S1ONTCM-AP19-580 | T&C - Startup of Equipment (FAHU/FCU/Exaust Fans) - AP#19 | 4 | 2025-11-17 | 2025-11-20
R7S1ONTCM-AP19-567 | T&C - Water Supply System - Disinfection (All together) - AP#19 | 4 | 2025-11-17 | 2025-11-22
R7S1ONTCM-AP19-560 | T&C - Chilled Water System Flushing - AP#19 | 18 | 2025-11-02 | 2025-11-23
R7S1ONTCM-AP19-559 | T&C - Fire Fighting System - AP#19 | 4 | 2025-11-20 | 2025-11-24
R7S1ONTCM-AP19-564 | T&C - HVAC Air Balancing (FCU & FAHU) - AP#19 | 4 | 2025-11-22 | 2025-11-25
R7S1ONTCM-AP19-565 | T&C - Hot Water System - Balancing - AP#19 | 4 | 2025-11-22 | 2025-11-25
R7S1ONTCM-AP19-561 | T&C - Chilled Water Balancing (FCU & FAHU) - AP#19 | 4 | 2025-11-25 | 2025-11-30
ELECTRICAL |  | 21 | 2025-10-30 | 2025-11-26
R7S1ONTCM-AP19-568 | T&C - Earthing & Lightning - AP#19 | 4 | 2025-10-30 | 2025-11-03
R7S1ONTCM-AP19-569 | T&C - Power System - AP#19 (Energization of Building MDB/SMDB of Building) | 4 | 2025-11-12 | 2025-11-16
R7S1ONTCM-AP19-578 | T&C - BMS - AP#19 | 4 | 2025-11-12 | 2025-11-17
R7S1ONTCM-AP19-570 | T&C - Lifts/Elevators - AP#19 | 4 | 2025-11-17 | 2025-11-20
R7S1ONTCM-AP19-571 | T&C - CCTV - AP#19 | 4 | 2025-11-17 | 2025-11-20
R7S1ONTCM-AP19-572 | T&C - Acess Control - AP#19 | 4 | 2025-11-17 | 2025-11-20
R7S1ONTCM-AP19-575 | T&C - CBS System (Pred-Installation of CBS 1st Floor) - AP#19 | 4 | 2025-11-17 | 2025-11-20
R7S1ONTCM-AP19-573 | T&C - HVAC Air Balancing - AP#19 | 4 | 2025-11-22 | 2025-11-25
R7S1ONTCM-AP19-576 | T&C - UPS System - AP#19 | 4 | 2025-11-22 | 2025-11-25
R7S1ONTCM-AP19-577 | T&C - Fire Alarm System - AP#19 | 4 | 2025-11-22 | 2025-11-25
R7S1ONTCM-AP19-574 | T&C - Lights System - AP#19 | 4 | 2025-11-23 | 2025-11-26
BUILDING # AP05 - TESTING & COMMISSIONING (MEDIUM STUDIO) |  | 37 | 2025-11-02 | 2025-12-01
MECHANICAL |  | 26 | 2025-11-02 | 2025-12-01
R7S1ONTCM-AP05-543 | T&C - Water Supply System (Internal) - AP#05 | 4 | 2025-11-08 | 2025-11-11
R7S1ONTCM-AP05-558 | T&C - Flow test for Drainage System - AP#05 | 4 | 2025-11-11 | 2025-11-15
R7S1ONTCM-AP05-544 | T&C - Water Supply System - Disinfection (All together) - AP#05 | 4 | 2025-11-12 | 2025-11-16
R7S1ONTCM-AP05-557 | T&C - Startup of Equipment (FAHU/FCU/Exaust Fans) - AP#05 | 4 | 2025-11-15 | 2025-11-18
R7S1ONTCM-AP05-540 | T&C - Solar System - AP#05 | 4 | 2025-11-16 | 2025-11-19
R7S1ONTCM-AP05-537 | T&C - Chilled Water System Flushing - AP#05 | 18 | 2025-11-02 | 2025-11-23
R7S1ONTCM-AP05-541 | T&C - HVAC Air Balancing (FCU & FAHU) - AP#05 | 4 | 2025-11-19 | 2025-11-23
R7S1ONTCM-AP05-542 | T&C - Hot Water System - Balancing - AP#05 | 4 | 2025-11-20 | 2025-11-24
R7S1ONTCM-AP05-536 | T&C - Fire Fighting System - AP#05 | 4 | 2025-11-22 | 2025-11-25
R7S1ONTCM-AP05-538 | T&C - Chilled Water Balancing (FCU & FAHU) - AP#05 | 4 | 2025-11-26 | 2025-12-01
ELECTRICAL |  | 29 | 2025-11-04 | 2025-11-29
R7S1ONTCM-AP05-555 | T&C - BMS - AP#05 | 4 | 2025-11-04 | 2025-11-08
R7S1ONTCM-AP05-545 | T&C - Earthing & Lightning - AP#05 | 4 | 2025-11-05 | 2025-11-09
R7S1ONTCM-AP05-546 | T&C - Power System - AP#05 (Energization of Building MDB/SMDB of Building) | 4 | 2025-11-10 | 2025-11-13
R7S1ONTCM-AP05-547 | T&C - Lifts/Elevators - AP#05 | 4 | 2025-11-15 | 2025-11-18
R7S1ONTCM-AP05-548 | T&C - CCTV - AP#05 | 4 | 2025-11-15 | 2025-11-18
R7S1ONTCM-AP05-549 | T&C - Acess Control - AP#05 | 4 | 2025-11-15 | 2025-11-18
R7S1ONTCM-AP05-552 | T&C - CBS System (Pred-Installation of CBS 1st Floor) - AP#05 | 4 | 2025-11-15 | 2025-11-18
R7S1ONTCM-AP05-550 | T&C - HVAC Air Balancing - AP#05 | 4 | 2025-11-19 | 2025-11-23
R7S1ONTCM-AP05-553 | T&C - UPS System - AP#05 | 4 | 2025-11-24 | 2025-11-27
R7S1ONTCM-AP05-554 | T&C - Fire Alarm System - AP#05 | 4 | 2025-11-24 | 2025-11-27
R7S1ONTCM-AP05-551 | T&C - Lights System - AP#05 | 4 | 2025-11-25 | 2025-11-29
BUILDING # AP14 - TESTING & COMMISSIONING (LARGE STUDIO) |  | 28 | 2025-11-02 | 2025-12-02
MECHANICAL |  | 27 | 2025-11-02 | 2025-12-02
R7S1ONTCM-AP14-635 | T&C - Water Supply System (Internal) - AP#14 (Large) | 4 | 2025-11-12 | 2025-11-17
R7S1ONTCM-AP14-650 | T&C - Flow test for Drainage System - AP#14 (Large) | 4 | 2025-11-13 | 2025-11-17
R7S1ONTCM-AP14-636 | T&C - Water Supply System - Disinfection (All together) - AP#14 (Large) | 4 | 2025-11-17 | 2025-11-22
R7S1ONTCM-AP14-629 | T&C - Chilled Water System Flushing - AP#14 (Large) | 18 | 2025-11-02 | 2025-11-23
R7S1ONTCM-AP14-628 | T&C - Fire Fighting System - AP#14 (Large) | 4 | 2025-11-20 | 2025-11-24
R7S1ONTCM-AP14-632 | T&C - Solar System - AP#14 (Large) | 4 | 2025-11-22 | 2025-11-26
R7S1ONTCM-AP14-633 | T&C - HVAC Air Balancing (FCU & FAHU) - AP#14 (Large) | 4 | 2025-11-22 | 2025-11-26
R7S1ONTCM-AP14-634 | T&C - Hot Water System - Balancing - AP#14 (Large) | 4 | 2025-11-22 | 2025-11-26
R7S1ONTCM-AP14-649 | T&C - Startup of Equipment (FAHU/FCU/Exaust Fans) - AP#14 (Large) | 4 | 2025-11-22 | 2025-11-26
R7S1ONTCM-AP14-630 | T&C - Chilled Water Balancing (FCU & FAHU) - AP#14 (Large) | 4 | 2025-11-27 | 2025-12-02
ELECTRICAL |  | 21 | 2025-11-12 | 2025-11-29
R7S1ONTCM-AP14-637 | T&C - Earthing & Lightning - AP#14 (Large) | 4 | 2025-11-12 | 2025-11-17
R7S1ONTCM-AP14-647 | T&C - BMS - AP#14 | 4 | 2025-11-12 | 2025-11-17
R7S1ONTCM-AP14-638 | T&C - Power System - AP#14 (Energization of Building MDB/SMDB of Building) | 4 | 2025-11-17 | 2025-11-22
R7S1ONTCM-AP14-639 | T&C - Lifts/Elevators - AP#14 (Large) | 4 | 2025-11-22 | 2025-11-26
R7S1ONTCM-AP14-640 | T&C - CCTV - AP#14 (Large) | 4 | 2025-11-22 | 2025-11-26
R7S1ONTCM-AP14-641 | T&C - Acess Control - AP#14 (Large) | 4 | 2025-11-22 | 2025-11-26
R7S1ONTCM-AP14-643 | T&C - Lights System - AP#14 (Large) | 4 | 2025-11-22 | 2025-11-26
R7S1ONTCM-AP14-644 | T&C - CBS System (Pred-Installation of CBS 1st Floor) - AP#14 (Large) | 4 | 2025-11-22 | 2025-11-26
R7S1ONTCM-AP14-645 | T&C - UPS System - AP#14 (Large) | 4 | 2025-11-22 | 2025-11-26
R7S1ONTCM-AP14-646 | T&C - Fire Alarm System - AP#14 (Large) | 4 | 2025-11-22 | 2025-11-26
R7S1ONTCM-AP14-642 | T&C - HVAC Air Balancing - AP#14 (Large) | 4 | 2025-11-24 | 2025-11-29
BUILDING # AP15 - TESTING & COMMISSIONING (LARGE STUDIO) |  | 31 | 2025-11-02 | 2025-12-03
MECHANICAL |  | 28 | 2025-11-02 | 2025-12-03
R7S1ONTCM-AP15-658 | T&C - Water Supply System (Internal) - AP#15 (Large) | 4 | 2025-11-13 | 2025-11-17
R7S1ONTCM-AP15-673 | T&C - Flow test for Drainage System - AP#15 (Large) | 4 | 2025-11-17 | 2025-11-20
R7S1ONTCM-AP15-659 | T&C - Water Supply System - Disinfection (All together) - AP#15 (Large) | 4 | 2025-11-18 | 2025-11-22
R7S1ONTCM-AP15-652 | T&C - Chilled Water System Flushing - AP#15 (Large) | 18 | 2025-11-02 | 2025-11-23
R7S1ONTCM-AP15-655 | T&C - Solar System - AP#15 (Large) | 4 | 2025-11-22 | 2025-11-25
R7S1ONTCM-AP15-672 | T&C - Startup of Equipment (FAHU/FCU/Exaust Fans) - AP#15 (Large) | 4 | 2025-11-22 | 2025-11-25
R7S1ONTCM-AP15-651 | T&C - Fire Fighting System - AP#15 (Large) | 4 | 2025-11-26 | 2025-11-30
R7S1ONTCM-AP15-657 | T&C - Hot Water System - Balancing - AP#15 (Large) | 4 | 2025-11-26 | 2025-11-30
R7S1ONTCM-AP15-656 | T&C - HVAC Air Balancing (FCU & FAHU) - AP#15 (Large) | 5 | 2025-11-26 | 2025-12-01
R7S1ONTCM-AP15-653 | T&C - Chilled Water Balancing (FCU & FAHU) - AP#15 (Large) | 4 | 2025-11-29 | 2025-12-03
ELECTRICAL |  | 25 | 2025-11-12 | 2025-12-03
R7S1ONTCM-AP15-660 | T&C - Earthing & Lightning - AP#15 (Large) | 4 | 2025-11-12 | 2025-11-16
R7S1ONTCM-AP15-670 | T&C - BMS - AP#15 | 4 | 2025-11-12 | 2025-11-17
R7S1ONTCM-AP15-661 | T&C - Power System - AP#15 (Energization of Building MDB/SMDB of Building) | 4 | 2025-11-17 | 2025-11-20
R7S1ONTCM-AP15-662 | T&C - Lifts/Elevators - AP#15 (Large) | 4 | 2025-11-22 | 2025-11-25
R7S1ONTCM-AP15-663 | T&C - CCTV - AP#15 (Large) | 4 | 2025-11-22 | 2025-11-25
R7S1ONTCM-AP15-664 | T&C - Acess Control - AP#15 (Large) | 4 | 2025-11-22 | 2025-11-25
R7S1ONTCM-AP15-667 | T&C - CBS System (Pred-Installation of CBS 1st Floor) - AP#15 (Large) | 4 | 2025-11-22 | 2025-11-25
R7S1ONTCM-AP15-665 | T&C - HVAC Air Balancing - AP#15 (Large) | 4 | 2025-11-26 | 2025-11-30
R7S1ONTCM-AP15-668 | T&C - UPS System - AP#15 (Large) | 4 | 2025-11-29 | 2025-12-02
R7S1ONTCM-AP15-669 | T&C - Fire Alarm System - AP#15 (Large) | 4 | 2025-11-29 | 2025-12-02
R7S1ONTCM-AP15-666 | T&C - Lights System - AP#15 (Large) | 4 | 2025-11-30 | 2025-12-03
CLOSE-OUT (SNAGGING / DESNAGGING) |  | 141 | 2025-09-18 | 2026-01-05
PRIORITY - 1 |  | 46 | 2025-09-18 | 2025-10-30
BUILDING # AP03 - CLOSE-OUT (SNAGGING / DESNAGGING) |  | 37 | 2025-09-29 | 2025-10-19
R7S1ONSNG-AP03-487 | Receipt of Preliminary Snag List From Employer - AP#03 | 1 | 2025-09-29 | 2025-09-30
R7S1ONSNG-AP03-488 | De-Snagging of Preliminary Snags For Civil/MEP Activities - AP#03 | 12 | 2025-09-30 | 2025-10-14
R7S1ONSNG-AP03-489 | O & M / Training - AP#03 | 12 | 2025-10-01 | 2025-10-15
R7S1ONSNG-AP03-490 | Asbuilt - AP#03 | 12 | 2025-10-02 | 2025-10-16
R7S1ONSNG-AP03-491 | Warranties / Guarantees / Spare Parts - AP#03 | 12 | 2025-10-04 | 2025-10-18
R7S1ONSNG-AP03-492 | Acknowledgement of Final Snags Closure - AP#03 | 4 | 2025-10-14 | 2025-10-19
BUILDING # AP02 - CLOSE-OUT (SNAGGING / DESNAGGING) |  | 29 | 2025-09-30 | 2025-10-20
R7S1ONSNG-AP02-481 | Receipt of Preliminary Snag List From Employer - AP#02 | 1 | 2025-09-30 | 2025-10-01
R7S1ONSNG-AP02-482 | De-Snagging of Preliminary Snags For Civil/MEP Activities - AP#02 | 14 | 2025-10-01 | 2025-10-18
R7S1ONSNG-AP02-483 | O & M / Training - AP#02 | 12 | 2025-10-04 | 2025-10-18
R7S1ONSNG-AP02-484 | Asbuilt - AP#02 | 12 | 2025-10-06 | 2025-10-20
R7S1ONSNG-AP02-485 | Warranties / Guarantees / Spare Parts - AP#02 | 12 | 2025-10-06 | 2025-10-20
R7S1ONSNG-AP02-486 | Acknowledgement of Final Snags Closure - AP#02 | 4 | 2025-10-15 | 2025-10-20
BUILDING # AP01 - CLOSE-OUT (SNAGGING / DESNAGGING) |  | 32 | 2025-09-29 | 2025-10-22
R7S1ONSNG-AP01-430 | Receipt of Preliminary Snag List From Employer - AP#01 | 1 | 2025-09-29 | 2025-09-30
R7S1ONSNG-AP01-450 | O & M / Training - AP#01 | 12 | 2025-10-02 | 2025-10-16
R7S1ONSNG-AP01-440 | De-Snagging of Preliminary Snags For Civil/MEP Activities - AP#01 | 15 | 2025-09-30 | 2025-10-18
R7S1ONSNG-AP01-460 | Asbuilt - AP#01 | 12 | 2025-10-05 | 2025-10-19
R7S1ONSNG-AP01-470 | Warranties / Guarantees / Spare Parts - AP#01 | 12 | 2025-10-07 | 2025-10-21
R7S1ONSNG-AP01-480 | Acknowledgement of Final Snags Closure - AP#01 | 4 | 2025-10-18 | 2025-10-22
BUILDING # AP04 - CLOSE-OUT (SNAGGING / DESNAGGING) |  | 25 | 2025-09-30 | 2025-10-23
R7S1ONSNG-AP04-493 | Receipt of Preliminary Snag List From Employer - AP#04 | 1 | 2025-09-30 | 2025-10-01
R7S1ONSNG-AP04-495 | O & M / Training - AP#04 | 12 | 2025-10-04 | 2025-10-18
R7S1ONSNG-AP04-494 | De-Snagging of Preliminary Snags For Civil/MEP Activities - AP#04 | 15 | 2025-10-01 | 2025-10-19
R7S1ONSNG-AP04-496 | Asbuilt - AP#04 | 12 | 2025-10-06 | 2025-10-20
R7S1ONSNG-AP04-497 | Warranties / Guarantees / Spare Parts - AP#04 | 12 | 2025-10-08 | 2025-10-22
R7S1ONSNG-AP04-498 | Acknowledgement of Final Snags Closure - AP#04 | 4 | 2025-10-19 | 2025-10-23
BUILDING # AP06 - CLOSE-OUT (SNAGGING / DESNAGGING) |  | 24 | 2025-10-01 | 2025-10-26
R7S1ONSNG-AP06-499 | Receipt of Preliminary Snag List From Employer - AP#06 | 1 | 2025-10-01 | 2025-10-02
R7S1ONSNG-AP06-501 | O & M / Training - AP#06 | 12 | 2025-10-05 | 2025-10-19
R7S1ONSNG-AP06-500 | De-Snagging of Preliminary Snags For Civil/MEP Activities - AP#06 | 15 | 2025-10-02 | 2025-10-20
R7S1ONSNG-AP06-502 | Asbuilt - AP#06 | 12 | 2025-10-07 | 2025-10-21
R7S1ONSNG-AP06-503 | Warranties / Guarantees / Spare Parts - AP#06 | 12 | 2025-10-11 | 2025-10-25
R7S1ONSNG-AP06-504 | Acknowledgement of Final Snags Closure - AP#06 | 4 | 2025-10-21 | 2025-10-26
BUILDING # AP07 - CLOSE-OUT (SNAGGING / DESNAGGING) |  | 25 | 2025-09-18 | 2025-10-27
R7S1ONSNG-AP07-505 | Receipt of Preliminary Snag List From Employer - AP#07 | 1 | 2025-09-18 | 2025-09-20
R7S1ONSNG-AP07-507 | O & M / Training - AP#07 | 12 | 2025-09-27 | 2025-10-11
R7S1ONSNG-AP07-508 | Asbuilt - AP#07 | 12 | 2025-09-28 | 2025-10-12
R7S1ONSNG-AP07-506 | De-Snagging of Preliminary Snags For Civil/MEP Activities - AP#07 | 15 | 2025-09-25 | 2025-10-13
R7S1ONSNG-AP07-509 | Warranties / Guarantees / Spare Parts - AP#07 | 18 | 2025-10-01 | 2025-10-22
R7S1ONSNG-AP07-510 | Acknowledgement of Final Snags Closure - AP#07 | 4 | 2025-10-22 | 2025-10-27
AUTHORITIES |  | 4 | 2025-10-27 | 2025-10-30
R7S1ONSNG-AP07-520 | Readiness for Authorities inspection, Hand-over - Priority - 01 | 4 | 2025-10-27 | 2025-10-30
PRIORITY - 2 |  | 97 | 2025-11-13 | 2026-01-05
BUILDING # AP016 - SNAGGING / DESNAGGING (LARGE STUDIO) |  | 37 | 2025-11-13 | 2025-12-21
R7S1ONSNG-AP16-547 | Receipt of Preliminary Snag List From Employer - AP#16 | 1 | 2025-11-13 | 2025-11-13
R7S1ONSNG-AP16-548 | De-Snagging of Preliminary Snags For Civil/MEP Activities - AP#16 | 15 | 2025-11-20 | 2025-12-08
R7S1ONSNG-AP16-549 | O & M / Training - AP#16 | 15 | 2025-11-24 | 2025-12-11
R7S1ONSNG-AP16-550 | Asbuilt - AP#16 | 15 | 2025-11-27 | 2025-12-15
R7S1ONSNG-AP16-551 | Warranties / Guarantees / Spare Parts - AP#16 | 15 | 2025-12-01 | 2025-12-18
R7S1ONSNG-AP16-552 | Acknowledgement of Final Snags Closure - AP#16 | 4 | 2025-12-16 | 2025-12-21
BUILDING # AP017 - SNAGGING / DESNAGGING (LARGE STUDIO) |  | 59 | 2025-11-22 | 2025-12-22
R7S1ONSNG-AP17-529 | Receipt of Preliminary Snag List From Employer - AP#17 | 2 | 2025-11-22 | 2025-11-23
R7S1ONSNG-AP17-530 | De-Snagging of Preliminary Snags For Civil/MEP Activities - AP#17 | 15 | 2025-11-27 | 2025-12-14
R7S1ONSNG-AP17-531 | O & M / Training - AP#17 | 15 | 2025-11-30 | 2025-12-16
R7S1ONSNG-AP17-532 | Asbuilt - AP#17 | 15 | 2025-12-02 | 2025-12-18
R7S1ONSNG-AP17-533 | Warranties / Guarantees / Spare Parts - AP#17 | 15 | 2025-12-04 | 2025-12-21
R7S1ONSNG-AP17-534 | Acknowledgement of Final Snags Closure - AP#17 | 4 | 2025-12-18 | 2025-12-22
BUILDING # AP018 - SNAGGING / DESNAGGING (LARGE STUDIO) |  | 58 | 2025-11-22 | 2025-12-24
R7S1ONSNG-AP18-523 | Receipt of Preliminary Snag List From Employer - AP#18 | 2 | 2025-11-22 | 2025-11-23
R7S1ONSNG-AP18-524 | De-Snagging of Preliminary Snags For Civil/MEP Activities - AP#18 | 15 | 2025-11-24 | 2025-12-10
R7S1ONSNG-AP18-525 | O & M / Training - AP#18 | 15 | 2025-11-27 | 2025-12-14
R7S1ONSNG-AP18-526 | Asbuilt - AP#18 | 15 | 2025-12-01 | 2025-12-17
R7S1ONSNG-AP18-527 | Warranties / Guarantees / Spare Parts - AP#18 | 15 | 2025-12-04 | 2025-12-21
R7S1ONSNG-AP18-528 | Acknowledgement of Final Snags Closure - AP#18 | 4 | 2025-12-21 | 2025-12-24
BUILDING # AP019 - SNAGGING / DESNAGGING (MEDIUM STUDIO) |  | 59 | 2025-11-25 | 2025-12-25
R7S1ONSNG-AP19-517 | Receipt of Preliminary Snag List From Employer - AP#19 | 2 | 2025-11-25 | 2025-11-26
R7S1ONSNG-AP19-518 | De-Snagging of Preliminary Snags For Civil/MEP Activities - AP#19 | 15 | 2025-11-27 | 2025-12-14
R7S1ONSNG-AP19-519 | O & M / Training - AP#19 | 15 | 2025-11-30 | 2025-12-16
R7S1ONSNG-AP19-520 | Asbuilt - AP#19 | 15 | 2025-12-02 | 2025-12-18
R7S1ONSNG-AP19-521 | Warranties / Guarantees / Spare Parts - AP#19 | 15 | 2025-12-04 | 2025-12-21
R7S1ONSNG-AP19-522 | Acknowledgement of Final Snags Closure - AP#19 | 4 | 2025-12-22 | 2025-12-25
BUILDING # AP05 - SNAGGING / DESNAGGING (MEDIUM STUDIO) |  | 54 | 2025-11-27 | 2025-12-27
R7S1ONSNG-AP05-511 | Receipt of Preliminary Snag List From Employer - AP#05 | 2 | 2025-11-27 | 2025-11-29
R7S1ONSNG-AP05-512 | De-Snagging of Preliminary Snags For Civil/MEP Activities - AP#05 | 15 | 2025-11-30 | 2025-12-16
R7S1ONSNG-AP05-513 | O & M / Training - AP#05 | 15 | 2025-12-02 | 2025-12-18
R7S1ONSNG-AP05-514 | Asbuilt - AP#05 | 15 | 2025-12-04 | 2025-12-21
R7S1ONSNG-AP05-515 | Warranties / Guarantees / Spare Parts - AP#05 | 15 | 2025-12-07 | 2025-12-23
R7S1ONSNG-AP05-516 | Acknowledgement of Final Snags Closure - AP#05 | 4 | 2025-12-23 | 2025-12-27
BUILDING # AP014 - SNAGGING / DESNAGGING (LARGE STUDIO) |  | 50 | 2025-12-03 | 2025-12-27
R7S1ONSNG-AP14-535 | Receipt of Preliminary Snag List From Employer - AP#14 | 2 | 2025-12-03 | 2025-12-04
R7S1ONSNG-AP14-536 | De-Snagging of Preliminary Snags For Civil/MEP Activities - AP#14 | 15 | 2025-12-06 | 2025-12-22
R7S1ONSNG-AP14-537 | O & M / Training - AP#14 | 15 | 2025-12-07 | 2025-12-23
R7S1ONSNG-AP14-538 | Asbuilt - AP#14 | 15 | 2025-12-08 | 2025-12-24
R7S1ONSNG-AP14-539 | Warranties / Guarantees / Spare Parts - AP#14 | 15 | 2025-12-09 | 2025-12-25
R7S1ONSNG-AP14-540 | Acknowledgement of Final Snags Closure - AP#14 | 4 | 2025-12-23 | 2025-12-27
BUILDING # AP015 - SNAGGING / DESNAGGING (LARGE STUDIO) |  | 72 | 2025-12-01 | 2025-12-29
R7S1ONSNG-AP15-541 | Receipt of Preliminary Snag List From Employer - AP#15 | 2 | 2025-12-01 | 2025-12-02
R7S1ONSNG-AP15-542 | De-Snagging of Preliminary Snags For Civil/MEP Activities - AP#15 | 15 | 2025-12-04 | 2025-12-21
R7S1ONSNG-AP15-543 | O & M / Training - AP#15 | 15 | 2025-12-07 | 2025-12-23
R7S1ONSNG-AP15-544 | Asbuilt - AP#15 | 15 | 2025-12-09 | 2025-12-25
R7S1ONSNG-AP15-545 | Warranties / Guarantees / Spare Parts - AP#15 | 15 | 2025-12-11 | 2025-12-28
R7S1ONSNG-AP15-546 | Acknowledgement of Final Snags Closure - AP#15 | 4 | 2025-12-25 | 2025-12-29
AUTHORITIES |  | 6 | 2025-12-30 | 2026-01-05
R7S1ONSNG-AP07-530 | Readiness for Authorities inspection, Hand-over - Priority - 02 | 6 | 2025-12-30 | 2026-01-05